## README
5D Mapping Template — IFC ↔ Cost Code ↔ P6 Task
The single control / configuration workbook for the 5D model. It carries MAPPING RULES + RATES only — no calculations.
Inputs to the whole 5D model are just two things: (1) the IFC model and (2) this workbook.
IMPORTANT — this file does NOT calculate anything.
Quantities, the effective unit rate, the planned/targeted cost, coverage % and any unmapped / missing items are ALL computed downstream in Power BI (Power Query + the model), never in this file. Here the end user fills only the mapping rules and the rates.
Power BI computes: effective rate per cost code = Σ over resources [ Coefficient × (1 + Waste%) × Unit Rate ] · element quantity per cost code = IFC model take-off · Planned Cost = quantity × effective rate · then surfaces elements with no cost code (unmapped) and cost codes with no elements (missing) on a Data-Quality view.
SHEETS
README — this page.
WBS — the P6 WBS as a parent-child TREE (WBS Code → Parent WBS Code). Handles any nesting depth. Comes from P6.
Task_P6 — the P6 activity export. Column names are P6’s own and are left exactly as P6 writes them. Comes from P6.
Cost_Code_Map — INPUT (rules): IFC Class + PredefinedType, OR the Uniclass classification → Cost Code (NRM2).
Task_Element — INPUT (rules): which Cost Code(s) each P6 Activity delivers (+ optional Level/Storey filter). No quantities, no cost.
Rate_Card — INPUT (rates): each Cost Code broken into its resources (Material / Labour / Plant) with a coefficient, waste % and unit rate.
Ref_Codes — reference pick-lists: RICS NRM2 work sections + Uniclass 2015 codes.
THE BACKBONE
IFC element ──(Cost_Code_Map)──► COST CODE ◄──(Task_Element)── P6 Activity COST CODE ──(Rate_Card)──► resources & rate
Cost Code is the shared key: an element carries a cost code, a task delivers cost codes, and a cost code prices out into resources. So one cost code ties 3D geometry, 4D task and 5D cost together.
REINFORCEMENT / MULTI-RESOURCE NOTE
Rebar is normally NOT modelled. So the concrete cost codes (11.1 foundations, 11.2 frame) INCLUDE reinforcement as a Resource line whose Coefficient is the reinforcement ratio in kg per m³ (e.g. 120 kg/m³ foundations, 150 kg/m³ frame), plus the concrete grade in the Notes. Formwork, concreting labour and the pump are separate resource lines on the same cost code. That is how one cost code — and therefore one task — carries several resources. (If you DO model rebar separately, map it to 11.7 and drop the ratio line, never both.)
WBS TREE NOTE
The WBS sheet is a parent-child tree. For deeper nesting just add rows (e.g. Rac1.2.1 with Parent WBS Code = Rac1.2, Level 3); Power BI rebuilds the hierarchy with PATH() so nothing is lost however deep the WBS goes. Task_P6[WBS Code] joins to WBS[WBS Code].
CONVENTIONS
• Every sheet is a real Excel Table (ListObject) so Power Query binds by table name and you can add rows cleanly. • Blue text = a cell you edit. • "*" = any / wildcard. • Standard used: Uniclass 2015 (classification) + RICS NRM2 (cost codes) + BCIS-style resource breakdown. Example data = RAC advanced sample.

## WBS
WBS — parent-child tree (handles nested multi-level WBS)
WBS Code joins from Task_P6. Parent WBS Code builds the tree — add rows at any depth (e.g. Rac1.2.1 under Rac1.2).
WBS Code | WBS Name | Parent WBS Code | WBS Level | Notes
Rac1 | RAC Advanced Sample Project |  | 1 | project root
Rac1.1 | Structure | Rac1 | 2
Rac1.2 | Envelope | Rac1 | 2
Rac1.3 | Fit-out | Rac1 | 2
Rac1.4 | External & MEP | Rac1 | 2

## Task_P6
Task — P6 Activity
Exported from Primavera P6. Column names are P6’s own — do not rename. Dates run Jun-2026 → May-2028; assumed data date ≈ 13-Sep-2027.
Activity ID | Activity Status | WBS Code | (*)WBS Name | Activity Name | (*)Start | (*)Finish | Actual Start | Actual Finish | Activity % Complete(%) | Actual Cost (EUR) | Notes
01.01 | Completed | Rac1.1 | Structure | Steel frame | 2026-06-15 | 2026-11-30 | 2026-06-15 | 2026-12-03 | 100 | 7736600
01.02 | Completed | Rac1.1 | Structure | Concrete columns & beams | 2026-07-01 | 2026-12-15 | 2026-07-01 | 2026-12-18 | 100 | 184170
01.03 | Completed | Rac1.1 | Structure | Floor slabs | 2026-09-01 | 2027-01-31 | 2026-09-01 | 2027-02-03 | 100 | 1983000
01.04 | Completed | Rac1.1 | Structure | Stairs | 2026-12-01 | 2027-02-28 | 2026-12-01 | 2027-03-02 | 100 | 118800
02.01 | Completed | Rac1.2 | Envelope | Masonry walls | 2027-01-15 | 2027-05-31 | 2027-01-15 | 2027-06-02 | 100 | 866600
02.02 | Completed | Rac1.2 | Envelope | Roof | 2027-03-01 | 2027-06-30 | 2027-03-01 | 2027-07-03 | 100 | 935970
02.03 | Completed | Rac1.2 | Envelope | Windows & doors | 2027-05-01 | 2027-08-31 | 2027-05-01 | 2027-09-02 | 100 | 262780
02.04 | In Progress | Rac1.2 | Envelope | Balustrades & railings | 2027-07-01 | 2027-10-31 | 2027-07-01 |  | 68 | 75385
03.01 | In Progress | Rac1.3 | Fit-out | Suspended ceilings | 2027-06-01 | 2027-11-30 | 2027-06-01 |  | 55 | 194680
03.02 | In Progress | Rac1.3 | Fit-out | FF&E / furniture | 2027-09-01 | 2028-01-31 | 2027-09-01 |  | 30 | 46685
03.03 | In Progress | Rac1.3 | Fit-out | Light fixtures | 2027-08-01 | 2027-12-15 | 2027-08-01 |  | 45 | 5410
04.01 | In Progress | Rac1.4 | External & MEP | Site works & landscaping | 2027-08-01 | 2028-05-31 | 2027-08-01 |  | 15 | 4775

## Cost_Code_Map
Cost_Code_Map — IFC Class / Type / Classification → Cost Code (NRM2)
INPUT (rules). Join onto the IFC element list by (IFC Class + PredefinedType) or by Classification Code. Unmatched elements are surfaced in Power BI, never dropped. "*" = any.
IFC Class | PredefinedType | Level group | Classification System | Classification Code | Classification Title | Cost Code (NRM2) | Cost Code Description | Base Unit | Cost Category | Confidence | Notes
IFCFOOTING | * | Foundation | Uniclass 2015 EF | EF_20_05_30 | Foundations | 11.1 | In-situ concrete: foundations | m3 | Substructure | rule | incl. reinforcement ratio (see Rate_Card)
IFCSLAB | * | Foundation | Uniclass 2015 EF | EF_30_20 | Floors | 13.1 | Precast concrete floors | m2 | Structure | rule | ground slab
IFCSLAB | * | Ground / L1 / L2 | Uniclass 2015 EF | EF_30_20 | Floors | 13.1 | Precast concrete floors | m2 | Structure | rule | suspended floors
IFCSLAB | ROOF | Roof | Uniclass 2015 EF | EF_30_10 | Roofs | 16.1 | Carpentry: roof structure | m2 | Structure | rule | roof slab
IFCWALL | * | Ground / L1 / L2 | Uniclass 2015 EF | EF_25_10 | Walls | 14.1 | Masonry: loadbearing | m2 | Structure | rule | kalkzandsteen inner leaf
IFCWALLSTANDARDCASE | * | * | Uniclass 2015 EF | EF_25_10 | Walls | 14.1 | Masonry: loadbearing | m2 | Structure | rule | resolve level in query
IFCWALL | PARTITIONING | * | Uniclass 2015 EF | EF_25_10 | Walls | 20.1 | Proprietary linings & partitions | m2 | Finishes | rule | internal partition
IFCCOLUMN | * | * | Uniclass 2015 EF | EF_20_10 | Superstructure | 11.2 | In-situ concrete: frame | m3 | Structure | rule | incl. reinforcement ratio
IFCBEAM | * | * | Uniclass 2015 EF | EF_20_10 | Superstructure | 11.2 | In-situ concrete: frame | m3 | Structure | rule | incl. reinforcement ratio
IFCMEMBER | * | * | Uniclass 2015 EF | EF_20_10 | Superstructure | 15.1 | Structural steel frame | kg | Structure | rule | measure by mass
IFCPLATE | * | * | Uniclass 2015 EF | EF_20_10 | Superstructure | 15.1 | Structural steel frame | kg | Structure | rule
IFCREINFORCINGBAR | * | * | Uniclass 2015 EF | EF_20_10 | Superstructure | 11.7 | Reinforcement | kg | Structure | rule | only if rebar modelled separately
IFCROOF | * | Roof | Uniclass 2015 EF | EF_30_10 | Roofs | 16.1 | Carpentry: roof structure | m2 | Structure | rule | kapconstructie
IFCSTAIR | * | * | Uniclass 2015 EF | EF_35_10 | Stairs | 25.1 | Stairs: precast | nr | Structure | rule | prefab trap
IFCSTAIRFLIGHT | * | * | Uniclass 2015 EF | EF_35_10 | Stairs | 25.1 | Stairs: precast | nr | Structure | rule
IFCFURNISHINGELEMENT | * | * | Uniclass 2015 Pr | Pr_40_50 | Furniture | 07.1 | FF&E / furniture | nr | Finishes | rule | mapped by category
IFCCURTAINWALL | * | * | Uniclass 2015 EF | EF_25_10 | Walls | 21.1 | Cladding & covering | m2 | Envelope | weak | or glazing (23.1)
IFCWINDOW | * | * | Uniclass 2015 EF | EF_25_30 | Doors and windows | 23.1 | Windows, screens & lights | m2 | Envelope | rule | houten kozijn
IFCDOOR | * | * | Uniclass 2015 EF | EF_25_30 | Doors and windows | 24.1 | Doors: external | nr | Envelope | rule | split ext/int by location
IFCDOOR | INTERNAL | * | Uniclass 2015 EF | EF_25_30 | Doors and windows | 24.2 | Doors: internal (incl. fire-rated) | nr | Finishes | rule | Pr_30_59 for fire set
IFCCOVERING | CLADDING | * | Uniclass 2015 EF | EF_25_10 | Walls | 21.1 | Cladding & covering | m2 | Envelope | rule | external cladding
IFCROOF | * | * | Uniclass 2015 EF | EF_30_10 | Roofs | 19.1 | Waterproofing | m2 | Envelope | weak | waterproofing (vs 16.1 structure)
IFCRAILING | * | * | Uniclass 2015 EF | EF_25 | Wall & barrier elements | 25.2 | Balustrades & railings | m | Envelope | rule | hekken
IFCCOVERING | FLOORING | * | Uniclass 2015 EF | EF_30_25 | Ceilings & soffits | 28.1 | Floor finishings | m2 | Finishes | rule
IFCCOVERING | CEILING | * | Uniclass 2015 EF | EF_30_25 | Ceilings & soffits | 30.1 | Suspended ceilings | m2 | Finishes | rule
IFCPIPESEGMENT | * | * | Uniclass 2015 Ss | Ss_60 | Piped supply systems | 38.1 | Mechanical: pipework | m | MEP | rule
IFCSANITARYTERMINAL | * | * | Uniclass 2015 Ss | Ss_60 | Piped supply systems | 38.2 | Mechanical: sanitary fixtures | nr | MEP | rule
IFCFLOWSEGMENT | * | * | Uniclass 2015 Ss | Ss_60 | Piped supply systems | 38.1 | Mechanical: pipework | m | MEP | weak | generic flow
IFCDUCTSEGMENT | * | * | Uniclass 2015 Ss | Ss_60_40 | Ventilation systems | 38.3 | Mechanical: ductwork | m | MEP | rule
IFCAIRTERMINAL | * | * | Uniclass 2015 Ss | Ss_60_40 | Ventilation systems | 38.4 | Mechanical: air terminals | nr | MEP | rule
IFCFLOWTERMINAL | * | * | Uniclass 2015 Ss | Ss_60_40 | Ventilation systems | 38.4 | Mechanical: air terminals | nr | MEP | weak | resolve discipline
IFCCABLECARRIERSEGMENT | * | * | Uniclass 2015 Ss | Ss_70 | Electrical systems | 39.1 | Electrical: cable containment | m | MEP | rule
IFCLIGHTFIXTURE | * | * | Uniclass 2015 Ss | Ss_70 | Electrical systems | 39.2 | Electrical: light fixtures | nr | MEP | rule
IFCOUTLET | * | * | Uniclass 2015 Ss | Ss_70 | Electrical systems | 39.3 | Electrical: points | nr | MEP | rule
IFCSPACE | * | * |  |  |  |  | (info only — not costed) | m2 | (Info Only) | info | spatial only

## Task_Element
Task_Element — which Cost Code(s) each P6 Activity delivers (mapping only)
INPUT (rules) — NO quantities, NO cost here. One row per Activity × Cost Code. Optional Level/Storey filter splits a cost code across activities. Quantity, rate and cost are computed in Power BI.
Activity ID | Activity Name | WBS Code | Cost Code | Cost Code Description | IFC Class(es) | Classification | Level / Storey filter | Coverage / Notes
01.01 | Steel frame | Rac1.1 | 15.1 | Structural steel frame | IFCMEMBER / IFCPLATE | EF_20_10 |  | Model
01.02 | Concrete columns & beams | Rac1.1 | 11.2 | In-situ concrete: frame | IFCCOLUMN / IFCBEAM | EF_20_10 |  | Model
01.03 | Floor slabs | Rac1.1 | 13.1 | Precast concrete floors | IFCSLAB (FLOOR) | EF_30_20 |  | Model
01.04 | Stairs | Rac1.1 | 25.1 | Stairs: precast | IFCSTAIRFLIGHT | EF_35_10 |  | Model
02.01 | Masonry walls | Rac1.2 | 14.1 | Masonry: loadbearing | IFCWALL / IFCWALLSTANDARDCASE | EF_25_10 |  | Model
02.02 | Roof | Rac1.2 | 16.1 | Carpentry: roof structure | IFCROOF / IFCSLAB (ROOF) | EF_30_10 |  | Model
02.03 | Windows & doors | Rac1.2 | 24.1 | Doors: external | IFCDOOR | EF_25_30 |  | Model
02.03 | Windows & doors | Rac1.2 | 23.1 | Windows, screens & lights | IFCWINDOW | EF_25_30 |  | Model
02.04 | Balustrades & railings | Rac1.2 | 25.2 | Balustrades & railings | IFCRAILING | EF_25 |  | Model
03.01 | Suspended ceilings | Rac1.3 | 30.1 | Suspended ceilings | IFCCOVERING (CEILING) | EF_30_25 |  | Model (by PredefinedType)
03.02 | FF&E / furniture | Rac1.3 | 07.1 | FF&E / furniture | IFCFURNISHINGELEMENT | Pr_40 |  | Model (by category)
03.03 | Light fixtures | Rac1.3 | 39.2 | Electrical: light fixtures | IFCFLOWTERMINAL (Lighting Fixtures) | Ss_70 |  | Model (by category)
04.01 | Site works & landscaping | Rac1.4 | 35.1 | Site works & landscaping | IFCSITE |  |  | Model (by category)

## Rate_Card
Rate_Card — Cost Code broken into resources (Material / Labour / Plant)
INPUT (rates). One or more resource rows per cost code. Coefficient = quantity of the resource per 1 Base Unit of the cost code (rebar ratio lives here). Power BI computes the effective rate = Σ Coefficient × (1+Waste%) × Unit Rate. No totals are calculated in this file.
Cost Code | Cost Code Description | Base Unit | Resource | Resource Type | Resource Unit | Coefficient / Base Unit | Waste % | Unit Rate (EUR) | Rate Basis / Source
5.1 | Excavating & filling | m3 | Bulk excavation | Plant | m3 | 1 | 0% | 33.75 | excavator dig
5.1 | Excavating & filling | m3 | Cart away / disposal | Plant | m3 | 1 | 10% | 33.75 | muckaway incl. bulking
11.1 | In-situ concrete: foundations | m3 | Concrete C30/37 | Material | m3 | 1 | 5% | 487.5 | ready-mix, grade C30/37
11.1 | In-situ concrete: foundations | m3 | Reinforcement (ratio) | Material | kg | 120 | 2.5% | 4.6875 | reinforcement ratio 120 kg/m3 - rebar not modelled
11.1 | In-situ concrete: foundations | m3 | Formwork | Material | m2 | 2 | 10% | 82.5 | edge / face formwork
11.1 | In-situ concrete: foundations | m3 | Concreting labour | Labour | hr | 1.2 | 0% | 131.25 | place, vibrate, finish
11.1 | In-situ concrete: foundations | m3 | Concrete pump | Plant | hr | 0.3 | 0% | 337.5 | pump hire
11.2 | In-situ concrete: frame | m3 | Concrete C30/37 | Material | m3 | 1 | 5% | 487.5 | ready-mix, grade C30/37
11.2 | In-situ concrete: frame | m3 | Reinforcement (ratio) | Material | kg | 150 | 2.5% | 4.6875 | reinforcement ratio 150 kg/m3 - frame
11.2 | In-situ concrete: frame | m3 | Formwork | Material | m2 | 4 | 10% | 93.75 | column / beam formwork
11.2 | In-situ concrete: frame | m3 | Concreting labour | Labour | hr | 1.5 | 0% | 131.25 | place, vibrate, finish
11.2 | In-situ concrete: frame | m3 | Concrete pump | Plant | hr | 0.4 | 0% | 337.5 | pump hire
11.7 | Reinforcement | kg | Reinforcing steel | Material | kg | 1 | 5% | 3.5625 | supply - use only if rebar modelled separately
11.7 | Reinforcement | kg | Cut / bend / fix labour | Labour | hr | 0.02 | 0% | 131.25 | fixing
13.1 | Precast concrete floors | m2 | Precast floor units | Material | m2 | 1 | 2% | 168.75 | hollowcore / breedplaat
13.1 | Precast concrete floors | m2 | Structural topping | Material | m2 | 1 | 5% | 45 | topping incl. mesh
13.1 | Precast concrete floors | m2 | Erection (crane+crew) | Plant | m2 | 1 | 0% | 30 | crane & crew
13.2 | Precast concrete: balconies | nr | Precast balcony unit | Material | nr | 1 | 0% | 7875 | supply
13.2 | Precast concrete: balconies | nr | Erection (crane+crew) | Plant | nr | 1 | 0% | 1125 | lift & fix
14.1 | Masonry: loadbearing | m2 | Kalkzandsteen + mortar | Material | m2 | 1 | 5% | 112.5 | loadbearing inner leaf
14.1 | Masonry: loadbearing | m2 | Bricklaying labour | Labour | m2 | 1 | 0% | 67.5 | lay & point
14.2 | Masonry: facade | m2 | Facing brick + cavity + ties | Material | m2 | 1 | 5% | 206.25 | outer leaf incl. insulation
14.2 | Masonry: facade | m2 | Bricklaying labour | Labour | m2 | 1 | 0% | 150 | lay & point
15.1 | Structural steel frame | kg | Steel sections | Material | kg | 1 | 3% | 5.25 | supply, fabricate, protect
15.1 | Structural steel frame | kg | Erection + crane | Labour | kg | 1 | 0% | 2.625 | erect & bolt
16.1 | Carpentry: roof structure | m2 | Timber roof structure | Material | m2 | 1 | 8% | 300 | kapconstructie
16.1 | Carpentry: roof structure | m2 | Carpentry labour | Labour | m2 | 1 | 0% | 150 | cut & fix
19.1 | Waterproofing | m2 | Membrane + insulation | Material | m2 | 1 | 10% | 206.25 | built-up / single-ply
19.1 | Waterproofing | m2 | Roofing labour | Labour | m2 | 1 | 0% | 112.5 | lay & detail
20.1 | Proprietary linings & partitions | m2 | Stud + plasterboard | Material | m2 | 1 | 8% | 112.5 | partition system
20.1 | Proprietary linings & partitions | m2 | Drylining labour | Labour | m2 | 1 | 0% | 67.5 | erect & board
21.1 | Cladding & covering | m2 | Cladding panels + fixings | Material | m2 | 1 | 5% | 262.5 | rainscreen
21.1 | Cladding & covering | m2 | Cladding labour | Labour | m2 | 1 | 0% | 93.75 | install
23.1 | Windows, screens & lights | m2 | Window unit (glazed) | Material | m2 | 1 | 0% | 1500 | incl. IGU
23.1 | Windows, screens & lights | m2 | Glazing labour | Labour | m2 | 1 | 0% | 300 | install & seal
24.1 | Doors: external | nr | External doorset | Material | nr | 1 | 0% | 2100 | incl. ironmongery
24.1 | Doors: external | nr | Install labour | Labour | nr | 1 | 0% | 337.5 | hang & adjust
24.2 | Doors: internal | nr | Internal doorset | Material | nr | 1 | 0% | 975 | fire-rated as spec.
24.2 | Doors: internal | nr | Install labour | Labour | nr | 1 | 0% | 225 | hang & adjust
25.1 | Stairs: precast | nr | Precast stair flight | Material | nr | 1 | 0% | 5625 | incl. bordes
25.1 | Stairs: precast | nr | Erection (crane+crew) | Plant | nr | 1 | 0% | 1125 | lift & fix
25.2 | Balustrades & railings | m | Balustrade / railing | Material | m | 1 | 3% | 412.5 | metal
25.2 | Balustrades & railings | m | Install labour | Labour | m | 1 | 0% | 112.5 | fix
28.1 | Floor finishings | m2 | Screed + floor finish | Material | m2 | 1 | 8% | 112.5 | screed + tile/vinyl
28.1 | Floor finishings | m2 | Flooring labour | Labour | m2 | 1 | 0% | 56.25 | lay
28.2 | Wall & ceiling finishings | m2 | Plaster + paint | Material | m2 | 1 | 10% | 60 | skim + emulsion
28.2 | Wall & ceiling finishings | m2 | Finishing labour | Labour | m2 | 1 | 0% | 45 | apply
30.1 | Suspended ceilings | m2 | Ceiling system | Material | m2 | 1 | 8% | 67.5 | grid + tiles / MF
30.1 | Suspended ceilings | m2 | Ceiling labour | Labour | m2 | 1 | 0% | 37.5 | install
35.1 | Site works & landscaping | m2 | Paving & landscaping | Material | m2 | 1 | 5% | 150 | paving, kerbs, planting
35.1 | Site works & landscaping | m2 | Site labour + plant | Labour | m2 | 1 | 0% | 75 | lay & finish
38.1 | Mechanical: pipework | m | Pipework + fittings | Material | m | 1 | 5% | 90 | PPR/steel
38.1 | Mechanical: pipework | m | Pipefitting labour | Labour | m | 1 | 0% | 52.5 | install & test
38.2 | Mechanical: sanitary fixtures | nr | Sanitary fixture | Material | nr | 1 | 0% | 825 | WC/basin incl. fittings
38.2 | Mechanical: sanitary fixtures | nr | Install labour | Labour | nr | 1 | 0% | 375 | connect
38.3 | Mechanical: ductwork | m | Ductwork (GI) | Material | m | 1 | 8% | 180 | incl. insulation
38.3 | Mechanical: ductwork | m | Ductwork labour | Labour | m | 1 | 0% | 90 | install
38.4 | Mechanical: air terminals | nr | Air terminal / unit | Material | nr | 1 | 0% | 675 | grille/diffuser/FCU
38.4 | Mechanical: air terminals | nr | Install labour | Labour | nr | 1 | 0% | 300 | install & balance
39.1 | Electrical: cable containment | m | Cable + containment | Material | m | 1 | 5% | 15 | tray/trunking + cable
39.1 | Electrical: cable containment | m | Electrical labour | Labour | m | 1 | 0% | 7.5 | install & terminate
39.2 | Electrical: light fixtures | nr | Light fixture (LED) | Material | nr | 1 | 0% | 206.25 | luminaire
39.2 | Electrical: light fixtures | nr | Install labour | Labour | nr | 1 | 0% | 112.5 | connect
39.3 | Electrical: points | nr | Wiring accessory | Material | nr | 1 | 0% | 131.25 | outlet/switch
39.3 | Electrical: points | nr | Install labour | Labour | nr | 1 | 0% | 112.5 | first & second fix
07.1 | FF&E / furniture | nr | Loose furniture (supply & install) | Material | nr | 1 | 0 | 1312.5 | FF&E allowance per item

## Ref_Codes
Ref_Codes — pick-lists
RICS NRM2 work sections (cost codes) and Uniclass 2015 codes used here. Extend as needed.
NRM2 Code | NRM2 Work Section | Uniclass Code | Title | Table
5 | Excavating and filling | EF_20_05 | Substructure | EF
11 | In-situ concrete works | EF_20_05_30 | Foundations | EF
13 | Precast concrete | EF_20_10 | Superstructure | EF
14 | Masonry | EF_25 | Wall and barrier elements | EF
15 | Structural metalwork | EF_25_10 | Walls | EF
16 | Carpentry | EF_25_30 | Doors and windows | EF
19 | Waterproofing | EF_30_10 | Roofs | EF
20 | Proprietary linings and partitions | EF_30_20 | Floors | EF
21 | Cladding and covering | EF_30_25 | Ceilings and soffits | EF
23 | Windows, screens and lights | EF_35_10 | Stairs | EF
24 | Doors, shutters and hatches | EF_40_10 | Site works (external) | EF
25 | Stairs, walkways and balustrades | Ss_60 | Piped supply systems | Ss
28 | Floor, wall, ceiling and roof finishings | Ss_60_40 | Ventilation systems | Ss
30 | Suspended ceilings | Ss_70 | Electrical systems | Ss
31 | Insulation, fire stopping and fire protection | Pr_30_59 | Fire-resisting doorsets | Pr
33 | Drainage above ground
34 | Drainage below ground
35 | Site works
38 | Mechanical services
39 | Electrical services
41 | Builder's work for services