[14 empty] | {"index":140,"total":402,"filename":"Advanced_Project.ifc","data":"a44Ce44CB44CA0eBC46C2WwlOPGL0mbPUeDAUWDgKHDOUTjtbYz5XGPOtY7zHAUOHAUGjgLnHIU7593XD9gp1HwE9nwEDnwEBj4C53yEJ0eOOdc6zvMROPARGPgInPMRnnHMYTzXfAT2fAQOfAQGPgLnfITztJ6VtHOt3zwfgQMfgYGPwDkfwXrWsXdHB1utn/BlbbvXb4GTwMBJ4JyTcN5RrUeYUWpOAntOAgdOAgMngXNOgrX3M6NAe9f6zXMSOHASGDgJnHMS7pyfCP7wRW2z12+Bk8DASeCck3DP2zaX4Sxa6zfPSeDASWDgJHDOSbjnsHvNgpxr/eY5CRw4CezqLtdvNpfd6zX07Vq/eT4CBz4CAx+Bcz7Cbes9yiDnWrd5PgIHPgIPrLtct1ltX8ksWus2z0fgwEdg4CNwwUewGPH3eG6u3Y/tb36Anqu5Cey5CRy4CTywB6d67uiWo8XLN44ClqCuE6/XAj+BgZ/AFT9BXAmOO4I7zDi1bvMcBQ4cBQaOAuccBcvxMJ/6O3Y8lqCuA6/fAkeBgaPABUfB9jC7BIetsnBfVvMU2PMUOPAUGHgKnPMULMfjjh1/JiUo68DzEzjwExj4CVzwE+4cLU56gy9q272eC9wEhjjMnHMTLEcrAb5IqnkJ7HkJHHgJDLwEznkJFqnfGAEDbjVqTgJ7TgIHTgJDdFzOOQnWzocRPFzOtc1ezwU+AgMfgXM+guX4lAB6WK3nPBeBAxeBIXIo51yEw26jt5I8sIfVOs7zEDjwEBh4CJzzEJ4cbyYEfFHb7HVc4CAwcBC44CCMezTF2q51nOcfcOAfMPAPOOcf2Ki629timRxQ67We8/wDDvwDBv4B5/wDy/G4OQiclKCuA6/rAv+AgX/AFf+AXQkOiywD92k194A994AD94CBe8A598ByPCya0s2CwBLUdeB1XuAfMPAPuOAf7BytBIfF+YFYBzUHgT0HgQMHgSfO1qnesxyPyxTnB5XClaSuC6//AheBgYvAORfhtGg6zf5C2Wud57kIHLgIDPHAOOciXEdzth8X2FzrO89F4MBFYOAicM5FOPaqeprGgVuvmovAnovAgYvAEIWJv3MRzrsE0OdrPee5CBy4CAxcBM65CKe9I71zFviitNlzEThwERi4CJxzEU4bXTeRocEXpc2ei8CBi8DAReCci/DYLNbe8EVts9dvgYvA+Ko/5yI8tdxibdf6zXMROHARGLgInHMRbDQ9tQ61Xes3z0PgwENg4CFwzkN4atm8FjDn2mav3wIPgYGHwDkPweawu9Zhp1jzENjzEDjwEBh4CJzzEJ72PcPsWfMQ2PMQOPAQGHgInPMQrLaPrG/X+s3zEDjwEBh9QHMegvWwe/6GPWnNQ2DPQ+DAQ2DgIXDOQ7AcH5thVNW6zfMQOPAQGN/M5jwEy/EuwYU51zZ7vRY4CAwcBC44CM18f8YugTECoI/Xes3zEDjwEBjvonMeQmteIeCaVfMQ2PMQOPAQGHgInPMQzNbH9jPaXus0z0XgwEVgPNPMuQg3/+L2AbO5Ddq/1meej8CBj8DAR+Ccj/DYLNH2Wp95PgIHPgLjSXLOR7CcrfYbRFWouQjsuQgcuAgMXATOuQh3zjuazoVrWK3PPA+BAw+B3RyZ6jNrZ/O4Q1+/moPAnoPAgYPAwEHgnINwbeVvNjfzsIST4JqDwJ6DwIGDwMBB4JyDYLVuJQFqANf8A/b8Aw78Awb+Aef8gzvHXesu51qnee4BB+4B+3Rym4ez2dV2rdM874AD74CBd8A57+Cp7Zv5Al/UNnudFjgHDJwDLjgH5m1oPp4302nAl7XtXq8FzgED54BzzoHl2Cy67U0dgRLUus3zDjjwDhh4B1zwDowysnO2kjTwFaq5B+y5Bxy4BwzcAy64B0Yb6eZhu/+CFqn5B+z5Bxz4Bwz8A875B1aCtk/4m8VNdyWo68DrucBBYOAgcM5BsBzbzf4YsQS1rvM8BA48BL5cOnkd+JytJA385GouAnsuAgcuAgMXgXMuQtv3bs3OIh/iCtdcBPZcBA5cBAYuAhdchLu9TysBfFHb7HVd4CIwcBE45yK0O3q12QyjrtZznovAgYvAwEXgnItgtXyXwOVc2+x1XOAiMHAROOciGGXE6DITTvprLgJ7LgIHLgIDF4FzLsLNs9klaHDeXnMR2HMROHARGLgInHMRmsUwM9txdq11nOcicOAiMHARuOAiWM86rdbxi9pmr+MCF4GBi8A5F+G2ec/nHV7I1FwE9lwEDlwEBi4C51yEJ+fd3h2/KG32XAQOXAQGLgLnXIQn593DoE/WXAT2XAQOXAQGLgLnXATLue07hQYRoGoeAnseAgceAgMPgXMegs0gd87QJ2seAnseAgceAgMPgXMewp2zWG2DzbVu8zwEDjwEBh4C5zyEx2b7C3271mueh8CBh8DAQ+Cch/DkvHcK8Gaj5h2w5x1w4B0w8A445x1YzhfbTgFyrvWZ5xxw4Byw4OhM9dmds51+wN6k5huw5xtw4Bsw8A045xs8OZvtkHOtxzzXgAPXgIFrwDnX4KltUwj4RW2z12GBZ8DAM+CcZ3AzuWaLM0mtwzzHgAPHgAUtKPhUpgiM8YE51zZ7HRY4BgwcA845Bs8qefOL4IvaZq/DAseA8ZV3zjF4cg4cG645Buw5Bhw4BgwcA845Bt90WM0xYM8x4MAxYME171/WYTXHgD3HgAPHgIFjwDnH4JsOqzkG7DkGHDgGjC+oco7BNx1WcwzYcww4cAwYOAY95xh80WG95hh0zzHogWPQIWpDzzkGX3RYrzkG3XMMeuAYdOAY9Jxj8EWH9Zpj0D3HoAeOQQeOQc85Bl90WK85Bt1zDHrgGHTgGPScY/BFh/WaY9A9x6AHjkEHjkHPOQZfdFivOQbdcwx64Bh04Bj0nGPwRYf1mmPQPcegB45BB45BzzkGX3RYrzkG3XMMeuAYdOAY9Jxj8EWH9Zpj0D3HoAeOQT9wdP6rOqzXHIPuOQY9cAw6cAx6zjH4osN6zTHonmPQA8egA8eg5xyDLzqs1xyD7jkGPXAMOnAMes4x+KLDes0x6J5j0APHoB9owb+qw3rNMeieY9ADx6ADx6DnHIMvOqzXHIPuOQY9cAw6eA33nGPwRYf1mmPQPcegB45BB45BzzkG3Xiw9rIF19VSh3XPMeiBY9APXPNyHWbEsl0Cwlmv1GHdcwx64Bh04Bj0nGNApr/MdoEeVuqw7jkGPXAM+oFrXs4xODyxrGMtlTqse45BDxyDDhyDXnAM+LZ1/23wRWmz5xP0wCfowCfoOZ/gyXm3t+AXpc2eS9ADl6ADl6BnXALMefcw0J41j6B7HkEPPIIOPIKe8wgsZ9rakx5vgV5zB7rnDvTAHejAHeg5d4B2jO475wE21zrMcwd64A504A70nDtw57zvs6iDzbUO87yBHngDHXgDPecNPDbvvxNyrnWY5w30wBvowBvoOW/gznl77xMog5o30D1voAfeQAfeQM95A3fOWxnAPVOveQPd8wZ64A10iP/Sc96A5Xzt9flyX9Q2ex0WeAMdeAM94w1Azt1yhnaudZjnDPTAGehw19tzzsCTs9mOOdc2ex0WOAMdOAM94wxgbRsHcMAXtc1ehwXOQG/YX/L3n8Z73GuWm8NqHeY5Az1wBjpwBnrOGbhXyZs4CXNYrcM8Z6AHzkAHzkAvOAOWs/HDcKavdZjnDPTAGejAGegFZ+BWBoHr2WvOQPecgR44Ax3PHjLOwOpZ5t1lUc6wnWsd5jkDPXAGOnAGes4ZuPYqeW1e0NUg51qHec5AD5yBjmcPOWfgMv9B8yskqO1ah3nOQA+cgQ6cgZ5zBmzfbDv3BrubmjPQPWegB85AB85AzzkDFxnD+gy72Joz0D1noAfOQAfOQM84A9DD2r2Dhy9qm70OC5yBDpyBnnMGLjJO97Z9Ys61zV6HBc5AB85AzzgDr3bdtWy1DTnXOsxzBnrgDHTgDPSMM7Dm6T2TXPf5NrRzrcM8Z6AHzkAHzkDPOANPzm3HIrmwrLUO85yBHjgDHXeGGWcAehbFOazmDHTPGeiBM9CBM9AzzsBzMvOUAHKudZjnDPTAGejAGegZZwDnMNMmDb6obfY6LHAGOnAGesYZwFG1T+IYcq51mOcM9MAZ6MAZ6BlnANaoZj0M+natwzxnoAfOQAfOQM84A1DL930VjOdah3nOQA+cgQ6cgZ5zBp5V0s56oYfVOsxzBnrgDHTgDPScM2A53zMKjudah3nOQA+cgQ6cgZ5zBh4tYjbjF7XNXocFzkAHzkDPOQP36bLN26A9a85A95yBHjgDHTgDPecM3CfqljOukrUO85yBHjgDHTgDPecM3D3MvG9xxah1mOcM9MAZ6MAZ6DlnwM547/PtC/p2rcM8Z6AHzkAHzkDPOAOghvYchjnXnIHuOQM9cAY6cAZ6zhm45+27jwt8UdrsOQM9cAY6cAZ6xhmAWbPHUVVzBrrnDPTAGejAGegZZ2DVrthtgo2q4fX3PZ97BUHPi5Ne8wi65xH0wCPowCPoGY/gKSHtFwi0SzSfV1a95hJ0zyXogUvQgUvQMy7BkyPZOy/JSlDXgddvgU/QgU/QMz6B5iQuZysJas6aU9A9p6AHTkFn7G/FeZqdNRjDeq+2cEJf8wq65xX0wCvowCvoGa/gOW95ziDsBBdKUOs6zy3ogVvQgVvQM26Bjk470dt/B7R/res8t6AHbkEHbkHPuAWa454Xhs1QkHOt6zy3oAduQQduQc+5Bdf/z9m5LEuP61b6dc7gjwzxBpBDR4cHntgO2+//LA0qCWlBIJRVddru7aqTAgmIIj+Cl9XU19UPmCdiny3XOd2CCroFda9boFlMzaNmoKtYt6Ba3YLqdAsq6BbUvW5Bb5rd0veNJcc+W65zugUVdAvqXrfgamH1yqfCE7HPluucbkEF3YK61y3oqmV5OI36GusWVKtbUJ1uQQXdgrrXLchKVTpnwfcTc53VLahOt6CCbkHd6xZk/arWX9PCYq6zugXV6RZU0C2oe92CfJXY9LuGJ2KfLdc53YIKugV1r1twt6xNHxZzndUtqE63oIJuQd3rFmie/KoBlBzrFlSrW1CdbkEFLYC61y24+zBtYQOeCH22ugXV6RZU0C2oe92C+6tSn6HkmOusbkF1ugUVdAvqXrfgGqOqtjCGJ2KfLa853YIKugV1r1twRbn5niTWLahWt6A63YIKugV1r1twjZLXOA0tLOYzq1tQnW5BBd2CutctuHqQe5yGJ2KfLZc5vYIKu0HrXq/gfs/qM5Yc+2x5zOkUVNApqHudgmutT/vtCm075jCrU1CdTkHF3aB7nYJrffMqGZ+IfbYc5nQKKugU1L1OwdXCVsk4YsQ6BdXqFFSnU1BBp6AGOgV6DltXG4F6Y52CanUKqtMpqKBTUPc6BRcNHZuSYw6zOgXV6RRU0Cmoe52Cq9++eBuiHXOY1SmoTqeggk5B3esUXL0mbb6qmMOsPkF1+gQV9AnqXp+gJe011edi+fvqz5EgeAwcTWNeszoG1ekYVNAxqHsdg7LuEiprtaqs9ZSial8MbynmN6trIP/oYgX8ttc1IM0UZb03S+8YgljEHGd1C6rTLaigW1D3ugXpvvHl+/e6TwvqHvOc1S+oTr+gVmPn7e6Z+6Y2iH7Mc1a/oDr9ggr6BVX1C/7fv/3P//37//7Hv/3nf//Xf/zn//3rXy1/mrTLnukQROE/qaePdDi5J2KZWf6p4wM2yt5G+cy2PSbSjK+Jqdh9cMrzSIQ10SITeeRxjHTMCxLoNJJoyocllglKfljhrRWqH+nhUkry5fWZd000PixviDMN+bfPuozIyqA2yjE3L3fqp5VyHF2+V84z/26spH1gqX2O+Z/a8hh1WTnmgi+Vo8+7sayVfWg3Vvgj/cS8ASPleYWztbKPrngkfVCe99ylPndfTCt05DoHBgkyP6yE0ZU2NkZvsy8VsJ5WZluRdst9SplZK0F0y2ml87y0rY9irBAf1VrJQXTLJx3j6IMG51q+VmiOwTOZNIc7ayWIbjmjWw4pPLVlZczWf8xjuaM/rATR9Vbmm54tmYY48PQoiG76jKkcN/fctrljeVo5z+ge8+q09mh1OYhu+uQ8U7Qlp6lp/iex/JuW5woqp/IISwmCe3wkhMKC3HvntIyMJpXJg2dPba0EwT0+SbqoqfDzPWcvX+Vn3oidKc9+4RHcEgT3+FRpqU1ayNx5Ms6wUKapMZ7nVbfWSBDb49PmK8qz3ab1LcqXzDLm9iF1fFgJYuutzNbCSWavh5DQw6EaBle+3IN6HvJK6tdKo9ZGG/JFHA+Pahjcs1tgnq+k9R/fYg163X56JCbmDehncF+t7KPbJApDBhCSnvuYrb9/0pBmPw/t5fToues+tqsmMgoleaR/rbB0ldJum3T3DystGMzku5unneX3lOSr+X6JiZt8zI2rsxIMZ9NKkVY3c6+HfL7TigxcTYbJdF6SZ62EsZ2LwAKDWQakms/m387Y0uz/Hr1CC2LbP/MiX3lC+tO5hjmtjDm4ioNprpdZK0F0ZwsTK1kaTC5nXdLnOPs56RTys/1TEN32kTmmDDp9yNxp9nNopT77OQqiK6PrbBhCZjzHZfWIinTlMit8WgmiWz+N54UkJH390TW6XM8WNOrjTVMQ3SIjvXyDMg7NDD6vN83z82bpAp9WguhWaS8TjjIJjlY6266MBEk6XQGI9hjpOYhu/fYu/Zh9YeHrC+DeZg0fceEgupMXpME3nt1l+35HUz5Y/tIM+cNKHN1HXd76Bd5Ht9IklTwXzSUM3Y70/RiP6PI+umIlzyVLISeW/zmNyJjUBGRkeE2PEa3vg1ubVEV+POYdWFVKnmEpxCzBam1e9mWt7IMrVmQ6O8UR5Ruat15+m4ugL0mAU3l8Rn0fXLFCUnPpGoXJ5kbFc6CXT0qCNPuGxyfdg+C2j/Rxk9OF6+Z7nR/A+THmebJhPOOyD24Zc3SVwTh3GabTLytjH90izV1GkCFfgLxw+naYneWTEAhpMi14WNlHV6zMiwHzMSOaj+9IL0UeNMm1PAfGsY9umc29kkBKyzJ3qOebFmIlaTAS4Ce7jH10C0/gl5FeWtmZ7Zpx+U6LJFbyqT+sBNEVJGVqc2Yps4n07XazDGkyO5lKqzYuFMzQxKN8DhgkMySJ5mnlrMsUxmJ+GAmabpWvaL4LYcxT+eXdSNByi7T2eTu2kEAbEkph04/8s7xz6mVuirdWgpZbPvIm8nzJ7bxzak71BBcEgQTwjgd0UzBJq98uqkg3O3eqdjNxlR7nYSWYpMnsV4ZEabZdOu9jDq/iUTrb/5G6xOFhJewXZgOVSfScj0hzN1ZGeVoJolvPwWgm3WT8Od/z+EjPScLzMmnLT4+C6Nb55Qluz6+1jtPIZKE076qflyJaI0Fw20dATd41zXup+rfJDfkcsozZws0PK8EcTaxwmeJ6dU6989eKfNkyJkgDqA9epmCOJv1/ynNRckh/IIRzWilt0ljOc1L8sBIElz4smDwnRTIMtG/7nxdjkiC0q0kQWv7MrTUCX9L8pVP6dgpzzwENaYftGZUgtvxJU2Y1lzI1Qs6ZyGw2SRi1PmbiFEzQxMa8GH4eN6T6HYikCz4Gjz4zZ/1Rk2CCJlakd2oShKlxPKd5kzjO8Vl68vogdwomaE3e6czzMcu8dd6Q8MNKQGJpNv52zDT7HF+/3bZMn0ue1Xt2lcEMTT7nLKycpJsfeSqlzugmqdi0Kj2WHUIomKEJFc7Edh/zw5v7yc5ue6ZgZIgX7n14FMzQToYqcwQUqG1ztshZOgVhyyojSH6+o2iGtphb5vt56mBMI+WboJBwPdCSoglan4A9My7iQuu/jASxFVRoQglJbAjA5dMK05xpZc71Edp4glakV5KJlARFOhQxUmSklRm1xEkmXI/XHE3QpOA2l7/GjGVtZyfXz2RhE6xsj48omqBlCe1U9JzDGY1vrz3vPqdUp0OPTiGaoNn8aXEJVLEv1DsHqZnF6QQWg0CbbKrM8J75VLEoZC0WpSeVMareFqOJ20quilWet43cydVJJ2MOntMkzwWLo49RoJLBLO6RaW0+0zq/lVmskL8UnTKYDJOUP9Kup0mhu7lpT/oaNBnkfX7mYMWkFDv/I43gONDxIAn0MyEbmwxmfr+zs6fjQkgyg5dow74BCqaBr6lantPj0+Q5yZPvMUEbCqaEqeLvXarooBeL+5fz26J8f3esCY7UUzBXFJOkGa3zUtG/YTKYOf42KX7jL6BVBtPIRwbcT65fLIYZaMyGN58NP032c31l5qmhUQbzS01qi10B1kPbuabGJ81Nk7ORzUKlqYLJMPOPefLq8+SxyWDm+UiaZ580F5MzhUbzGmYZeqFZBtPQRwZ9uAz6aVFgkuZFInANsFj8S+sDzu/yR6ZlcwYt5fW53gVvJ5if/k7zy9xTKiewLnNg3J9NwVxVLEqjFF6XNjZHnxNuWaJYxYy0TTumcjBXFSs8VZDlKYk4r5y/TIGkcco8Rl6xjDjCUuJnmyl9qmAyeB8yRZN6tclNpw73OdLIKNHkjdJcWpc3+REsO+bQb87vcDCPfaxvDL++Ie9YCkk1zRQGXkjB0crjOeEr8r0I4snEdi121C72JB7fPnzMREQRCGuJMpgMlxveVz5Oi23eTNjmVty7L+NoSfLnMshp8hw5pBV12BbO0frkzzWRF5Ph24EFkubXR06L0m/JpGtOguDlRAuXZrHEDobniuNp8RyxT0xGi+FAgw/k56jQXkwGs+XfJsOxi4Ops8ykkg41AivPNO67yQgDfpmcKwH4CzAZzk5+LEK9mAzXO15XpMRgPvPkUhyqBFcOJtyP5anql6euOsqw00H8pXIw+36sVVW/ViUmD0FioQSZzBY4QcXRVPznwtUyKRMrGS7xkiKO5uW6ijXmu5lYv1axporAHBVOv5vEbdTpNnze0RzdrmiV54rWCuWYd0RLwxSAuU1GE/bX5a16gkXN50S68JjVBpPhp4MP0GPFrI43k+Gn88Nk/DUGE3sxWU/X60wZlva3TEY92y+T4rj5xW0ymvS/rhvmc9gJTf7TRcQ5rZ8Nba6FJTweylE64OeK4mlynjkW5koVK/mXVheHX108p91HER6Q7zPBzkiOcgM/lxrPSso8uo6ZfoBpGEfJAbvWN/y649fvOTRJZ1dhPzZHS7w/FyHPFz7OF5gturys9z5q6QeJqJbhx2Me2A5lkcnw4/lhMv4eg+SANDSZPtTZyNJcZPxbJqO+7ZdJ+QTxF9ADB9mBx1Jv3b2e0GS4egzrvossYeGXviaF0HqW+Qps7+doJfnnIrBYlA9s3rd4SFeV73kYx+vKuCKsIy6sCJ8mhYYFYKcGDfRD8SLzj+Xh02SRCU+SalU4B8PxijOuFTe/ynualN5vSq+ShBdMRh+PeeBpcnafscno4/llMm7pQXpAonPMGZJ0lzNvTX/LZPTx/DI5E9n4CzAZLFnbRfinyfP1hCaD9Wu7It/8iryYlEFYmPAYcwoEfVu0mP1jeb5/TUoIZoJxgMZY7fHKNqzVn4lPs1afvybHhAYZShh6jR5kCx4L937dXizmD52z0S7TaAKL4YaCH9sSBGw+gteCIW3mfsHiX9pc4OvYc5ESBs3bWAcejOlBqmBuNBDAGIcQkADQypFI65GukSg9lrF7kB6YVuYUe+ov5bLyVDMtLf2hfJFCQHzI8DbnVV3wgoB5e5AekODJozRz+Eeh+p03Cae3LvO4PheAWCYkMhzI4D7VvgD2e5Ae+L2p4nzFs6cbMiE44JbhHuQHHjssitkccV4mdLZDnrPUJvG4JQ1qDxME5oHnpo0T1CKTYYLgl8mwM+thgkBQjZM0tDZzkX/PZDTL+WVSOiD8BToebml437vyYjEggZ8bWcQkCclJg2jiOtz91KMl+Z+7Wk6TguoyWEk3DwnAHq3P/9zicjo+eVM+yJm0BZMvbwceeJg8YT80GZLAD5NxGwpSBILRuGTa/o7JIEXw22S4TtujBf6fe4dOkzLXlwFWSoGBIc4Q4O+twXaSX2QwnOK8G3yJ4wukCRkPCVM6yt+xGGQHflo8QfL+AVr8S9ux8u7FhCb/6d6s87uZU/m5FIxp7h5kB35u1DotysiYZm0PbJBBcuCxa6v4XVun3wKB81jGXBa+TQbJgd9buE6TQgRzvO54PV8PkgOP/VzV7+c653V9biES8iimln9lcxcVu7mLx5p95jxvipVvARYWe5Ac0L1eaXbdlGCr17z2/0zdyPc/5kKXwEiGdcUe5AbMvq+z837u/DpNSn/Upqo8VRgggtzAYxtY99vATpM0F1ImYMEB5R7kBn7vCTtNClzNm2GpwZnaHu4csA9Yk+U7jEUmwzHnh8m4Gwq3DlRh1TZX5nI6av87JsOtA79MynvHX0CnESQHHpvt6u71hCbD/Xs/dt6dJqd5mUpK5wPfY5Ac+L0N7xzIOJd5NRmhgEcPkgN2T17ufk/emUuVzlf6NQkIThWD5MBjg17zG/RW/u9MKUu3DL1GkBx43603CBLdcyUZLoboQW7gTsefD+SHyVreTP5aNIhMxi09yA2cq4LHubwqL/bcL/xXTY4gN/Db5LlMdP+igcng7dhtkMnvg3wxGa64vW+KPBfcWk1zvGS87XIEyYHfOyRPkyQT6nmFc4F5xAiyA7+3S56fo/w3cwfDaLClZcT75n/snTxNNhpzyWfOoMBkuOKGuxrLY9tjbvG+xxGkCk6T967G9tz3WGHfY5qXQzOYfNm0BrsaH/seqcf7Hke8lwB3NabHvkfieN/jiPcS4BbE9tz3mONNiiNMFTiTZt9jezP5sqUQdjU+9z2WeN/jCFIF52492Ob23AiX4o1wI8gVnCZhT9pzIxxsWhOzBTh9BKmCjUXcD3aMeB/cCFIFYhJ3uZXHPrhK8T64EaYKzDY3fmwxqy8b4UaQKhhzo9aEF5oXaD63waU3t4Oe7ZgbO+am2Zll7PSsY3+pY3Q8e+7ikBF8nAf4vrvgZhRlMiHjAn8Ntjl4SiRrgrcdpAl6kj5nXog7iXxKHHx3hs2N0wJpdO7zmAnINvFo7v0Bt4M8gdDadzRNZ/+9rrlIU8tnqnCcC1mFZxcv0ZXRCFa/R5gpsBveHlvi0oi3xI0wVWA2vKXnlri8tsTNgYlmyhkcD3MFdsfbY0tcp3hP3AiSBafJe3vac09ce9nANoJkwcak2RNX30y+vJ57y1t+boqr8aa4EWQLzu0o9x4ofuySOtdzgl1SI8gWXJvDvnug7iPM311SxPEuqRFkC8Qk7oGixy6pr8n9LqkRZAuWSd0D9dwkVeNNUiPeSWD2QD02SVHDXVJSAmElX4ga9kDZXVJ5cLxLaoQ7CeyOmOeemXjLzAg3EuCGmKp+65aZ77mS7ZaZEeYKzIYYPWGtW2Zqj7fMjDBXYDbElOeWmRRvmRlxruC5zcNsmYk3jow4VYD7YZ4bZnK8YWYEmYJzk8e1OYLHc/tECrdPjCBRcCZq780R7bl9IsXbJ8bbLoJ7c0R+bJ84EwXB9onxtovg3hzRH9snOsXbJ0a8iwCXyp/H2+dmpGgxfcS7CHCpvD8XlWu8mD7CTIFdKn8spqceL6aPMFNg1sqbXan+zvKC1fQRZApksDuzpvOeRjp3glnHKXS8HUGmQCZZnymQdbR5eX56rqeHdWxHvIdAJtvziuAs/fWiqzmDSHnSM68FZvnYZ76+H2gxBrYvWDTpbqV7lQa5tiLMyX6afcc9voqZ/fsQzP1IT3rIx9fmXoBrNV0qUU8N+DN4MzEoQZF/hcEL16lxrfyxmN5GuJjejiA1IB+gWTl9rK2e2Yb92mo7wtSAWTlNz7XVGq6tismXhdB7uaY/F3RquKAjJl8WQu/1mvZY0Sk9XNFpR5gaMOs17bGiQz1c0WlHmBqw6zXPFZ0arui0I95FgOs17oR+uKAjFsO3g8s19bmg08IFHTH5smQA6zWPFZ3KsKLTST6fCibDt4PrNem5opPDFZ12hKkBs16THys6PMIVHTEZQhpm79szvx+m98XiyzL1nbzPz/R+DdP7c9NFzH2QvH+k93MP0/ti8hXSNHlfH+l9vijNpfflawopzSRzH9neMwe2T/eKyZf5zZ3MTY90bxlhulf+xcvruZO5/Ez35jDdKyZf9hHcydzyTPeWMN07e6a4Ty9JhtljHu379unHTHHONdfa3JIB9EPxToLXkcftZkKTIaflz0T6PBcFVtd28JCXLt/OuqwyMhlymsERD1UvJkNO+4F+LyZf9q+9AmpsMswO0DE7HprH5qeg3zQpU0tht/nFjLc3HmYHfsH+i8mXWc7rlOTF5Mss53Xi9GIy/Hp+zO5ik3F6wE1Bz3RQOhOXbqs0WnxLD7xMk18svqYHhpCAjAR5JYPOQ+zy2fNrHV8GnteEw4vJt4HnLSsSm4zTA++pmxeLL0dDX/NLLyZfjoaeOa7Sy3evEF54yW9fTpgf+JGqe7H4tlJdzgOngi6aDZLns0x3+LUJhemBX1nPF5Mvpw/PzOucfcABKsFpcf11cAzTAzM/fMwtZ0zfnSPnyth85zMn//Z2wvTArzz3i8mXNYPXbHxoMoUbCabjrSf5eLqmB455XwRLKIVZ30y+rBnAuoVf2Xgx+fJ6XtdfXkyGr+fHAt6LyfD1vC4zvjT1FKYLfi2GvpgMXw8uyD5XbN9AI4XpgrlqLE1o7ncYjXT9pcwj5lReLb5sJHhd/H4xGb6dH0v0scl/vJHgxWT4dsTxUuTH0lt+m1CbFtuYkP7SaaS3fQSvezJeTL5gwXdfyOwhrBhBe2vmYa5g7v+UdzEyza2V3/3nOWdBHfl3fks7mAxzBb8mZS8mw3Hnx9TxxeTLatvrBPfF5AsVNPmpDAzCBt9puFRynsIX//vb63lLFkjfQOdWfv7mH4a88mOeaM3thadTnCz4kdJ4Mfnyel4SL28feJwseM8OvVh8SbS9prBeTP7TRFtsMs4V3Mm+Phe7zV2eb9yfwlzBr6Tli8mXPOhbZvXF4stc9DX9+2LynyapY5NhquBXKv3F5EuqYN67UfrcDrh6yxnLufNPwvtm8gUKXtHlutfraHMDEJr8x8x2Xuw1N4HPfmVUMPnCbG3eXSOv51z/vi72GsTnztpif3GbDFMFc8OSdOHieOkrl54l8vPIgNT+upErzft3Oix0pDBVcB5hHee2q7quxaWp8yM+soT3vuSLpwzCLdo4r5z9hxms69xun6MIod9/aT10k7r7ntztMsuS7o8zmnxbf6O5PtfLvIj4Prk7N4w1XWy8fnGvQ6UwWTAfOKZ0vYyxesvXxBZp5iwD3XWMl2cL7gViGWYLzmVF6YnmBR0Ex3jb/FcyiNOcoM70/ryq7z7MKs98344RvJoKQ3++f8f3L0Zq5QK84NU0BoJX8o+3NNa/1g/gExvHtuTyx9QASx45LHkcpmSQA1sljwx23n3WGkCURuzzsD4P5zP0VPKCtyVrlJPzOR+hz2IMS87H0+d8bzqaI8iu5Lx8/QrSV+xc8hH6PBPtpuSnzxm60pz2Picb7Xt3oTwR+5ysz8n5DCtPOW19Pla0tQam5NjnZH1OzucEPuetz1qyRhujlGOfs/U5O58z+Jz373mVmHlTcuxztj5n5zOsPgv2bn1mUzJI2csTsc/F+lyczwV8Lvv3fJW4aoAlxz4X63NxPhfwue58ppb+WN+h5Br7XK3P1fkMC9S57nymr0DtXQNTcuxztT5X53MFn9v2PecV5fItmWBjkPBRWHKzPjfncwOf25vPd8lY19jnZn1uzucGdmj7niubkluDnoRin8n6TM5nWETOtG3bWmIpm5Jjn8n6TM5nAp95+55be5QMIwbHPrP1mZ3PDD7z3uemJWoN4InYZ7Y+s/OZwee+91lLVN/xidjnbn3uzucOPu85TL/jqwZYcuyz5bDsOCwDh+U9h5X1VWkNsOSYw7LlsOw4LAOH5T2HXSWuGlR4zzGHZcth2XFYBg4rew67Skyu5BJzWLEcVhyHFeCwsuewut5v1Tae4InQ52I5rDgOKzDOlz2H1cd7vjfHyhOxz5bDiuOwAhxW9hymvafWwJQc+2w5rDgOK8BhZcthV7+tfVnDJ2KfLYcVx2EFOKxsOewuWf8OeCL22XJYcRxWgMPKnsPaIoPVwnCULDGHFcthxXFYAQ4rew6jZEo2PsccViyHFcdhBXqksuWwu+SiNYAnYp8thxXHYQU4rAQctr7nVYMGyYsSc1ixHFYchxV8a1sOo2p9NiXHHFYshxXHYQU4rAQcdvm6/kK0Yw4rlsOK47CCX2fAYVryamGET8Q+Ww4rjsNwM1/Zcthd8pprQPqnxBxWLIcVx2EFPdhyGOlYtUpuBCXHHFYshxXHYQU4rGw5jMrl66bk2GfLYcVxGEjaz7382+95lcirD8MeIOawYjmsOA4rwGFlz2GcTMnG55jDiuWw4jgMjsMJfGx91hKvGsD3HHNYsRxWHIcV4LCy5TB9z3e04XuOOaxYDiuOwwpwWN1yGClnX77jE6HP1XJYdRxWgcPqlsPukrWNF3gi9LlaDquOwypwWN1z2FVi8iXHHFYth1XHYRU4rO45jPU9D60BPBH7bDmsOg6rwGF1z2E6i10lw7E5eSL22XJYdRxWgcPqnsPyMNG2Jcc+Ww6rjsMqcFjdc1hfLJI3PsccVi2HVcdhFTisbjmMNAN3lQwtLOawajmsOg6r0AvXPYf11YNo9hFLjjmsWg6rjsMqcFjdc9hVotagwROxz5bDquOwChxW9/mwq8TiS445rFoOq47DKnBY3XOY5vRXDVrHusY+Ww6rjsMqcFjdc9hav7hrgE/EPlsOq47D8LxY3XOYrpz01cYPaGExh1XLYdVxGJwEn/urdiUfxZTcboUNeSL22XJYdRxWgcPqnsOukldfdkBPEnNYtRxWHYdVHG33HLZKnJc/upJjDquWw6rjsAocVvcctkpsY+NzzGHVclh1HFaxpe45bLApuQ0oOeawajmsOg6rwGF1nw+7fF7vG/kp5rBqOaw6Dqtgp+3zYavErutW5onQ52Y5rDkOa8BhbZ8Pu3xtWgN4IvS5WQ5rjsNw3attOUy/KlprsgRnxFrMYc1yWHMcBrdCyf+9/Z61xKsGWNfYZ8thzXFYQzt7DktsSz4aPBH7bDmsOQ5rwGFtz2HHGiVT8z7HHNYshzXHYQ04rG057CpZVwlhtb/FHNYshzXHYQ04rO05bH1Nl8/YJmMOa5bDmuMwzNC3/brkVXLxPscc1iyHNcdhDTis7TlMS9SeBPrtFnNYsxzWHIc14LC2z4fp/oJjjVUJSo45rFkOa47DGnBY23LYVWJrm5Jjny2HNcdhmK1uWw5r+h1rfhujHXNYsxzWHIc14LC2X5dUJtGvC9YlW8xhzXJYcxyGGb2257D29BlKjjmsWQ5rjsMacFjbc1h7+gzRjjmsWQ5rjsMw69G2HHbvM/D7SVrMYc1yWHMc1oDD2p7DjsdXtdYzCHL7LeaxZnmsOR7DmUPb8hjR0/cCT8S+Wx5rjsca8Fjb58Wukov3OeaxZnmsOR5DuqI9j+l+Em1pkNunmMfI8hg5HiPgMdrnxXQlhYr7uijmMbI8Ro7HcOyjfV7sGjHY1IBgdYFiLiPLZeS4DG8qoD2XaYZd94vpKGpqEMfA8hk5PkPmof2+sWtHor4FjcWAJ+MYWE4jx2kEnEZ7TluZd9IsdPL7BSnmNbK8Ro7XCHiN9ry2Sia+9ofCE7HvltfI8RoBr9Ge1y6ftR3Ae495jSyvkeM1XL2gPa9pTlgzs93GgGAfL8X8RpbfyPEbXnxCe37TErtGH1pezG9k+Y0cv+EqNG35jVdmh1dOiddORl5vg7EmMc+R5TlyPEfAc7TnOV2/XiurjC0w5jmyPEeO5wh4jrY8x+vr49USeb0NZrtaoeslTPoXLcexsdxHjvsIuI/23Kc7mHUmCatUFHMfWe4jx32EHuy5T/PpVwtN8ETss+U+ctxHwH2034+m83X9JjKWHPtsuY8c94Fs1zxmsitZ86zqO1yvRDH3keU+ctxHwH205T7SrLZmO2GnOsW8R5b3yPEeAe/Rnvc0m5030Y55jyzvkeM9At6jff4t25JtXWOfLe+R4z08wcT7dVDNZmuGd2hNGjwZ+s6W+9hxHwP38Zb7+NB9xKu3BcrmmPvYch877sOjVrzPw62sJytlQ16dY95jy3vseA+uVWy85b2rxKsGCZ6Ifbacx47zcLzgPefpapWOcRjtmO/Y8h07vmPgOw7OB2gL079Y19hny3XsuI6B63jLddrCNNpD9y8N8D3mO7Z8x47vGPiO93w3tG3vSo59t3zHju8Y+I73fLe+a21x+t5BIW/eShPWwHIdO65j4Drect39Xavv8JXFXMeW69hxHQPX8T4vN+zpDPOVxRzHluPYcRwDx/Ge43TN/2rzWpNFVTC35Zjr2HIdO65j4Drec53O58um5JjX2PIaO15j4DV+PT/Amj2B3SYc8xpbXmPHa0icvD8/cO2hV5+hxcW8xpbX2PEaA6/xltdYMwlXyVjX2GfLa+x4jYHXeMtrrJkD3VFVmvc95ja23MaO2xi4jff5Ot2rV3TWtN4/zN855je2/MaO3xiYiF/PE3DS2ZPOpuC7jzmOLcex4zgGjuMtx2mJOnPE3f0ccxxbjmPHcQxjZd9y3O1rcT73mN+65bfu+A0ulW99z286S1aygB3QPea3bvmtO37r8O30Lb9piXcNoOSY37rlt+74rQO/9eBcQTM+s+53qljn2HfLcd1xXAeO61uOYx1hrpMNV03gyTgGlue647kOPNe3PMfX6SxbE4a9fT3mum65rjuuw1uH+57rnqe1Vk1AAE2ejGNgua47ruvAdX1/7qDZGjDsX+0x13XLdd1xXQeu61uuU99Z+3tYBesxz3XLc93xXAee61ueu0vclRz7bHmuO57r+O3s83TXeTFW3+GJ2GfLc93xXAee61ueY92D3541gK8t5rhuOa47juvAcX3Pcdrj6HeuX5t+fWRrqDVmGIF6zHvd8l53vNeB9/qW9+6aXOdS4Ik4Npb3uuO9DrzXt7zH+v2vkhlWR3vMe93yXne814H3+p739Pu/ToVoDSDqMfd1y33dcV8H7uvBeQU2NdAa4cygx9zXLfd1x30duK9vuY/1m9CTE6tGtgZxDCz3dcd9Hbivb7lPa8D6DehqCqxd9Zj7uuW+7rivA/f1ff5OV4w0e076F9pBzH/d8l93/NeB/8ae/7TlaUu88vYFngxjMCwHDseBAzhw7PfTrRUCXTHge88/PBnGYFgeHI4HB/Dg2PPgVYNr37uvQcyFw3LhcFw4gAvHngs1T9+TqQnDisGIuXBYLhyOCwdw4dhzoZZ81UR3aEM7iLlwWC4cjgsHcOHYc+G9J9zUgE0N4hhYLhyOCwdw4dhzoea8NLuqWRfNbeve4lVDvmqIluMYWW4cjhsHcOPYcqPWhK8dv7q3HFpqzI/D8uNw/DiAjMaeHzUjuXJjXbM0165YaLExTw7Lk8Px5ACeHFue7Gu23jWDAZnJEfPksDw5HE8O4Mmx5cm+MpJaA4bM5Ih5clieHI4nB/Dk2PLkXfJVA3gi9tly5HAcOWDMHft9e8O+Z1NyzIfD8uFwfDiAD8c+H7hanO70xvn9iPlwWD4cjg8H8OHY8uFVokYbS475cFg+HI4PB/Dh2PLhXeL5d16Guf4Zoh7z4bB8OBwfDuDDsc8L6vet+3uu/fbwlcV8OCwfDseHA/hwbPnwjsHw33fMhcNy4XBcOLC33nLhXXLx7z3mwWF5cDgeHMCDIzhPcZ1m0JJtTWB/z4i5cFguHI4Lx82FdGy5sF/77q9TLfBEFINpDEqm48mD81mws3/v9jQL+ExHyIHTmC25u5LB5/fzFVcvu6K/dlP0tbehr9X2vtbEIOM0VRrCGiYbmycnEgh+07Hf73edDNAarBpmeDshJ06jtgYuRgk82Z/H0L2Oh/q+YnNn7+TJOAbZxuDJifNZsLNtH8Xu19ca2RrEMcg2Bk9OnM/edoJ745Kpgdaor9xaL1qj9d/runFDy3GMio3RkxPns2BnG6OV7ekr29NXjqXrTvTrlMX69yv73yt8ayFHzkJtDV0MC3i65ci7JnoCocATcWyqjc2TG+ezYGcbm+vMQ9OYwBOxz9X6/OTG+extZ8+NuhNd+9arBhD1kB+nUVODJz/OZ8HO6zku7dma/oX+I+TIadTWwMUAW/iWI7vu1tZ9Ytq3Yg1CnpxGTQ2ePDmfBTvb979q0HW39nUKGvqPkCunUVsDFwOCGOz3BepeCh1HSP9COwj5cho1NXjy5XwW7OxjoOft9S+WHPvO1vcnV85nbztbrrxLbt7nkCenMVPykyfns2Dn9V4FHTMJWlzIk9OYLdn53MHnPU/SVaLWAJ6IfR7W5ydPzmfBzvY96850vblDR2v0PeTIadTWwPkOHJn2HLlq0HUPrI7eMFqnmCeT5cnkeDIBT6bXe1O0ZK1JX/nGvrJ/feXc+sqE9TvvRCnmzmS5MznuTMCdacudXXeuXrcXNV+DmCuT5crkuDIBV6YtV2oNuu7qLHoHCdY9joHlyuS4MgFXpuDeu2RK1pr0O7MlT8YxsFyZHFcm4MoU3H+nN7Hp+181GdBSY65MliuT48oEX33acmUf111w6y+8/5gXk+XF5HgxAS+mPS9eJRfvc8yByXJgchyYsP3s9xkuUlWftSZdT9frTHjNBsdi73FAbGJeTJYXk+PFBLyYtrw4dM6l9xevGtsaxDGy3JgcNybgxrTlxqFzrpZMTcadi5En4xhYbkyOGxNwY9pz43WCVaOvMYCvM+bGZLkxOW5MwI1py41jzbWGnjNTigd6TzE3JsuNyXFjAm5Me26sds6kNRgJvpWYG5PlxuS4MQE3puAcsc7qtAYQ/ZgXk+XF5HgxAS+m4ByxnckOmK2lmBeT5cXkeDEBL6YtL441Ux06TySIdsyLyfJicryYgBf3OhNa8nW+FKMd86LVmSCnM0GgM0F7nYn7HKlGG77zmBetzgQ5nQkCnQna60xolIfOUAnec8yJVmeCnM4Egc4E7XUm1GcteehMFeYHsd4EWb0JcnoTBHoTtNeb0BKHzkyvk6xYgzAGVneCnO4Ege4E7XUnrpOsq2StybhPMlGsP0FWf4Kc/gSB/gTt9SfGmpEOnaHq/AHmC7EOBVkdCnI6FAQ6FLTXobhL1r96hi7Bk3EMLAc6PQoCPQra61HcJ9c0+nrSCdpBzIFWl4KcLgWBLgXtdSm0xKEz1o5PxL5bDnS6FAS6FLTXpbh93fgcc6DVpSCnS0GgS0GBLkUfpuQBGe1Yl4KsLgU5XQoCXQra61JolMeaIw+dhXWsQey75TunT0GgT0F7fYqhZHGdM4Kox1xn9SnI6VMQ6FPQXp9irDnxWPQ9YFYe61OQ1acgp09BoE9Be32Ku0StAfRxMcdZfQpy+hQE+hS016fQKGuLM9GO+c3qU5DTpyDQp6C9PsUoWuLyuUDJMb9ZfQpy+hQE+hS016e4Szz/Tr23TQ1i3y3HOZ0KAp0K2utU3Gfnkn/fMcdZnQpyOhUEOhW016m4vmudVet7xz4p5jmrV0FOr4Iy9s5bntP3rqe4RoWvLOY5q1dBTq+CQK+C9noVd4vbRD3mOatXQU6vgkCvgvZ6FXp66/K5XC1u1QQthDGw+hXk9CsI9Ctor18xdMezzllNyWEMrH4FOf0KAv0K2utXaAyG7r02T8Q+W45z+hUE+hW016+4fVXfBzwR+2z5zelXEOhX0F6/Qk+yacnj3lNNsX4FWf0KcvoVBPoVtNevGJqb0DMVeo4MfY+5zepYkNOxINCxoL2OxX1+zNZkwPperGdBVs+CnJ4FgZ4F7fUstAZDcxN63iBhDeIYWI5zuhYEuha017W4S9QzdfhE7LvlOKdrQaBrQXtdi7vkjc8xv1ldC3K6FlSwvwjugbnOka2oL9+BYWN9C7L6FuT0LQj0LWivb6ElDt0/rmdoTQ3iGFieczoXBDoXtNe50JKH7ifXk6xAlLHeBVm9C3J6FwR6F7TXuxh6kuE64VS0RvBkHAPLd073gkD3gva6F3rCSWswIHMQ616Q1b0gp3tBoHtBe90L9X3oGQr8TmOus7oX5HQvCHQvaK97cZc4fMkx11ndC3K6FwS6F7TXvRh685CSBb6fmOes7gU53QsC3Qva616w3rKkZ6WuGsDXFnOd1b8gp39BoH9Be/0LPcU19NyIjnk42sZ8Z3UwyOlgEOhg0F4HY+g9T9e5oaI1gifDGFg9DHJ6GAR6GLTXw2Dt73WsY61BgyfDGFhdDHK6GAS6GLTXxRisJWtN9GwdPhnHwHKe08cg0MegvT7G0HMi2u/rOMBYgzgGlvecTgaBTgbtdTK0ZK3J0HMk0OvGehlk9TLI6WUQ6GXQXi/jLnG9heuGMaxBHAPLfU43g0A3g/a6GffJpdUCu96Bhk/GMbDc5/QzCPQzaK+foSUOPZGi7cLUII6B5T6no0Ggo0F7HQ1+nFzSmsBua4r1NMjqaZDT0yDQ06C9nsbQzKGe4tG30KFHijnQ6mqQ09Ug0NWgva4Gu3NB+lYGPBnHwHKg09cg0Negvb6Gnlga1wkmPa0DfWLMgVZng5zOBlXs2fYcqPmdqyZ6pkr/ooU4FpYHne4Gge4GbXU32nHYk0rj+gv9QsyDVn+DnP4Ggf4GbfU32vGd/181GfgWYh60+hvk9DcI9Ddoq78hJeq5kfUVYtRjHrT6G+T0N6hif7Lf33ckjHrDXfex/gZZ/Q1y+hsE+hvyf+991mhfZ2bgidhny4NOf4Mq9mA7HoTTOVfU4YnYZ8uBTn+DQH+Dtvob8H6/viftffF9xxxodTjI6XAQ6HDQVofjqsHtOz4R+m51OMjpcBDocNBWh0Pfs56NMe871uEgq8NBToeDGnqw577x/K6h5Jj3rA4HOR0OAh0O2utwdN0xfvmsvS2vfx5gIY6B5T6ny0FwgzFtdTlmSd+a6P5t80QcA8t7TpeDQJeDtrocULKezmnwROyz5Tyny0Ggy0F7XY7rrMt16ma1A9gBFOtzkNXnIKfPQaDPQXt9jlWDWeL6qydPsAZxDCznOZ0OAp0O2up0QIl61mVTg5jzrF4HOb0OAr0O2ut1rLMs7bhPT6y/8BXGnGd1O8jpdhDcxURb3Q4p+Xl6QtsBtMSY86x+Bzn9DgL9Dtrrd3Tdj9XWd5/0L3z/MedZHQ9yOh4EOh601fGYJX1L1DNxeqoCdknFeh5k9TzI6XkQ6HnQVs9DSn6enkhaI3gyjoHlO6frQaDrQXtdj1Wy1qQdmzMNsb4HWX0PcvoeBPoetNX30BLlr54wwDrHvlvOc/oeBPoetNX3AF/Z+xxzntX3IKfvQaDvQXt9Dz1FsUpueF4v1vUgq+tBTteDQNeDtroeGmX5609RxLoeZHU9yOl6EOh60FbXQ0sUTNLTFGlTg9h3y3lO34NA34P2+h73aYmCNZg1gifDGFidD3I6HwQ6H7TX+VjnMqTEVYPrzEKBJ8MYWL0PcnofBHoftNX7aMd1LoOxBrNG8GQcA8t/Tu+DQO+D9nof15mEvlpi0Rpg3eMYWO5zeh8Eeh+01/tYNZglrr/+lESs90FW74Oc3geB3gdt9T6gxOeJAaxBHAPLgU7vg/B01l7vY+hcR3dV6CwMZiCx7gdZ3Q9yuh8Euh+01f2Qkld25dqH37RG8GQcA8uBTv+D8NzPXv/j2o9/rHZQ1xgIu6li3Q+yuh/kdD8IdD9oq/sxS1ol6o5hfRsDnoxjYDnQ6X8Q6H/QXv+j65kVfRtK5ebJOAaWA53uB4HuB211P1rSPeqqwsJYcuy75T+n+0F4Un2r+wElf99/AvKM9TzI6nmQ0/Mg0POgrZ6HltySnghgLDn22fKe0/Mg0POgrZ7H9HGVnNZf+N5jzrN6HuT0PAj0PGir5yElXVH27znmPKvnQU7Pg4ydLefdvi7fga5jPQ+yeh7k9DwI9Dxoq+dxl5z1L0Q75jyr50FOz4NwN/VWz6OlRdV3DaDkmPOsngc5PQ8CPQ/a6nncJR9XS4MnYp8t3zk9DwLNBNrqedwlXjXAJ0KfrY4HOR0PAh0P2up43CWWXcmhz1bHg5yOB+Fuu62Ox13y4voEu2FjHQ+yOh7kdDwIdDxoq+Nx+3qVXOCJ2GfLb07Hg3C31VbHQ0pKWqLWAJ6Ifbbc5nQ8CHQ8aKvjcZesPsPepFjHg6yOBzkdD2L0YMdrULLe1wIlx5xm9TvI6XcQ6HfQXr/jvgFG33OCJ2KfLZ85/Q7CXTZ7/Y7rBpirBuBzzGVWt4OcbgeBbgftdTt6HbZkU9fYZ8tjTreDQLeDtrodLWkmqG5KjjnM6naQ0+0g0O2grW6HEN/qPbUGpuTYZ8thTqeDcCfJVqdDS7xqcMAOoFing6xOBzmdDgKdDtrqdEjJ6Y+pgSk59tlymNPpINDpoK1Oxyxp5d/1NAOUHHOY1ekgp9NBoNNBW50O9fkuGbKdsU4HWZ0OcjodhPs09jodd4nsS445zOpzkNPnINDnoL0+x7oVVUueNYEnYp8thzldDoJbU2mvy3Hdw6pZDyw55jCrx0FOj4NAj4P2ehx605vWwJYc+2w5zOlxEO5+2OtxrJLbQVcN4InQZ6vHQU6Pg0CPg/Z6HFfJrWgN4InQZ6vHQU6Pg+D2RNrqcaivd8mwXz7W4yCrx0FOj4NAj4O2ehyzpFXi8D7HHGZ1OMjpcBCuhm51OKREtiWjzzGHWf0NcvobBPobtNXfaGn5rN8zw+6kWHeDrO4GOd0NwlsQt7obWvLVoxywQy/W2yCrt0FOb4NAb4O2ehtSsvaebVNy7LPlMKe3QTjOb/U2Zkmr5DVawiplrLdBVm+DnN4Ggd4GbfU2rpIP0vcNbTvmMKu3If/ofAYO2+ptXL5eJQN7xnobZPU2yOltEOht0FZvQ0pkLVFrAE/EPlsOczobBDobtNXZgJLZ+xxzmNXPIKefQaCfQVv9DCl5mJLx/rlYP4OsfgY5/QzCtcStfgaUeGkAwxOxz5bDnH4GgX4GbfUztORLdRj0LijWzSCrm0FON4OMnf29yFeJw5ccc5jVyyCnl0Ggl0GBXoaue/Im2jGHWZ0McjoZBDoZFOhkXC1M1wChbcccZvUxyOljEOhj0FYf4ypRa3DA3v5YF4OsLgY5XQwCXQza6mLMkh4lF3gi9NnqYZDTwyDQw6CtHsYs6VFygidCn60OBjkdDAIdDNrqYKjPEvWi7xueiH22HOb0Lwj0L2irf3GVfOhqApxTjnUvyOpekNO9INC9oK3uhZSUjM94g2Wsd0FW74Kc3gWB3gVt9S4uXw/Wrwvec8xhVueCnM4Fgc4FbXUuLp+vkiEfFutXkNWvIKdfQaBfQVv9iqvEo6dNybHPlsOcbgXhWf6tbsUsCUuupgeIOczqVJDTqSDQqaCtTsVVoipw2ZJjny2HOZ0KwnPsgU6F7v6/tL/ge445zOpUkNOpINCpoECnQu9uH7uSY58thzmdCgKdCtrqVEi0dTfA8CXHHGZ1KsjpVBDoVNBep6Lrjve+epKOJcc+Ww5zOhWE5xq3OhWzpLVyojsi4KuKOczqVJDTqSDQqaCtToWWCDWAfjvmMKtPQU6fgvD82lafYpZkSsZbeGNdCrK6FOR0KQh0KWirSwElr7HqgH475jCrS0FOl4LwpNRWl2KWZEo+8D3HHGZ1KcjpUhDoUtBWl0JKHFqij3bMYVaHgpwOBcE5Bd7qUECJWgN8IvKZrQ4FOx0KBh0K3upQaImVNS9mSo58ZqtDwU6HguGEBG91KKDkojWAJ2Kfk/X5yWEM+hK815dg3cl6RRtLjn1O1ucnhzHoSvBeV+IqeWi0CzwR+5ytz08OY9CT4K2exHyvj/fc4InY52x9fnIYw75U3upIXL1nOnR1EJ+IfS7W5yeHMehD8FYfYpaEo+SsCTwR+1ysz08O4wM9CDhMV/u198QnYp+r9fnJYQy6DxzoPui9zkV3Ogx4Iva5Wp+fHMaw24sD3Ydq15/h9lSO9R7Y6j2w03tg0Hvgvd7DSNcq/yoZ3nPIYWx1HtjpPDDoPPBW5wFKLD7aIYex1Xdgp+/AoO/Ae32H+wbRa48FPBH7TNbnJ4cx5NV4q+sAOxuuW1Thidhntj4/OYxBz4H3eg4jmZJxxxLHeg5s9RzY6TkwzIZ5r+dwl6x7IOE9hxzGVs+BnZ4Dg54D7/Ucxr0j7VsyjpIhh7HVc2Cn58DANrzVc7hLvGoA0Q45jK2eAzs9BwY9B97rOdz3sz72xmHUQx5jq+fATs+BkXH2eg5D16GvvZB6X2eDJ8MYWD0HdnoODHoOHOg5rNs29IbYce3Ww7qHMbB6Dez0GhhHpL1eg94MS5o/gV411mlgq9PATqeBQaeB9zoNpHkTvac5Y11jny2fOX0GNrEL7uXVHajaAgc8Efts+czpMjDoMvBWlwFKZB/tmM+sHgM7PQbGcWGvx7Buhr33geotS/cuLo51GdjqMrDTZWDQZeCtLgPsdU4+6jGnWV0GdroMjKS512UYumdO7zS5dyhyrLfAVm+Bnd4Cg94Cb/UW7p2ofPkOT8Q+W05zOgsMOgu81VmQ97ta2DrbZHqCmNOsvgI7fQUGfQXe6ytc97Kqzww+x5xmdRXY6Sow6CrwVlfhLvGKOpQcc5rVU2Cnp8Cgp8BbPYU7yhp1grYdc5rVUWCno8Cgo8BbHYV7vnW9Zyg55jSro8BOR4FBR4G3OgrwNZkexbbxmNesngI7PQUGPQXe6ilotPUeVhv1mNesngI7PQUGPQXe6inAncObNh7zmtVTYKenwKCnwFs9hSsvqvew3r77OWisr8BWX4GdvgKDvgJv9RVgxq83AWPJcQwstzl9BQZ9Bd7rK1z3ser+hDtTy7GuAltdBXa6Cgy6ChzoKuje2EN7mgRPhD5bPQV2egoMegq811O4S9b7WKHkmNOsjgI7HQUGHQUOdBR0B4zeOdQg2jGnWf0EdvoJDPoJvNVPgBKTj3bMaVY3gZ1uAoNuAu91E+47Zwv6bvKmsW4CW90EdroJDLoJHOgm6O4uvQ0FMnmxbgJb3QR2ugkMugkc6CZcJV/37sITsc+W05xuAoNuAu91E65bb3XHKswEY90EtroJ7HQTGHQTeK+boCWOtol2zGlWL4GdXgKDXgLv9RL0nt07ZwxfV8xpVi+BnV4Cg14C7/USWO9b0NvNGkQ75jSrl8BOL4Eztpf9vWrtysh/Syb4rmNOs3oJ7PQSGPQSeKuXcJd41QCiHXOa1Utgp5fAoJfAW72Eey1Ab+xHn2NOs3oJ7PQSGPQSONBLUDUiumoAT8Q+Wz5zOgkMOgm81UnQtT240ReiHfOZ1Ulgp5PAoJPAW52Ee83nqgGWHPts+czpIzDoI3Cgj0DGZ1w551gfga0+Ajt9BAZ9BN7qI9wrqXpbJWHJsc+Wx5w+AoM+Am/1Ea59CoPY+RzrIbDVQ2Cnh8Cgh8CBHoJy+FVygSdCn60eAjs9BAY9BN7qIVw+s+7q03PzMAeJdRHY6iKw00Vg0EXgrS7CtRfnujdZ9REq1j2OgeUzp4/AoI/AW32Ea+fToTf1XbcWJ3gyjoHlNKeTwKCTwIFOwnVrccGa4M43jnUS2OoksNNJYNBJ4K1OAux805pA2485zeojsNNHYNBH4L0+gt7UPK79hlhy7LPlNKeLwKCLwFtdhGtX53VPMkY75jSri8BOF4FBF4G3ugiwt7JsSo59tpzmdBG44Dez17W6Wpa2NGjjMadZPQR2eggMeggc6CFcJa/vvWPJsc+W05wOAoMOAgc6CNdt1HozNz4R+2w5zekfMOgf8F7/QEscVw8DPsecZnUP2OkecEEP9rpW133X+lfPf0C/HvOa1T9gp3/AoH/AW/0DPX0Bt06XTQ3iGFhuczoIXPCb2a+DdlOD6zwInEDhWA+BrR4COz0EBj0E3uoh6Hmf6/7r0Xc1iGNgOc7pIjDoIvBWF+GqAV83cF83csOTcQwszzldBAZdBA50EXTGcJ2eBLaJec7qIbDTQ2DQQ+BAD+G6cdudnuRYB4GtDgI7HQQGHQTe6yAM9blpBl/vBC7wZOi71UFgp4PAoIPAWx0EOL+ptw+D7zHPWf0DdvoHDPoHHOgfrGgnpWnIQcS6B2x1D9jpHjDoHvBW90CjfEf9qgFEPeY4q3vATveAQfeAt7oHUoOVydX+voHvMb9ZvQN2egcMege81Tu4SkzayzZ8IvbZ8pvTOWDQOeCtzsF1avYuecATsc+W35y+AYO+AW/1DW6fNeoMJcf8ZnUN2OkaMOga8FbXAEoevo3H/Gb1DNjpGTDoGfBWz0B9vW6XNj7H/GZ1DNjpGDDoGPBWxwDaNPu2HfOb1S9gp1/AFVvqfj20F/yqbLRjfrN6Bez0Chj0CjjQK1AFnSvaG99jjrN6Bez0Chj0CnirV3DfIq4ZfFgXjfUK2OoVsNMrYNAr4EivQG94WHs0E5Yc+2y5zekVMOgVcKBXoLt+Dz2HD/13zGtWr4CdXgGDXoH831ufk94tsU5taDYbVqlqzGvV8prTLZjP3nb2vKb3FepqVYWox5xmdQvY6RYw6BZwoFtw3ZSo95lD1GNOs3oF7PQKGPQKONAruO4v1/uRGjwR+mz1CtjpFTDoFfBWr0BL1BqYaMd6BWz1CtjpFTDoFfBer6A/byeCFhbrFbDVK2CnV8CgV8BbvQK4o/26KwieiH22fOb0CRj0CXivT6C3E903o8N7jrnM6hOw0ydg0CfgvT6B3od01wBLjn22XOb0CRj0CXirT3Dfya57cvWGJqCkWJ+ArT4BO30CBn0C3uoTzJJWiXpTtsYAaxDHwHKa0ydg0CfgvT7BdcPHdSe7xgCfjGNgec3pEzDoE/BWn+Aq+b5n5bodHp6MY2C5zekTMOgT8F6f4L7tRG/Exydi3y23OV0CBl0C3uoSgK/sfY65zeoRsNMj4IZvb3/uU29I112i2MfF3GZ1CNjpEDDoEPBeh+C62UXHMtijGesPsNUfYKc/wKA/wFv9gavE6x6OknwNYm6z+gPs9AcY9Ad4qz8g/36Nojob1n1t2EZjfrM6BOx0CBh0CHirQ1D7dXr+uov9WyPI+MZ6BGz1CNjpETDoEfBWj+C+OaCYGuDtCRzrErDVJWCnS8CgS8CBLsF1F/vz/gaIQcxzVp+AnT4Bgz4BB/oEeppLTzoVaIExz1ldAna6BAy6BLzVJbhL1vP9UHKsR8BWj4CdHgGDHgFv9QjgHno9S9fgidBnq0PAToeAQYeAtzoEWqLWwEQ71h9gqz/ATn+AQX+AA/0BPS9Y9N75BE/EPluec7oDDLoDvNUdgLv2tYXhE7HPluec3gCD3gDv9Qb0xOJ9wz34HPOc1RlgpzPAoDPAW52B+4zkVQMoOeY4qy/ATl+AQV+AI30B6/N9arPAk7HvluOcvgATvr3gnOh1l/4frJGpQcxxVl+Anb4Ag74A7/UFkmqt6L0dt94APBnHwHKc0xdgQjuL4/7fv/3P//37//7Hv/3nf//Xf/zn//3rXzV//iTiz5g7rilTmykaqvOfaxrSU5QG+WbVGthbGZ8jH1N8Oh1za+aLlfpqRQhYJqHzmlYBH7HSy+BahvTlmK+nRq9WZhuRYE69jzatUM9T47WkuekRrPTYSk8f+d8+es1ZgvOnlY/YyCO3SgcNuq3QS3TFSq3H3DnfeYqbtPzpMo0ZEvDZTKFPp5foTis8l59GFirr04owq7y6Y7SMO9SJXqLrrByfMaRapUw5UlOXl+iKFfG/lDLHkpSnFZKayDBPY2CmWzUQIiujysy719rmXetipYx563ovhxmW+SW4I31mENKRzt0yf6o0ZZJOJfciUzlYnFX5hL2VLC829yNPZe0yjcggytJgZBQn2L1E/BJbMfKNbZfhZ4gVktjKtyD/O/f1oJWX2D6t5PaZ8hllhiXjOqdqLURh6acViYv8dlo5pvLVmEuPo9TbSn8Pbp5WxAH5IPNLXfpbcMGKNJs/NX2O2S8ctefasY/qb9GVp6Z84GymWTwSK1UG2zzv/R3FePQW3ePDM4s7kkT3KNNKm3XJEqpm3nR/a7ldejaxMg8ASIdyWTkGSQkZ6jLe+oX+kTie4mg0DxKIldJLmj1d7pjHUkWIyMpsL2fCWB5c0S2TbMUHpJ7x1i906WXnwUeeU6b2p4yPBCTXqVqDaUTp9F6N5LMqXYYB6VzESJ5VkfqPghd9qHzE3gp/2ry0W/rwMs+/ipU2RdObWBauuDtdlZmIrJx1GS1JjySv6DjrIu9LWk2GfkGlJ35Z6fKutOlKe5EaSscJVt6CK31SqvI953m+ov6Rf1mPQ6LbpZ+TFgBW3qNrG12WpiwAV6ZGa4fmokIV0QfQJphTqfN+zthIeusXZNTI0rhGz2lmFeVfSn8lPcKpkQnjompchF/02S/IpK5n6brL+Yp4bss+8KSTRPxvWKFPKtL80ryQGtQqxMp7vzCyoIsMyfOaQzHSZEQTEJGmXE1YfsRW2kaZlzLOObpYkW/yxId6NEiRqnDG/j0f8ikm6WLP+7PEIfmKSprykSMfzFCX/NZypb13mZvMA/xzP65YaadE4Uy6F9gKzPmt5R4a3LmwXOYQnY8kn5RUTjzCury13KcVGfhLO+807D1ntPISXZYuST5GeeHyFTNNAJLWNm/ClraMBytUoiOywi3TIRWQEa1OK9Lm5lXAXeKCTbe8RJfLR+AnSQc1T7anP218ZAgRThU0zAObbnmJLkvZMt8dQsx19gtiJc/p57xoIIOgjlh5iS5/gaHPDkrmQX9aF6vSDKWv7AdedqAiH7+tSHDbR4azqUAvwEuQZ1ItkMjIkWQmdKQkIwBNXhb3hnxHEiSGMVr1QfZWlBeko56XP7QZbEHcaedgdKi+BVeaap4EJG7JF3y+6CxYWevMNkEGhOv7PEJocp5WK6Xl04r0lNL3ySwgpYFxeQkujeVRHvO5s+nOc+rijvTWDI3u5yztjIu0s+8M4LQiTVc6YhzSXmdpwrY5yXRGPoXWzs9I/s8J8iS2GAaj11kaf5vLkCkjp3NOM+d6JedJUjCP4NdZ2tNK/XoklesJd/vz2yyN+kfajPCFFN3nbERYV96XsIuMI7juy2+zNLHyJUNhLxkKZ13KWZcJYzwgum+ztDkHnrME+azzFK6eX4AEO83v2uSg+G2WNufAs+0eXSbSMtRPK6XX+Yak/wSQ4rdZGs+hfno0Zj9Zp0dtfgrSf86jFBiXt45BRsZ6SCcrLyTLfFysyKyCZsdbKt59xm/TNNZRWgh5ihqv/kUGkamJAlV5m6VZI9JchBSlY5igWuT/QdN9m6adDqU5AZZ2Nl9R/xwyPZMOUxoLwwYkfpumncGVBpbnLSt0WplZiqlblQ9YGeC3Wdr5nmXmIMVPWJkDwCGDkLBDlfcNUXmbpNHkwikBzPM/ddZkcJZ3KpN86aEgKm+TNNv887TSzi5KXjIjLrzN0daX2GcPcJQ6X9CswiFvSXg3YVX+Tq/Qv73CPBw5Z4xg5S22YGUq9klsv9koaX4CQDAWvc3RtLfs8j+j5D90fIp8y/JC+pxDgpH3LvfsuOdI2tO0cfpD87pEvM+O32Zo3zGkzwFQmth4WkF/3putNHZhA4EOeVGnP9JtnyfBDzxHx29TNLFSpEuuMpYevZ1RSVInmiklBs0y7m9TNPmcpaELf87JkNACTWQtbcyVtQPvoelvU7RJCzJpmFMy6afFI/nnOrU4D2kvBY28B7ef2gg0u5MxjcytPqPOybDALlh5hwVhlnk9S5GOhP/Qd1CUbyjNe50LWHlvuKa1oBE8JdrfZmiu3ZZPmqN8lrgmnIr0txna80sUK7PNSQNqcxGSwMpfZIX5JdIa5SVOMjWBNtffZminRzItLLNDOVPU4pv8E0nf2TG2wQwt"} |  |  | - |  | - | -
[14 empty] | {"index":139,"total":402,"filename":"Advanced_Project.ifc","data":"vsA9nu8S4Be1zV6/Bb6AAF9Acr7AM4smo6vWb54vIIEvIMAXkIIvMN387dq55gqI5wpI4AoIcAUk5wo8K8YMNtdcAfFcAQlcAQGugORcAVufn/XaehqUoNZxni8ggS8gwBeQnC9w9zBbu57ILlLzBcTzBSTwBQT4AlLwBcwjymYYm13NV2e/0nM9p9Z1njsggTsgwB2QlDugOe0c9/m5nYbAeVvNHxDPH5DAHxDgD0jKH7iZ5rsEYxpzA7x/a96AeN6ABN6AAG9Act7AtDOJw+jalJSgrgOv4wJvQIA3IDlvwJjmuwRr3baSdPiyrgOv5wJvQIA3IDlvYOe4/prtMylBXQde1wWugABXQFKugJHFjWmuJYAvatu9rgtcAQGugKRcgYeivkvgxnGt6zxXQAJXQIArIDlX4Knly0oAX9Q2e10XuAICXAFJuQJj7vjys2U51zZ7XRe4AjJxBUv90yzHpwSQc63rPE9AAk9AgCcgKU9g5ej6uJYAvqht9rou8AQEeAKS8gQgRxvX+EVts9dzgScgwBOQnCewe5b1NF/btZ7zPAEJPAEBnoDkPAHr03et26wKr3RrroB4roAEroAAV0ByrsC0WXW/ZGmclaCuA6/vAl9AgC8gOV9g52glWNut3f5wR1xzBsRzBiRwBgQ4A5JyBizH9ddsn0kJyjrwvAEJvAEB3oCkvAHLeW0+rQSXlQS+rOvA673AHRDgDkjKHbCc19+t+0x93XcSxsK1foI21XXj9WDgEghwCaTgElhJLG493EHVXALxXAIJXAIBLoEUXALL0fhioL5rLoF4LoEELoEAl0AKLoGt77s/MLxHqbkE4rkEErgEAlwCKbgE9/mN1TaWtbbZ67vAJZAT+0uu77rd9AXes9RcAvFcAglcAgEugRRcgu0nsfv+mPCar+YSiOcSSOASCHAJJOcSGFGa7vMb/KK22eu5wCUQ4BJIwSXYe5q5X6bPaXWAJaht97ou8AkE+ARS8An26LL2duO61nWeTyCBTyDAJ5CUT6C17Gsdx3Wt6zyfQAKfQCCWneR8gnt0SdLHa13n+QQS+AQCfAJJ+QTPeL5LgGWtbfa6LvAJBPgEkvIJYBbtcXTVus7zCSTwCQT4BJLyCcDmK/btWtd5PoEEPoGcOErzc7p7xZjR5lrPeT6BBD6BAJ9AUj7BvU4/67b1NCxBbbvXc4FTIMApkJRTcPewe1w/rBWpOQXiOQUSOAUCnAJJOQXPbGrje3ujzb7b/7QZZyvMiSUr68RzDCRwDATjRaUcA/PouFnm/ESxlZpjIJ5jIIFjIMAxkJRjoDntHLe+gxuCmmMgnmMggWMgENtQUo6B1bLmaCWAL2qbvW4LHAMBjoGkHIOHWb9Pjn3Otc1etwWOgQDHQFKOgdXyXesYSaDmGIjnGEjgGAhwDCTlGNw23+2NfbLWbZ5jIIFjIPjOIeUYWI7WzmPaPA/eSzXPQDzPQALPQIBnIDnP4O5h1uPgrLrmGYjnGUjgGQjwDCTlGdzj+vFSwy9qm71+CzwDAZ6BpDyDZ0a5ax9qu9ZtnmcggWcgwDOQlGdwz57W190sWus2zzOQwDMQ4BlIyjMA0nT0g6x5BuJ5BhJ4BnLhKP3Kb2c7n7nwi9pmr9sCz0CAZyApz+D2vLx9P+G8veYZiOcZSOAZCPAMJOcZ7BzN33X9hVm01m2eZyCBZyDAM5CUZ3DXMrcZa7vWbZ5nIIFnIBemk+o23qdgTztD3651m+cZSOAZCPAMJOUZ3H3bSuBzrm32ei3wDAR4BpLzDM59BnkeZnts75prIJ5rIIFrIMA1kJRrYDk+7Q59vOYaiOcaSOAaCHANJOcanAe5Wkef7pprIJ5rIIFrIMA1kJRrcOd4t3vDstY2e10WuAYimE6uy9r8qG2wudZlnmsggWsgwDWQlGsA7XzEHlbrMs81kMA1EOAaSMo1AJutb0MPq3WZ5xpI4BoIcA0k5RrcfHYjxLO9mLC4q4wlqevA67TAORB815RyDqwkmuP+a3RdKEGt0zzvQALvQIB3IDnvYOd489rFfAxcCeo68HotcA8EuAdi3IP//m//67/+/X//j3/7j//85//4j//6xz/G+KG5ZE87aO0Xz/NPm/xDa/NJRz+Izz/uBwO8V42LkKR49q4BGM5DjznfKY7OB49+qV+7+wVuX2SMKsm1/x3XQV1fZc1Xkifpu6p2aIwi94M2GqR4/r0UG/f+09TrUU6Mi2ukhX/d6leKNMZxUiO3CMy/1DRXaJpXiueaow8FEMACafiGkCL9tNXdSemrr6chS6v+rG5Ic2m+V4gt9wt4oCezaBmf4hlTXIU8f9ZWcpXw9DU5i6ahH76T5HOsJM+ffpIe/6yqa69CMmQKnXwWjUM/B8/VMVYtDqF3kkc/26B5ttavP/gLF5HVOBJpklcfooeRTPxKsh2TpgIXLnnbvZpWOSpE1wkplo3zi92vJOddlZjkX2qdpL3X5vSHlh0aoXz1I0zy77bOeYyfsexehZ3umZLBK/5GH1r/48/rTWCbLj6eES+y1um0WoIvre/xSlLfUa5SyaHxtlYr/4w1oObUq7ADZoyrHjtropiq4IcGqNQkL57H6nTn7L3vnq6xE462ml0gybp5jjVDXNpr1pzwqkteg/qcr4Me+rMk288a7ddxHOeyfkCSZfMcU8FG6/+vgb9eSZJGRTzWXKTxPdaM9jM1HOqaNFYFQU+/yuZZRTjXcjnaOYeluOriOJte1LofnHBDa2yObPI9SW2eXb2T27x+5hirqddAGvO15jw/OFGPSbnmkAZgXC3ZqbG8kuRXl+P5ovq4XxBBTUrROP3nGmoirXq7WjILuR8IFrJoG59ikuTqQeOndV7tpzdQ0M+lXHXA7s7R7r1GKAZmqHvxTlJ71F9qnBZb57000mrq9X963mppkkXr/Gr4eR4/S7uTrp9rNBAkWSuCr11o0rVGQu/rX23NlWh3qQjG2jKNNfmfV5/vLjTo0vG5uvl49crnF2NMSLJsnb6GzGqIfrC6b2qSa9Vp+qZlLeHyZ1z95/UesQ3hJ3j9SrKVrdPmmquZ1a+f3lW5ktPpYY3uVbf9WuvQEgO8RMD64QlJlmNHpqpR9a7VG/M1x/6stlopHjpJvAx/frGKCkmWrYNJxhRfXWgpo9V112oy0O6ydY45lu5Z3WfNbK8U13yoS+HVjncZnx+IS7FsnDkma1x2Xmvpu5ByXmvoUZ860blfPHF/V5JUNg4meX4mOd92c+c1Zlf7QUVS2TZoNkW7XylqTJmh4VsZRg79pbYZsXF06PS1F13/8+q3WJX0lxonKeVaZ3466Rv/o/VVQ5Bk2Trf25vXMsZrcImOApowGLluHDrW4kxrmbZOuTrKkthTgWC82nst6Ke2zbU2Bgytw2Xr9GPoFpbWZy+BLmttXWpgakS6Q5OEX6xNLyT5d1unHeP8WX2qKynV2V3vdFb36KpKlUT4p625ds0FelC1xO2ahNYUt6bz1SrnUsODYT7nsnFGu1aZVvt0jUmihbzWvKhyuNGfJSzWKnZoYy0d2KAD9bJtfrGa+xIZayJfM9yypsFY7GXbXOfkizX80rDmXv9vzTh06M3oamUdisqT7WvqhBWil4pgrM63OuTqgye/k1xC6LUv5rW4/XG/WL+BJEtJoAqn98b8ipKsSbbrUNfna2gQJfeL59GBJlk0jk+SY5IvlbEW7rUXvZaIA8OrM4JfDX8luZpFD7PnI9A1yVqw6XylgXv1LeurV7J6CK2Fa3XD/sf94nmboknWgk3D45P6+6054t3R1+ibq0GX3r3++F8IdPTqlMB90D5TlC3YlvDVs7sLGqc+JfjF7Lde01nvOC8+YBKqTwlWF9c9jMZg22YvabTFFb2X7+cXAjVZHROs8b22wrTm+4usJnV+0I3KmjheSyP8AmuyOidwH+yqdEm+DF+b+f5yVYQBXh0TOKvWrBPsfouMOfRUpz/R8zXJonX0oGJ9u5YI0iDlH61zrV0E/uJ5bLaSrI4Jzp+1iq1Vpq29kj69+bD7/ON+cWKDV+cES9+1VYJLd+wyswaHX4wDF/DqnMAleeZ1ST9KyF6F1H0eJFk0jze8R8NfSeoh01SFhMtOdU7gm4c/m4ffSbZzNcxahE+c2apzgqV0TGboQdDHzKabW/wFqKvqlOD6WVt/faulm4j5OQm184/7xTmgvatTgl+TbCqGrlXZcgxqA2qyOiXwZs9o9ivJYbKSsCbLxpFn6Rv9U7Fdf9wvhCHJ6phglXJpkFXVa3e0NnefK9m7ce5fnGB3dUzgU7xiim+79SBxyc6HcK1JlkMH7N46A+ye70553Gsj9KHqnOD8WQ2z1PK1pOpaVpINGf6iNUyybJ0188+1zV5z/jIs2ezgL5asvpNs1TmBT3LEJF+Gz3bwmkg0DiMkWc5sx0lLmKyJUOncb1256nDVq1rb30lq2OlrDm4HJlk2z5qh+pr4+isO56sq12qt/pOrgcZrs9P0oHBVIzjpaopl60CDX8lmZ5IsvaRPvRQLd2Ihy9bRQ2JRqrPK4F2VTZG9a9XUdadfS3Kv7c6qV37ccFaS1TmB2q3xP1dNsdKOX4av2pt6U6lMoXfjiJ47rkRBu7TqnGAtEq+JVgfsebWtqF9268Ho+LOKvlbw2XisrUnrJyRZrztrX7R6zBp9q+9+HOO8V7L7B0tRQ4pl68AHR356RXofocva2otCR68OClYHUfxuo2Pq+XRyEgi/GKBUW3VOoBs4VtfUVVuz9eS00v1CoJDVQYFPcqYHgbqFWmNVNFTHgCTrdQfsvtLjyrXutGNNbq++Bkn+ldbZpXStc57tR4Mc6W0A88Qk/1LrnLGUa+v9c6wtnrorro4IvbI6KbjW8qrTmE76vb0NvxS4uRZCPVj/437xsFE0ybJ5Lg212dS56jzOl+Fr47Ta47UQ80py/vSXAGsIfNAky7EzaOhSp4eR5z5bPNfiRpfyotf+do14Up2wlgmCWag4KJhrJ7Pq6GzHKtfUHqN3JqtBlrJaTbbqwf3iZKzJvHFmXxPE2sSsTYfeAPZ9wbGmkDVJqP/RH/eLE46nW3FUsD5YOyM931zLzLgoaW/8xYQTklYcFXwkmV688doxK+KBV28CzdaKo4IPw89o+CtJ3YmsrSqEvNUk/27zrCTXfvVYMnVphOGSLJpHjwHOvpJcW9yjvS/ejrOzHpqKYtjdL9oBw7E4KvhI8opJvko5O60+DkFsNMWidc4fvWnsivBZHWS8b+q7nn+/eK+rkPiLCxeJ4qTgI8krJrkKST96W60n64+HgiZZtM5cq+syZ22eVo953ZrwD53Hay3s+ibT/YIIumVxVqClVI8MhVYp5PWd5Jotpb+8CNof9ws8C2zFWcFHkmdM8m34NYgOPTqHFIvWcXa/Lt4+7F4pah599XNSVQdJlmPnoPbaG+lWUxeJ8aMbOl79aK7t4x/3izWAIMmidXyS52eS7T0c9Y3NoK73b5Bk0Tpq1FqNp84bNN43zO2eNJZqd79g2O+04qxAO6G+hdSbay3Ve+ysgpFeUa9F7o/7xRr6kGTRPLw2cbrqkJ5P7ULqBcV83XnojpnXuqMr26FlB7uLo4IPu2e0+5Xkmk5X7ep8CSO8OipYcnkNAloTG79E/1iFXr9eO6ahotD/76hUq4OCJcjXFobV3/g6ttXL/qZeYVPvl/EHDY4eWnVOsJTu2m+/Ts3He0v2YbX7BW7JWnVS4JJkyiqyH9r+a9ZUnQEpFopgWcUK+aTXKdruP6s7X7zq8xzjneJql7VsnL3BwVCrDgpc1R89Ns4ryb62yq83kHDk0qqDAm93S6pSnXNmH6T7FZyDqnMCX8ikBy3J+zr7HyxMeLPTqoOCXwu5BOuPAhXONX3qYTwkWbeOXvIuu8Ya0/Junat3WauBHqL+WTvpH0jmL7VIYuzSF2vpWv9s6vWBLVIdDvzeyMdSp4qpOLouik+/oepwQPSCQZfOte/uu2+/OsXSono0sHa7P6vnsJ5h4dkfVUcD6+evFVodn9rrmEVncA14P1RT9T/uFwQyn6qjAd22rybWm9L3oedKUnnKU49hO8kfIb3O43MpaKU+TkiybJw19nipn0MdmnYh59oSL2Gu21mWn0trtbE6bQxIsGwaJZavaYm0o9hUdqnDgF5i0Xv8sbq1rzE8YA9GxcnAPNaWbe231j5jbUQGf3g+tiUr8BcXLFxUnAx8JHnFJPUuau3TxhKray8CVxBUnAysJNUVpDcNaEmv40Tn+zj/uF+wK2UhAg49+Vmd+vXYpp2fHpryx/0CN/JUHA34JCmm+LJ7Nd0a32uoMPSg4mjgw+4R7X4lqduSNe30CRcl9OVo4HgB6vvsL7+11c37arDOrN42f/wPYKGh6mTgtxTfZw1KHlVZP9DsYuCs6eU6lnZfe1f9/7JFAX4xJppdH3kuhaOOUdqYew7SSyjtgXq7439xwYxRHQz4JDkm+T7ypDXkNaYktnd1MOAN51QF8I+ufWt8r10XJllfU+uuX5laOhslggp/MbEuKx+CvkTfVP+BJeM7nYmiwl+sEQ9JltfUa/v3ere3TD8SHel/AeO7ciJwv0+W7Ndlre5LeSoxB9q78iFYRqkT6Rpyx6Ws6kxQjZ+lpdYKvqqzYSH/UuN8LN9tX6Qr9+HQfT2MxdqDAOsxU6bz7Wq1clpLG/bJ2oPgaxlVpyxhsWYfOpfShWmy9h/4pYwXvz1AlhQYzHCvSpX/QH9t4S9lmopp/KWm1i7pWKpiSQynpqj2GfgyVtrSUmvHvPZfa/JVzzfo1rXHwPf2XVPij955Huc5D2yMymNA/cWOJU80NOhJu1uv7eE11ANQz0OWPv2Za+BNdZ+GqqscBlaKa/s31sZkyvtcV31lDr1UWcKGX24s9otTnZ8gybo11oCYTetl8F4R1vqgnu+XBu1c+zZ18LxUrp2CfaZyGFhJNtFzh6Fja489et09qLvrWG2ztpm6/Z96xAkX51R5DPw65fAhrxtp7VL9iZOjSZat05ckJvXFlDFsEzemHokc+iCv62Z4rkVwteKFyrlyGOjqZHrOs8m8SD4Fn80Qx6rDJQsY1//KX0CHigaMJg2d3e3wQx3pD7307H9W5/oZGo9kKbbj8djXJPPGWQWBxzFDPgXfLJ7PaIp527xShMcxn1KKq+czmmTeNq8kn9cxn1LKvDHj+5nroOIYYCWJb1nesw68VGjVaxdNMm+dV5LwTOSPf0dyjeohiSZZtg4+E5mf59lUPSTRJPPmOa+mMnb1I70oP8Kpe/+WZN48a7r50SlsSfFjjD2xQV32L3VZHASwevTNvgbI6uLE/Jnk+JZk5QrVVt2rG3rXfv1OUoETehuvb4V384xLnXoJFUBxDrCma/7Rc7G5SkDHe4SvXdYSleoW9vZiWSmuCWqpyrMRLDrFmYBOuz+XPpS49Nzw3eBr1tSQHUoZvXaSayes7z7cjF6cCWhV6qSma/zStPzZ4KNucK7OBC7+UX9RnbCXnW/XdV6r61xLJe0hvkqpd5yH8l4ZkvwyeC49vF7r37VPvFZdnvPlZWZ1+fwCS1kOHnyCEXo6VY80NMkvc9vzBOP6uJvtV/1Ig4tzgfcEfD/B4M+LVK4faXBxLrC2sD/q/MV6e/t6dJUM8cLw4lxAJZh662rH7iLhund8K2XePKun/bzrT30s9aXsPHYyK5FTz/M7HL5y/ZxA336ONZ+uwhzvJllTxtBIrb3zXht09dJz9j7Q2KJJ1vywurNeGc+3Enjdxy798wousRu5M722D7iAcXkW8LojXqvymgs0zrxd8er/jVjMZfLUuzXCiYKLo4BXt3meXdCnZxHVDzO4OAt4JXm/aOjy6QbUyjcPXJwFvFJ8XjS0Twcbrt88cHEWsDbreqxCekR1jGj3+GJ3cRawVsE1+63RsDYtKnk+S9m/lLI4C2B9SEd6RHayJIbPb0lWx2jtR50MSP3059itowG6Vwc8adiLlCUGl+glfIHE9XuCvnYKa0F8QYpenoN65KkrTTMH5nE1lj6OteZCgsXAWbsZPRXtr7jsuwdB4/CXximOAtZv1shRd2P1TGvhAdL8lmQhBFZNTr01JT3II9reT2vHeakncLvnslWHTeNdwFJTnAXou4uue7A1SZBc+2XGoW9SSD+zJNeQX/Oy4EMKLk4DZOht+2ppvdea4908+iK9D9FZfY/GPlnPF1eVw5xRnAa8FsTntUDuM5m/J+DiPOCVJLwW+OPdT5vU7wm4OA94L9vmiD+C87+tXtFVn4ujgfeq/Tjif7rq1576XJwNvFK8PdzP4FZfusBzcTbwns5vB/fgtm0j5/nFk2RxOKB3CuDnnaaYO4JzcTbwShHcvD+tptoRnIuzgVeSj5t3eEVx1Y7gXJwN6NYaXKj508maaydrLs4GXkmCC/VHL38fSOZO1lwcDryTvL2TP9/2dEsy8V/m4nTgVZePd3JYdFrtv8z16QD6/YaXla32DOb6eAD9fvnDM/ithV6/WHJoLYyEpaw1wdICOoZe+7ntGqyPw7Wk87IkV2UspYgX8FwcD2xxGnVAUX+VZ8DkH177F62tNre0EHXjVbbTsVMcq8d0jdkAr2+4OhHQJbZ37Xr67GgvsXpYP18Hprdj9cpAj4lwMitOBHSJ1UCDTWUF9b3E8uqD6l58MVmSx9rUnA3PdLk4EehCS4lcy8zDXLXVr6mtjrJKvf3Jly7S6G1XO2GBLc4DVul+9M2pumq/+JXvp49DXzj04zx2kqe+1ZND4+VAknnb6NPGtWbrGfOxr4BWR1T3ttV1p82PfW0cpelVP4zp6jyge3/kdCsHv0CzvwyWx9P30724n7UvMBfHAe/p8fb0TTfFuStwL04DVnGW2D31pubSC/Z0b5g7avfiNEC9PPToVXRxIcp3sFUpf9ludr32O0VfL+/Bom9lpZ347KR/eTKgCDmtxev1Fkof7a/+szZMeg5kc+zRNd7P0s6YZLXb1BcB+kZ7jecx3ocpKqL1kPk47alEO3RfqHL0aeNeOgaoR8vqxUvO6xbzXcqmF3prm0P386q1Jqz/WV1pIMlqcXF+sz3rN4VnbS8OAF5JPn6z/OlZ22vP2l4cBugmDvxm+dOztteetb06DOjOyfXTC5ZKL9henAVoC4BDKn26rFLtstrLwwB09Tzkwxl0mhdsdAbt5VmAd/X0zqAvN+jKGbSXhwHOL7N9eG6Os/bc7MVhQOvO5bF9OEWS1E6RvTgMeCX5uDyenzdLXDtF9uIwYM0V6PyXpZh7B/biKOCV4OP7R5+X2a32DuzFUcArycf37/r0NBi1d2AvDgPW3KLH60OjdOlj1M8k55cki8OAPYe76pt19RX7/7Uo/RDrLazu1oO35vklwep5jVa/soP1AOEKll7fLC1uacb7Yl7d7JjabuL1pTJbx+jWxGvZ6e+HvpBktc4swaNO0KJPi87QD0dtd+UMoN6Gp/rw6arL20tVeKnjS6/YT7ObNAC5DJdk3jZLELycy4S478duUx80Kxl4qGnb7kaqOPoJ58y92P2vLYQG2dA7TV57wMTNsm6dYvvf9bK4qcP61eUds+jlwviacpco2b58Z6dXWMQGZ3G9PgB4aurlf4R1ebXL1yU+1O/VAcBSFq9TSFKPxR2MrWnYFgU/kDX4qXP9dYyOpaxOAJp6USx75ssD5V8Z0tUBwKqRtQFaW/FzdeRm3qCXrs0aPbzfVTn1N3Bn2qsXAofoQdv6/dq5vRboVz9fvfzSsJxjN85arul1kt2hVxb7/7WLVNVNqzjncYn4JLvVpCVJsFnv5f7fuVHSx737cdaOlr3c/3sPxc+L9177MPZy/+88FENIUap9GPu3/f/jUDg+XQ7teePzC0iyHDvoqjc+nflqX75eewegp16+Zue+fL32DkCXteCywrVTW6+9A9Bl7Up1QO7U1ouzgPd57u20FpayUbu19eIsYO2sftaom2sa1IvykOT5JcniNKDUAUX9FScA3NYA0xfTert+RC+i81uSlRRYOy8NvXZpcAsaqRSojP1VCqw9NYtJga4Blk62+tPDUXX6aHC30KszgFXra7bSe3VV3sGLb9SGj8ol4OUt13T/p3GAydavl6fbmPL4Q176QvOAmWIUhwD90KNgDWw59UW9LV+ksRHmZSF7TnVmUT+BiYUspEC71u+XZJpqfGwdqVtnFAcCS5Vo6NA1D3TdXQ/b1SxJ1F/PYHcpV4bE6nY/IcliwCx9qg54a7JamwyyyWft3taWVY6+L0D0+Pp1GjeeYT2KAwFN7EfPxpZi0hnrPemuTedUPxO2LnSxOmx09Ewa1XnAkmg/+jp5TdPtfeijc65CD9dIf8lqTXJSU+c06Qe0d/lQYO3V1U1FTw35dvt92722ruzsvlACjfI8wHnYmbez+eCZ4ZkP3ijPA747zI0qgvWllw1/xWMuPD7gKsy2JvnFPeCrx9xHMHDo6bV7wC8ecx8RpwmSLJvnF485F5sZPUNHeSTwm8dcEXJ6JVkeCfyWpIZe1lVX52B1LoYkv3k7fatLDb28JgEV1YeGsYYkvzSPHk2OVU/tsjjJx+otb0fqP9fbe1z3I6u3wzIx6kOBlSTrsdSYist7+WS9D5vV43n+WZugn1WVXf/fHK4uvzSPxjQ+TlWI78NO7YdrU34tc89XLL+1zM3X4iPgpz2KQ4HtOaYLFffX9fDrGPGcq0XOQw+P5Vrr/BrbSqNfYwFm4OKE4HdntFe8Zw01ubZTB969j+KM4HdntCII8Wtn9jed0T4iJcOArD0EfnFGK+I5X3r/9jcN1yA7x7U6hP6TYTs2ag+BX0r5ij3CunlY6x1D63zzEFirwFJMl+qVPx8Rg/f1+/ML6EPfXASWHFydkobsyyCIGDz+rDXoh3TWuV4OorDmfnMSWN1wLZTz7dnmIgavPaO0tSjrqaReZQ/weh+1k4BznoluZD5iMHSh2kngFy+yj2C80N61k8BXNzL6DBkMrVM7Cfxit3Yhfa6/frNGF4rL2kngl1Jq+JpxqicC+V5Z+wj8kuKag1bPv9TlVm+HwO7aR6DrHDE1tu2gHZ/qDp3LEEJ2rSOEr6HHtxcEY0lmFcy0fQTu0LmXOcM8v8Ak/27r+CCyqF6+PSFYqncJh1d07c/YueOJGUxrHUaH8lEfEqwpQVfToWeb20PLYue2tWysHvkKFqSvbS68nB31IcEvhvuYwTh46kMCnSx5Nr3m5m6X8RY9d80ZXcfjqpP1/78m2v1FVH91I/uIdAvTUHFG8LsbWRmPdxRnBL+7kZUxZEdxXvCrH5kPdAvpfVt1vniRlbFZR+0v8Isb2UcEWVBstb/AdzeyMkTpLI4KfncjKwOpzvr1wC9uZB/hXrGUZeP84kbmw3+CN8esXw/84kbmQ5RCNLJZvx746kZ2fgbWBMOrs4Jf3ch8+E+4Q5+l88BvbmQfMSsxyS++No+TWItuZO8QlBoTZon405Xyq2caqROUXr7/+Ygw+ZIE1xLS6tatL5cgxS9j50tV0ouW0Zu6KtP6JzhCzfqsgLTBT913MH8GmFw9/RrtR12ZNTq+BsCHJL+0jmjQvbWk8Nzuc3eASdWZx6t99NT4IFTosz4roBdR59QF9jIX6zvA5J+V8JraWKM3rKEA3gOzPir4xbfKRSQkeJQx66OCr85V12fsxmdGn/VRwXfnqiq+5KwPCn4x+0VHGepBpscP0IHqc4LvRVTAg7qd6+ttd/0y62OCtdtSEfViZL63JRBkcTvcwi8gyS9No9wBddxo/N7hPUEWVaY2Xlpal6SlhQbO5/UxwVp1zq5sTWr9eYKzoyyqENKnJXr2q/AjiM8/y2OC33yiygCGszwm+M0n6iPMIib5d32iymCQszwm+MUn6iPYIMy95SnBb05RPjQgnKrO8pTgN6eoMujeLI8JnM/TFb2iPkIDQrcsjwl+84r6CJGHdfl3vaJcLDkBN/1ZHhP85hXlQ+RhKetzgu9eUR9h2CDBv+sV5aKqXThX1qcEv3hF+YBbgmZ/9fP4luQq9tQDs9GPjnEGZn1M8L0mXfyMWZ8M/OKlppHDVsnX/40Zr8ZmfTDwi6kXq3v8GGtmf0liSPJLg6gfj4aeMN8tHQhrIjun9nWLD6f/6xJ/mOSXBvlmtwZhk7XdO1QmEFy2zfpcYO1nRDEjr0X2naRGjNMYc6xadf3ff+Z8BYs70B1z1ucCv7nnWVy3rsci8Dxo1ucCWpW6e5nq1f+eeC7dahynhq79I/NQQlnT43pm7Ij1wcChDvP9UGDZNH+w+XqBqB4Ir+HCryezc5UVJ576YED9aljNW/rRokmpyFtVt4T0KxCb6M5THZ0FzulmfTBgSZ6qzX2SS1T9WQvXjx78apTnceGOtjwY+O7MMz8CscHV2CzPBn5z5ilDnM3ycOA3Zx4fiM2V8puE/ubMU0YkO7+dDnxz5iljfZ314cAvzjxlRLLzW2iBr848Vcirsz4b+MWXx4WwooGF/Hao9s2Xp4wedtZnA78lqdpijYQm76sNSPLv+kW55euszwN+c6/SeE16rNQ0sCdct5xfnQe+GXup0FrDeqUhKv8gyS9Nck49mtN5sdv6NXSrrpMDrl/6MOQZ1Wd9IPCL4Rr5qqtc1edSHeLRn/WBwCqlPkFT753Nx32t0fJ6tacxP5tCLESlMGxBzvo44DevMgumtfR/g3Ovsz4O0IrUeex4vVB7LV56r6KuvmOuxYt/5uvY5sUSQKO/jRYNW7bExLwuW7yGXilMeQWxe0VeUyeehkc1Z30YsMqor/3Xmi+3Djhex3t6KfiKe7U2sm0NaDnwnflZHwf8UpEa90qPTtc+SQOJwsRTnweoe9LrpPM0n6jVV9RzQJaQllfcK24qfdauE2TAWZ8HaKHW9lTF9rjX7PlCrq5/r43JmsLVnV6nnQYJfmkaS/A4mk9QJ8uhQ3vN7zrtrPaDiqxeEviQRQGn3Qt8uqZYREh5x1VaA3EN7esKjI1eO56c1WFA06sZfUG3JoJ+hkLSl0IWQQXaSkCGQmKGnsS+zwL0aEt32bTp6eqNM5qecsOV1VmdBWgh1yZWA/ovRRfCC/EXu4vDAFHvC1ZCdD9eg3mHF1Inj7VEjleShz6F0zdzV4ej97N6V6DRFJZRrJ5512aLvI5+VOi0l++SRg9ZO1f1+wAw7lmcBSz9opd92havaE1Je1cOHWdxFqAPKZu2jWKOX7c3nw8pP7wv0O4iNFcaZEfvqUg9mvQKT2BLc35zE3hC6NCfjyA7rxt4CMNzYZJFi/Rlm7ozvuqc2h8fZed9+bW2lrPpfgIPfM7iAOCS1SJKXOn6blTuuD07yM6179Nora3HqRsdSDFvkCXcVDDrUdm1ZvEAM+2fPGXo2xVsoGtwaw3PuDpfuz5vBEbtynBW2/+1V1vK8dJfq1T8TJK/JVk9jV6tu5bCNaR1Brdn63esmTdQmTVohIaAvOBG4PzqJXDHktl4vifazB8fjAYcTc7iLMBFhun2Eh4jw1SuK2d1FODC14xAa+MvzV2cBay+pkPvEIWTGKztCTXT3yNakYcrAx3TkGLxNHrNZEOvJNbnS0mGUDMvs/XUc81Nh97owMCpaANrf7Tk+trwqeeuvYR/Qs287H655M21eVwKA6qyOArQkbMmBvVYP7rsJCEkwxt8dyrLbS0seloGSX6dyj6Hi7uLxGSK7f9aQ37mWyWqx+a+i7xDMrwvDruim1b3Ft2vQZJVtKe15xlaJNYXJfsC7YnJMN/GasDlU938IcFvQR54lfLQt+p73nkiMrzTk1dtTp3ZIMUqruBx/ugd86rw+X5E4EIyvK/P5uswoKl3CTRxsfefp148na+rzeOlTj5DMgw9X7/0NnqNnxOufa5i7796mPZtWc0h+mTtz0dIhtc9sd5L6VLd9aIPkqwD161FZW0bNfD+mQSuK+8Nr2Lzv4bq6oOsd1tDe02y8vtbPkyyfuPxJwQn0LMTrcs1Jl/hPiCZb/fNT+yBPz46wXvUPfELTthoXcWOv+ttsnrB6aRN/E4SohO8+rb655+vGWyiscWOf/16rUdEzEt9NnnXH0QneLN55VCPtD4PXF2uij6oR9Nq2CqQ+md8boJnDXW5it3/bpKPp0ofAJsLkqlfQQ9tEkWFyL0Zgqc21T3HVWz478dPx6UPl/S2g19kHVLeq8ZIaYIFKzb5fY21U7e2yjaU8JTz+rzawIJVs9Z+HLqa8HiFs/58HVrXXrXNbwf9qKf48Qosa1dZGs/6VE33uiVaOwN9E6t+0nDQdhX7/NfBwKEa+9BboPAc+Fspq43+8fLi0Ls2Dc68X9foZao6575TJN0ikXS9CoeJsIofKONHn8CsndhcieyQ2axeaqei4N/co7UR1EAbazK8MMnqGTS+ej9DRzy/DJFio6/PoDWg9+vGj559Oa1ZX4lMmmJXN0Z9+7RmcJgaygCCGgl8nqRRJNoZ3ub3L4UsdvrX642YnnBfem+7Y2afr7dqugl+JUlrIdCnSnrKDO1dBRC8+OVc1vSM+rhCKWd5+nsVO31749df2MJdSD/xVEe115etvor3S0/KpYUr2/GlkF8FmE48+vBdoze9Nrk6s5G6k7ogSVexuV8NoXH4r6EMz4PD+Lu+mFrd9Dc9e9FH7m0t6b0lQ7pOsprLjrVpYnphgIX340N+XemtJZ9fDaKOZhoRq5GTDcXufvW2H8UrLzXUj+QO71sbVzf9x8k/Xe9P1Wt5T+L62Od1bHu87Fbw9HhpqA7nBVex0Wc9hl0bkiWxt8f5a95ZKuYVt5betxCauDoXnHCYfBX7fHxkuzZlAeZx1v2w2OerJNHACmtEX9PCjTf1yFW/FAVGjFdcTA2JPdd2DebG6p5/adSfF4BbiX5HmBv7lzIWEQO6urDq0bP60e3gJ7qlGsoIG/s6R/dTSzGv+oZLxmvv8//zn//z//7Pf/7zP//xj/9nbUg1atr777n/yv6LX76b4P/7t//+7//8P//17//rv/3z//zH//uPneifn//6eX7Z71/+Y/8A05lpCXaOqw3f/25JCa66BNOXQEIJoDNdeR00X4K56+TcJTv3v+GQ+rrqOrl8nVyhTi5MJ62Ty0qwWwWuI6+rrovL18UV6gJXIUnr4tp1YCXAnKW2WbzNEmyGQBNruH7L+bxLAF/UNou3WYLN4IwuR2rz5I92FviitHklhjnL8WkzRvBeu6UsZ8vRbHc5lzYrNcTl/GmzwLNoaanN1rfvWh/wRW1z8za3YDO8/1xSIc159+kZ+7a02ubmbW7BZjg2E/puM5vt8EVtM3mbKdgM/nhCqc02o1jOEMB/bQXqnL3NFGyGhVI4H8/DjyqYj4Vrm9nbzMFmxnS+jufbZqhtrm1mbzMHmxls7nk7n34OQ5t7bXP3Nvdgc8d0cputb0vsYb22uXube7AZ3O1l5HOY2SwfJYDRNWrbh7d9BNthNZYRbVdXWK1t/Xvuv9DHR2378LaPYDvc7MmMtr+dcF9/2+5xAjnP2ubpbZ7BZljv1+YwzZktRysBfFHbPL3NM9gMIl0S3WY2a84cc671mni9JkGvubGS6zVpH+0MK0et08TrNAk6TUCnSaLT0OZ3bWvgjff/HWyvdZl4XSZBlwnoMsl1mdW29Tg4xZdal4nXZRJ0GR6sSaLLsG9bj4Nar3WZeF0mQZcJ6DJJdBmOa4m1Xesy8bpMgi6TR5fpq5G0tk8/uh49tb6obNbEIOf1zw+bm0+nHtdY6wO+qGzWxHzOEnIGm3Nddo8uq/X977b/zfsv7b/d/newqdRvmqkr4ad+az6dtG5450h79D2HM+p/XOfs6+ZTvzUI3aR+YOkY2P3ASsBQ1lK/aWIu50/9pt9COqnN3fqDxNou9Zsm5nMONhPYnOg3yNFK8LzvV0xYmTN7mz/1W3N1l+g3zWm3L0uSc20ze5s/9Zt++6ST6Dfo49bnCXIu9Zsm5nL+1G/6LaST2kwfo+zxnVOvyTpnb/OnftNvn3QS/fYaRdanY22Xuk0Tczl/6rYGD6fVr/1bO1sPI5jrSt2mifmcg80DbM51m/Useo9ntpLgeCz1mybqSvCp3xpg6Nd/5+1t4/mMM0qp3zQxn3OwfYLtuX6z2fOey2AWLfWbJuZy/tRvDfhM67+/j+tkdJX6TRPzOQebT7A512/0MaNgO5e6TRNzOX/qNv0W0sltttF1RptL3aaJ+ZyDzRfYnOs2W5/v9ZrjClLqt9ezeCzBp37TbyGdr+v1vYLAnFbqtxdMzOUcbAf91hL9pjmefnTZaLuVwy7Rc/C9Uirronld14Kua6DrWq7r+i7BsDqxVjnhy7JOmtd3Lei7BvquJfoOcrQSjF0Xz4NojXpRlsDrtxb0G4Tp1MgrWQnuHK0uOClBXQdex7Wg4xrouJbruDvHXYK56wTm61brueb1XAt6DoDj67/TOrhz3HUxW1KCug68rmtB1zXQdS3Xdeeug3OX5NwleU7J1pd1HXh914K+a7CStVzf3TlaK0hSgroOvM5rQec10Hkt13l3jvvvtesC5vNW673m9V4Leq91TCetgzvHXRdXS0pQ14HXfS3ovga6r+W6785xl8BOGARaodZ/zeu/FvQfQBrWf6d1cOf4rotm5zqXJCWp68LrwRb0YAM92FI92NquC7G6gHWh1oHN68AWdGDDUZ3qQMtZnxW86wDmwloHNq8DW9CBDXRgS3Xgk6PEnGsd2LwObEEHAhtAnV/Sdhdvc4N2rnVg8zqwBR3YQAe2XAfaec5lNkM71zqweR3Ygg5sOGpTHdiO8VHbYHOtA5vXgS3oQHhjvhbEtJ33Oc49uuBEqdX6r3n914L+a6D/Wqr/HputBPhFbbPXfy3ovwb6j1L9Z7ZabR+PQ/H6orSZvM6joPPAK0Y9Yb/m3EIPo1rfkdd3FPQdgb6jVN/dPatxmMOo1nXkdR0FXQdxdTUgYzqqts1bbTeyfw/4srbd6zoKug5wo41SXWc5PyWx2h+h51Gt78jrOwr6DuKfrP9O23/vNNre+6AaolrXkdd1FHQdga6jVNe1fX7T9u4atSjVeo68nqOg5wgtSPXck2OL7V7rOPI6joKOI9BxlOq422bLmSHnWr+R128U9BuBfqNUv7X20c5wFk21biOv2yjoNghv1ijVbY/N77/dZhw4PaNat5HXbRR0G4Fuo1S3PX2ck5xr271Oo6DTIATA2ud8G+dme3scADXCa5mz12kUdBqBTqNcp9FHztjTap1GXqdR0GkEOo1ynXb3bcu5wRe1zV6nUdBpEDJy/fdXm21847iudRp5nUZBpxHoNEp1WttnV22fHLV9dtHgrJJqvUZer1HQawR6jXK9Zjl2q4MzKUFdB163UdBt4IW/hlNeB+JztpIMaP9av5HXbxT0GwCY1n+ndTCs9sVy3n+hH9Q6jryOo6DjCHQc5zrOSjB2a0wrgcCXZR2w13Mc9ByDLuBcz1mO00pyJiUo64C9ruOg6xh0Hee6bp8Y3TlbSZ7IQBpwoSyB13cc9B2DvuNU37V9VtVOq4sBX9S2e13HQddBMJXGua7bZ1VPzmBzrePY6zgOOo5BG3Gu407rcbvvn/hFbbPXcRx0HIOO41zHma1m+4SeVus49jqOg45j0HGc67h9LkfbB6EJ1Hat49jrOA46jkHHca7j9jlcs3057FG51nHsdRwHHceg4zjXcdvrgWynALsmrnUcex3HQccx6DjOddw+f7ttPiHnWr+x128c9BuDfuNcv+0Tv2bnMBfUdq3f2Os3DvqNQb9xrt/u9uXYzrV+Y6/fOOg3iOW2/juzmUwly93H4YvaZq/fOOg3wOWuhTq3mXeOzWyHL2qbvX7joN8YZ6Rcv8lnzlDbtX5jr9846DcG/capfrPRdOeMPazWbex1GwfdxqDbONVtTzu3OIfVeo29XuOg1xj0Gud6TbzNBOepXOs09jqNg05j7C+5Trt72Ht09XHXupUIUqjrwOs1DnqNQa/1VK89tT9CHfRap3Wv03rQaR1Ga8912l5BrATkviht7l6f9aDPAPPWeq7PRPwKAn2917qse13Wgy7roMt6rsvuteuMtV3rsu51WQ+6rIMu64Uuk492PuGL2mavy3rQZR10WU91GdnJ3unn82e825q26wRrsdZt3eu2HnQbRJlrPdVtVjLa56+0T4ioQd3U+q17/daDfuug33qq3+4cyUoykhLUdeB1XA86roOO66mOI2Kfs5UEToh6ree613M96LkOeq6neo62twux5Wx1gl/WdeB1XQ+6roOu66muo31OQ/v05C4BnNv0Wt91r+960Hcd9F1P9R3t8xrae1eC/Xqv9V33+q4HfQeRzlpP9R3tswrauyaCnWKv9V33+q4HfddB3/Vc33XLcdf+gD5f67vu9V0P+q6DvuupvqO9O6Z+2w5f1DZ7fdeDvgN6+frv3OZhtu4S4Be1zV7f9aDvILhk67m+M1uH9TDIudZ33eu7HvQdhAdd/53abH16jti3a33Xvb7rQd910Hc91XfUzVYx2+GL2mav73rQdx30XU/13VPLEmu71nPd67ke9FwHPTdyPXePJgk9bNR6bng9N4Keg+DO679Tm0/LeYSZZNR6bng9N4KeG6DnRqrnaHzYDHPPqPXc8HpuBD03GqaTj+fdzvsEaNhOot8lghTqOvD6bgR9N0DfjVTf3bVurQB+kqPWd8PruxH03YBVeOT6zmrfet6JX9Q2e/02gn4boN9Grt9sFrWcsa/Xum143TaCbhuM6eRz2seqCX6yo9Zrw+u1EfTaAL02cr02P5QC5lzrtOF12gg6bWDd5TrtXkE4rJqj1mfD67MR9NkAfTZyfWa1bVoFbnRGrcuG12Uj6LIBs/LIddld23EeH7UuG16XjaDLAFPcRq7LBvvxjLNprcuG12Uj6LKBc2Ouy86P8YwzSa3LhtdlI+gyiGnfxpf4IqCG7d+mFG/VdMchgRTrOvG6bQTdNnDGKuKO7JxPm2XvCCjwZV03Xr+NoN8G6LeR6zc76be4BHcEFChBreOG13Ej6LgBOm7k71ltxrFzm30aTvuEmOSOiAIp1XXi9d0I+g6iYLWR6zs7Lb1LADnX+m54fTeCvhug70au7yznfZbBcF43an03vL4bQd8N0Hcz13eXzxltnrW+m17fzaDvJui7mccfsdgMNieCr++s9d30+m4GfTdB3838nettc4gO0Wat76bXdzPouwn6bub6znK2c1k4m561nptez82g5ybouZnrORtddl4H/pCz1nPT67kZ9NwEPTdzPScWySip7VrPTa/nZtBzE/TcTPUcm3q+SwA513puej03g56DgKBKWvw6nlus7VrPTa/nZtBzE/TczPWc9em7j4PNtZ6bXs/NoOcm6LmZ6jk+rG/zR0/DEtS2e103g66boOtmrutkfMxlUOZa102v62bQdXNgOvm4Pn3OcAMwa103va6bQddN0HUz13V3zhJWjlnruul13Qy6boKum7muu+61Ks5lta6bXtfNoOsgSGCb+XnbHl3vnD/Gda3bptdtM+i2CbptpudtvE/4ed/0cNvKEW2vddv0um0G3TZBt808Xpy1M1mshl0iOOGftW6bXrfNoNsm6LaZnr9xM9vvksAXte1en82gzybos5nqsztnq324c5q1Ppten82gzybOE6k+e3I+zXb4orbZ67MZ9NkEfXam+uyu5X2nhLV91vrs9PrsDPrsBH12pudvT9+W0MfPWp+dXp+dQZ+doM/O9PzN+rbZDFFf2lnrs9PrszPosxP02Znqs7u2dzuPYe0u8GVtu9dpZ9BpJ+i0M9VpdzvfJYGca512ep12Bp12gk47U51293EKkayUs1vn7G0OOg0CqrYzf496+Pbmw2aW/W+2f++/d9yZASnXdeP13Bn03Al67kz1HO8TBGaLFoFf1HXj9dwZ9NwJeu7M36ne8SmsBDAKaz13ej13Bj13gp47cz3X+aPWobZrHXd6HXcGHXeCjjuLeCTbZisBeNqftY47vY47g447QcedqY7jfZ/G+2zS51zb7HXcGXTcCTruTHXcnfPd1yHnWsedXsedQcedoOPOVMc9OXKSc22z13Fn0HEn6Lgz1XH3OKZkPNc67vQ67gw6DqKyr//ObbaelbRzrd9Or9/OoN9O0G9neu5296ztpTBOm3VhXNf67fT67Qz67QT9dub6zaL83LMr5lzb7vXbGfTbCfrtzPXbbu9nRoGy1vrt9PrtDPrtFEwnH9d+RsEYLGet306v386g307Qb1eu32zetrkMZtGr1m+X129X0G8X6Lcr12/3HNZCH79q/XZ5/XYF/XaBfrty/WZzmbUz3K9ctX67vH67gn67QL9duX4zW+9RdsIXtc1et11BtwEWq125brMcb9uhtmvddnnddgXddoFuu4r4cPIxntm3O1nJoBVqPXd5PXcFPXeBnrvyc7ddIr7jzFjEGyhBrdcur9euoNcuUF9XHl9k58j3X4v6Av2h1m2X121X0G0X6LYr1W2WIw+LuSOxBLV+u7x+u4J+u2DuvPL4IkNcCdhi78B9ylXruMvruCvouAt03JXqOMuR71g7SQlqPXd5PXcFPQcY8/XfeZyZbfu+a+JpkW+gFWpdd3lddwVdd4Guu3Jdt3Nki/pj8WawBLW+u7y+u4K+A3jt+u+8DsSVgK0V4IzyqnXe5XXeFXTeBTov4zw8ObLF3LmSEtR6z3MeWuA8NOA8tIzz8ORoJeDTor3gl3UdeN0XOA8NOA8t4zw8OfK+DWeLvbPPrF1Jav3n+Q4t8B0a8B1axnfQnC0+hUV/afBFXQde/wW+QwO+Q8v4Ditn8bbj+5Wa79A836EFvkO7sO5y/bdvu3nfu/EJPa/Wf57v0ALfoQHfoWV8hycKCO87ZX5iorea79A836EFvkMDvkPL+A5qo/ic4Sao5js0z3doge/QgO/QMr6D5nj3LOvj8EVts9d/ge/QgO/QMr4D2CxW65hzbbPXf4Hv0IDv0DK+A7Yvx9qu9Z/nO7TAd2jAd2gZ3wFG08Wxtmud5/kOLfAdGvAdWsZ3wFo2m6Gstb7zfIcW+A4N+A4t4zs8c9hd6/BysuY7NM93aIHv0IDv0DK+A9h6x4+Cdq71nOc7tMB3aMB3aBnfAWrbNA327VrHeb5DC3yHBnyHlvEdoIfd8zeUtdZvnuvQAtehAdeh5VyHO0ezGUdVrds816EFrkMDrkPLuQ5PjhzWqprr0DzXoQWuQwOuQ8u5DrYu81YG3V5Qwg1fzXdonu/QAt+hAd+h5XwHvqPxcVyzap3m+Q4t8B2aYB2mOs1sfWwf0fZap3nOQwuchwach5ZzHu6YOvbKjKwkUIJan3nOQwuchyY4dlJ9dttscWbQ9lqfec5DC5wHBKi2nPNgOVvtM9z41ZyH5jkPLXAemuC6kOqzJ+dz1zbM57U+85yHFjgPDTgPlHEennbupoafcxuqOQ/kOQ8UOA8EnAfKOQ/dbrm2zdPOop97N6p5D+R5DxR4DwS8B8p4D0+tW0n6E4WRao4DeY4DBY4DQXxpyjkOd44HJznXNjdv86dOI+A4UM5xuHO8ax9qu9Rp5DkOFDgOBPHEKec43LV9zyz4RW0zeZs/dRoBx4FyjoPFUOrN/lpkI+jrpV4jz3OgwHMgiFxPOc/BcuwWvcsiGbkS1HXAvg4+dRsB14FyrsMduWjnbCXpDdq/1G/k+Q4U+A4EfAfK+Q53BKNdkr5v+DtB3y91HHnOAwXOAwHngXLOg5Wg7/u2bivMhBKUeo4874EC74GA90A578Fy7GSxdbIS1HUwfB186joC7gPl3Ic7ktH0JQGQLNXcB/LcBwrcB4Io3pRzH/o+j+8WQ++O8oMlqOtg+jr41HcE/AfK+Q/dIhZahKPT6gLGQqnzyHMgKHAgCDgQlHMg+j4d7zYaB9he6jvyHAgKHAgCDgTlHIgn5/0Xa73UdeQ5EBQ4EARRuynnQDy2ZjnXNl/e5k9dR8CBoJwDcdtqr0gtTiyWudR35DkQFDgQBGeXlHMgOlsJ9pzXoaeV+o48B4ICB4KAA0E5B6LbON9eDv25e6Ca90Ce90CB90AQT5Zy3kPfN7993z3052UN1ZwH8pwHCpwHAs4D5ZyH29Z9F9kfwgTVfAfyfAcKfAcCvgPlfAfr2xZ3pj8vpKnmOpDnOlDgOhBwHSjnOnRbXe10+4J2rnWd5zlQ4DkQqrSc5/D0sG0zQ23Xus5zHChwHAg4DpRzHJ4edvc0+KK22eu5wG8giFhMOb+hb3+KPiXMZTW3gTy3gQK3gYDbQDm34ZnLOPawWr95XgMFXgMBr4FyXsPTp20ehx5W6zbPaaDAaSDgNFDOabjHseWM47nWa57PQIHPQMBnoJzPYKPqyRlsrnWa5zFQ4DEQ8Bgo5zE87ZuM51qfeR4DBR4DAY+Bch5D7+LXKhxVtS7zPAYKPAYCHgPlPIZ7VFkJJqwYtR7zPAYKPAaCyJWU8xieFeOMq2StxzyPgQKPgYDHQDmP4Z49bQ5jyLnWY57HQIHHQKhtch7DvS7PZJWs9ZjnMVDgMRDwGCjnMTy1fMZ2rnWY5zFQ4DEQxBWknMfwzNs2nvGL2mavwwKPgYDHQDmP4VkpWqjtmsdAnsdAgcdAEOWNch7D085Re9Y8BvI8Bgo8BgIeA+U8BosDZprknk1tPr81qSmI/bvnPRPV3Aby3AYK3AaCyGeUcxushH17J3R7qw+nIjW3gTy3gQK3gYDbQDm3wXLs9hL+jlwGJaj1m+c1UOA1EET9opzXcMcLs1ORXZJ+Qg+tdZznNlDgNhBwGyjnNvTT2v2OE7ZLNODLug68ngv8BgJ+A+X8hm6vgy1yGVtdQCvUus5zHChwHAg4DpRzHIady+7T8HFA7de6znMcKHAcCGK4UM5xeHJ+/x0Nar3WdZ7jQIHjQMBxoJzj8Nia5FzrOs9voMBvIIgqQjm/4bbV3m6eFmcIZp5a33mOAwWOAwHHgXKOw9hnEKOZ7ZBzre88x4ECx4EgVhPlHIduOn7Pyj7n2mav7wLHgYDjQDnHoe+3m/0ym6Gstb7zHAcKHAeCCEmUcxz69lbodq8qMLpqfec5DhQ4DgQcB8o5Dta3LYLVOKC2a33n+Q0U+A0E/AbK+Q3DIhBbjDycCWp957kNFLgNBNwGyrkNz7iW2MNqfed5DRR4DQTv2SnnNViOffuKdLjdqjkN5DkNFDgNBJwGyjkNz4wS27nmM5DnM1DgMxDwGSjnMzw9y2p9wBelzZ7LQIHLQMBloJzLYKPJcsZRVfMYyPMYKPAYCHgMlPMYrG8/OYPNtV7zPAYKPAYCHgPlPIanfUPESap5DOR5DBR4DAQ8Bsp5DNann1EFNtf6zPMYKPAYCHgMlPMYhvkI3LMotHOtyzyPgQKPgeAVKeU8BsvxKQHmXNvs9VjgMRDwGCjnMdhada/Pj0cG1TwG8jwGCjwGYuwvuR6zPclep3H2rHkM5HkMFHgMBDwGynkMz7p8fpQAylzrMs9loMBlIOAyUM5luFeONmKt13rMcxkocBkIuAyUcxnu0WU39bDW1FwG8lwGClwGAi4DZVwGiIXWzWYrwfCjziKdnDDua73muQ0UuA0E3AbKuQ0WnW3sm/phe1PYGdb8BvL8Bgr8BgKfQsr5DZbjsKjatkN0JajrwOu3wHEg4DhQwXE4xZVg2LtV2yleMDprPee5DhS4DgQ+pZRzHQb7nAfcs9RcB/JcBwpcBwKuA+Vch7HPacY+PRtwRllzHchzHShwHYhxjOV6bvsK3CVAm2s95zkOFDgOBBwHKjgO5uds6z3YXHMcyHMcKHAcCDgOlHMcnjhSVtv4RWmz5zhQ4DgQcBwo5zjctU1W2wJf1DZ7PRc4DgQcB8o5Ds+oOqPNtZ7zHAcKHAcCjgPlHAeLRPf07QZf1DZ7PRc4DgQcB8o5Dvd4tpjHF35R2+z1XOA0EHAaKOc0WM5P34acaz3n+QwU+AzUXTqpzbZXuce19TgYXbWu83wGCnwGAj4D5XyGp4dJHNe1rvNcBgpcBsKbhJzLMLj5nMHbqOYxkOcxUOAxEPAYqOAxmK67exrYXOs5z2GgwGEg4DBQzmG4bb5HF9hc6znPYaDAYSDgMFDOYRj7/tQiGA3wsKo5DOQ5DBQ4DAQcBso5DGNY7CRbNTHn2mav1wKHgYDDQDmHYQyr7bsE8EVts9dpgcNAwGGgnMNgNj9xozDn2mavzwKHgYDDQD1/V2q74budoay1HutejwUOA3WcjXM9Zu28a/ucVvtge63LPI+BAo+BgMdAOY/hqe07Whd8UdvudVngMRDufXIeg/XtOx7cgTnXNntdFngMBDwGynkMz7g+Q23XPAbyPAYKPAYCHgPlPIZh+7N7dDX4orTZ8xgo8BgIeAyU8xjucX3X+oAvapu9Lgs8BsJ9fc5jeEaXrSD739bX983d2Pfpw1QzYcp13Xj9FjgNBJwGyjkNY9+fjn27PeDuuOY0kOc0UOA00EAL8nendwSjXQLYl9ecBvKcBgqcBgJOA+WchmGvuGnE2q71m+c0UOA0EOrAnNNw23zdtsMXtc1etwVOAwGngXJOw7B9uO2KMOdat3lOAwVOAwGngXJOw9PHd84Tv6ht9rotcBoIOA2UcxruUWUlgNvomtNAntNAgdNAuEbmnIZh/JUzaedat3lOAwVOAwGngXJOw9POw2YW+KK22eu2wGkg12q5brvu9n2v52Y7+ILVvAbyvAYKvAYCXgNlvIan1i1ikZtRav3meQwUeAzkWi/Xb/fsyTbK4IvaZq/fAoeBgMNAOYfhbu97lEFZa/3m+QsU+AsE/AXK+Atg893uUNu1bvOcBQqcBQLOAuWchWcOk2hzrds8Z4ECZ4GAs0A5Z8HW52e9TlaQWr953gIF3gIBb4Fy3sLTw0aY02reAnneAgXeAgFvgTLeAkTlukeXtbu1gq1tJ6RU1oXnMFDgMBBwGCjjMLxy2jn6eGEQqYxqHgN5HgMFHgMBj4FyHoPlaCUYFmNh4Jd1HXj9FrgMBFwGyrkMluOwOAN3tC4oQa3jPJ+BAp+BgM9AOZ/BcrQSDHv9DScGNaeBPKeBAqeBgNNAOafBchxGP7kjl0EJal3neQ0UeA0EvAbKeQ0WH2zsW89pcQgmflnXgdd3gdtAwG2gnNtgOU6LuXBH64IS1DrP8xso8BsI+A1U8Bt2jlaCaW/yQYHU/Aby/AYK/AYCfgPl/AbLcdqu2qJ1YQlq3ec5DhQ4DjRxTOXxRqa4Ekx7JQ67qprnQJ7nQIHnQMBzoJznYDnOfeM/LQ64xQ3DktR60PMdKPAdaGK/SvXgtHiSFjsL1FjNdyDPd6DAdyDgO1DOd7Cc595tzQbtX+tAz3egwHcg4DtQzne4c6SW5Fzb7HVg4DoQcB0o4zo88WaeEkBZax3oeQ4UeA4EPAcqeA4W6ea0WoceVutAz3OgwHMg4DlQznOY28/iqW0oa60DPc+BAs+BgOdAOc9hbh8TG10TfExqngN5ngMFngMBz4FynsNt812CAV+UNnueAwWeAwHPgXKew22rRVc/8YvSZs9zoMBzIOA5UM5zeGo59rCa50Ce50CB50DAc6Cc53D3LDspgjms5jiQ5zhQ4DgQcByo4Dic1rctussd1Qm+rG33ui7wHAh4DpTzHCznpyT4RW2713OB50DAc6Cc5zD3/apFtJlw61VzGshzGihwGgg4DZRzGua+W5zd2h1zrm32+i1wGgg4DZRzGixHi+bj2rnWbZ7TQIHTQMBpoJzTYDbfcYTAh7/mNJDnNFDgNBBwGijnNLCp5budweZap3lOAwVOAwGngXJOw93O21PjMtUE3gs1r4E8r4ECr4GA10A5r+Hp40nOtS7zvAYKvAYCXgPlvIZ7RiHLGb+obfa6LPAaCHgNlPMabA67c8aeVusyz2ugwGugE1einNdwx8i6exx8UdvsdVngNRDwGijnNdw23+Mb+nityzyngQKngYDTQDmnwaI1zW5/LYYSlqC23euzwGsg4DVQzmuwHGeImQQlqHWa5zZQ4DYQcBso5zbcMZJMNXX7C/N6rdc8v4ECv4GA30A5v+GOlWQaZp+iTbj9vGrd5jkO65+fdXCBbss5DlaCOeyvRevBL8s68DwHCjwHAp4D5TwHy3He8aNGLEGt4zzXgQLXgYDrQDnX4YmZNFxJJpwQ1XwH8nwHCnwHAr4D5XyHue/bp0UFIPsLJaj1nOc8UOA80IV1mes5e8dsbzNtFgZfk5rrQJ7rQIHrQMB1oJzrYBER5mUlGfBFbbvXdYHnQMBzoJznYDlO26MKjL5a13mOAwWOAwHHgXKOw9wnw/M026G9a13n+Q0U+A0E/AbK+Q13/AlbgU78orbZ67rAbSDgNlDObZj7BnDu8/kJdxQ1r4E8r4ECr4GA10A5r2Hue5lp53BwJ1VzGshzGihwGgg4DZRzGub18QYf+3at5zyfgQKfgYDPQDmf4bbVToDAt7/mMpDnMlDgMhBwGSjnMjyjatc6+EXWPAbyPAYKPAa6sKfm52yX9TCzGXOubfZ6LnAYCDgMlHMYpp1y37UOtV3rOc9doMBdIOAuUM5duGdNm0Wxlmod57kLFLgLBNwFyrkLzxzW4niu9ZvnLlDgLhBwFyjnLjw5n3HernWb5y5Q4C4QcBco5y5YbKy7h0H71NwF8twFCtwFAu4C5dyFexxfcTzX3AXy3AUK3AUC7gLl3IV7PNsLd5jDau4Cee4CBe4CAXeBcu7C3bOsvaWFPl7zF8jzFyjwFwj4C5TzF+5xfcV1uuYvkOcvUOAvEPAXKOcv3Dnfs6jAF7XNXo8F/gIBf4Fy/sJTy5Zzgy9qm70eC/wFAv4C5fyFO16MnfzYfH5+zK62ngumWNeJ12uBz0DAZ6Ccz2Alm2JK0aK5QAlq3eY5DRQ4DQScBso5DZbjtFjmZ1aCug68fgu8BgJeA+W8hieejC/JhGgANbeBPLeBAreBgNtAObdh7pPB87jjyOy/MCprPef5DRT4DQT8Bsr5DadFdbl8CU6IS1BzHMhzHChwHAg4DpRzHOwV8Wkxj0Fd1fwG8vwGCvwGAn4D5fwGy/Hcb3lPOC2r+Q3k+Q0U+A0k2INTXXfuPem596gn3PTU3Aby3AYK3AYCbgPl3IbnzfZtO3xR2+x1XeA1kKBuSHXdub0WbtvR5lrXeV4DBV4DAa+Bcl7DyWbrrm1c72td53kNFHgNJDhbp7rutBMgi2yGfbvWdZ7XQIHXQMBr4JzXcNu8PTTO54U817wG9rwGDrwGBl4D57yGu5ZtXDfMubKZPaeBA6eBgdPAOafhGc/Ww074ora5eZs/dR0Dp4FzToO180lmM+Zc29y8zZ96joHTwDmn4W5ftjmswRe1zeRt/tRzDJwGzjkNVtv3/P3MJFxzGthzGjhwGhg4DZxzGs594n+yfM7bXPMZ2PMZOPAZGPgMnPMZnp7FSc61zext/tRrDFwGzrkMFmPj7mEEtV3qNPY8Bg48BgYeA+c8hnscUzKeS33GnsPAgcPAwGHgnMNw1zKF2ZNr/gJ7/gIH/gIDf4Fz/sJJzfcwnAFKPcaeu8CBu8DAXeCcu3DP2zaeD+hhpQ5jz1vgwFtg4C1wzlt4tIgkOdc2T2/zpw5j4Cxwzll4Vgz5XJ+55iuw5ytw4Csw8BU45yvcNlttY98udRh7vgIHvgIDX4FzvsJjq83fkHOpw9jzFTjwFRj4CpzzFZ7ZM5m3Sx3Gnq/Aga/AwFfgnK/wzNct1napw9hzFThwFRi4CpxzFZ52DtqTa64Ce64CB64CA1eBc66CxcYxBXgrhXvVtJKZXrN4UgIpl3Xj+Qsc+AsM/AXO+QvvqD0aX2jsvxZ7ocGXZR15DgMHDgMDh4EzDoPlqH99FB9Xglq/eR4DBx4DA4+Bcx7DHVeEsCTrr73x2l4N5xPXnWtOA3tOAwdOAwOngXNOwxMBY8Sca13nOQ0cOA0MnAbOOQ1nN5vv+BPvfw9ojVrfeV4DB14DA6+Bc17D2cdHrZ/wRW2713eB18DAa+Cc1/DO0dpd/8IorPWd5zVw4DUw8Bo45zXctb7HAPh2cc1rYM9r4MBrYOA1cM5rGHd7W4wVqO1a33leAwdeAwOvgTNew6rda888+/TzHEmt1zrPcxs4cBu4YR3mOq9jzh99vNZ5ntvAgdvAwG3gjNvwstHV+tkh51rneW4DB24DA7eBc27D3c53u8PMUus8z23gwG1g4DZwzm2waD7nPc9DO9c6z3MbOHAbGLgNnHMbnnZusY/XOs9zGzhwGxi4DZxzG55xbX0bcq51nuc2cOA2MHAbOOM2QA8bHGfRWud5bgMHbgMDt4FzbsMdF8wiYeCoqnWe5zZw4DYwcBs45zbcOdsLyQP6dq3zPLeBA7eBgdvAObfhWSUt+seAL0qbPbeBA7eBgdvAObfhnfNq732fcg7MubTZcxs4cBsYuA2ccRueHG/bH29DrnkM7HkMHHgMDDwGznkMbHF9Oc4kNYeBPYeBA4eBgcPAGYcBarmbzVDWWpd5/gIH/gIDf4Ez/gLmHGeSmrvAnrvAgbvAwF3gjLvwrM/HwdbT4IvaZq/HAm+BgbfAGW/BctYc7xLAF7XNXo8FzgIDZ4EzzoLlCCU4obZrPeY5Cxw4C0zYXxI9Bjmf9he/qG32eixwFhg4C5xxFjDnHVlSYFTVOsxzFjhwFhg4C5xxFp72pX0fShfUdq3DPF+BA1+Bga/AGV8BcraouXDGWPMV2PMVOPAVGPgKnPMVLKKkzWX8vK3jmq/Anq/Aga/AwFfgnK9gOd4xLeHOoOYrsOcrcOArMGFPTXXYbXNrNq7hi9pmr8MCX4GBr8AFX+GLJqn5Cuz5Chz4CgzROLngK3zRJDVfgT1fgQNfgYGvwDlf4asmqXWY5ytw4Csw8BW44Ct80yS1DvN8BQ58BQa+Amd8he+apOYrsOcrcOArMPAVOOcrfNMkNV+BPV+BA1+Bga/AGV/huyap+Qrs+Qoc+AoMfAXO+ArfNUnNV2DPV+DAV2DgK3DGV/iuSWq+Anu+Age+AkOEG874Ct81Sc1XYM9X4MBXYOArcMZX+K5Jar4Ce74CB74CA1+BM77Cd01S8xXY8xU48BUY+Aqc8RW+a5Kar8Cer8CBr8CMY+SLDss1Sc1XYM9X4MBXYOArcMZX+K5Jaq4Ce64CB64CQ6wczrkK3zRJzVVgz1XgwFVg4CpwzlX4pklqrgJ7rgIHrgJDXBjOuArfNUnNTWDPTeDATWDgJnDOTZh7pbCXix3n21qHeV4CB14CM47O/F2BvZU0wj2cPtacBPacBA6cBAZOAuechGYvznfOF6ihmovAnovAgYvAwEXgnItwvxO9XySDzbUO81wEDlwEBi4C51wEs/nafbzB3V7NRWDPReDARWDgInDORbCc275txtuAmovAnovAgYvAwEXgnIvQdg+7cwY1VHMR2HMROHARGLgInHMR7pzJch7wRWmz5yJw4CIwcBE45yI8Oe87XyxrrcM8F4EDF4FxXsi5CJZzt6hYsErWXAT2XAQOXAQGLgLnXASLbWCjC3tYzUVgz0XgwEVgeDPLORfBcnyiK0A71zrMcxE4cBEYuAiccxFOuym/dzf33hK+rG33eizwERj4CFzxESyWuO3stvJ/GNxc8xHY8xE48BEY+Aic8xHM5tNuyCfYXusyz0fgwEfgjv0n90cbuLfUv/hFbbPXZYGPwMBH4JyP8ORsNkPOtS7zfAQOfAQGPgLnfIS7lscZa7vWZZ6PwIGPwMBH4JyP8PTtM/bxWpd5PgIHPgJ3rLv8nnIOZzNEcOeaj8Cej8CBj8DAR+Ccj3Da7f9u5+OwHR+MrlqfeU4CB04CwwsXzjkJTztzknNtu9dngZPAwEngnJPwjOs7ij18Udvs9VngJOi3kE4+pwm098vmd+2bv9ppdbL/3lFxoW5qHec5Chw4CgwcBc45Cudp436X9IScax3nOQocOArccQbLz9PuWNN3zGn4orbZ67jAUWDgKHDOUTj3u6C71qEd"} |  |  | - |  | - | -
[14 empty] | {"index":100,"total":402,"filename":"Advanced_Project.ifc","data":"fD4xn9xn62FkfRxS1D6f3ucz+AxhE26pz3t8X+Y7pKh9bt7nFnyG8x9uqc/H0zKmqH1u3ucWfIbIN/e8bz8sYw/rtc/d+9yDzx3zSX1u1rcpziS99rl7n3vwGQ7omVKfj+Z9hsuWTLXP5H2m4DM8M8eU+3w8VhRMUftM3mcKPkOMkfmrz9becCmSufaZvc8cfAbZw5z3bfGWsYdx7TN7nzn4DEfeLLnP5FdJ7GFS+yzeZwk+Qwyf5etaZSXA2pbaZ/E+S/AZbopwqt/2WmXrMwBAuNZt7HUbB93GoNs41W33itHiKlnrNfZ6jYNew48mOdVr9/psowtqu9Zh7HUYBx2GZ+Kc6rB7jUrm7VqHsddhHHQYgw6TXIfZ3GVrFswkUusw8TpMgg6TF+aTj2ez/GlnOePKIbUeE6/HJOgxAT0muR6zHtbiyiG1HhOvxyToMYHWk1yPbYs2l12QovbZ6zEJekxAj0mux2jVMi/LcBYitR4Tr8ck6DEBdSW5HjOLvGodvj+RWo+J12MS9JiAHpNcj23LEn2u9Zh4PSZBj+HDupLrMVrtTKsEhClqn70ek6DHBPSY5HqMbcVY7Q2ftEmtx8TrMQl6TECPSa7HrIf11c5wxUFqPSZej0nQYwJ6THI9RtazJPawWo+J12MS9Jhgq+V6jB61DR9hSK3HxOsxCXpMQI9JrseaPHyGstZ6TLwek6DHhDGf1OcufjxjO9d6TLwek6DH8Aqi5HpsjypTvzCeaz0mXo9J0GMCekxyPbbHMZnvkKL22esxCXoMP5yTXI/ZHLZHF9R2rcfE6zEJekxAj0mux+gxb8OdQan1mHg9JkGPCegxyfWYWdxrFfhc6zHxekyCHhPQY5LrMZs9ezKeaz0mXo9J0GMCekxzPWaWOfZtrfWYej2mQY8pqCrN9Rg9LMMFVq11mHodpkGHIatDcx2257DmV0ubYWT9WT+/3SI7aiWFOqp1m3rdpkG3Keg2zXXbtepIKLFc15HXbRp0G77hrbluM8vLZ3zrUWvdpl63adBtCrpNc90m4mq/wadDWus29bpNg25T0G2a6zZr3yup7Vq3qddtGnQbviKjuW5Tq+01/hVT1D573aZBtynoNs112zoz6Baxhc8ltNZt6nWbBt2moNs01W3d9t3mM3zErrVuU6/bNOg2Bd2muW5b5yPNollwQqO1blOv2zToNgUtpLlu233aRhWmqH32uk2DblPQbZrqtvk0+ef3sjkNUtQ+e92mQbcpKBLNdZtY+27fIUXts9dtGnSbgm7TXLfZaZO1N+gtrXWbet2mQbepyydv5+b6Nr4cprVuU6/bNOg2Bd2muW6zlcL6Nrx+q7VuU6/bNOg2xRkp1236sKxoufbZ6zYNug0ZCZrrtj2ek5mk1m3qdZsG3aag2zTXbdfDZ7gzorVuU6/bNOg2fKLoynXb1iYtjOer1m2X121X0G0XzEhXrtu2IrC+LZCi9Pnyuu0Kuu0C3Xblum3PmhRmz6vWYZfXYVfQYYhbvAoddvhVEuawq9Zhl9dhV9Bh+MnIleqwu30pjKqr1mGX12FX0GEX6LAr12GX1bKEUXXVOuzyOuwKOgyvgV+FDruc5Q7RyqvWYZfXYVfQYRfosKvQYdejb2OK2mevw66gwy7QYVeqw2yPYZbxW8ur1mGX12FX0GEX6LAr12HHXh39ark1qf29rd+rbuDuxlXrtcvrtSvoNfww+Ur1Wl+nUX2dyPV16txx3Na67fK67Qq67SLMJ6+jw5dgncx1OIG9av12ef12Bf2GDJcr12/botXFFUtQ67jL67gr6LgLdNyV6rjb4irBOsHpcF521Xru8nruCnruAj13pXpuW2xWFxJLUOu6y+u6K+g6JLhdqa7rK97a+yrJijl3uIV51fru8vruCvruAn13pfpuW+zWChRLUOu8y+u8K+i8C3Teleq8bdFKQFYX0Aq13ru83ruC3rtA712p3tsWyepCYglq3Xd53XcF3XeB7rtS3bctWglWlBSfGbpq/Xd5/XcF/Xfd+q+/Uv23La5YZRf7tZLRs0STQlWUaBqBEo0/PupkpoV80jpZ60e3iIKi5aouZmbe8hUsQ12kurCvGOZt+YAUtc+H9/mpC2dayOe7z6vWb/0/UtQ+H97npy6cae98cl1o7b1W6S5Q26UunJk5y09dONNCPqnP1uPYfIbaLnXhzMxbDj6f4HOqC3eftj7OUNulLpyZOctPXdjhnYPx33k7P32+IEXtc/M+P3VhB+xsf+W60PZ51rcFylrqwpmZs/zUhTMt5JO3s9XyFft2qfdmZt5y8LmDz7neM5/XeYxr51Lnzcyc5afOm2khn7ydL9/OOIeV+m5m5i0Hnwl8zvXdnrso9rBS183MnOWnrptpIZ+8nclbVkxR+8ze56eem2nvfHI9Z7W9fYaZpNRxMzNn+anj+gvHSK7jbAYxy9jDSv02M/OWg88CPuf6TcivGAw9rNRtMzNn+anbZlrI52vfNssuRe2zep+feq3DK3lj85qvz6tvrx0krd0UvezPViLo86V+m0ZciZ76DR/PHv+d1sX1mGFsxrH13FqJsUR1HV2+jp56bqbd+Rypntt1snbjdMfzRoqyLg6v246g2+D5gvkZVWp5WVy7bLrjeSNF6fPhddsRdNsBuu1IdRtZfGdFmui4IEXts9dtR9BtB+i2I9VtZpleVtsEKWqfvW47gm6DT5/6keq23dctugZ9/qh12+F12xF02wG67Uh1m/Ww3fcvaOdatx1etx1Btx2g245ct11Wy1es7Vq3HV63HUG3HaDbjly3rRMB69vO51q3HV63HUG3HaDbjlS33aPqiuO51m2H121H0G0H6LYj1W30okdtg8+1bju8bjuCbjtAtx2pbrtH1WV9HFLUPnvddgTddoBuO1Lddo9jsfaGFLXPXrcdQbcdoNuOVLfd7ZyMqlq3HV63HUG3wUOI47+/+rz7NswktW47vG47gm47QLcdqW7bK8XRos+1bju8bjuCbjtAtx2pbrPZ81YO4HOt2w6v246g2w7QbUeq27blI+nbtW47vG47gm47QIUdqW67+7TNZZii9tnrtiPotgN025HqNlqRXlpxVlo35gnXmlqnHV6nHUGnHRfmk/puFlfkl84jKUFdB16XHUGXHaDLzlyXrVjztmwlub+M6Wetz06vz86gz07QZ2euz9ZttV2SFX+l+6beSFnWwel12hl02gk67cx12i7Bao0V+SVYi85ar51er51Br50H5pPWwba4SrLi774EdR143XYG3XaCbjtz3davh+VVkpuK0s9av51ev51Bv53Qo89cv62oN5HVBbR/rd9Or9/OoN9O0G9nqt+IxFtGn2v9dnr9dgb9doJ+O1P9RivKTSvOThDNPmv9dnr9dgb9Bi8r9jPXb9tX8x3KWuu30+u3M+i3E3tsqt/YdoK2W1aYaWr9dnr9dgb9doJ+O3P9tmJQtKIiBBrkrPXb6fXbGfTbiXWX6je21dUsX9DDav12ev12Bv12gn47c/22otm8NA3jXFTrt9PrtzPotxPrLtdvapYl+lzrt9PrtzPotxP025nrtxX9ohXlANhfP2v9dnr9dgb9doJ+O3P9tu5XEJvP0Ldr/XZ6/XYG/XaCfjtT/ca2K1oRHsZ1t9Zvp9dvZ9Bv8CzbJAqkPcxqucVRVeu30+u3M+i3E/Tbmeu3a9fy+/eyWoeo1lnrt9PrtzPotxP025nrN334Lmi59t3rtjPothN0W8t12+7bRxhdrdZrzeu1FvQafC06n0JOe9oa17b/hn1Zq3Va8zqtBZ3WQKe1VKfx2insvg7jutX6rHl91oI+g6+Dx3+n7XztnmW+Q4raZ6/LWtBlDXRZy3XZXiX3nAYpap+9HmtBjzXQYy3VY1bbZpkP6GG1Hmtej7Wgx4Dm2luux2wWtbgp7L9brcea12Mt6LEGeqzleszG8zpLcD7Xeqx5PdaCHmugx1qqx9iiHdt38LnWY83rsRb0WAM91vJ42uVHFa4crdZjzeuxFvRYAz3Wcj0mZvmIM0mtx5rXYy3oMfhmc/x36rM85jBGy7XPXo+1oMca6LGW6rHtq0icw2o91rwea0GPwZeT82nq1Of2aGe0XPvs9VgLeqyBHmupHrstHtHnWo81r8da0GPwvcNE9X1dq5KZpNZjzeuxFvQYkGF6K/SYaRNTBlDWWo81r8da0GPw5dT473w8Wzsn83atx5rXYy3osQZ6rH3VYzaqGM4EWq3DmtdhLeiwBjqs5Trsuvx4FrRc++x1WAs6DPByvec6zGrbdrWgAHutw7rXYT3oMLiZPf479/nwlmFU9VqHda/DetBhHXRYz3XYYaujzWEHpKh99jqsBx0G953Hf+f7aLNstU6QovbZ67AedFgHHdZzHcZm8YqWax3WvQ7rQYd10GE9j4spudpmOBPotQ7rXof1oMM66LCe6zD28RJnudZh3euwHnRYBx3WUx12t+8Ve1itw7rXYT3osA46rOc6zOLgO25idWDj2xSize97xvn8e2zPWrd1r9t60G29Yz5pHZ3b4vpdPfOEeaDWb93rtx70Wwf91lP9ti02KwnFEtQ6rnsd14OO66Djeh5Xa81btpLA6UWv9Vz3eq4HPddBz/Vcz63TCu5m2eoEyl7ruu51XQ+6rjPmk9bBujHP6xRjl6DDmKn1Xff6rgd910Hf9VzfrX0ar7HBoKZ7re+613c96Du8C9pzfbciPmz78g49r9Z33eu7HvRdB33Xc323LMpSmILrda3vutd3Peg7vLXWU33H66yITfOApu21vute3/Wg7zrou57qO/N11zbEInqt77rXdz3ouw76rqf6jm02JrOMKWqfvb7rQd910HeU6jte5yNsURC4z0S1viOv7yjoO3gqffx36rPFzz+xiPaycU6YsvSdvM6joPMIdB7lOm+dCe5RBqOLap1HXudR0Hl4wk+5zjPFYepaMUXts9d5FHQegc6jVOftvr1nFrBc6zzyOo+CzsMTfcrjbda3mcLoolrnkdd5FHQegc6jVOfdtXzEHlbrPPI6j4LOo4b5pD6baqLd1yFF7bPXeRR0HoHOo1zn2e5J44xCtW4jr9so6DY8sadct9kqafEYAp9rvUZer1HQawR6jXK9Zj6bZTidolqnkddpFHQanh1TrtPEzWUnsJhGitpnr88o6DMCfUa5PtvjOfG51mXkdRkFXYanXJTrMlsxzHf0udZj5PUYBT1GoMco12P66NsQGaBaj5HXYxT0GMawqNBjZpnivF3rMfJ6jIIeI9BjOR+B6bFiYJ+s9ZjnIvTAReiEHuR6zHzlI84ktR7zPIQeeAgdeAg95yHc2sSUIPSwWo95zkEPnIMOnIOecw7unkXR51qPec5BD5yDDpyDnnMO7p4VZ5Kac9A956AHzkHHU4+cc3DPnqvW4a5OzTnonnPQA+egA+eg55yDbdFKAHNYzTnonnPQA+eg412QnHOwZ5KtENBy7bPXYYFz0IFz0HPOAWt7jGewXOswzznogXPQMT6Tcw7u2rZxjSlqn70OC5yDDpyDnnMOtjK44qiqOQfdcw564Bx0jEXknANZp4/3Dg9qu9ZhnnPQA+egA+eg55wDs8x2dgBngDXnoHvOQQ+cgw6cg55zDnjdcLxLgJZrn70OC5yDDpyDnnMOdi3veAnUdq3DPOegB85BxzUv5xyYz3f0AlPUPnsdFjgHHTgHPeccWPvu2kafax3mOQc9cA66G52pDjNy0h03sTogH1PY2mXPOH980kO/qHWb5yL0wEXowEXoORfB2E6yTivlZfwiWONq/eb5CD3wEbqbT1L9ZhblZZSplpSgrgOv4wInoQMnoeecBLNoJZB1uiUrwivrREBWa8q5yR2Qc11HXu8FnkJHxZrzFHYJrETdSiRWMsihriuv/wJfoQNfoed8hbtOVh3hPF/rP89X6IGv0IGv0HO+gtX6Zgy0Fluh1oGes9ADZ6EDZ6HnnAWzLMZZgJms5ix0z1nogbPQxeWT+r4i/mKchQNTlD57vkIPfIUOfIWe8xVknTHIYT0NLNc60PMVeuArdOdBqgNlnYLJikEKnK/UfIXu+Qo98BU68BV6zlfYvp5GtRBIUfvsdWDgK3TgK/SCr2CaqFlPQ8u1z14HBr5CB75Cz/kKYu8325t42CdrHej5Cj3wFTrODzlf4e5h1rehnWsd6PkKPfAVOvAVes5X2LPoaX0barvWgZ6v0ANfobsxkurAu32P2MNqHej5Cj3wFTrwFXrOV7gtmu8HpKh99jow8BU68BV6zlfYK0dLxnOtAz1foQe+Qge+Qs/5Cvd4TuawWgd6vkIPfIUOfIWe8xX2DNKu2M61rvN8hR74Ch34Cj3nK9h4vi1DWWs95/kKPfAVOvAVes5X2D3MOBo4k9Q6zvMVeuArdOAr9JyvsGeSnqyStT7zfIUe+Aod+Ao95yvs9bknK0atxzxfoQe+Qge+Qs/5ClsVmTZtMJ5rPeb5Cj3wFTrwFXrOV9jas+0SQIraZ6/DAl+hA1+h53yFbfmU4HPNV+ier9ADX6EDX6HnfIW9Ylh7QzvXfIXu+Qo98BU68BV6zle4e9jeCUCK2mevwwIvoQMvoee8BFl7VlknOAJnRzUvoXteQg+8hA68hJ7zEmTFmoXNMpS11mGel9ADL6EDL6HnvARZ+3NZ5ygCLwrVvITueQk98BI68BJ6zkuQ9VXmrm2IWdS8hO55CT3wEjrwEnrOS7h9DXSaXvMSuucl9MBL6MBL6DkvYbfzx/d2mAqG+GvNTeiem9ADN6EDN6Hn3ITdx9eZsOtptR7z3IQeuAkduAm94CbYirG5ZuBzrcc8N6EHbkJX9CDXY3t0Wbtjitpnr8cCN6EDN6Hn3ITb4hUt13rMcxN64CZ0dfnk7Xw5n4GD1GtuQvfchB64CR24CT3nJuw5jPfMAilqn70eC9yEDtyEXnATTBnscQ0+13rMcxN64CZ04Cb0nJuwfbaZBW6X1NyE7rkJPXATOnATes5NsNFklt2oqvWY5yb0wE3owE3oOTfhXjla9LnWY56b0AM3oQM3oefchLu2k9Wy1mOem9ADN6EDN6Hn3ITb8lYKkKL02XMTeuAmdOAm9JybcFu0efuCFKXPnpvQAzehAzehF9yE/pg99xpmJVp/XpF9tSi3xds3heoAS3VdeR0XeAsdeAs95y3IOskVi3bDuWrNW+iet9ADb6EDb6HnvAW1WLFKtFzrOM9b6IG30IG30HPegrWC2umGYoraZ6/jAm+hA2+h57yFXcvr5Ad1ds1b6J630ANvoQNvoee8BTX1ZOQWuN9W8xa65y30wFvowFvoOW9B1/mJHvYLfbvWb5630ANvoQNvoee8BRtdelg7g8+1fvMchR44Ch04Cj3nKGxfVw9TiKfV/ITu+Qk98BM68BN6zk+QzccRm1EgRe2z12+Bm9CBm9BzboJazGHdEj4sxgT3YmpuQvfchB64CR24CT3nJmyenc376Hut4zwvoQdeQgdeQs95CVbrNr4VvjesOQndcxJ64CT0C9fMPK62V46kvWsd5/kIPfAROvARes5HsBlF7bsDuLVQcxG65yL0wEXoF87GuY5ba9ZtGVPUPnsdF3gIHXgIPech2Ox5W4Z2rnWc5yD0wEHoF3qQ86/2eLa1C1PUPnsdF/gHHfgHlPMPzNd7BRFIUflMnnNAgXNAwDmgnHPQ9jrdnmsW1ZwD8pwDCpwDAs4B5ZyDNYfdCkHA51KPkeccUOAcEHAOKOcc3KqInn2bas4Bec4BBc4BAeeAcs7BrUnNd/C51GPkOQcUOAcEnAPKOQc2h9k6rVhLpR4jzzmgwDkg4BxQzjkwX2/fCVLUPjfv81OPEXAOKOccmOq19tYD+napx8hzDihwDgg4B5RzDm49FmZPqjkH5DkHFDgHBJwDyjkHW4fZKontXOox8pwDCpwDAs4B5ZwDPbzuBiVINeeAPOeAAueAgHNAOedg92nraVjbpR4jzzmgwDkg4BxQzjm4LdssCj6XOow854AC54CAc0A552Cr39P6NswkpQ4jzzmgwDkg4BxQzjm4R9UVLZc6jDzngALngIBzQDnnYCv9rfyhtksdRp5zQIFzQMA5oJxzoOsce+vvW29TzTkgzzmgwDkg4BxQzjnY7btXSfC51GHkOQcUOAcEnAMqOAeHxUlsVNnvY/Xc/cHG/SoxrkmlbiPPP6DAP6AXjuZUt+k669dNkzOyHqw0pX4jzzugwDsg4B1Qzjvou3/YXnST9SBlWQeee0CBe0DAPaCce2AW9Xxw7VwJyjrw/AMK/AMC/gHl/IO+fV+jc/PtDkhZ14HXdYGDQMBBoJyDYBbViHr7F0tQ14HXd4GHQMBDoJyHYCQ9XWfG2ozlBmWvdZ7nIlDgItCBrZnqPLOom+1HSQnqOvB6L/ARCPgIVPAROrkSqNEFCVqh1n2ek0CBk0DASaCck2AW1eiCm2uHJajrwOu/wEsg4CVQzkswi1YC3XTBC1LWdeB1YOAm0IGtmetAa4UVLVerA+OduZLUdeF1YeAoEHAUKOcoGH1KjXfGYLnWhZ6jQIGjQMBRoJyjYL6a74o+17rQcxQocBQIOAqUcxR08wyNiwQ9r9aFnqNAgaNAwFGgnKOw23vdVlGspVoXeo4CBY4CAUeBco6Ckm9nV9u1LvQcBQocBQKOAuUchd2+22e0XPvsdWHgKBBwFCjnKChZD9u1Dilqn70uDBwFAo4C5RyFu7avxHLts9eFgaNAwFGgnKNwj2erbYIUtc9e5wV+AgE/gXJ+grH71Mb1OoNU+3vjoF0w2mrd53kKFHgKBDwFynkKuumRsS5qjgJ5jgIFjgIBR4FyjsL23aIqMKvW/ATy/AQK/AQCfgLl/AS19hezDGWt9Z3nJlDgJhBwEyjnJtyWrf0xRe2z13WBl0DAS6Ccl6DrnH3XtkA713rOcxIocBIIOAmUcxLUdlPGu4PIcM1JIM9JoMBJIOAkUM5J2LX98b2dh7U3+F7rOM9LoMBLIOAlUM5LuNv5iu1d6zfPS6DASyDgJVDOS7gtGgcJRlet2zwvgQIvgYCXQDkvYc9lu92hvWud5nkJFHgJBLwEynkJ92x6xHFd6zTPS6DASyDgJVDOSzCG2z1/g8+1TvO8BAq8BAJeAuW8hD2Hya51SFH77HVa4CXQiXWXc0rtjGmPa+hhtU7zvAQKvAQCXgLlvITts/UwhfFc6zTPS6DAS6ATR2eu0+ysyfiU2M61TvO8BAq8BAJeAuW8hHtUtehzrdM8L4ECL4GAl0A5L+Gu7WS1rHWa5yVQ4CUQ8BIo5yXclrdSgBS1z16nBU4CASeBck7CbdFmEujbtR7znAQKnAQCTgIVnASLgllM0t5XPy9IWfrueQkUeAkEX9RQzkswi2ov+W/WF5agrAPPTaDATSDgJlDOTbiJWocrCdxjpJqfQJ6fQIGfQMBPoIKfYGQti4LZWdR9b4JqjgJ5jgIFjgIBR4EKjoLFni4rgZG2oAS1bvM8BQo8BQKewvjvtB/Y/G4vxvasBHUdeP0WuAoz7Z1PwbnybC8ryXXfm6Gar0CerzD+GOoA9FvOV7jWrYbLaAebPoUlqOvA67jAWSDgLFDOWbjsJfhN3hIrEaSs68DrucBbIOAtUM5buNbKc63o+AU7xJq3QJ63QIG3QMBboJy3cK1oyLX6wXWC5VrPed4CBd4CAW+Bct7CtrjOY68D2rvWc563QIG3QMBboJy3cK12vtgYQVDWWs953gIF3gI1l0/q82HtLLG2az3neQsUeAsEvAXKeQvXOiG8uvkMK02t5zxvgQJvgYC3QDlv4bJ53vr4zcFafy+QQ10HXt8F/gIBf4Fy/sK19qbXWvMunJtqfef5CxT4CwT8Bcr5C9c6+b+6/UK71/rO8xco8BcI+AuU8xeubr4aKwhGWa3vPH+BAn+BGuqEVN/tuWydu15wr6bmL5DnL1DgLxDwFyjnL1wr0nuRzaYCKUqfPX+BAn+BgL9AOX9hj2ubYZzl0mfPX6DAXyDgL1DOX9iWbYYB/VXzF8jzFyjwF6i7fPLx3bzPcIpR8xfI8xco8BcI+AuU8xeudW5293GCFLXPXrcF/gLhaXjOX7ga+RWkYYraZ6/XAn+BgL9AOX/hOq19Jfpc6zTPX6DAX6COHuQ6zXxutoZdkKL22euzwF8g4C9Qzl/YFq0EHXpYrcs8T4ECT4HwtDvnKeza3msYjOdal3mOAgWOAgFHgXKOwu7T1scbWK51mecnUOAnEPATKOcnmGWjVwAHi2puAnluAgVuAgE3gXJuwm7nnliudZnnJVDgJRDwEijnJdyKwNZnTFH77HVZ4CQQcBIo5yTc7bu1CaSoffa6LHASCDgJlHMSbsvJHFbrMM9JoMBJIOAkUM5J2Bp0qyFo51qHeU4CBU4CASeBck7C3u2cUQXXnATynAQKnAQCTgLlnIS9y7ESdBjPtQ7znAQKnAQCTgLlnIR7Z9fCnqPmJJDnJFDgJBBwEijnJGyLVgLY4dWcBPKcBAqcBAJOAuWchG3RahvugNZ8BPJ8BAp8BAI+AuV8hOswzWm+C6SoffY6LPARCPgIlPMRbrVr7Qy1Xeswz0egwEcg4CNQzkfYlrfiB59rHeb5CBT4CAR8BMr5CHdtb90NKWqfvQ4LfAQCPgLlfIRb6dsvQYraZ6/DAh+BgI9AOR/hYttPUfS51mGej0CBj0DAR6Ccj3CxjeMWVoyaj0Cej0CBj0DAR6Ccj7At710Opqh99jos8BEI+AiU8xG2Zbpi3651mOcjUOAjEPARKOcjbIVv7Q0n6jUfgTwfgQIfgYCPQDkf4bZsygAs1zrM8xEo8BEI+AiU8xG2CuKkb9c6zPMRKPARCPgIlPMR9kphUSqI0NR8BPJ8BAp8BAI+AuV8hB2ZM8s4k9Q6zPMRKPARCPgIVPARTuOQPtRve4zzHbW0P6//O8SSap4CeZ4CBZ4CAU+BCp6CWbaSGq0E9qA1V4E8V4ECV4GAq0A5V8EsXvY+9+bbQQlqHef5ChT4CgR8BSr4Cs1btpJccPej5iyQ5yxQ4CwQcBYo5yxc62T+MmLL5tsRpCzrwPMWKPAWCHgLlPMWLmMPGPfKdsnwvUvNXSDPXaDAXSDgLlDKXWivz96lvT6nVu0F+7Wau0Ceu0CBu0DAXaCUu9Be57L8WQNnCSBF7bPXd4G7QMBdoJS7YBZH7a8ed7NjqOYukOcuUOAuEHAXKOUujNpdPnerbWjnWt957gIF7gIBd4Fy7sJ1WTu3WNu1vvPcBQrcBQLuAuXcheta7Xsun2ElqrkL5LkLFLgLBNwFSrkL7XXY6/fLZxtlNt7hRLbmMJDnMFDgMBBwGCjnMFy6+HYv6+vQ7rXe8xwGChwGAg4D5RyGS5fvp/2Cz7Xe8xwGChwGAg4DpRyGUfvLV+Pcgg6oOQzkOQwUOAwEHAZKOQw2l42et9Z5uIFRcxjIcxgocBgIOAyUchhG7V42i65fTFH77PVe4CoQcBUo5Src49pmGLRc6z3PU6DAUyDgKVDKUzDLNsPMvg4pap+93gscBQKOAqUchTmKHj7DPF7rN89HoMBHIOAjUMpHGH16Wd59HEZVrds8D4ECD4GAh0ApD2Fa8isIziS1XvM8BAo8BAIeAqU8hGFpte/Vos+1TvMcBAocBAIOAqUchNvnw9YwghSlz56DQIGDQMBBoJSDcFvcJRBIUfrsOQgUOAgEHARKOQhW27CGHZCi9tnrssBBIHijmlIOAvRp6+OYovbZ67LAQSDgIFDKQTDLN+cO1piag0Ceg0CBg0DwFjmlHARoZ0ks1z57XRY4CAQcBEo5CLciOGxUXZCi9tnrssBBIOAgUMpBuNv3tbUJpKh99roscBAIOAiUchCgZ8U5rOYgkOcgUOAgELyzTykH4dagWw3BTFLrMM9BoMBBIOAgUMpBuHc7r6iCaw4CeQ4CBQ4CCfbUPO6mts+yX0xR++x1WOAgEHAQKOUg3Pusy3oYzGG1DvMcBAocBIL3eynnIGyLe6cHfbvWYZ6DQIGDQMBBoJSDcO9m7ewA7tzXHATyHAQKHASCN04p5yBcl/VtU0WYovbZ67DAQSDgIFDKQbjVrt0ugC8cag4CeQ4CBQ4CweuZlHIQbss2qnBFr3WY5yBQ4CAQcBAo5yDs2m5bd0OK2mevwwIHgfAVn5SDAErffmFU1TrMcxAocBAIOAiUchBmtOIP7ztBitJnz0GgwEEgeHGOUg7CVPa2twgrRs1BIM9BoMBBIOAgUMpBMMv3Lgd2NzUHgTwHgQIHgfCFqpSDcFtuFPp2zUEgz0GgwEEg4CBQzkHYCr9dtteAFLXPXocFDgLh2zg5B2Fbtt3NgZZrn70OCxwEAg4CpRyEWwX1pG/XOsxzEChwEAg4CJRyEO512SKxEKGpOQjkOQgUOAgEHATKOQg7MmeWYSap+Qfk+QcU+AcE/APK+QdGgVxK/1a/LzfO75iCRXLsRWfYAda8BPK8BAq8BAJeAuW8BLF9WLe6Mn6lQMq6rrx+C9wEwpcqUm6CWWwvY0W8shLUdeB1XOAnEPATqOAnvFwJxu9qLV5/z+vv7V12HLW1zvN8BQp8BcKvBgu+gq2B9i4vzqq1zvN8BQp8BQK+AqV8BbNoPrcX6Lyar0Cer0CBr0D4tXfKVxgWV48U8x0t1z57nRf4CgR8BSr4CpsGuX2HFLXPXucFvgLhN5opX+Huaavnrfdbh+8wBmq95zkLFDgLBJwFSjkL7aXW91dJsMy13vOcBQqcBcLvE1POwrBo7X1Fn2u95zkLFDgLBJwFSjkLt6/W4+C2cM1ZIM9ZoMBZIPwOLeUswOiS0MdrzgJ5zgIFzgIBZ4FSzoKNqkmFDDNKzUsgz0ugwEugy+WT+rx72KptuGlX8xLI8xIo8BIIeAmU8hJui3ZWBKfPNS+BPC+BAi+BgJdAKS8BVg4bVWKzaZhhan4CeX4CBX4CAT+BUn7CvYLYioKWa/3n+QkU+AmEd8pSfgL08SOsJDU/gTw/gQI/gYCfQDk/QY69gtiKAilqn73+C/wEwtvmKT8B1rBkZqn1nOcnUOAnEPATKOUn3LUsyfiudZznJ1DgJxDwEyjlJ9x9fK9dMMpq/eb5CRT4CQT8BEr5CffMYuMbTmJrbgJ5bgIFbgLhd6YpNwFWEAmrZs1NIM9NoMBNIOAmUMpNuFdL8xl7WK3PPDeBAjeBLhwjhT57zGGKlmufvT4L3AQCbgKl3IR79pQr+lzrM89NoMBNoAtbLddn8pi/4TuEmptAnptAgZtAwE2glJvQjrU/O+wcBc76a24CeW4CBW4CATeBUm7Ctnis3dEB0e2am0Cem0CBm0DATeCUm3Bbtvn79plrbgJ7bgIHbgJDhIlTbsL0cVm02r4gReUze24CB24CAzeBU25CO+xNeeNV3uehXHMT2HMTOHATGE43OeUm7B72stjjhZZrnw/v81OXMXATOOUmzNpdPas9exjX3AT23AQO3ASGEyBOuQnWzjchE2up1GHsuQkcuAkM3ATOuQmLZ7Z9dj2s1GHsuQkcuAkMpyGcchOGpebGs2vnUoex5yZw4CYwcBM45SbsUXVzSKGspQ5jz03gwE1g4CZwyk3Y4/guAdR2qcPYcxM4cBMYuAmcchNg9qRY26UOY89N4MBN4BfWXa7DLnm0M6aofSbv81OHMXATOOUmwEoh0edSh7HnJnDgJjDsVTjlJtjsOVeKOJ5LHcaem8CBm8DATeCUm7AtH0fSt0sdxp6bwIGbwLBX4ZSbcPfpw8a1QIraZ/E+P3UYAzeBc26CzWE2f9+rpc2mqxXWbYRjnTkcxhcXKGmp29hzFjhwFhjUNqechXYY5dtoB85yXUfq6+ip2xg4C5xyFoblNQrX6dbRwXKp29hzEzhwE9iN5ly3rftNu/YPUE+lbmPPS+DAS2DgJXDKS7D2hVoXSFH67DkJHDgJDJwETjkJw7L1uDUDnZii9NnzETjwERj4CJzyEaal1b6rBPcZE9dcBPZcBA5cBMYZLOUizB7lfW5Q27Vu8zwEDjwEBh4CpzyEYamZxVUCghS1z163BQ4Cu1bLddvu08tyxxS1z163Bf4BA/+AU/7BtLQsXjanQYraZ6/bAveAgXvAKfdg+Grtu32HFLXPXrcF3gED74BT3oFxKK29kY/DNeeAPeeAA+eAXaulum2PKuvbHXpYrds814AD14CBa8A51+BmcNpcdkGK2mev2wLXgIFrwCnX4J7D9qhCy7XPXrcFrgED14BTrgGM52QmqXWb5xpw4BowcA045Rrcq2MzZQA+17rNcw04cA0YuAaccg1Am7Q4nmvd5rkGHLgGDFwDTrkG9yq5ZxKo7Vq3ea4BB64BA9eAU64BzJoUZ89ah3muAQeuAQPXgFOuwT13mWWcw2od5rkGHLgGDFwDTrkG0L4UR1WtwzzXgAPXgIFrwCnXAOau3d6QovbZ67DAL2DgF3DKL7gt2ui6v4Hnml/Anl/AgV/AwC/glF8APl+hh9X8Avb8Ag78AgZ+Aaf8gnuPYZbR51qHeX4BB34BA7+AC37BuVdHXC1Bk9rsauv3KiFE+GrOAXvOAQfOAQPngFPOwbS0LHqiGtxX45p3wJ53wIF3wKfLJ68jwhKM301Ug5R1HXj9FrgHDNwDTrkHZnH8eqKaK0Gt4zz3gAP3gIF7wAX3wMYGrdFppBXYMdT8A/b8Aw78Awb+Aaf8A7PYDmMBLF3nSlDrOs9B4MBB4BNHe85BsBlp3So6eBPVIGVdB17fBR4CAw+BUx6CWRy/nqjmSlDrPM9F4MBFYOAicM5FUFNZ6xztsFfsQYHUfAT2fAQOfAQGPgKnfASz2A4jcWyeGZSg1n2ek8CBk8DASeCck6C2Kq/T6sNetQedX/MS2PMSOPASGHgJnPISzOL4Xf3BZm97Y34Tt6BEtS70HAUOHAUGjgKnHIVheZXIomgX9MhaF3qOAgeOAgNHgQuOgq2Z2zL0g1oXeo4CB44CA0eBU44C+LzGgkJt17rQcxQ4cBQYOAqcchTu9raIsUJt17rQcxQ4cBQYOAqcchTuHifmM9R2rQs9R4EDR4GBo8A5R0FNF+4+fkGK0mfPT+DAT2DgJ3DKT7hre/uMlkufPTeBAzeBgZvAKTdh9mXft6FP1rwE9rwEDrwEBl4Cp7yE21eLKEDfrjkJ7DkJHDgJDJwETjkJ5vPNscN2rnWe5yNw4CMw8BE45SPMdvXtDHNYzUVgz0UYfww+g75rub7bcxfFHlbruuZ1XeAhzLSQT76WXd7yhSlqn72eCxwEBg4CpxyEu7a3zwekqH32Oi7wDxj4B5zyD2wGMcu+h9X6zfMPOPAPGPgHnPIP5ijyKwacMdT8A/b8Aw78Awb+Aaf8A6htie1c6zXPP+DAP2DgH3DOP1Dbv63ztnOdr53rbPk0mjhD+9f6zXMROHARGLgInHIRrCRQMrRc14XXbYGLwMBF4JSLcPu+YlnnC2bVWp95LgIHLgIDF4FTLsJt8bBWAJ9rfeY5CBw4CAwcBE45CNPSat/F7MN5uNZnnoPAgYPADdfCVJ8ty6OWrbZhnNf6zHMQOHAQGDgInHIQoE+32LdrfeY5CBw4CNxw1Kb6zHrYHm0vtFz77PVZ4CAwcBA45yAoW99uobZrDgJ7DgIHDgIDB4FTDsKw1HzfBp9rDgJ7DgIHDgIDB4FTDsI9qs4WxnPNQWDPQeDAQWDgIHDKQZi162sbxnPNQWDPQeDAQWDgIHDKQbhH1WZvQllrfeY5CBw4CAwcBE45CPc43iWAHlbrM89B4MBBYOAgcMpBgNmTYg+r9ZnnIHDgIDBwEDjlIIDP1rcxRe2z12eBg8DAQeCUgwArhUSfa33mOQgcOAgMHAROOQg2e4JCwBS1z16fBQ4CAweBUw7CbflM+natzzwHgQMHgYGDwCkH4e7TNpPAGVPNQWDPQeDAQWDgIHDOQVhcwmHZantzCiFl7bvXY4GHwB3rMNVjy+L49ZxCX4K6DrwuC1wEBi4C51yEmwZ4YEnGlhH6fK3PPB+BAx+BgY/AOR/hpgI2s7x+MWVdB16nBU4CAyeBc07CKsG0uH43pxBS1nXg9VrgJTDwEjjlJZjF8evpgL4EdR143Ra4CQzcBK64CQdatpKMX+iJtX7z/AQO/AQGfgKn/IRp6WPR3pq1ly1w9q11nOcocOAoMHAUOOUoDMtmkbAEs0SQsqwDz1PgwFNg4ClwylOYT0J/LNpoFLRc+u55Chx4Cgw8BU55CvMDw49F26vA7Yaap8Cep8CBp8DAU+CCp2DrvARiB9c8BfY8BQ48BQaeAqc8heHjGnViJSBIUfvs9VzgKTDwFDjlKUz05cciWa2j5dpnr+cCT4GBp8ApT2H2qD9cexPUdq3nPE+BA0+BgafAKU/h7tvrNPOE2EPNU2DPU+DAU2DgKXDKU5gP6356likNtV8oc63rPFeBA1eBgavAKVehnbQtrl9o71rXea4CB64CA1eBU67CxHqvHnbEcV3rOs9V4MBVYOAqcMpVmD3L9zSIBNRcBfZcBQ5cBQauAqdchWFpzyQ2s0CK2mev5wJXgYGrwClXoa33Yybue/V18LnWcZ6rwIGrwMBV4JSrcM8oFotg8LnWb56rwIGrwMBV4JSrYPM2lAAt1z573Ra4CgxcBU65CjaO73ZGy7Ve85wEDpwEJpwXcr1m67OtlrhO1zrN8xE48BEY+Aic8hHuHrZnFJhJan3muQgcuAgMXAROuQj3DCKJQqh1mechcOAhMPAQOOUhQC3H2q45COw5CBw4CAwcBE45CPdaJda3MUXps+cfcOAfMPAPOOcfbIumTdByrcc8/4AD/4CBf8A5/+Cu7Y9lsj0qtHfNQWDPQeDAQWDgIHDKQbjHs41viKfWHAT2HAQOHAQGDgKnHASjx92WIbZYcxDYcxA4cBAYOAicchDuedv0GUQAag4Cew4CBw4CAweBUw4CqCEKqqjmILDnIHDgIDBwEDjnIGyLbBqFIEXts9djgXvAwD3glHtwW9w+QzvXesxzDzhwDxi4B5xyD25VZAoB57Jaj3nuAQfuAcPL0JxzD3YP2xoFarvWY557wIF7wMA94Jx7sH01y+hzrcc894AD94AZ58Rcj9k6bfO4S1H77PVY4B4wcA845x7snd3e7YDlWo957gEH7gED94Bz7sHeZ/HeY0KK2mevxwL3gIF7wDn3YFu2OQzHc63HPPeAA/eAGWeknDcqe75elq3HWSscftTZKNy7ImslLHFdV17HBV4CAy+BU16ClXhaXL/GfAJfaz3nuQkcuAnM2N9yPbfuQ5z2huXmXGHKug68rgv8BAZ+Aqf8BOBcEZZkPrsJKcs68BwFDhwFBo4C5xyFtr7FbhZrtBgU3E6peQrseQoceAoMPAXOeQrNYo2mOMTqAMpe6z3PVeDAVWB4R4pzrkJb+7Zmbxg2TFH77nVe4CowcBU45yq0FfVu6/ylgc6ruQrsuQocuAoMXAVOuQqbPtTsVV2XovbZ67zAVWDgKnDOVWgr2tlWtLvB/fWaq8Ceq8CBq8CCrZbqvLZOM9thtY6Wa5+9zgtcBQauAudchdasZy3LcHpdcxXYcxU4cBUYuAqccxV2316nm3hbrOYqsOcqcOAqMHAVOOcqNHtzfq04rVuPI0hZ++71XuArML5XkfIV5odLZnH9QnvXes/zFTjwFRj4CpzzFdpahds60XXjutZ7nq/Aga/AwFfglK8we5bvaTiua73n+Qoc+AoMfAXO+Qptswb2zAIpap+93gt8BQa+Aqd8hdaWtmlLw+AN55qvwJ6vwIGvwMBX4JyvsGeU0+Y08LnWe56vwIGvwMBX4JyvYPP2LoGzXPvsdVvgKzDwFTjlK+xxvNsZLdd6zfMVOPAVGPgKnPMV9vpsqyXO+LVO83wFDnwFBr4C53yF3cP2jCKQovTZ8xU48BUY+Aqc8xX2DNKiQqj5Cuz5Chz4Cgx8Bc75Cnctx9qu+Qrs+Qoc+AoMfAXO+Qp7rWo2ughS1D57PRb4Cgx8BU75CrdF0yZoudZjnq/Aga/A+L1qyleA2v5Ypq2Cob1rXeY5Cxw4CwycBS44C3veNp4G+F7rMs9Z4MBZYMV+k3NIlR6WYXTVusxzFjhwFhg4C5xyFmDeXr7DaVXNWWDPWeDAWWDgLHDKWQA1ZOoIarvWZZ6bwIGbwMBN4JSbcFtsplGgtms95nkJHHgJDLwEznkJ2+L2GVPUPns9FjgJDJwETjkJtyoyhYB9stZjnoPAgYPAeEcw5SDcPWxrFKjtWo95DgIHDgIDB4FzDsL21Syjz7Ue8xwEDhwEBg4C5xyEe50+4ixa6zHPQeDAQWDgIHDKQYCdne12wHKtxzwHgQMHgYGDwDkH4d5n7T0mpKh99nos8A8Y+Aec8w+2ZZvDcDzXeszzDzjwDxj4B5zyD4zAcu/wThtltsttftTZKLSVZhNTscR1XXkdF7gJDNwELrgJ69voFQU97fTjBV+B1fwE9vwEDvwEBn4Cp/wEs3ie+8XvIylBWQeeo8CBo8DAUeCCo7C+rVwlOC3+2sTWwNWaKzLc7AVpmN9r3gJ73gIH3gIDb4Fz3kJb53HNYlT2bjfc1Kq5C+y5Cxy4CwzcBc65C23Fpts6CW6gSGruAnvuAgfuAgN3gXPuwmoFa5UTI8E1Z4E9Z4EDZ4GBs8A5Z6GtE0EjuDS4M1RzFthzFjhwFhg4C5xzFto6p9k9Dtu51n+es8CBs8DAWeCUs3D3NPMdNG/NWWDPWeDAWWDgLHDKWTjXHHjuiD9jitpnr/8CZ4GBs8A5Z2H17XNF/k+MENWcBfacBQ6cBb5wfkjfD9lnDbJnHEhR++z1X+AsMHAWOOcs7J61exr07Vr/ec4CB84CX9hquf6zfdwuAVquffb6L3AWGDgLXHAWiB59G2aSWv95zgIHzgLj6VjOWbhnT2tnGFW1/vOcBQ6cBQbOAuechd23TWFg+9T6z3MWOHAWGDgLnHMWmu1hzWdcMWr95zkLHDgLDJwFzjkLe72WXQJIUfvs9V/gLDBwFjjnLGzFYJZx3q51nOcscOAsMHAWJOcs7B4mYZWUmrMgnrMggbMgwFmQnLNwc872agkpKp/FcxYkcBYEOAuScxbaJq0ZoUdiCUpdJp63IIG3IMBbkJy3sGeUzcNCy7Xvh/f9qccEeAuS8xa2EtQ9urw+owtyqOvg9HXw1GcCp6CS8xdubWolwRR1HZy+Dp76TIC/ICl/AWaWsIZJzV8Qz1+QwF8Q4C9Izl+4a9vmcxhtpT4Tz1+QwF8Q4C9Izl94kRF77H1+ghS1z937/NRnAvwFKfgL9tbdpiCg5drn7n1+6jMB/oLk/IXt8yYCQG2X+kw8f0ECf0Fg/yYFf8F83kQXtFz7TN7npz4T4C9Izl8wy83e5Vfo26U+E89fkMBfEOAvSM5fuC0fVgJIUfvM3uenPhPgL0jOX7gt7xJAitpn8T4/9ZkAf0Fy/sKyfO4zxAvm8VKfiecvSOAvCPAXJOcv7NsmO8YAlkt9Jp6nIIGnIC+chdP7cWJxlmztKvWZeJ6CBJ6CAE9BUp7CXcsriuFWjFKfiecpSOApCPAUJOUp3JY1WSVLfSaepyCBpyDAU5CUp3BbprC7lZqnIJ6nIIGnIMBTkJSnALW999eQovTZ8xQk8BQEeAqS8hRsJ3+uVfKE+w9S8xTE8xQk8BQEeAqS8hRuy32XAFLUPntdFngKAjwFSXkKt2XaJYAUtc9ehwWeggBPQVKeAvjcrASQovbZ67DAUxDgKUjKU9gWdwkOqO1ah3meggSeggBPQVKewu3rYbse8LnWYZ6nIIGnIMBTkJSncFt+mc8CKWqfvQ4LPAWBV7Yl5SmAz2vNAgVY8xTE8xQk8BQEeAqS8xRunxcTpoHPtQ7zPAUJPAUBnoKkPIVtWYwtgKOh1mGepyCBpyDAU5CUp3BbtpfBsZ1rHeZ5ChJ4CnLg/J++q7str3YWnD1rHeZ5ChJ4CgI8BUl5CrflbqR66GG1DvM8BQk8BQGegqQ8hZtkvU5kBOftWod5noIEnoIAT0FSnsJt8Qh8Yal5CuJ5ChJ4CgJvlErKU7h9ZvMd5rBah3meggSeggBPQVKeAtT2ImqB9qx5CuJ5ChJ4CgKvKUrKUwCfTXdjitpnr8MCT0GApyApT+FWvWKsXYIUpc+epyCBpyDwEpWkPIXbsvGkoZ1rnoJ4noIEnoIAT0FSnsJt2QjHd9xbap6CeJ6CBJ6CAE9BUp7C12hFzUkQz0mQwEkQ4CRIzkn4Fq2o+Qji+QgS+AgCr29Jykf4Gq2ouQjiuQgSuAgCXATJuQjfohU1D0E8D0ECD0Hg1SVJeQhfoxU1B0E8B0ECB0GAgyA5B+FbtKLmH4jnH0jgHwjwDyTlH3yNVtTcA/HcAwncAwHugeTcg2/Ripp3IJ53IIF3IPBVoOS8g2/RippzIJ5zIIFzIMA5kJRz8DVaUfMNxPMNJPANBL7+lJxv8C1aUXMNxHMNJHANBLgGknINvkYran6BeH6BBH6BAL9AUn7B12hFzS8Qzy+QwC8Q4BdIzi/4Fq2o+QXi+QUS+AVyYqulOuxbtKLmF4jnF0jgFwjwCyTlF3yNVtT8AvH8Agn8AoHviyXlF3yNVtT8AvH8Agn8AgF+geT8gm/RippfIJ5fIIFfIPCNpKT8gq/RippfIJ5fIIFfIMAvkJRf8DVaUfMLxPMLJPALBL7ukZRf8DVaUfMLxPMLJPALBPgFkvILvkYran6BeH6BBH6BwB0dSfkFX6MVNb9APL9AAr9AgF8gKb/ga7Si1TrM8wsk8AtmWsjna8wgiVbU/IKZmbccfAYdlvILvkYran6BeH6BBH6B4M4w5Rd8jVbU/ALx/AIJ/AIBfoGk/IKv0YqaXyCeXyCBXyDwRaqk/IKv0YqaXyCeXyCBXyDAL5CcX/AtWlFzCsRzCiRwCgQVRsop+BqtqDkF4jkFEjgFApwCSTkFX6MVNadAPKdAAqdAGrZaHg/7Eq2oOQXiOQUSOAUCnAJJOQVfoxU1p0A8p0ACp0BQPaecgq/RippTIJ5TIIFTIMApkIJTYG+7GlNRoYfVOsxzCiRwCgQ4BVJwCuy16fXmBJ3QzrUO85wCCZwCAU6B5JwC8pbHrHhAitJnzymQwCkQ4BRIyim4X9rePApMUfrsOQUSOAUCnAJJOQXb575uoHbYS9acAvGcAgmcAgFOgaScgtvy2sHDC8hScwrEcwokcAoEOAWScgrM8rS4ehj4XOswzymQwCkQ4BRIyik411txt2VQgDWnQDynQAKnQIBTICmnYFumpQAJe1itwzynQAKnQIBTICmnACy35fsFKWqfvQ4LnAIBToGknAKo7fVaONxMqzkF4jkFEjgFApwCSTkF27IaiRLW55pTIJ5TIIFTIMApkJRTcFs2DiiskjWnQDynQAKnQIBTICmnwCgvNpf5UVXrMM8pkMApEOAUyFdOwc2Zgb1kzScQzyeQwCcQ4BNIyieAedsYHOBzrcM8l0ACl0CASyApl2BHWvuK6WPEteYRiOcRSOARCPAIJOURjO3PioPZN0gNarvWYZ5DIIFDIMAhkJRDsOPafa3PGN+u+QPi+QMS+AMC/AFJ+QOnfXd/1za0c63DPHdAAndAgDsgKXdg+9rX1zEvbOdah3negATegLjVNr+/r9cf4PvZLNIOsYOaNyCeNyCBNyDAG5CcN7D6uMVBXU+rOQPiOQMSOAOCa1/OGXjtPn6FWq85A+I5AxI4AwKcAck5A/fosj5OkKL22euxwBkQ4AxIyhnYFq2necu1z16PBc6AAGdAcs7AbXHt7KBv1pwB8ZwBCZwBAc6A5JyBNYftEqBSrzkD4jkDEjgDApwByTkDrz2XHdHnWo95zoAEzoAAZ0ByzsDts7W3QIraZ6/HAmdAgDMgOWfARpNZdqOq1mOeLyCBLyDAF5CcL3CvHBR9rvWY5wtI4AsI8AUk5wvctR1Xy5ovIJ4vIIEvIMAXkJwvcFveSgFS1D57PRb4AgJ8Acn5ArdFm8OgnWs95vkCEvgCAnwByfkCh8UA9+xpXwbZWrZWFLaeuH7X6wh9pR9bPbBU15XXcYFLIMAlkJxL0NcLXX29ftDhhkTNJRDPJZDAJRDgEkjOJejNLLfEcu2z13GBSyDAJZCUS3DXfrNRCWOi1nGeSyCBSyDAJZCcS9BNx527vSFF7bPXcYFLIMAlkJxL0E+zbDdhwOdax3kugQQugRCuG6mO6+uFrr7e3eig32ougXgugQQugQCXQHIuwR5V6xwba7vmEojnEkjgEghwCSTnEty+Lsv3GyJScwnEcwkkcAkEuASScwmsZx02rmEmqbkE4rkEErgEAlwCybkEfb1esr96tTNdwZS1717HBS6BAJdAUi7B9vlIZtGaSyCeSyCBSyDAJZCUSwDj2UYZtHet4zyXQAKXQIBLIDmX4F4xWvS51nGeSyCBSyDAJZCcS3DPKNbTYHTVOs5zCSRwCQS4BJJzCfaade61C1LUPnsdF7gEAlwCybkENnvelqGdax3nuQQSuAQCXALJuQT3eLZ2Bp9rHee5BBK4BAJcAsm5BHf77rULUtQ+ex0XuAQCXALJuQS3z1dYs2ougXgugQQugQCXQFIugc1hNn+f+DVzzSUQzyWQwCUQ4BJIziW4VdER+3atxzyXQAKXQBhn4VyPbS1qvmOK2mevxwKXQIBLIDmXYM9htk7DHqXmEojnEkjgEghwCSTlEty+bt9h9qz1mOcLSOALCPAFJOUL3KrX2rvD7FnrMc8VkMAVEOAKSM4VuNs3mT1rPeZ5AhJ4AgI8AUl5Arf6PeJMUnMExHMEJHAEBDgCknMEbgV4hR5W8wPE8wMk8AME+AGS8wPuPk2htmtugHhugARugAA3QHJuwG3ZehpBitpnr8MCN0CAGyA5N2Cr3259G8pa6zDPDZDADRC8u5VyA+5RtUuAKWqfvQ4L3AABboDk3IBb6VOs7VqHeW6ABG6AADdAcm5A7w1r2+ntmhsgnhsggRsgwA2QnBuw29dWSQGfax3muQESuAEi2GqpDjvWvZTj8LvaO5ph493qplndvH/xdkDNGRDPGZDAGRDgDEjKGThXCU4r0bFe6Dnge5CaMyCeMyCBMyDAGZCcM7AsWgnOflpJoLVqHed5AxJ4AwK8AUl5A2bxtNn3sG9jsAS1nvPcAQncAQHugOTcgcPueHxKcG5FCTepav6AeP6ABP6AAH9AUv6AWTxNTR98xBLU+s5zCCRwCERw1Kf6bltct/kVZ6ha33kOgQQOgQCHQHIOwbJoJTjd6lvrO88hkMAhEOAQSMohmD4uX3cJIEXts9d3gUMgwCGQlENg7Xya5nGWa33nOQQSOAQCHAJJOQRm8S5BR8u1z17fBQ6BAIdAUg7BuZTGuZTHiVGQmkMgnkMggUMgwCGQlENwW2zWtzFF6bPnEEjgEAhwCCTlEFjP2j0Na7vmEIjnEEjgEAhwCCTnENg43u3dbGYhSFn77nVe4BEI8Agk5RGYxdO07cFJCWq957kEErgEAlwCybkEy6KVYNS+jbYLUtZ14HVf4BIIcAkk5RKYxdO00CFHLEGt/zyfQAKfQFxPTvXfsmglOLutroIp6zrwOjBwCgQ4BZJyCs59g5JMda9WWFEUV5JaF3pugQRugQC3QHJuwbFeHeymDwVaodZ5nlsggVsgwC2QnFtgvprvHbRNzS0Qzy2QwC0Q4BZIzi2wWjffD0HLtc9e1wVugQC3QFJugbX32Xn7Dilqn72eC9wCAW6B5NyCvlS0tbOr7VrHeW6BBG6BALdAcm7BHu/mM1qu9ZvnFkjgFojiGEm/P+hsPjcrAaSoffb6LXALBLgFknML7tqmaLnWb55bIIFbIMAtkJxbcI9nq21YXWv95rkFErgFAtwCybkFxyJN9nUf6m5v+/MabXAHsOYZiOcZSOAZCPAMJOcZWElWyXxd1LrOcwkkcAkEuASScwm272L94IIUpc+eRyCBRyDAI5CUR2B381s3rQN3wmoOgXgOgQQOgQCHQHIOwW35sBJAitpnr+sCX0CALyApX2D66GsbRlvNFRDPFZDAFRDgCkjOFehivtpt4gNS1D57HRe4AgJcAcm5Avc3GPZ1wBp9F6asffc6LvAFBPgCkvMF7na+YnvX+s3zBSTwBQT4ApLzBW6LiziMo6LWbZ4vIIEvIMAXkJwvsOey3e4CKWqfvU4LfAEBvoCkfAGbUWxO8+O61mmeLyCBLyDAF5CcL3Bcfv52fbzWaZ4vIIEvIMAXkJQv0Pb6zbvWIUXts9dpgS8gwBeQnC9wvp7jGspa6zTPF5DAF5ALx0iu08xn62GgTWu+gHi+gAS+gABfQHK+gLWvWXbtXOs0zxeQwBcQ4AtIzhe4R1WLPtc6zfMFJPAFBPgCkvMF7tpOVstap3m+gAS+gABfQHK+wG15r12QovbZ67TAFxDgC0jOF7gt2k4AtEmtxzxfQAJfQC5ceb59J7q/5qPTvliFWbTWZZ4zIIEzIMAZ0JQzYBZPWhH9c0W1oQRa8wbU8wY08AYUeAOa8wbO5ixbSU64Ba41d0A9d0ADd0CBO6A5d+Bckd1Vkml5/UIdlHpNPXdAA3dAgTugOXfgvC1+fruViCBlXQeHr4OnblPgD2jKHzCLJ60T33NFAl0JSv2mnjuggTugwB3QnDtwrij3uetgtcYdEdCaP6CeP6CBP6DAH9CUPzAtfSyuneLZwHKp39TzBzTwB/SFPTnVb+eu9V0CSFH73LzPT/2mwB/QlD8wLK2eZj3ujj1rzR9Qzx/QwB9Q4A9oyh+wWoYSoOXa5+59fuo3Bf6ApvyB8/rc7R+/ZL5Ditpn8j4/9ZsCf0BT/oBZ3CUggh5W6jf1/AEN/AEF/oCm/IFpyVm+OvSwUr+p5w9o4A8o8Ac05w/sniW7BJCi9pm9z0/9psAf0JQ/cPvcV62f0MNK/aaeP6CBP6DwOoum/IHb8lrLLuwZpX5Tzx/QwB9Q4A9ozh/YlleE7zqgnUv9pp4/oIE/oMAf0Jw/sC2v11Uu7BmlflPPH9DAH1DgD2jOH9iW2XyGHlbqN/X8AQ38AYXv2TTnD9w+r1F1wngudZt6/oAG/oACf0Bz/sDdw9aKce+7teYPqOcPaOAPKPAHNOcPmGVim8MwRemz5w9o4A8o8Ac05w+sleK2fL9KqjV/QD1/QAN/QIE/oDl/YFtesQbGWqp1mecPaOAPKPAHNOcPmGW2l2Rg7qn5A+r5Axr4Awr8Ac35A9vntROEr3S05g+o5w9o4A8o8Ac05w9sy/bCiEA71zrM8wc08AcU+AOa8wdun1cfV0xR++x1WOAPKPAHNOcP3D3M+jhBitpnr8MCf0CBP6A5f+AeVR81BO+5aM0fUM8f0MAfUOAPaM4fMOVH9kUr1natwzx/QAN/QA+ckVIdZpb7eom13193as0fUM8f0MAfUOAPaM4f2Jbta16BebvWYZ4/oIE/oMAf0Jw/sC3beZii5dpnr8MCf0CBP6A5f+Cu7WX5gh5W6zDPH9DAH9AD58JCh1ltm9JHy7XPXocF/oACf0BT/sC0hPsqv0rWOszzBzTwB/TAMZLG0e6d3CqBgM+1DvP8AQ38AQX+gKb8AVD6yzLsbmr+gHr+gAb+gB648uRxNLO84qYn1natwzx/QAN/QIE/oCl/ACzbL0GK0mfPH9DAH1CIr2vKHwDL1s4XpCh99vwBDfwBBf6A5vyBb/vnmj+gnj+ggT+gwB/QlD/wdf9c8wfU8wc08AcU+AOa8ge+7p9r/oB6/oAG/oACf0Bz/sC3/XPNH1DPH9DAH1DgD2jKH/i6f675A+r5Axr4Awr8AU35A1/3zzV/QD1/QAN/QIE/oCl/4Ov+ueYPqOcPaOAPqBsjhQ6r9881f0A9f0ADf0CBP6Apf+Dr/rnmD6jnD2jgDyjOwjl/4Nv+ueYPqOcPaOAPKPAHNOcPfNs/1/wB9fwBDfwBPbHVCh1W759r/oB6/oAG/oACf0Bz/sC3/XPNH1DPH9DAH1DgD2jOH/i2f675A+r5Axr4Awr8Ac35A9/2zzV/QD1/QAN/QIE/oDl/4Nv+ueYPqOcPaOAPKPAHNOcPfNs/1/wB9fwBDfwBPdGDIh5W759r/oB6/oAG/oACf0Bz/sC3/XPNH1DPH9DAH1DgD2jOH/i2f675A+r5Axr4Awr8Ac35A9/2zzV/QD1/QAN/QIE/oDl/4Nv+ueYPqOcPaOAPKPAHNOcPfNs/1/wB9fwBDfwBBf6A5vyBb/vnmj+gnj+ggT+gwB/QnD/wbf/cah3m+QPjj8Fn0GE5f+Db/rnVOszzBzTwB2baO5/0Xtm3/XPNH1DPH9DAH1B4611T/sDX/XPNH1DPH9DAH1DgD2jKH/i6f675A+r5Axr4A9qw7tJ7Zd/2zzV/QD1/QAN/QIE/oCl/4Ov+ueYPqOcPaOAPKPAHNOUPfN0/1/wB9fwBDfwBBf6A5vyBa61R12JfNVwxah3m+QMa+AMKX21rzh9YFncJGEdDrcM8f0ADf0CBP6A5f4B7Q8vtBXvJmj+gnj+ggT+gDde8NB7W7L3bvn2HFLXPXocF/oACf0BT/oD5PH39WL5gxah1mOcPaOAPKPAHNOUP3LW9Xlh+wb6q5g+o5w9o4A8o8Ac05w/cPq/9FSiDmj+gnj+ggT+g8Kqp5vyB2+f1Ginc3qn5A+r5Axr4Awr8Ac35A9vnZj5DWWsd5vkDGvgDCi8MaM4fuH1eJYCZpOYPqOcPaOAPKPAHNOcPbJ9XRI4J2rnWYZ4/oIE/oPCei+b8AfOZFzOH4ZZezR9Qzx/QwB9Q4A9ozh/gdTNtWxbwudZhnj+ggT+g8EqS5vyBbXl9p8mgPWv+gHr+gAb+gAJ/QHP+wLas5jtYrnWY5w9o4A8ovKqiOX/grm3zHS3XPnsdFvgDCvwBzfkDd22vX9ASNX9APX9AA39AgT+gOX9gW16ROIaoVM0fUM8f0MAfUOAPaM4fuC2vX7h1WfMH1PMHNPAHtGPdpfGwbXl99Upw47TmD6jnD2jgDyjwBzTlD5jlafHzy+BzrcM8f0ADf0Dh5rqm/IHb8vqagk60XPvsdVjgDyjwBzTlD9yWT6ttsFzrMM8f0MAfUIw95PyBu7aXZdhL1vwB9fwBDfwBBf6ApvyB2/La0TU4Qan5A+r5Axr4A9pxnc/5A+sVaWMWurWq1mGeO6CBO6DAHdCCO/Davn5+wXLNHVDPHdDAHVDgDmjOHdiWV603UPo1d0A9d0ADd0CBO6AFd8Asr28ZgASqNXdAPXdAA3dAgTugBXfALB/2C7Vd6zDPHdDAHVDgDmjOHbgti+1yIEXts9dhgTugwB3QnDuwvq9stL4MowMt1z57HRa4AwrcAc25A/vr1hUPoxdYrnWY5w5o4A4ofnGScwd27M+ij/eX21pzB9RzBzRwBxS4A5pzB/riiJApA+zbtQ7z3AEN3AEF7oDm3AE6dlw7RNZr7oB67oAG7oACd0Bz7oB9k2Rfrbt2rnWY5w5o4A4oxhJz7sCq7eG7/WKK2mevwwJ3QIE7oAV3YO3kNlkOe1itwzx3QAN3QIE7oDl3wPr2Xeswh9U6zPMDNPADFPgBmvMD7Ks36+Oub9c6zPMDNPADFM/6Cn6Akq9tiAHW/AD1/AAN/AAFfoCm/IDdw7raTAJlrXWY5wdo4AconrgV/ADrYeslPcK1qtZhnh+ggR+gwA/QnB+we9aeRaG2ax3m+QEa+AGKJ6sFP8C4QFbb2M61DvP8AA38AAV+gOb8ADIaZrfRtf4s9vcEOZR14HkCGngCiifqOU/gXq/tfOOCFGUdeJ6ABp6AAk9Ac57AXkGOfV4JKWqfvS4LPAEFnoAWPAF7eeWyfRZarn32uixwBBQ4AppzBHaPM8sH1HatyzxHQANHQIEjoDlHYOsxI9jAaWHNEVDPEdDAEVDgCGjOETCLdwnA51qXeY6ABo6AAkdAC47ARc5nN6pqXeY5Aho4AgocAc05AntUHeYzlLXWZZ4joIEjoHgyk3ME7NTfRhXuwGuOgHqOgAaOgAJHQHOOgPl8dvsVSFH77HVZ4AgocAQ05wjcPSyzXPvsdVngCChwBDTnCGyl8LLV84AUtc9elwWOgGJsMeUI7J615zKFvl3rMs8R0MARUOAIaM4RuPv0LgGkqH32uixwBBQ4AlpwBLT5FQM0Ss0RUM8R0MARUOAIaMER2MrfLENt17rMcwQ0cASUcXSmumyr4K0Iwedal3mOgAaOgAJHQFOOgO0pbZ12O7yaI6CeI6CBI6DAEdCCI2D76N3e0MNqXeY5Aho4AgocAS04AlsFS6jtmiOgniOggSOgwBHQnCNw7ymvMG/XHAH1HAENHAEFjoAWHIHr8JZBf9ccAfUcAQ0cAQWOgBYcAfV7S9zJ1xwB9RwBDRwBBY6AFhwBix2cMWJTcwTUcwQ0cAQUOAKacwTu0dRiD6t1mOcIaOAIKHAENOUIzP3zsrxqG8ta6zDPEdDAEVDgCGjBEdi1TWGtqjkC6jkCGjgCChwBLTgC8rAMc0/NEVDPEdDAEVDgCGjOETj33Ti/vzLFYCWzeX2/uLNeMmeIj9ccAfUcAQ0cAQWOgKYcASvptLh+l1rGnlnrN88R0MARUOAIaMoRMIvjd9XZ2h35EtR14HVc4AgocAQ05Qi0trTMsmwlOXGPUXME1HMENHAEFDgCmnIEpqVlcVGSjTCKc2Kt6zxHQANHQIEjoDlHwM7D7jOiXSJIWdeB13eBI6DAEdCcI0BkJ3Lrl9By7bvXd4EjoMAR0JwjYGeA9ykk9Lxa33mOgAaOgAqu4rm+276uEsAeteYIqOcIaOAIKHAENOUItH1PfL1wjmf7NUdAPUdAA0dABefYVN/tFagfsbZrfec5Aho4AgocAc05Amzj29ob7ifVHAH1HAENHAEFjoCmHIFmb3fdq+8FKUqfPUdAA0dAgSOgKUcALK+eBuOw5gio5who4AgocAQ05wjs2wTmM8wkNT9APT9AAz9AgR+gKT+g0Xqzb/sM63XNDVDPDdDADVDgBmjODaB9h8NGF/SwWt95XoAGXoACL0BTXsBtcY8qKGut7zwnQAMnQIEToDkngNZbfeubpoY7xZoPoJ4PoIEPoMAH0JQPcN+UsT6Oo6rWd54HoIEHoIp1l8fZyFbJVYKl59pevwVyqOvA67fAB1DgA2jOB7hXzWUZYlA1H0A9H0ADH0CBD6A5H+Bes2wNA59rveb5ABr4AAp8AE35AG1/v2eW4RZgzQdQzwfQwAdQ4ANozgfYtU3W86DH1frM8wE08AEU+ACa8wGIbJSZVmnR91qfeU6ABk6AKq4L+f203c5W++B7rc88J0ADJ0CBE6A5J2Drsz3qwOdan3lOgAZOgAInQHNOgLV3O+yrDPC51meeE6CBE6DACdCcE7BHl5UALdf6zPMANPAAFHgAmvIA7jXM9q6ElmufvT4LPAAFHoDmPIB7VJliEEhR+ux5ABp4AAo8AM15ALdl8/2AFKXPngeggQegwAPQnAew9xwc1XDNA1DPA9DAA1DgAWjKA7hrmaNiqHkA6nkAGngACjwAzXkAt+UW27nWZ54HoIEHoMAD0JwHsL/HNWXYMEXts9dngQOgwAHQnAOwNcpWSWC51meeA6CBA6AXepDrMxG/YsD98ZoDoJ4DoIEDoMAB0JwDcO89TCXBqKr1mecAaOAA6IU9NddndnvbdrnOcu2z12OBA6DAAdCcA3Dvsw4rAaSoffZ6LHAA9HL5fPV5734uSFH77PVY4AAocAA05wDscSxx11NzANRzADRwABRfO8k5AHs8S9K3az3mOQAaOAAKHADNOQBk34EsOhrDGULNAVDPAdDAAVDgAGjOAbiVYGa59tnrsMABUOAAaM4B2H2bovasOQDqOQAaOACKX1/mHIBX9zpsa5P9/YD1+ac63pEejPycp2LJ6zrzOi5wBBQ4AppyBE5dEX1dL1vr+nJJIfZU8wTU8wQ08AQUvyvMeQJG"} |  |  | - |  | - | -
[14 empty] | {"index":138,"total":402,"filename":"Advanced_Project.ifc","data":"ptTJDBQ4kSDj0mMAr+m1xKDkZQJFqDwWjvQmaVRC0IVuVqm+agFpZatoAUWuB0dEKpm7SNUDYrkeDvkhUb5XoRmvp3wCcPMBrzYCV6QLynQnaKK3vsXuZ+IoAE82Bt5jSsn8AkbHiQXs+eun7eN1dMLN6Hjvs0Qp8TV7cWytu70jR9mmBS2JM97XYhJrK/uOHEEJBbqYDH6v/sFKjDcSHcAsxziZkEmneNI66TskCwK25Tg7JlAUVypH5p0hKYPI9dhUrX4lyCOrzo2H2npkEqgSdiiRlBpKEEwRJcrp1Yr7OMt8cJUY7yS6bypQq3TV+0ZtJxKgMZW86Wk36Hj3pcjq/Ukaiz31uOq6TKwESSDSXTjmg4vIUO9EOoNTXoNWmKwyszu6pVcZJNmvihwEuT1EsmxpAtY3IGovxQkF7L08P8hXkeVOpLNwZMsRYEt6jt20JptIzIfDaH0pyoE+ySFM3FQFic7oKAySVZy1VNyeGB60OF3TUMUmhmsPkZssAjnBtWA6effg5fggX0WWO5E3r8pPtcpFcaYbxZ1QQJHVWOTYFjU0t+1zqMqRWtFE1ZBsD4EoyopajROmkBMJEImyOcrWoAfYst8IyFYpwysdJqXqfkiU890mm60e5ECkc57RUqDihmok2viq9j7eWRmXZDkKxohQTqL4N8r4QVhZ0hXpnmeMVle9w43efh4rmv4yNg/Ygj+AwXECAYJGdUMQf6MH+zjNoHajtxMIoC28JgE4pL5VNy3byepPICcM0I82coiocpxsVYFlnzQicEsCVc5iaKV4J3/RS6vCawRFyV52iTlRS1UPHV2gbnxBK7dGWCreyV9czasMZdkhRddUa7JLn7LO+C5StwTSwwXgFOfoX+VcI9heieZkd06HREHSTUPWXaL0cGulMRzoinf0JzlZifcWQNfENOrAxaXrc4UsPSqZHyKbuloBhhsEnIt/9JcPkkbi5Qi9H+iKYMAm/6JVvrcehzt/AXPGow7VcsEyI8RSLCC/7iLltCBOQ0wVQjeljDVtgj1E/1Okd/an17Qf5jTmKMtORIpPZ4G1QfygqNADkII6tCRxgnf4xa1eYj7IF5GJ70TexDRPteJF8Uc+g6e4A9FkubRN77Sa/L99opvhadfhgRXoRAXEP8lSE0cl04i1LtSll/Wml05UQFoXaFK0tmfc62FeRLY7kd7iCbLYtLCxeHktwaciNzkFC7pqfA7PpgVlMz4TLx4lqWzQctqWcZGDZardlKT17LWLpc+hpDdYJM4O4uLFiQrIlKmvstKCPruK5fnigdHxwgIlverAbHo7l/cLPxQZbiR6jKR6z6ms2rIDcKO+dqpISBr6OECA/I4FV+JZ1okKCJZ7FSgvMF+DMqlL1KCuuPS81T42LH5uv2oD7+tVPy/1NVQtvVzlQN21lr1fcEuirfb5I2fMJIedmvGQ6GUF8L5DRLGzDER4SEwyI2UrE+M+ApBh3yIoB3wWVDw2Upa5kTTSwYLpymP+iBE0DiZrrXSJWpl+q1Wvqw6R1c8KwA/yVWS4E+m6NdTqqnZw1a7ee0V61cC3eEZZvvstmuBz8Y8C/7Ro19i7ZdPd1HFiD92R0cnTssaxHlFJnT1VA4ot1gPw6arUW5SGIl10hh/ki8hHwM8R6UYEUKs86R18vT0mUtKIgo6ibGNcaZcYk7kJkJW9aQ6S5klFkOgOjRZ2DHrnqk9DVKCAta0KwBM3GQ6AIUdbUmwDEm/QAHxwEbnVO5E3yPnUKlzUpnqjt5cdIB5xZ9yNehwO5TI2qWc60V5wnuR3FUQ6g1Ne9SXIptmfsk7q1ZZdZNa3jbmq/iDSGZ3y2rQ6uWx3mny4HO/8urFsHoKTAiT7VzckYD5IS1N6Im/e+Z5aXce73ajtRgSs6a8Lp90Mzk1ywAEoawoXp8Y9DS0f8AL09pIDBLDsHKmb7KPbHpY0Tqhng4SdTkIQ54aKu6MDH1wFljuBN4kboNTVl7cbtb2AgOyqY1eU43ZaQnPt99geEoh0B6dGvSqMW37sD/MWphlHm66BBsH36mcGwO/zVWKmG4k36+bUacLl9U5rN3mzZZ08gk23/bBuYVo35KaVDSiJdWBsnHhA0SScVquG0bZG8XrG6S4oyYE0afwOrtaqExDYFT8/WB5xPIl3JcJOra6It97p7RxxclOSjU0wdHmwvC8OD87oOOEBWXKvss0GTcrQHLRrL/mml058QHF52vQGn+QIkWmFyz2J/gknaWTukTjVx1sGhlTJPX9lHx2Z7FoUCviqRaS75Yh/1FRt2RtzN+WmlBmbXj61kVKcZKUk2bwBmVcvPiD4/VUgsSa4KCvfZXDoZnCc8ICcOl6z2DAoUU/uUwh80I1ELzogltSgjJq6bV1tvQoSVBQ0IPQQWVi5YqKp31ud6AALXGwcql4nycnoseWE/XJG1nz3vSJSfLveOWBOY/XSBOSMw0mPOEmGovXx1oTyPTg90rOTYIYs51w4h1UnOCDDzXoSkfHVklm8DO9mvWzV69aajcgbPHB+kJcBP0ekExzQrVYO8kXPbm3P1F0EeIse/xQkcEXU4gQHFABqPuzOer3lvIxCP6h75FiOb4urExx4oJbxe70RWMR3HYl3cOBQKi2D0J7azrV0YzkLKm+w1vntEUUYHL4ZHCc4QNu+GMXQRRB9bcuQsdNLJzpwRHg1L71pUCCOyU2bCC2ylKC6cPUeCojnSkmziFXX+Ajib5pOoRliYUxu2TA1NhY2eKRXvUQB8YGvstMlsQ0xd5F6rZ9kUHPsk5urHhQFIiXYD52ggLiC15Y0jUMDX32UBQiFID72wSH1EBk0ESclCCqRExQQ9xh0sQQxX0k9iVxv+NQWgl72OJUcynU8WCyaUaSzXuKrnJc0NVOpuvethnbXwZp3oa9Nd5ECyTW1VeuvgEhneOJrOnoZ6XrH8ljV9FqPXqLIm4eA5we0XDGeyJtn5I1lPxYcsPFD8RY0JUrzyEsnL4RfnCL9wAAav16GJ9DN8DiRARIJVfd4mfApxEnxdqO4ExogDq+aHyXzU3YSouskuuukBwRku8qtyoCLxDp1ku866dBvqZPQ3FlZ41T3vEN6JU1X0fyBHLreTXZhQTzKmnCK9Cu5aryqyIrWzPNHL2XCiQ+XUe84DX+BIr38NFFcJkx/Y9GuA95ubOmRo2kIPsquLYBSfv+YQ0GzcpR2rwdQSRNHW5IZxVAYgpzYQNYIqjSvN9ZhPG/QLCU5JoWRViUii1KAaOGPACKdM454DW7bI9Ur9kRT6bY+PIlx63NIEHCTARZwCKZ0YgO6b2uduro1TaOha4Z238BIicRT2/DRODmxgcfGfXwwJX2nO5E+io4s+LRpFnkql+TnDi6iDozYm+HBLPmhAfPBKp3aFXkD1PynfufjQg1vQAYL+a8Gnjz1M08gC9x/kv9q4MkzOn26pzw7+nRCpMDQ3MUGbp/RmfeFGfIwyQ8OPBNZ9YVhVEpIwV0NbXkTuLm1pez9r6cYP0Hg2etLOdu9st5OPt7NgMibIblVVs54GpsT5yT+CFa0Hw8oe6ZUVj9GPUuJ5EijQTR1GvLn8eZaVpTeu4DImwG5VVs8h6YpZnW+cnCCMXbiAY9eNtGz1fIIrbB6101RspyXxYVv6jY2PZ7pUzzopf9S4NmDTh0cOS7suZkBOILILfWriu9vSNPjUc0uknYYLUjwRSD+a9D0DrVsQyfhVvrVl1361kmwDZX+yKbpOOj2s+3LRRyIZl62qBlaIPJmdGSCyGDsIdluStlJFRfowTgp5ak0UZLsOhHinOS/FXhiyrS1V8V4+lBaXB34CSci8DBlbfIBKatyFykoPIvUFF80hVQakCkreGOD+2jy0wV0ovNOwtPf5W26G6hdU2kvrAUZNLQqAyOtosTbpbNLfGSxnhL3LNaiizuoEkp7BeEfcqlOnr38Mq/NMjyFJj8e8OTll3kTVyBLgrwnBE9ffpmXe1akm9D55JmWeRsWUeLXewCVX8yrqwzvMMkNCDx7AGWehhEwLZETEHj+XMk+kQLCOvJLCNw9BaoqMdYtRmUdzRuCXb+IwJOnQPhGKpjF6FcveybykdtM+vwpmdV494jg1pR2z/ZLBzx7QLZx3S2q7pKh6Bz7SQJPlOWerazPPmSMK4i8GZIduPHjDeK+aeutkrhsOW3gph1lfiaQeDMit3onkiWqbKmx6iEG9b57lCZbdqSkkdfHTqOUERpa3tRxbGqJooWVogmtsB8OePYqTUdHXIZe+QsuPQEQ++EAfUmkT923sLXxfneHJgq+6aXp2yGNWKllMJzNXhWB/T2LBvDF8Wwp9J1BVFQzsDrIJj5XBDTNsGkJe3kzPLqtJGUC1UjKLrIkORnrAUEWjDgn1miqNLph5JD9VIFTZKhG5J4c8EJa10kxloJmeDPIbqbAs6ci5nlKxAH33w48eSpS9e3epvddMjUhLMn+24EnL0XMSx82nXzLw440v+swT0kCPIxl/+3A/ZMJfKZRIKzCbprAkxcT5ikJoQu6ezhw+7wB31SILjB/3FDAs7cI5gFEBZTPTijgeZq/eVtQgW+F714O3Kb5mwcQBVK02I8FPMl3Nzn2wMld2A8HPMl3Ny8BKlDd8F0RAT/ffZcIrxUaSnS92hO9RV851ckEYEFo+GqL/WjAXScFBVB4lfPnpuAI31jx3cOBUsWUVU3f88o1+1Y2mcZ1pKofv4DFePdwQLYvfcMT97wAFbnHPLQAixygWCOWelmtKZD4fon9uEB8DfqsU1Y3h8c1kMxoWc+cxc/lFxkQfXusL1X1WSUsHT8ycJtYXnW8xQMplGqyegD2sR8ZeJKybfLEq+nlzfDcpmybbHbGpeNHBp4oLsOsqWFNY+0NCluwHxi47aTsYrHpJYagIk3TQi/kRwZuRSq4UlqJqHS3GmKE0bl7SVA0pVMktq3n8GrJH/GUNcb6wno83Yszad2qgiJvRkcmsIbe9wJmaknN6Ih6mBlZ/+cPYI/wAwNPBmevjaIxg5D0yTCsnbuHBLobyCSTNdwzv7K+fMhZ9mylytAihnqhyFtCLmC+e0igjlcwoHz2yLrQK8Yk8Flv6V7KlmUTqZs+o66YQ8d+bOCJ4vuAK8AQ/ykLDObQXWxAt1fpgOag9gQW2WHFm2uo5UUrI+hKpVj0pgp66ccGniREmyzsCo892Y0NPEmINpniyODIfq7Ak2xjk+JcUe2bwblNNjZZ2AFXox8auM3k3aMsZ/Zwhfgk+6GBJ5m8JsW5wa0V+7GBJxmtJouWgS+d/djAXUYrv5hU34Dg1w8N3Ga07iLPhGQMWPFdhcGbXFGTnooUp+2uvuBtrqhJoiW4a2l+kOBJHqZJ/QwNe3kzNreJmCZBlYGeoPlRgvsUR0yrDLgY2y310V2Ko0n+JIgmNj9I8ERv+Y+yHevLI4WpODp+kOBJL2vUCiXSv6wFQQD7tlv619vcThl42eLVuOKi4b6p+UECXX1JDgq5ldaHp+rmqBfGbYcEMtA7DtLrbpB4d+8pm+AWiwD7/i5Mzu56di615+WdPziXd7sjf70dnP3FzLa/AlVEjSJvBkcL/GsQqXZ0JfJ06+U9/UIhAe1xEoFTWK2yuUGCx32vQvKwFx57ZA+2vU6m5kcpJCCtkaMVQQm2iHb3nOA+LXrTzbFpcXV1bCjyZnRku2l76b7WUYaWXRSnoREXgQTyH+Rsq7ur7Dqg+N17AkhpmzMSTRpkTSjyLmfgLtnPJBgGnOhuoOBZtp9Jg+QNe3kzPLeK6wqvmu4h4jjCXXe7e1Fw20s9mqRHct8eAztF+oECjYDoI2tKjyfJAgJkj9miorice5re+QsQeTM8AnRk2vQUurBnzmo6N1X5n5xvqyzxKEtBEFgAKq7mRwryPpEFLmsppZfxFlt2DcFbxDIvNaFNxlzjbvisst2Vrb/NVjMpcgl3njuyrJtstaIit9A0+iCWaZCm1+7Ism6z1Uy6YcY17scKnogUCwj+1ViwQNUcUeQNq8CtLWmTbbw2zY2RAUSJN6OjUaUmp7DaHknHe3FYgfxaDf5FDjmviij3XjaIXzU/VCAi95CK5oA/stXqHmBhvRNsL1mnpRxMtBBWq3Cwb36o4BFdiEEWMD9MKQAraM5rEUvKsn9V3xnk/KRZpiDxZnBkykY1FPUCTpoDrzla4sflTMbtVW8YZddNmoYFIm8GR47DTcsiPCpXaUpd0C1c/LieoPTwIihT98NUM4q8Q9R3SVsmUyxDnK35oYInKVYmrYug9n/znhXYAu15LtDuZlk1J1ZwKSMfrtdkfMmyAjar5sQKTA5VSuFyY5uDn2XVvHcFz2q0X5KswP86oQKtVa5XV3oBkVNKF4l0J9IJFfQ080sJSN98bvVBU3B5UbzxRqRXD1L2lhx0zcnqSFMVdbpT1qmaksd9rF679QQm2Q5FiN7iaMLf/qxHYLOmHQVIUmtOgEDLn59JVHFSnG4U9wIEmxagkTNsVcbtbdy2yfqVtS4wd7elFlbY1RY3CljACxCMiuqaXB/LdCdY/YS/5gUI9kovTevPaJBi3NjKoUtjyvkB1bQaluaEiQtKqLhXF7pqYmwU16/la8aloBYwkLOz4uCyn0n04Kw/QvTnRAgeN9WyfGUscxkFsQWrs+z71B6LULe3INaJ+khiiKybEyPQcuWacCwbfdz5ePdeSn92QhRpqw+PuAXNLstnbrSIdJ5JtfSq96ikwfawWcVJpgMqHms5FReRrj9LVVFZ1LBFrw8J1Rz3Xh6/0DoZINLlR8Ya23NVQy8tSiS6JW6wEDhf0qJCdtOiNEvAE4nlyvmSFvWIAWJaFIyOV4LQFsQuc0HsS1pUBJFOKTVba7rOtaa9vCgR6ZbtxoLYca6IbfOiTC/fVBh68m1s86IiziGv5gCkPaVWVtuskxil/80TiaWhr/sEu3lRItErpaZ1tTR7ZX8GOnnLW5G39bqu26xvPgeePan6mm9EOoEBvVxI4vnF2VCiPGU70o2yTmAAtlm9WxiJUVHvsPRCeLdfzBpP1CSHdj6Y1iphzjabIe2pLFhabhT3nrE15VSRtZI1j6D1bVZjYJo0pGBAS4TLuYarvtbAqegFBkZZZ41e1xmf1astwZ95gYFNs3rl6KF5MvUYnlT3nYD1DksUFxcZ9jtLyqC4W3xQr3f3HCV9KzVSjoLyVkifaJ9EUV9Tkw4RN+ylMzyJZTSyRjM1+SSNbXZ3udwekygJLmha/zgHAq/rBAbSxmLKqBGQTG0k9opbkD1X1X1MoqBB0KzNJti5ncAAt002KH3mqKkWJaPim5JjgN5aWxZmuldsQLSipo8xI+8l4+0mu+dknj+oEQbHYyEwpYOvq5Hd3C2dtZ7AMzOrjFl+pG6xl7olP/YKDWAJ5jKmD5RgtqlbsHU5IQFb4zdNJXnpmroFnXRCApcCunEuoOvkbolEZ2BMld/W5iq/NnmrglNzQgK23G3Il+QtwSqX5C0YbSckYGvTlnRN3mrX5C0U6YyOLfsar8lb7ZK81QBYOCEBW5u2v1g0r1695C29iHH27CflT73cLZHoloXCGq31Gt4ubu6WiHSJb47ULH7wMV2D8Ji8FRDvOiEBTadOWgdLeiQ/m5K32o3iXkhA38fLcagIKEuPS9DbXgbwk054YF2uVG/jZbnLrpYpQkKmiLlJ6DjLkV7rleZd5FnRtBCK9B58htcsaHP3jo87JlOwNO4idVHv59JoeultM+IIZI/SXUuAbXm5VCwtPWdATjlyxpEzOXhIr/jgmeOV9NXS5U4xhEsWGMIfJyRga4HS9co3x2sWGEh0FwwULC3XqkiPXAlIAiswu52IgFagEQWa7s9tS9dyMRtfs99QpFe9O8is051LbxHbVLfz2ktQPHhZA0Hvg/SMlHdw8Uzk+ehTRHoRAQFUursprNhCe5nqduroiF3kDCpdhPNh8JMGsCrno5Nn3c78eC90VPbMZ9qJiHQgmimySdOs9AcneEkDthLotR7Uw5KOSCcg0GQ1agEI0VwRd7/xPet27s5MDlR7TEgHDCQ6SEBvSquSB8Wttals5/6WK+xPDliAATzd013cCdYkvdUUZROpQ3i51O3cLZmb3ja2VBS4gUi3PCSW2UzXFLByTQHLINKt3Am1QLcpB6xccsBgXwheOMAWsSzXFJ5wzQEDxb1wgCm0yXxNMyqXJDA4fAYvHmALRIZLMtTD+y6TwESkiwSwimW9ZGzxNQcMZqVXZsDWSWyzRCcFTF/meRKhmOOkdXJTwESiX3AIKk6my9j0C6szBQxn0NsqENJ1BrVrEhiBSPfeBuskXqY550sOGPbRGRpT248Xxf1sChgEocPbKhCGy5YTwiUFrKJId3CwcF5aAAKTAwbgKnicBKa83xK2mBywBGvRCQvIcVBzSjRaKIfscFX8Mc8x9w1Feohg09fdMiDiwdvIj8bi4H4vvXwB3cdk8j1qndRJJN2J9BFB3V9TaFR5pIAdZe72i9k9lsViB9nAYWe8K0IIRexeLmXuHuUvjkJ4BZeOExuwRenSNRfqOitxcLx0AVs4b6qJTjcindiAjPGronl9jq3T+OVS525PhcqacqGvh7VKGIj0IAELbNEyUPr6vm+NZ527fVJq7QCNRuhLUBgcrwahQALRUl9O6wV/GIlqo8xdeAyOMtppnLWiq3RiA7bO3fVYl90EMBHobjm39ePqNQEMRHrJAk+r3F0SwGBOevSEWiBSkzYU8YcykW/wVXEU6ZSFavucTEG1oin/q9118gmfh6n2puYTZKmPx2QxMQzxXd1BqOX2Yqu9Pab2WQ8uIVJxogHiUF73o7Gs7fCghTPV3nbzhaQgTfMfgSdTRHquLAqI56ihrm2ngbPV3spDJAu814pVBgZ4rAS2jlpczBuTRoZuwuMqxCQxjnxJI6tuFpliD0/ik5J0XhaZTFQnViMS1EBaukbW9CTyTqKzXFiWi24iMo00kWwxuV1LulyFpubZdVFrBpAv0qFf35PIxIcLdm4l95pn4rT0ZkQLkuyjk7Jm8gq+bhCUDF6qQK17OIqrhnfDQ/Fak2xm+iBp222pjyBJKR5kvp8IOjqBAfF6slQUWoiI+LgH0zvKTLQ/XH10smmQIWhEjEDifRU1zV3WUmzXrEH2Bzw6gYFRPk7ro3Grj/tTmUt7kqcGe/ZeZgEzQXuZzueAItJdOmcm22BIg1y3esl1Q4n+VgMlz6Y7eLqmuoFIL1PA1idrU30yL9NNb/rfkpa2uC9nfUefd2r2aHaa6EYGTA7Z9Sr6rAslk0zrPkeQ6J5unnSy6I2QvsPTq+4EwaroBQY0pb7JitBdfueB03sMmUr741px2aboh16mfj1dwxaVOkp2iqgdBV29WICVOLNG94pIshfqK8UMQ+yFAjS1R3PcKOvpr5fAagLaN3FgrEWWKuspWS9H5LCIS9oLBcipuhWZtUr0kmtPq2mCAJSOiuuLdFVgetH9UI7qETvpjwdp2RZlbOGR5pY1v10D0mpHzTfSiqUCLSGGFr1IwNM5cymhBhLdkRETixMTt7enmeodovRPlVbnuBfp0iv0qG/YW0CJ7sjsT6r1kF5oJFtqDE4BmN73ydyR/6us7Vjhci56UQCb/EKrxZxk3pPGVFMoRmk3nwYzVeYEKl0mm0bv9TY3Q5QvemGAp50senXKUcOjMnQZ1owXBmiaaSaHDr22jD2dRsaesz5kkOG5LGbv6P9MV5mEoqzui5Q1aAYS3QFBibN7EAz6qpdmoQqKR9AdPfYBTSAIekaXbjwuunQx60Og/fktvSTaXrUqX1AmOLi9j34+QFYqLc1JEAV7H1ViEveylSiLWfmtBZLktAdVQKQ7HlnTqeR0KbYa7kEmdtDkPdmmZKAEh0bNVdLcO+zkm5giF1hZn9HJ8UV8utbfQAzhnPttzYmwOGPtj2y05J7mfUVICog33ISCsarW6dvSeGtyVnzYw+zwiwarxTn47xccGrwqyrrXusij4kPVaHMRxQVK6SUjRu6jc/DXWLK4/dAeBef7geus+MAvIv9VczbTpoVp0ZY37IRw19fmoJmWKdg0hC3oRLOsQKQ7PHAzNz9Ra/uDJb1cUhpIrcIBIt/ETjhHerQAQKOoZRpZkf8p0ScnzFpmTB89ibsZVHWj8EE63//rO2ioZKPHMXe8ZbZp4eOdW+rlUvhgv8g+fkEb7gp+UgAMzjWup+FIfP7PG6zvm5yAlncwr+/9+zP4s+4B1HvQpWQ8pfdMgLTwZ9Vx1ABSfzd51j2gF/Hnr1q6WUnuE7zakbF60wX0YlLagg+4dDz2AfUZGjco+ra+9efbZ92D9iJ70KvePe87RMso0i92f8/Lo5VspA3xl6lWg+m9KIBlqLkyR4awl7KR/SEpib2+DASRbyK9WYjUchx5L5CpuwiuHS8/oGhsWJxjUdILHiQoxwPhcryUFY8sOxHD5ujlB4jlSKdL1iSQNr0QfpyPjl8kiPvEGy6CJ7RJ9qUsSHRHR2kttTiyHrIHk+vxQrgeL6M1wSRhVDx6/IT7Y6Sgfk13yZfLA+G6r52oSYJq3wjJkcljIniqtnkZXWA5Jo+JoGjSipLTagofTw+E9clbfpXu7x6A8DI/eQ8GbHQ4XsPDj4mexKlpzDlC8Qz5iXuygWBuWJAb6E5Wi56WxNW180m4iHRHR05Aj9KH4tH6fnu+k31c/xy/wMNN8uMAsjtoHTMZ8cSPOlDnO9m9tIkciGUy0aYcQufrehHp0+ApiI96Adm2MwPo8U5W1qeswNeq7NL6XpHg2J68QMDTAOflbSf20o/SQDiS53Dk4wVq2BMycLy9OIDtY577KIjoNel17z56cDhOXkxAA2QyCLLoxAf0ilqyFGW/FASwacJ7ajujqZzvmxaEBZE+i0fRQ6qoWB/0L/q2UwN0OltFZNYiXSFqbV3dcFGkOzjqqvXdy3582EVqVKFoHV0NVwlmedXc1qypLxGuylOPCvzww+///PsffvjD//ov+a9y1ueX/W/b+t+4/1Vylf3vNv4+/nsCQJ16VOBb33z3/Q8//uj9H7/z4cc/eO+/emMvrx+9nr9sxy//q/8AepbComc5br0nuf+FuZuS23IKpuV+iIeWE5g5rWyidrU9wJZ9nZPVOU06J9A5L3VOvcXQewDpVjLv3Jaz1TlPOmfQOS/nQatjfGeds69ztjrnSWe40xR3v7T20LnPsIZf+DoXq3OZdIYTUCrrcY6XOY4t+zoXq3OZdC4gpy51DmO1jbmd4Qtf52p1rpPOuP3Wpc5jXYc8dIcvfJ2r1blOOkPCVKL1OF9bxi98ncnqTJPOkBeTaD23+bKqwNrk60xWZ5p0hsclsovf+bCt6xw2+MLXma3OPOmMeyQvx3noengU0Jl9ndnqzJPOCJ3aWud62UnwC1/nZnVuk84NdG5rnePwmmO84Qtf52Z1bpPO4JHytl7P0cww+4WrswjDlvN21RmeRyvovNurxqpKG3zh6qyL0bR81RlXpyCoZcvZ7pLYcvB1DlbnMOkMl/A5rH3Y8Ntx8iQ5+DoHq3OYdIb5kuNa5zGnZzQkB2q35Wh1jpPOAP3yEqeNHeNEQ2BtH4dli8PyhMNwdWYHh+U+p2dkkH0cli0OyxMOAx4Yzctc+u0xp+OlBxm+9HW3eCxPeCwDHstrPDZW1dg10Vo+HssWj+UJj2XAY3mJxzTdxe5doLOPx7LFY3nCY0Dzpvkudx5l7Bw403w8li0eyxMew4h0dvBYvuxZsLp8PJYtHssTHsuAx/Iaj+XeYu7rO/Xxxhni47JscVmecBmGRfIal+Whe7Y9gIub7OOzbPFZnvAZFofIa3yWq+3B6BHOGB+nZYvT8oTToCiQ/PPaBn3mld5y6aMB1+XZx2vZ4rU84bUMeC2v8drRcrdF2UZP4EvfBha35Qm3ZcBteY3bjhZ7D2r/9+ELafwd/338HnXzbWTxXZ7wHVRL1Ay5VQ9rH5VxUkSr+vguW3yXJ3yXAd/lNb6rXfeBLE1ffZ0tvssTvsuA1soa39FosfeAN/jC1blYfFcmfFcA35U1vhvje4x3hC9cnYvFd2XCd/gQuazxXeWha5+JFb7wdbb4rkz4DpMsyxrfDV2PuY4t+zpbfFcmfFcA35U1vhszjIfu0LKP74rFd2XCdxgtLGt8N9Y3x6E7fOHrbPFdmfBdAcRS1viOri2Dzj6+KxbflQnfAQuR/PNSZ760jDPMx3XF4roy4boCu3ZZ47qBqognT1J8XFcsrisTriuA68oa11G1OsMNePFxXbG4rky4rsAuXda4bsywY0cBa/u4rlhcVyZcB2Vm5Z/vdR7+G/vq62xxXZlwHfBd1rLGdcN3jZZxhvl4rlg8VyY8VwDPlTWeO2ZWnWeYj+OKxXFlwnEFcFxZ47ixV40eoLV9/FYsfisTfiuA38oavx1+u857lY/bisVtZcJtBRBGWeO2duyOfZxhVfl4rVi8Via8VgCvlTVeGy2PnQPnpI/DisVhZcJhBefLGoeNPaot/LaPw4rFYWXCYQVwWFnjsOG7hkdBT+LjsGJxWJlwWIGZWtc4bEQA6uFF4QtX52pxWJ1wWAUcVtc47JjT845RfRxWLQ6rEw6rgMPqGocdLQ40BDr7OKxaHFYnHIYPueoSh5UesS896oXVAKuPw6rFYXXCYRVwWF3isNJjEGfLFb7wdbY4rE44rAIOq0scVnqcrWzjL/bV19nisDrhsAo4rC5x2Knr0H2DL3ydLQ6rEw6rgMPqEoeVEK3OwwYQc6o+HqsWj9UJj1XAY3WJx0qPs5U4Wu42gAyV6uOyanFZnXBZBVxWl7jsaLlHdku/Q8AzQ/XxWbX4rE74rAI+q0t8Vnqc9Wh59ATy8KqP06rFaXXCaZhdW5c4rfSY49GTHvUsENmvPl6rFq/VCa9V2BvrEq8dPegRwJJGD2Am+ritWtxWJ9xWAbfVJW47Wxw9iYse+Daw+K1O+A0LS9Qlfisdn5ceiyoV1oCP36rFb3XCbxXwW13it9IjO0fLGcbdx2/V4rc64bcK+K0u8VvpscfSo16lxx4LxN2qj+OqxXF1wnFAh6Z14pY9iJeWYdX5OK5aHFcnHFcRJyxxXOlRz1N3aNnHcdXiuDrhuAo4ri5x3Nli70GF8fZxXLU4rk44rgKOoyWOO1oecx3mOPk4jiyOownHEeA4WuI4JRs34z3mPMx18vEcWTxHE54jwAu0xHOHzt3qfIw/9MDHdWRxHU24jgDX0RrXHZ5lW7Ts625xHU24jmCvpDWuO8Z9WB3G3cd1ZHEdTbiOANfRGtfli1ctY+b1HvVzeqHx72NNZJDs28biP5rwHwH+ozX+Gz0YPQKcTz7+I4v/aMJ/BPiP1vivnyBLP88VxpZ9nS3uown3EeA+WuO+YWXaZmv7eI8s3qMJ7xHgPVrjvX6GLT1KUiCiTz7OI4vzaMJ5QEGuhd9urb2NGQdf+DpbfEcTviPAd7TGd6NlXswwH9eRxXU04ToCXEdrXNfjcIUXM8zHc2TxHE14jgDP0RrPHeO8DavDF77OFsfRhOMIcBytcdzQuY4ZBnPbx3FkcRxNOA7rQNEax4113COBPHpA2ANfd4vnaMJzBHiO1nhuWH2MN4HVfRxHFsfRhOOAJU3+eT3ebP04jreP48jiOJpwHAGOozWOGy0f6xpa9nEcWRxHE44jwHG0xnF88SgQdyUfx5HFcTThOAIcx2scd8w0ntY1+ziOLY7jCccx4Dhe47jhy479usIXrs5s8RtP+I0Bv/Eavw1dD90zfOHrbHEbT7iNAbfxGreNFg/dwdo+bmOL23jCbQy4jde4rfHFl2123PsdYoWYFft4ji2e4wnPMeA5XuK52mNVdUTN2ljvqItvE4vXeMJrDHiN13ittzh6UHvcrkKskn3cxha38YTbGHAbL3Hb0WIYtsiLHvg2sPiNJ/zGgN94id+OFkcPeuwKeCKVP8rtgcVxPOE4BhzHSxx3tjhsERc98G1g8RxPeI4Bz/ESz9UeLas9WlZ7DKtCniT7uI4truMJ1zHgOl7iuqPFHjWrcVv0wLeBxXc84TsGfMdLfHe0OHrQo2hY2419nMcW5/GE8xhwHi9x3tnisEVc9MC3gcV7POE9rM7MS7x3tNwjSDWPHsAo+LiPLe7jCfcx4D5e4r6z5W6LfpKsZfz76OE2eggSfdtYPMgTHmTAg7zEg0dPRs8grsc+HmSLB3nCgwx4kJd48NC5DJ1hh/LxIFs8yBMeZMCDvMSDtaPvOvZGiHGxjwfZ4kGe8CADHuQlHqw9unLoDEiUfTzIFg/yhAcZ9ta2xINny93qEFFsPh5sFg+2CQ82wINtiQdPa29jzsMXrs7N4sE24cEGeLAt8eDRcp3ndvPxYLN4sE14sAEebEs8WOuY08PaGb7wdbZ4sE14sAEebEs8eMzpnqHbxu4Lxb2bj/+axX9twn8N8F9b47+he51XV/NxX7O4r024D6srtiXuO+b4aBmip83He83ivTbhvQZ4r63x3uHL6rSum4/zmsV5bcJ5DXBeW+O80fKxuqBlH981i+/ahO8a4Lu2xnf1sq7hzNN8XNcsrmsTrmuA69oa1x1znOcZ5uO5ZvFcm/BcAzzX1nhueJRj3wZf5uO4ZnFcm3BcAxzX1jhu6HroDuvZx2/N4rc24bcG+K2t8dto8dAdrO3jtmZxW5twG9KJtDVuO7znZse7jB71f+dhGxgNH881i+fahOca4Lm2xnPjhNnjOniv1ny81ixeaxNea4DX2hqv9fP+0TJEx5uP15rFa23Ca1jboa3xWo9x1B7TOnpieuDrbnFbm3Ablv5oa9w2WqZhfZiJPm5rFre1Cbc1wG1tjdt6tLS20QPsq6+zxW1twm1QuIu2NW4bLR49qPCFp7MKg5Zpu+I2/Rbk3M7x3nIbZxPGHni6q1Dbgzb1AHR38BtfrD56hF/6NgjWBlccp9+CnLUNxlyv13VOm4vjVJhtedI9gJw1jjs8S52t7uI3FWZavuI3Au5O2tb4rV3Xd4QvfJ2j1fmK3/TbU84Sv1GP11DPOaMIOrv4TYWZlq/4Tb8FOSudqaNk6nE7Ot+x0ubiNxVmW550TqDzEr9RzyU7dR422OBLX/dsdb/iOP0W5Cx130aLvScbjLeL41SYbXnSPYPuSxx3tHhYH1p2cZwKMy1fcZx+C3LW411tywFb9nUuVucrjtNvTzlLHEc9Ok5x9ABmmovjVJhp+Yrj9FuQc6tzjwgS+iAXx6kw2/KkcwU5SxxH27VlWNcuTlNhpuUrTiNgZ6VtidMobHZV4Z7j4jQVZluedCaQs8Rpx8waOmPLLk5TYablK07Tb0HOej1fVhV6URefqTDb8qQz7rpLfHZY+Zjb+IWvc7M6X/GZfgtyljrHw4PYHmzgRV2cpkJtDybdYd8PS5xGaYzzdvHnYzT6fz9jzvKfXJsEi9/ChN8C4LewxG/U4+zU4+/UX4/TmTNMwcdvweK3MOE3IPuisMRvo+Wjglk/p9EZ+ZcvfRtY/BYm/AbschSW+G20TP0GgDqGpX5+p37CpHLUWAOJvm0svgsTvgsw88P6PeuYsWWqSyNf+Dax+C5M+C4AvgtLfDdaHDpD5UEKPr4LFt+FCd8FwHdhje96XI56PJbOSLB84ets8V2Y8F0AfBfW71mPmh1x6A5f+DpbfBcmfBcA34U1vhszbuiOOvu4LlhcFyZcFwDXhTWuq2POd2sT6OzjumBxXZhwXQBcF9a4brxj3bZ5bvu4LlhcFyZcFwDXhTWuO3Tu45zB0/i4LlhcFyZcFwDXhTWuG1YuY4ZByz6uCxbXhQnXBcB1YY3rjvU8VhesZx/XBYvrwoTrAuC6sMZ1dcztoTO07OO6YHFdmHBdAFwX1rhujC+NHsCq8nFdsLguTLguAK4La1xXRgVKnj2Jj+uCxXVhwnVQS5fCGtcde9VYz3n470VPfBtYnBcmnBcA54U1zhszbcw83EF8nBcszgsTzguA88IS542aS8eMq6Czj++CxXdhwncBPFRc47uxruu8vqOP46LFcXHCcRFwXFzjuGJ1Tqavrs7R4rc44TeoQEtxjd+GNx2r7MxK0FLabssWt8UJt0XAbXGJ2w6EMHZN07Kvs8VlccJlwJoswPzej+dp14w+LosWl8UJl0EJYYprXFartTbOMB+XRYvL4oTLIuCyuMZl5eJJCFr2cVm0uCxOuCwCLovruBtdESG27OtscVmccFkEXBbXuKxevCjgsujjsmhxWZxwWQRcFte4jEbLfScZlc0yzDQfn0WLz+KEz4CrlOIan43aG0cdsTHu+KVvA4vT4oTTIuC0uK47MuqJ9R6MHhHEmqOP16LFa3HCaxHwWlzjtX6XROPt/qgvhtbzcVu0uC1OuC0Cbotr3MZD91HRbPyFNeDjt2jxW5zwWwT8Ftf1SAZOH4iCx9/+/m1EhvsdBOHO4+O7aPFdnPBdBHwX1/VKeos8KhMDvos+vosW38UJ30Wc4Ut8N1qkjjQYYpXRx3fR4rs44TtgbqW4xHfcI0bD6gwx6ejjuWjxXJzwXAQ8F9f1So7aHds8zj6eixbPxQnPRcBzcR23GzOt3wTwBnPfx3PR4rk44bkIGqQ1nhuRgDbm+AZfuDoni+fShOcS4Lm0xHM8qniOKm4wt5OP55LFc2nCcwnwXFrjuTZm2Nb/RvjC19niuTThuQR4Li3x3FhV3OOzDLdbycdzyeK5NOG5BHguLfHcsDaHoTO07OO5ZPFcmvBcAjy35m+gEXs8rA7W9vGc5WegiZ+BgJ+B1vwMh9dc+G2fn4EsPwNN/AwE/Ay05mc4fNi4azr8eIYvfd0trpt4Ggh4GmjN03B60Tj5b5+ngSxPA008DQQ8DbTmaRiVj86Zhn31dbZ4buJpIOBpoDVPw7Gew2Jd+zjO8jTQxNNAwNNAa56GY12PGtjoy3z8ZnkaaOJpIOBpoDVPw1hd54wDnX3cZnkaaOJpIOBpoDVPw9HyMcNgbvt4zfI00MTTQMDTQGuehmM1hcW69vGY5WmgiaeBgKeB1jwNo8VD5w3G2cdjlqeBJp4GAp4GWvM0cL/F5FEF6KjBBD3wcZnla6CJr4GAr4HWfA181B2yPeAIO4mPzyxvA028DQS8DbTmbThqMI313XvEkKXi8zeQ5W+gib+BgL+B1vwN3G92edQdOqpBYQ98G1i8NvE4EMa01jwOo2U+KiGNGkwbfOnawPI50MTnQMDnQGs+h6Pm0mH9Pg8S9sC1geV1oInXgYArgda8DkftpWGL/u8Md8o+vwNZfgea+B0I+B1oze9Qzhb73z4zTxZF8nkeyPI80MTzQMDzQGueh9EiT9WgoAc+rrN8DzTxPRDwPdCa74F7hHBUh2GIu/t8D2T5HmjieyBgMKA13wP3G1vusWiGiJHP90CW74EmvgcCvgda8z1wv8XkPKyPffV1tnhu4nmgjHLWdUhGDZ5hdbhj8nkeyPI80MTzQMDzQGueh8PKox5Nxr76Ols8N/E8EEaY1jwP5ZxZY6bBF77OFs9NPA8EPA+05nngo9rXqmVfZ4vnJp4HgtqrtOZ5OFbV0TKMs4/nLL8DTfwOSHtJa36HY07nbZ5hPp6zvA408ToQ8DrQmtfh1HX/WzfOs+4+rrO8DjTxOhDwOiiJ8J3uZVR9Ai/q47pscd3E50DAPEBrPodzhg1vOlZb71G/BeEek+JRTQJOGD7fA1m+B5r4Hgj4HmjN93D04KjVAt7Wx3uWx4EmHgeC+rS05nE4Wux3E4w6+zjP8jjQxONAwONAax6Hs2WedfbxneVxoInHgaDSNa15HHicnuuwdoYvXJ0tjwNNPA4EPA605nEYVb34qJgR4QtXZ8vjQBOPA0F9WlrzOBwzbMx5uIPyeRzI8jjQxONAwONAax4HrmNm8TTDfB4HsjwONPE4ENRkpTWPA5811IbV4QtfZ4vbJh4HZH2lNY9DoavOMMN83GZ5HGjicSDgcaA1j8Oxjh/3LDWMCH/BL33dLX6b+BwI+Bxozedwrq7FHPfxm+VzoInPgYDPgdZ8Dud6HqsMrO7jN8vnQBOfAwGfA635HE5fts2ry8dvls+BJj4HQhy45nM4dKbFOPv4zfI50MTnQMDnQGs+h6PFoTvq7OM3y+dAE58DFdRgjd9ozLDNelP0LD6Os7wONPE6EPA60JrXgS9+nHGO+zjO8jrQxOtAwOtAa16HUfHo9DDZ7mU9g4fPl5Lk8z2Q5Xugie+BgO+B1nwP3O/TebyYPCohYQ98m1h8N/E+UEGvvX6nOiKFPP6OCkj4pW8Di98m/gcC/gda8z+MFplHHaJt0QPfBhbHTTwQBDwQtOaBGC2OHvB4pwx3Ej4fBFk+CJr4IAj4IGjNBzFa5PGaMKx64NvA4rqJF4KgpheteSFG7SXu9608XhFH/NK1geWHoIkfgoAfgtb8EKNFHi8pj1pM2APXBpYngiaeCML5tOaJGC2OHvB4WQkxK58vgixfBE18EQR8EbTmixgttlGbLa164NvA4r6JN4KAN4LWvBGj5TY80aiIlPBL3wYW/038EQT8EbTmjxgtt46+Wo9ht75K26gSNiohQe64zy9Bll+CJn4JMvNsiQ+PnsRRs2WDL3ybWFw48UsQ8EvQml/iaLHH9xv4BZ9XgiyvBE28EmRGdYkL26gON+rUoJV8XGj5JGjikyDgk6A1n8RouYVhbRhnHxdaHgmaeCQIeCRozSMxZlYbVeEg0uTzR5Dlj6CJP4KAP4LW/BHHDBtzH27PfN4IsrwRNPFGEPBG0Jo3YtTqGHWIjLV9PGj5ImjiiyDgi6A1X8Qxp7d+6ho9QX/t40LLF0ETXwQBXwSt+SLO1cXzuvbxn+WLoIkvgoAvgtZ8ES1crQ7j7eM+yxdBE18EQd0LWvNFnKtrMcd9vGd5ImjiiSDgiaA1T8S5nscqg5nm4zzLE0ETTwRhtYk1T8Q5ztu8unx8Z3kiaOKJIOCJoDVPxKFzXMxtH9dZngiaeCII61yseSKOFofuoLPPE0GWJ4ImnggCngha80SMffrct0ftROyBq7vliaCJJ4LwpfaaJ+KcYTxsAF/4ulscN/FDEPBD0Jof4qiIcnjVbPeynpvQOuJsgO98/giy/BE08UcQvuRe80e0jihHlZgGdxg+fwRZ/gia+CMI+CNozR/R+s1B64iyJWzZ19nitokXgoAXgta8EK3fQbd09AC+8HW2uG3ihSDghaA1L8RRDYh40bKvs8VtEy8EAS8ErXkhDiuPGqoMLfu4zfJC0MQLQcALQWteiLMO0bD2Bl/4OlvcNvFCEPBC0JoX4mjxMc41DKvDO3afH4IsPwRN/BAE/BAablrOtNGDMeNAdx+/kcVvEz+EfnvKWeK3sa5rj2EYq/v4zfJD0MQPQcAPQWt+iNOjxNnaPm6z/BA08UMQ8EPQmh/isHI+Vhl84etscdvED0HAD0FrfojWX2K04d9xfHzcZnkhaOKFIHzZs+aFaD1u23rMskHk2OeFIMsLQRMvBAEvBK15IVrPdjh6gDr7uM3yQtDEC0HAC0FrXoiz2tM26+zjNssLQRMvBAEvBK15Ic6qMMd4wxe+zha3TbwQhBmha16Iw9pljPcGX7g6W14ImnghCHghaM0L0cbpt/Cks88LQZYXgiZeCMI86zUvxKi9cs7tCF/4Olu8NvFCEPBC0JoX4ljP49Ww6auvs8VjEy8EAS8ErXkhRsvn3AZr+3jM8j/QxP9AwP9Aa/6HVsc+zXa8AZ/7/A9k+R9o4n8g4H+gNf/D0WKd17XP+0CW94Em3gcC3gda8z60Ec06WobV5eMyy/dAE98DYb7dmu9h+LJjpkGswed5IMvzQBPPAwHPA615Hk6d4+xRfFxm+R1o4ncgzD1b8zscFY7G+h49OXwbjLuPzyzPA008DwQ8D7TmeRg9aXWs91HpCHvg28LitInngfAGec3zcLY4Kt1scw98vGZ5HmjieSDgeaA1z8NoufX79tbvoFu/g2r9TrKNl7eAJH3+B7L8DzTxPxDwP9Ca/6G10XIfnQa+0MdzlveBJt4HAt4HWvM+nC0/Tg4bvMzxeR3I8jrQxOtAmDWz5nU4dd3mln08Z3kdaOJ1IOB1oDWvw1mz4dAdvvB1tnhu4nUg4HWgNa9De9yvia69ZURDPp6zvA408ToQ8DrQmteh9Zv/RnXRsq+zxXMTrwMBrwOteR2O1UVjhm3whauz5XWgideBgNeB1rwObZyCx7kcKtT6vA5keR1o4nUgjGGueR3GqjqqAEEml8/rQJbXgSZeBwJeB1rzOrTxanjULYAol8/rQJbXgSZeBwJeB1rzOpzreZ5hPp8DWT4HmvgcCPgcaM3ncK6qePHj2ANfd4vnJl4Hwpu/Na/D2DGOccfx9vGc5XWgideBgNeB1rwOY4a1nkPQoD6gz+tAlteBJl4HAl4HWvM6HKuqLVaXj+csrwNNvA4EvA605nUYc/xsGazt4znL60ATrwMBrwOteR2O3bItVpeP3yyvA028DgS8DrTmdWgjP+LwaWBtH7dZXgeaeB0IYxlrXoejxaMH0LKP1yyvA028DgS8DrTmdeg7B+yW2LKvs8VjE68DAa8DLXkdzhbHrom+zMdjlreBJt4GAt4GWvM2nLtkxh7YXdPHZZa/gSb+BgL+BlrzN3Q/fnpTtLqPyyx/A038DQT8DbTmb+h+G/w4rC4fl1neBpp4G8jsAytcVrdt6DzqiY2/oLuPzyx/A038DQT8DbTkb6jbqL476gzRmPvYd98GFqdNPA4EM5jXPA5nvaE+CmH8jfClZwO2fA488Tkw8Dnwks9BW+otjrpD4y/2wLMBWz4HnvgcGGzJSz6H0XLdxvv1o95Qhi99GwRrgyt+Y+Bz4DWfA43VF8bfPg9S71ns/31Ud2TUybdNsLa54jsGvgde8j3ULfWW+x3Tdp6O2ed7YMv3wBPfAwPfAy/5Hs6WY7dFxr76Oker8xXXMfA98JLv4dR19ABbdnEdW74HnvgeGPgeeM33MOoN0dgDTV99nZPV+YrrGPgeeMn3IDqO8R06w9x3cR1bngeeeB4YeB54yfMgOnaPE+OiZV/nbHW+4jo2o7bCdefqGqvtjASzz/PAlueBJ54HBp4HXvI8iK695bSN1QVf+DoXq/MV1zHwPPCS52HMaahTAi27uI4tzwNPPA8MPA+85HmQlrvvOipcgSdxcR1bngeeeB4YeB54yfMAvmsxw1xcx5bngSeeBwaeB17yPECLbP14wh74upPV/YrrGPgeeMn3cHrPVOfxdnEdW74HnvgeGPge2OF7GBG+8YoYfZCL69jyPfDE98Ab7n1rXJeuLYPOLp5jy/fAE98DA98DL/kexhyHlmGOuziOLc8DTzwPDDwPvOR5gL1qm1aXz+fAls+BJz4HBj4HXvI56Gp6sT4twheuzpbHgSceBwYeB17yOJwtHj2Aln28ZvkbeOJvYOBv4CV/w7lzHLsltuzrbPHYxM/AwM/AS36Gs8Wxa4Iv8/kZ2PIz8MTPwMDPwEt+hnOXLNulBxW+9HW3uGziaWDgaeAlTwP4cZ6t7uMyy9PAE08DA08DL3kaTr+dZ1zm8zSw5WngiaeBgaeBlzwNYu2u83iLHce+jV/6ult8NvE1MPA18JKvoW5lVDiK2APtEXzp28DitIm3gYG3gde8DWeVp2GLPhoFv/RtYPHaxN/AwN/AS/4GbenR4nhFelR9Ahv4uM3yOPDE48ABNVnjttqtPt5ujipPEVafj98snwNPfA4MfA685nM4qjoNRFH7aFSwgY/jLK8DT7wODLwOvOZ1OKs7DVt0L1zBBj6es/wOPPE7MPA78JrfgYcHqn0Gjjf7gOd8nge2PA888Tww8DzwkudhtFi38Xp84DrsgY/rLN8DT3wPDHwPvOR7qNuIVYyIEWOffd0trpv4HTignDWuG6fi8YoY/b+P6yy/A0/8Dgz8DrzkdxBr93Efr4YHzsPx8vGd5XngieeBgeeB1zwPRxWg0TJEx3yeB7Y8DzzxPDDwPPCS50F0zKi72gK+cHW2PA888Tww8DzwkucBWhw9qPCFr7PFdxPPAwPPAy95Hs6Wj7mOffV1tvhu4nlg4HngJc8D1Fo6Vtc0132+B7Z8DzzxPTDwPfCS7+HUuVs9jr2PwPo+zrO8DzzxPjDwPvCS9wE8S51b9nGe5X3gifeBgfeBl7wPMO7D6ht84etscd7E+8DA+8Br3gcekYKhO3Xd+yk6jLuKNmq1jFpsGST7trE4cOKHYOCH4CU/BPSg97DBjPTxn+WF4IkXgoEXgpe8EKBrnXX2cZ/lg+CJD4KBD4KXfBA19LuJ0G8IwgY6+3jP8kDwxAPBwAPBSx4IbalbmXvLMBN9nGf5H3jif2Dgf+Al/wPoPMYZVp+P7yzvA0+8Dwy8D7zkfThbPmYaWNvHdZbXgSdeBwZeB17yOqh1e8uLcfbxnOV14InXgYHXgZe8DmOczxpMAcbZx3GW14EnXgcGXgde8joMnUcVGNUdvvB1tjhu4nXgiHvlEseN1bQ9IsE1DnTVoAc+nrP8DjzxOzDwO/CS3+FYXWfFK5jjPo6z/A488Tsw8Dvwkt9h+LLTj8N4+/wObPkdeOJ3YOB34CW/w9FyGNVfQGef34EtvwNP/A4M/A685Hc4rd09SoAYtM/vwJbfgSd+BwZ+B17yO8BM42ld+/wObPkdeOJ3YOB34CW/w+HLzv0arO3jN8vvwBO/AwO/Ay/5HU5dD90zfOHrbHHbxO/AwO/AS36Hc5c8dAdr+7jN8jvwxO/AwO/ADr8DX33ZZsZ9a6NnMAo+nrN8DzzxPTDwPfCS70Fb6i2OGluj3hSsdx+vWd4HnngfGHgfeM370FscPahhRA4hq8Hnf2DL/8AT/wMD/wMv+R9Gi/J36F7nHvj4zfJA8MQDwcADwQ4PRD9B9B7I31F7C/vu28DiuIkPgoEPgpd8EKPFGo56U9vcAx/PWV4InnghGHgheM0L0StcSQ/6PDiqPsEo+LjO8kPwxA/BwA/BS36I0aL8HbW26twDH99ZngieeCIYeCLY4YkYXni8lB7V2nG/9nGe5YvgiS+CgS+Cl3wRo8Uaxhvegb6wBz7es3wRPPFFMPBF8JIvYrQsf0fNrVGbATySj/ssXwRPfBGccEavcV+PXYUe2wgD8+ZRCWf0bFQNgf3Dx4OWR4InHgkGHgle8khAT3rPMrbs28TiwYk/goE/gpf8EaDzmBcZvnB1trwRPPFGMPBG8JI3ooYevw89ih7O16fs80Ww5YvgiS+CgS+Cl3wR2hLqLD3Y4AtfZ4sHJ54IBp4IXvJEjJZlfPtMLNiyr7PFgxM/BAM/BC/5IcDaY4ZV+MLX2eLBiReCgReCl7wQZ8vHHIdx9vGg5YXgiReCgReCl7wQat0+zsPaMLd9PGh5IXjihWDgheAlL8Q5p3tULY49MGMPfN0t/pv4IRj4IXjJDzF0H9W97OrycZ/lh+CJH4KBH4KX/BDnHD/qisFM8/Ge5YfgiR+CgR+Cl/wQw5ed/hzXtY/zLD8ET/wQDPwQvOSHOFse75tRZx/fWX4InvghGPgheMkPcVp7rOsK4+zjOssPwRM/BAM/BC/5IWCO8zzDfDxn+SF44odg4IfgJT/E6VGOfRus7eM4ywvBEy8EAy+E/PNS56HroTusZx+/ZYvfJl4I/faUs8Zvo8VDd7C2j9ss3wNPfA8MfA+85ns4vedmxzuPHvVRGO+aIefM54NgywfBEx8EAx8EL/kgauh3FaHfFAW4k/T5INjyQfDEB8HAB8FLPghtCVvGGjzs80Gw5YPgiQ+CgQ+Cl3wQUGMpvkBPTA98Xgi2vBA88UIw8ELwmhfirLk0rF/hC1d3ywvBEy8EAy8EL3khZKbxaHHMPPjC19nitokXgoEXgpe8ENBi7wFEUXxeCLa8EDzxQjDwQvCSF+Kc473lNFYjQQ98/Gb5IXjih2Dgh+AlPwSs73oZ9whf+jawOG7iiWDgieAlT8Rp/WELWOc+PwRbfgie+CEY+CF4yQ8BnmWbre7jN8sPwRM/BAM/BC/5IUDno8YafOHrbPHbxA/BwA/BS36IGkasYmBW9Ek+frP8EDzxQzDwQ/CSH+JoOfboaYSzqM8PwZYfgid+CAZ+CF7yQ9TAtmWjs4/fLD8ET/wQDPwQvOaHOKsCDauDzj5+s7wQPPFCMPBC8JoXog1EMV7O4/j4+M3yQvDEC8HAC8FLXojD2qHnU0WIAPn8D2z5H3jif2Dgf+Al/4O0OHTmMcfhC19ni98m3gcG3gde8j6IjpcaPGhtH79Zvgee+B4Y+B54yfegq+jF9MC07Ots8dnE88DA88BLngfwJHm2to/PLL8DT/wODPwOvOR3OOf0McdhVfn4zPI68MTrwMDrwEtehxpHTGnM8THT4M7B53Vgy+vAE68DA68DL3kdjhZPX1bhC1d3y+fAE58DA58DL/kcpKXNtsz4ha+zxWcTjwMDjwMveRyg5TjtHD5/A1v+Bp74Gxj4G3jJ3wAt58mX+bwNbHkbeOJtYOBt4CVvA+yWeVrXPi8DW14GnngZGHgZ2OFlGNW8irX6sMXp11GSbwuL0ya+Bga+Bnb4GuqwRW/5qGyIPfBtYvHaxNvAwNvAS96Gs0Ua9cV47oGP2yx/A0/8DQz8DezwN/SWU88dTAPTdLwe+614HFW6Ab/7/A5s+R144nfgivNuietif70S+01whLOqz+/Alt+BJ34HBn4HXvI7aEuPFvvdY4ywOn1cZ/kdeOJ3YOB34CW/w6lzv3/FzFuf34EtvwNP/A4M/A685HcY4z3GXw4f4P99XGd5HXjideCKM9mpXzKqh0TUXauJwJe+7hbfTfwODPwOvOR3OGdYGDMO5riP7yy/A0/8DgyVjnnJ7yC6dnQ1Tsmos4/vLL8DT/wODPwOvOR3OGdYXLXs62zx3cTvwBV37yW+O1bXsDruHD6+s/wOPPE7MPA78JrfIfcYVGp5Xtc+vrP8DjzxOzDwO/CS3wFm1tA5wxeuzpbfgSd+BwZ+B17yO4C1j/GGL1ydLa8DT7wODLV3ecnrAHN70bKP6yyvA0+8Dgy8DrzkdRCdo/XfAfvq62xx3cTbwIRylrgu9tyh3rLOOPjC19niuom3gYG3gZe8DcPasGvCDPNxneVt4Im3gYG3gZe8DYeuqZ+ejM4+frO8DTzxNjDwNvCSt+HEKGO8A7bs62xx28TbwMDbwGvehjRQ9GgZbi983ga2vA088TYw8DbwkrfhxGOHzthXX2eLxybeBgbeBl7yNpyr6fCisJ59PGb5Gnjia2Dga+AlX8PpPQ9kAOPs4zHL1yD/OukMeIwcPLZZ7wkY1OdrUGGm5QmPAV8DO3wN4yVNz7CB6l7s8zWw5Wvgia+Bga+Bl3wNR4sDk2DWgM/XwJavgSe+Bga+Bl7zNeSj5vEYbxhnH4dZvgae+BoY+Bp4zddAB/6a6gayz9fAlq+BJ74GBr4GXvM1dJ1P/41+28dhlq+BJ74Gxlpba76Go+UwoyGfr4EtXwNPfA0MfA285ms4dd4GHoMvfJ0tDpv4Ghj4GnjN15CPet4PT5LhpZzP18CWr4EnvgYGvgZe8zXkvNmWA7bs6mz5Gnjia2Dga+A1X8NoOfdYQ4Yol8/XwJavgSe+Bga+Bl7zNRwtb0PnCl/4OlscNvE1MFaRWPM1nDp3HwbIwOdrYMvXwBNfAwNfA6/5Gs6WY9cdxtnHYZangSeeBgaeBl7zNJzWHnV9oWUfh1meBp54Ghh4GnjN0zBapp7HRJDT4/M0sOVp4ImngYGngdc8DUfLZVSShhnm4zDL08ATTwMDTwOveRqOljsPC+6rPk8DW54GnngaGHgaeM3TcFq7VyaDbCKfl4EtLwNPvAwMvAzs8DKMOt0DGaD39HGY5WPgiY+BgY+B13wMo8XRA6gczT4PA1seBp54GBh4GNjhYThq0I86r2BtH4dZngWeeBaYcb4s64YcLY/a1YRf+DpbHDbxLDDwLLDDs3CDPX2eBbY8CzzxLDCjBus6ITfY0+dZYMuzwBPPAgPPAq95Fu6wp8+zwJZngSeeBcYXM2uehTvs6fMssOVZ4IlngYFngdc8C3fY0+dZYMuzwBPPAuPrkDXPwh329HkW2PIs8MSzwMCzwGuehTvs6fMssOVZ4IlngYFngdc8C3fY0+dZYMuzwBPPAgPPAq95Fu6wp8+zwJZngSeeBQaeBV7zLNxhT59ngS3PAk88Cww8C7zmWbjDnj6/Alt+BZ74FRj4FXjNr3CHPX1+Bbb8CjzxKzDwK/CaX+EOe/r8Cmz5FXjiV2DgV+A1v8Id9vT5FdjyK/DEr8DAr8BrfoU77OnzK7DlV+CJX4HxXnzNr3CHPX1+Bbb8CjzxKzDwK/CaX+EOe/r8Cmz5FXjiV2DgV+A1v8Id9vT5FdjyK/DEr8DAr8BrfoU77OnzK7DlV+CJX4Hxpn3Jr3CLPX1+Bbb8CjzxKzDwK/CaX+EOe/q8Cmx5FXjiVWBEkmtehTvs6fMqsOVV4IlXgYFXgZe8Cmc97b6q8Kzv8yqw5VXgiVeBgVeBHV6FUbOy31sV3Kt8HGb5FHjiU2DgU+Aln4K2hC3XiJ7Ex2GWR4EnHgUGHoW25lHgUR01Hj2ALzydm+VPaBN/QgP+hLbkTzh0jnncpGBfPZ2b5U1oE29CA96EtuRNOFseSPD0Yc3nS2iWL6FNfAkN+BLami/h1LljkgrWdnFYs3wIbeJDaMCH0JZ8CKNlbbHP7Qpf+DpHq/MVhzXgQ2hLPgRtybScCfvq6xytzlcc1v5/zt5uV5Zdx858mL45FwsTIVJSBC/L7mrAgFGnYJcv/P4v0mKmGDGYJHPus91Az73qZEiifockih/EspWUh/DkvPdV/YTaLnWYeB6CBB6CAA9Bch7Ck/O2+Xn3ITUPQTwPQQIPQQ4cI6kOu3PekUXgVZzUPATxPAQJPAQBHoKkPARo5x05BMdhqcPE8xAk8BAEeAiS8hDunC+Lt3ZAbZc6TDwPQQIPQYCHICkPAXK26OUwk5Q6TDwPQQIPQSBCsKQ8hDvn09heAn271GHieQgSeAgCPARJeQg3B2GvHH4mKXWYeB6CBB6CHNhT8zi6zZEYphsNpQ4Tz0OQwEMQ4CFIykN4VkmLYsrQw0odJp6DIIGDIAfOhakOe3K26OXQw0odJp6DIIGDIMBBkJyDYKcV3SL0WwQwbO9Sj4nnIUjgIQjEJpWUh7ByNs7JgSXQEsGXdR2Ir4NPXSbARZCCi3AznvZsynZygyWo60B8HXzqMwE+gqR8BM3pnaNp05v5RPBlWQeekyCBkyDASZCUk2A5r79G2DLWU4cvyzrwvAQJvAQBXoIUvAQ7R9lvYPowP5StHC3mbMOU6jrxOi5wFAQ4CpJzFG7laJ7sA1qj1nGeoyCBoyANLcj9y4btEG4NC1/UNnsdFzgKAhwFyTkKt63dVDPYXOs4z0+QwE8Q4CdIzk/Y7WztvhQG9Lxax3l+ggR+ggA/QQp+wt3nL2f78ZxWS81REM9RkMBRkIatl78PsEgg3TzdJnxR2+71XOAnCPATJOcn0E3soGhzrec8N0ECN0GAmyApN+Gx2dod27vWc56XIIGXIMBLkJSXoDnZeI59vNZznpMggZMgwEmQlJMw+uV2SW5PWvMRxPMRJPARBPgIkvIRnp519zQsa22z13OBiyDARZCUiwA9zGZR6GG1nvM8BAk8BAEegqQ8hGcOe5gw8EVts9dzgYMgwEGQnINw96x7NoUeVus5zz+QwD8Q4B9Izj+4z1ksZ5x7ah3n+QcS+AcCr/Uk5x+QKQh7WYR9u9Zvnn8ggX8gwD+QlH/w5GglwJmk1m2eeyCBeyDwzltS7gGMqitok5p7IJ57IIF7IMA9kJR7cJ/0jOM+R4UvSps990AC90DgVZ4U3IMdM8pObscBOdd6zHMPJHAPBLgHknIPVk7G9jHCTocvapu9HgvcAyFsteJczWwNdCGpeQfieQcSeAcCvAMpeAfGN9jR5XcJxoCdQc07EM87kMA7EHiVIynvQHPaOTrKEPKNpOYeiOceSOAeCHAPJOUeWM5j2J7kZvsc8GVdB16fBf6B4ByZ8g+A5UNYkjFgn17zDcTzDSTwDQT4BpLzDR6mT7ec918se10HXq8FzoGgHsg5B7sEmuP7r+3bJ35Z14HXbYF3IMA7kJR3YDmuv0ZeOZIS1HXg9VvgHghhj0712+bbGNdISwBf1LZ7/Ra4BwLcA0m5B0BSstrHstY2e/0WuAdCWHfpedy4bTbqCPT5Wr957oEE7oEA90By7sHdvuddAviittnrt8A9EOAeSMo9eGzeNzgDToJq7oF47oEE7oEA90BS7sGd89gnQoNhnq/1m+ceSOAeCHAPJOUe2Kh6ckZFUes3zzuQwDsQ4B1Iyjt4cjZFgT2s1m+edyCBdyDAO5CUdwA2246wwxelzZ53IIF3IMA7kJR3cM9hZGoKbq1q3oF43oEE3oEA70By3sFNC9sRAbCH1bwD8bwDCbwDAd6B5LyDZzxbCbCstc1evwXegQDvQFLewdd5u+YdiOcdSOAdCPAOJOUdfJ23a96BeN6BBN6BAO9AUt7B13m75h2I5x1I4B0I8A4k5R18nbdrroF4roEEroEwppPfi36Zt2uegXiegQSegQDPQHKewbd5u+YYiOcYSOAYCHAMJOUYfJ23a36BeH6BBH6BAL9Acn7Bt3m75haI5xZI4BYIcAsk5RZ8n7drHeZ5BRJ4BQK8Asl5BV/n7VqHeU6BBE6BAKdAck7B13m71mGeTyCBTyDAJ5CUT/B93q51mOcSSOASCGM6qQ7bce80fukr53ZCO9c6zPMIJPAIBHgEkvIInoh7FuMRV4xah3kOgQQOgQCHQFIOAdhssVzB5lqHec6ABM6AAGdAUs7AnfO87hLAF7XNXocFzoAAZ0BSzsCTo9kO47nmDIjnDEjgDAhwBqTgDJwWB+2OtAhflDZ7zoAEzoAAZ0BSzsBj846EfsKNe80ZEM8ZkMAZEOAMSMoZ0Jze7bxpL/PCnGubvQ4LnAEBzoCknIEn5+23tEoAX9Q2ex0WOAMCnAFJOQN3jlaCs4HNtQ7znAEJnAEBzoCknIEn52Y5E3xR2+x1WOAMCHAGJOUMQM7bc/2AUVXrMM8XkMAXEHitJSlfAGr7PXsyeBHUfAHxfAEJfAEBvoCkfAHLWXPcf7Gstc1ehwW+gABfQFK+AOQcYjpKzRcQzxeQwBcQ4AtIwRe47jXqXQKcSWod5vkCEvgCAnwBKfgCNnvekVOhb9c6zPMFJPAFBPgCUvAFdo78zCjwRW2z12GBLyDoSVnwBe4Vw+IaQjvXOszzBSTwBQT4Auu/c98Mu+fa95pw/t1rHda9DutBh6Gvbs4XoH3mT3b+DfeZNV9APF9AAl9AgC8gOV9gdKe33R6j5geI5wdI4AcI8AMk5wfcXG+LVwde3DU/QDw/QAI/QIAfIDk/gMw7wG5aQPXW/ADx/AAJ/AABfoDk/ICbqm3tPfCL0mbPDZDADRDgBkjKDbj7tpGlfc6lzZ4bIIEbIMANkJwbcI+q/bJsPC+OpOYGiOcGSOAGCHADJOcGPH069rCaGyCeGyCBGyDADZCcG/DYajv4K9pe6zHPDZDADRDgBkjODbD9s/V13EfXvADxvAAJvADB+7CcF/D0sGk2v/+aV9A9BvZfY56DVq25AuK5AhK4AgJcAcm5AncJrKTgz1BzBcRzBSRwBQTPHnOuwJ3juVcY2PXWXAHxXAEJXAEBroDkXIE754uizbVu81wBCVwBAa6A5FwBOm1ts9rGL2qbvW4LXAEBroDkXAFj1ZvNQKSVmisgnisggSsgA+fOPN7ZJtMMu03Gdq51m+cKSOAKCHAFJOUKaO3unkWxh9W6zXMFJHAFZGCr5X5odoplXO8LarvWbZ4rIIErIMAVkJwrYHzf22ZX1tpmr9sCV0CAKyAFV2CfwA87M7ys3fHL2nav3wJfQIAvIAVfwEbXmfTxWr95voAEvoAAX0By"} |  |  | - |  | - | -
[14 empty] | {"index":136,"total":402,"filename":"Advanced_Project.ifc","data":"TfDLl+fFZCja+ge6pnHhUO8+RcahMUiMrdzyZjIUba8Ky6RRoMlQtP2iA2OT4VLBb2r1xeRLMm4fWXt36bGm7yy8v4ZjLjKugzSJ7Ggy/PL8IvxfTL7MeF6nJy8mX2Y8r5Oo2GS4WPA+03s1+c9PR8fa0D0uVRtQoheLb2sFb3PmF5OviwVtQFMyXWtp6B7L8qNvvlby5cPzuvwQm3xdK4jXSN66ULxW8MtKzovJl8Ohr+tNLyZfDofONa8Z631Wxb4XXr5ZDJ/O+8JdbDFcKxi7vXmeOO3SRdaG+gd3jMHttQuFawW/rYG+mHw5fDjXYcf0o+S9ODSGupZfv47hYsFYLf6MxDMe36+1TTYSp0qfSr8ZfFmgfl3zjk2GCQW/rcy/mHzZPuiT425pHEj/yv6xEEhjSF+3E0YmX/YPYAvDbnK8mHx5OPFOzOsXPFoq0Jt5bDfzYpPhUsFvW44vJv/NfdEXi+HTwa3Z597tq8wIFwvG/nGv2ch7aIXWVkzqA8JFXF4tvqQUvG6DhyZrnFLwy2b9i8l/N6XgxWT4dMrYtezPe7yy3wF9WkxDor9W8iWj4DU748Xkiyb4Zoi0GzJIJoWgvAznNVwoGCmgfWzo07qRXfnNQB+XZtxTY7yFHS4U/DYlezEZfnR+mTi+mHzZeHub3b5YfFEE45qc6+KuC74Wu6YaZ5TGasHb03lbKGi9ejOXn78pYne3nz6fMZV8GYRqvFDwupzx1injhYJfFl1eTIZP531l6MXiyyLb6/JVbDJeKPhlke3F5Msimyz01U+FpcCRWXC/1vJlDfR1wfLF5Msa6Ouy6ovJl5no6+JvbDJcKPhtifrFZPh4fllIfzH5slAw7tyYW3h1jZYjnX/kBHX1/2byRRS8KZdzq9fdEsFpqhquE/ym2NatXgOd0fgDZ6pruE6Quff0GUWXYN+koevOfYL/PbL+p49Juc8s+iSQ2weXVWu4TjDylvr0ivqc7FpzsjYSSObMdOTflU+XR+OrxAPVzWDyJZXtmtyj0Tm/Gn28F73GI1O7/OFxN1Kfkl8jRRZzdGu4UPDb+tU5tdtnfrjNUcOVgt+2Rtep3TGb7cMInNGq4UrBWF7sH5l6j5u+FvHle2p33iC9dgj338hgMlxlu35y74KlfHpTrUu+2kigLwP4OlriU8a25DxL3jsOmHzZuR77t5/Pte7m7c+pjSuku3jtT+tzXXPVbR6oBH5nXesEinY10EKDcjXgQOsXHudaB3BoV+OFANpVBTbY39ZfAM98uZ4n6QtqAJ75Dj33j63yXJ6e8VHzW8ynBtDfOI6ZdczVxIzDSvViPq2cbcw1jrnqmKuJuULM1Yv5+pLdBjRJYocSccxVx9xMzHDFVO/Vbmtn1doXbFvXFsfcdMzNxAwH3mvzn3P6gzXQnuOYm4q5fUzMsP/cPn7MSbd2xRJhzOMOcuX5GXODnPv28Z8zL8/N8RzGPE45oOf0jLmXPXaSG3NtynOGdIc+6Ieek445mZghIawl9znX7fFbg4Se45iTjvkyMSeI+fJizjn/UbGj5yuO+dIxXyZm2LNrlxdzzt9YpQbacxzzpWPOJuYLYs7uGJaklfOqAXjOccxZx5xNzBlizm8xb8+qrnHMWcd8m5jhK9lu9zlfTXm+MkOJOOZbx3ybmOEcQLvd91k8puJ4jmO+dczFxAyJXV05ep4zPzwXKBHHXHTMxcRcIObix8ziUWoAJeKYi46ZTMxAcO/CzI1ZPErsWCKOmXTMZGImiNnVYZe8x7sG6DmOWeuwZnRYAx3WXB12Xeut2iMJlohj1jqsGR3WQIc1V4dtj1IDOIDQYh3WtA5rRoc10GHN12HbY7aeYx3WtA5rRoc10GHN12HXer6X9PEMJeKYtQ5rRoc1/M67OuzKj+cMs6wW67CmdVgzOqyBDmuuDrtk9JQaKM9xzEqHdRlmYj46rP/p67gtY1nGElHMw5j2/Ih5lAU77rdqe16/J7Ny3AUWe9YxP3XYKHvsuDrsupcyWD0MvpK9RBxz0jE/ddgoC3bc53xn5VnFHOqwYUx5fuqwUfbYcXXY8VykBlAijvnSMT912CgLdvznvN7nVYPrJJ/3EnHMl475qcNG2WPH1WH50jErz6EOG8a0ZxNzhph9HXbtWNcvtHaow4Yx5fmpw0bZYyfQYeJZehiWiGO+dcxPHdbgPGb/9/eY11zjgr4d6rBhTHl+6rD2wQhcHZblW7U8XwU8hzpsGNOeTcwFYnZ1WE47VsdzHHPRMT912Ch77Pg6rIjHNYbhCBDqsGFMezYxE8Ts67CSlWcVc6jDhjHl+anDRtljx9dh26PUAN7nUIcNY9qziZkhZleHyXM+rQ3vc6jDhjHl+anDRtljx9VhWXT2jh1LxDFXHfNTh42yYMePeXtcMUNrhzpsGFOenzpslD12fB22PWbrOdRhw5j2bGJuELOvw5bni5LUAErEMWsdlp46bJT96/yp/5yz8nxRhhJhzEnrsGR0WAIdlnwdltIfXQP0HMactA5LRocl0GHJ12G0tEhyYo51WNI6LBkdlkCHJVeHZVmB254LlIhj1josGR2WYBROvg6jNYJ8mvUc67CkdVgyOiyBDku+DtsepQYMJeKYtQ5LRocl0GHJXw/bHov1HOuwpHVYMjosgQ5Lvg6TNf1Vg4uwrnHMWoclo8MS6LDk67C1f3FqgCXimLUOS0aHJdBhyddhsnNC63lX6GGxDktahyWjw+CgY/9T9znXoj1zghJxzFqHJaPDEuiw5K+HiWde73OFkSTWYUnrsGR0WIKvbfJ1mHjkbD3HOixpHZaMDkugw5Kvw7ZHJ+ZYhyWtw5LRYQl7qq/DuGnPDJ5jHZa0DktGhyXQYclfD5OYWZ431jWOWeuwZHRYQjv+etjyeMu+lSoRx6x1WDI6LIEOS/562I6VpQZQIo5Z67BkdBjse/U/fXuf89qTzR94zrEOS1qHJaPD4CLucRmMO4ZJn16xo36KdVjSOuwyOiyBncvVYVdr2vO5rmMcKI48X1qHXUaHXaDDLn9fsq5vVGMT8xXrsEvrsMvosAt02OXrMPEse3QNYo512KV12GV02AU67PLXw+RtarsGUCKOWeuwy+gwWKHvf+o/Z/FcbMyxDru0DruMDrtAh12uDjse1947jNtXrMMurcMuo8Mu0GGXr8Mkm6OuUbSB51iHXVqHXUaHXaDDLleHiccsq8zKcxyz1mGX0WG4Wn25OizJGJbZtnaswy6twy6jw+Ae3f7vfszS2iw1gBJxzFqHXUaH4Yre5a+H5WfM4DnWYZfWYZfRYRfosMtfD8vPmKG1Yx12aR12GR2Gqx6Xq8NOnoHJJ+kl4pi1DruMDrtAh11+fljVb1Ve+xkZ1vavWI9dWo9dRo/hzOFy9Vi+n7EXKBHHrvXYZfTYBXrs8tfFtudiY4712KX12GX0GKqry9Vjkk+yexqs7V+xHru0HruMHrtAj13+upjspNzFvl2xHru0HruMHlPfviBPTL4YTdUgw+7CFeuyS+uyy+iyC3TZ5euyW/ICJWMtOTWI20Drs2z0GWqeHOSNFVUDqVGGVegc67SsdVo2Oi2DTsv+etlaec9F2sDkCw4CcVwD3QZGr2XQa9nVa+J5nD/6esYScexar2Wj1zLoteyvm+2YpR8wlIhj1notG72GuxfZzyOTNWFZmSXdBrlATWL9lrV+y0a/ZdBv2V9HE48k2ZrQ82L9lrV+y0a/4S50dvXbvVZ27rWmdK9Mxryexo01ifVc1nouGz2XQc9lV8/t3AzZTcYeGOu5rPVcNnoug57Lrp6719t3r554r6dxF71bIfsl9y2/aDluG637stF9GXRf9vPRPkm9Ixl2qXKs+7LWfdnovowR+LpP1tN3D81QIo5Z675sdF8G3Zf99TdZIdjvBHqOY9a6Lxvdl0H3ZX/9TdZZJXaCcSDWfVnrvmx0Xwbdl13dl2VVW1Y7P/CcY72Xtd7LRu9l0HvZ13uymv1xWjvWe1nrvWz0Xga9l/31N1nBX6uemaUm0Oqx7sta92Wj+zLovuzvh67WlhqoVo91X9a6Lxvdl0H3ZV/3yWrnzt6GVo91X9a6Lxvdl0H3ZVf3ZZlZiMqG9dYc672s9V42ei+D3su+3lvPN/OuAZSIY9Y67zY6D78Xt78OJ7tV8o0Dz3es726t726j727Qd7e/Dif7oVX6ONY1jPnWuu42uu4GXXf7uo51lj72sDvWdbfWdbfRdTfoutvXddLD1nMmyZxiaPVY391a391G392g725f30kP2z0uQYk4dq3nbqPnbtBzt6/ndqs7Mcd67tZ67jZ67gY9d/v5afI+y3oc9pBYv91av91Gv92g325/X5RZjSg4ft+xfru1fruNfrtBv92ufjvZ+vvtklZfNYKaxDrt1jrtNjrtBp12+/uk+0SK5zluA63TbqPTUGne/j6p5LXIujvkt9yxTru1TruNTrtBp93v5wYkZthLumOddmuddhuddoNOu/31OVlv362NJeKYtU67jU67Qafdvk6Ts22Sw5XYxh7rtVvrtdvotRv02v1+fkCyBWXtAlYM7li33Vq33Ua33aDbbl+3rRrkJs9d5m/whYl126112210243fSF+3NT1XhfMEvUQcu9Ztt9FtN+i229dtTc9VVcyxbru1bruNbruxB/u6bc/LJWYYYWLddmvddhvddoNuu13dJh5PDdBzHLPWbcXotht0W/F121oZkBrckmF1Yckw9qL1WzH6rYB+K65+u/cJtO1ZagIlwzYoWscVo+MKfKWLq+PufR5M1+SGbMIS67mi9Vwxeg4AAK24eu5+ng9bNbnhS1NiPVe0nitGzxXQc8XfX826BjdkzJZYzxWt54rRc3BXayuunpPYbxnvM3qOY9Z6rhg9V7AH++tz26PjOdZzReu5YvRcAT1XXD137xNq0texrnHMWs8Vo+fgdoT+p27MO+v/UQPI/i+xjitaxxWj4wrouOLquFtGHHnP5W2Tt+/WNZQaA8ynlVjvFa33itF7BfRecfXeqck+CQMl4rbReq8YvVdA7xVX793y/i/Pd0bPccxa7xWj9wroveLqvVve/30ORWoArR7rvqJ1XzG6r4DuK35+nJwGkRXgLL9Y97gNtO4rRvcV0H3F1X23vBNyVuNutgax7ita9xWj+wrovuLqPqnBLe/APjkBb2es+4rWfcXoPoCu9z/1c/mL8iw1uWG/tsT6r2j9V4z+K6D/iqv/bul50hP3TgHWIG4DrQOL0YEFdGB5Pc8gexT3OWUAJeM20HqwGD1YQA8WXw9KDc7pAqcGcRtoXUhGFxbQheTrQtkZWJ6lJjfsUVCsC0nrQjK6EFibjXxduD0/c8ILlAzbgLQuJKMLCXQh+brwZKGrGtxYg1gXktaFZHQhgS4kXxeuVfN7rbbdktUq6/iyqk7SX6SGGFvcRlo3ktGNBLqEXN0oNbklx3hn/CYoGbeR1o9k9COBfiRfPy7P91qFvWWVZufhQo+N9SRpPUlGTxLoSfL15FoXvJv8Qj+J9SRpPUlGTxLoSfL15Ip5t4HkLDLWII5d60oyupLgC0i+rtyxF6kJlIhj13qSjJ4k0JPk79+yft6q1WOdSFonktGJwOnrf/qWVy855rjCQLFOJK0TyehEAp1Ivk6UHrZanaq0OsQe60XSepGMXiTQi+Trxdp0X0fPsU4krRPJ6EQCnUjBOQp+vGXQ02J9SFofktGHhGOmrw/r43lDVizFupC0LiSjCwl0Ifm6UN4qWRtlhhJxzFoPktGDcG3kuKTQa+19ZkRGWfmVGkFNYl1IWheS0YUEupB8Xbgz/fc5GigRt4HWg2T0IOFb6+rB4znZmGMdSFoHktGBBDqQ/POt+1SD9PVvTcrK3ygrm6Ksff6ydl9xzYtinUhaJ7LRiQQ6kX2duM8iSA1WDWH1jmOdyFonstGJDDqRg3MY8nRYPK/fDCXDNmCtE9noRIa2ZFcnFlk/lD2T2mwNYp3IWiey0YkMOpGD++KyqoHUqCRpk1Wjte5UZL84Y2xxG2mdyEYnMuhEdnViWas9Za32lLXGUmTFY5+yWP/7Wv0vsAbPsY5krSPZ6EgGHcmujjw1kTMPBUrEbaN1IxvdyKAb2dWNZZ+yYGkTKBHHrHUjG93IoBvZ1Y1FVj5lhNs1gFaPdSNr3chGNzL2r+DcbVI1kBoVyEznWD+y1o9s9CODfmRXPxbJD98ngJNTg7gNtI5koyMZdCS7OlJqUCQ/fJ+7hvEj1pOs9SQbPcmgJ9k/ByJZO/IdueUX+kGsJ1nrSTZ6kkFPsqsni+SFy04Y7IBxrCdZ60k2epJBT7KrJ49ntjHHepK1nmSjJxn0JPt5gZJTId9MWOXjWE+y1pNs9CRcDd3Y1ZMScym7BlAijlnrSTZ6kkFPsqsni+TC77tCko091pGsdSQbHcmgI9nVkVKDIlm3kuGAX+tYT7LWk2z0JIOeZH+fWTIa5Ctd5Hf1wLX6V9aaW1krYQXWnTjWnax1JxvdyaA72dWdRXJlJQNCdISqQdxGWldWoysZdGV1daXUoEj+qGREJCwZtkHVurIaXVlBV9bgvrusPEtNCqxs1VhXVq0rq9GVFd656ucX7rvfsnhevxlKxm2gdWU1urKCrqyuriyS5bVv3itQIo5d68Vq9GLFp+jrxe252JhjHVi1DqxGB1bQgTW4/66pmKUmheW/Vz9Ys8GytDfwtVuN9WLVerEavVhBL1ZfL+7TmnIvYrM1iHVj1bqxGt1YQTdWXzfKibacVU0K5OTVWDdWrRur0Y0VdGP1deM+Myutv9oAVoNqrBur1o3V6MYKurH6ulHmWpIdluWpwFOIdWPVurEa3VhBN1ZfN156ziQ1KLAuVWPdWLVurEY3VtCNNTg/LPNKOd0HrR/rxar1YjV6sYJerH5+4q1nsgVmazXWi1XrxWr0YgW96PMlypqpFsmQg+yAmC/RNF+iGb5EA75E8/kS4vmcaIXWjvWi5ks0w5dowJdoPl/inFyV1ob3PNaLmi/RDF+iAV+i+XwJaeUip7NgHzrmSzTNl2iGL9GAL9F8voTELJ5JzkzB/CDmTDTNmWiGM9GAM9F8zoR4JJmZykwFaxDrQM2baIY30YA30XzexD47ezdVE4JTPDF3omnuRDPciQbcieZzJ2jNSElmqPssbYKSYRto/kQz/IkG/Inm8yeOZ/mVU3sZSoZtoDkUzXAoGnAoms+hOGflpPXlbC1DybgNtA40PIoGPIrm8yjEI8mMlbDOcexaBxoeRQMeRfN5FCdWJ+ZYB2oeRTM8igY8ihbwKDgpzwQr2jGPomkeRTM8igY8iubzKKSVac2RSWZhMPOIuRRNcyma4VI04FI0n0tBa84j54oIdH/MpWiaS9EMl6IBl6L5XApamoaW+ibIgI25FE1zKZrhUjTgUjSfSyGtTGnXAErEMWsdZ7gUDbgUzedSnLNUyXqO9ZvmUjTDpWjApWg+l+I85xVzQs9xzFq/GS5FAy5F87kU5+SatDaMprF+01yKZrgUDbgUzedSnFidmGP9prkUzXApWsMx0dVvx6P0NIg51m+aS9EMl6IBl6L5XAp5znJqS7V2rN80l6IZLkUDLkXzuRTS2ud5Q2vH+k1zKZrhUjTgUjSfS7FbWdYucPSMdZvmUjTDpWjApWg+l0LOiZ3WlvF8jWn4BYj1m+ZUNMOpaMCpaD6ngmSFoDbHc9wGqNv4YzgV7XAqxp++tQHJakrFEkHM05j2rGOeZcHO2znBHfteERglgpinMeX5odNm2WPH12lrRUA8087eHiXimJOOOZmYE8Ts67O1CkKyKrJPrEHskU6bRlUNLhN7gtj988BNe5aa0N5JHCXjNrh0G1ymDS5oA1+vte1x/cqZKqxB3AaXboNs2uCCNvB1m5ylkJkiviWRXpvGtGcTe4bYfb22Y3VijvTaNKY83ybmDBH4eX9ybmzNkkgy2BP0vEi3TaO6Bib2G2L3ddvySJKpnrJTg7gNbt0GxbTBDW3g6jfxTJK5nuQX3v9Ix02jugamDQq0ga/j5MzEPktVpEZQMm6DotuATBsUaAM/HzA1VQO6oQdGem4a055N7ASx+3ruFo/Ps1SjRBwz6ZjZxExgx9dz4vFK1nOk56Yx7dnEzBCzr+fkViVRFthHIz03jSnP1cTMYMfVc/fSc+dU1qpBgbct0nXTqK6Bib1C7H4eoHxd5YSKnFjEr22k76ZRVYNm2gCVir8uJ3dY7RNKRWoEJeM2aLoNmmmDBm3gnw+RL41864rUAN66SN9No1iDJ/9ilv3r/KnfBuJ51UTG/YwlwzZIWuc9ORizLNhx3wE5kbJPKEm/wBqEbZC03nvyMGbZY8c/HyLj/qoJyYkVGHVDLsY0qmtg2gB0n8/FOB7lKbBTg7gNtO578jFm2WPHP/+xz0itHkhyvxuWjNtA674nJ2OWBTt+G4hnOfuSnBrEbaB135OXMcseO/65j8cZKakJEZaM20Drvyc3Y5YFO34brDmPnBeSp0AZSsZtoHXgk58xyx47vg40J5CK1AhKxm2gdeCTozHLgh3/HJB4lLNSq0bMUDJuA60DnzyNWfbY8XWgrHFITfaJJDnFhRbittB68MnXmGXBjtsfdpZ+UjUhhnEh1oNJ68EnZ2OWPXZcPUgrW0JqojzHejBpPfjkbMyyYOct9lMDeP6xHkxaDz45G7PssROcD8mPVscSccxaDz45G7Ms2PFjlnNAK2bsabEeTFoPPjkbs+yx46/vbY/f3ypjoCoZx6714JO3McuCHT92OfuU7fOOdWDSOvDJ25hljx1fB+5Td9k+71j/Ja3/nryNWRbsvD1vOYVDFd6uWPclrfuevI1Z9q/zp37M+sQZtnbI25jGtOdnzBfoPZ+3cTd+xCyj7XrfYa0r5G9M46omRvddoPt8/gZJ5s9HzgNhibgNtN578jdmWbDjPvd98kxOokHrxzrv0jrvyd+YZY8dPx9P8nQlV1nWe1qGknHsWuc9ORyzLNhx825kV1RWGCUPJ2EN4jbQOu/J45hljx1/fW97lFM1Tg1inXdpnffkcsyyYMc/ryGx73Ma67dAybgNtM578jlm2WPH3599ntOQGSj2xFjnXVrnPTkdsyzY8XPXk6qB1Ig/8P7HOu/SOu/J65hljx1X5/F671lO3+3zG1CDWN9dWt89uR2zLNjx2oDNOY0sNYKScRtofffkd8yyx05wXqP8wZqwOT0xSsZtoHXek+Mxy4Idvw14eZYTQ1jnOHat8578jln22HF13om12ZhjnXdpnffkd8yyYMc/u5CUZ4Y17pDfMY0pz0bnXaDWfH6HtDKnZFs71neX1ndPfscsC3bc57w8cpJzG/ILscc679I678nxmGWPHVfnnXMZRdWAcdyP9d6l9d6T4zHLgh3/PIZ4XDXYpyNg3I9136V135PjMcv+df7Uff77BEhTNeBUoGTYBlnrvyfHY5YFO/5ZBH0OQ2rECesetkHWuu/J8Zhljx3/nC9LT1w1kJMhnKFk3AZa/z15HrMs2HHfhe3xeTYBaxC3gdaBT67HLHvs+DpwqW6WvGs5dQ0zkJDnMY3qGpg2AB3o8zxYToRIxv+qAV/QBrEOzFoHPrkes+yx45+/EP1fpR+sb+DFUDJuA60DnzyPWRbs+G0gMcupB8nLTlAybgOtA59cj1n22HF1YJHTMfI0mvQLLBm3gdaBT27HLAt23DaQjAMhzBT0HMeu9d+T2zHLHju+/hPPa++jgvIMuR3TmPZsYgbd53M7xDPL2QNCz3HMWu89uR2z7LHj6r0qmleec4P3PdZ5Weu8J7djlgU7fsy7le1zjnVe1jrvye2YZY8dX+etWMVzBXUdcjumMe3ZxAw6z+d2HM/yC60d67ysdd6T1zHLHjuuzquiqpvjOdZ5Weu8J69jlgU7XszH8+5pUCKOWeu7J69jlj12XH0nHncNVIk4Zq3rnryOWRbsvMVck+c5jlnruSevY5b96/zp23OuS9fXxFAijPnWOu7J65hlwY4bc3p6LlAijPnW+u3J65hljx1Xv9U1g6hLRVdVIo5Z67Ynr2OWBTt+zPkRc4ISccxarz05HbPssePqtROznJcDz7FOu7VOe3I6Zlmw4+r1fdeMxJyhRByz1mdPTscse+z4+kxUkdQgQ8yxLru1LntyOmZZsOOvzyXtGZ9PrMdurceenI5Z9thx9ViVlaDseI512K112JPLMcuCHfdbtTzuGijPccxahz25HLPssePqMPEoNWDIAAq5HNOY9mxiBh3mcznqWm87NUDPccxahz25HLPssePqMJbzzmvdrd7gOdZht9ZhTy7HLAt23mI+nuGtinXYrXXYbXTYDTrM53Fsj2vFV3mOdditddiTwzHLgp23+1fFcwE1FPI3pjHl2egwzATw+RvnxtdkPcc67NY67MnfmGXBjjuGCbWSs+M5jlnrsCd/Y5Y9dvx1tuWZ710DKBHHrHXYk78xy4Kdt5h5ZfIxvlWxDru1DnvyN2bZv86fuu/z/fAM+fIhd2Ma056fMRfQYT53g9fODa/9FIw55G1MY8qz0WEFVJXP2+D1Nm3PGHOsw4rWYU/OxiwLdtwxbMUs7/MN2UkhX2MaU56NDsNvns/XEM/yPjNk6IV8jWlMezYxgw7z+Ro1y+jJjuc4Zq3DnnyNWfbYcXUY3+J5fS1hlzLka0xj2rOJGXSYz9cQz3zL84a+HeuwonXYk68xyx47vg7L+eEZelisw4rWYU+uxiwLdvyYm3iUGkCJOGatw568jFn22PHXw8Tz1WzMsQ4rWoc9eRmzLNhxY177YeKZVV3jmLUOe/IyZtljx18PE4+Hbwwl4pi1DntyMmZZsOO+z8JN2ftgWNc4Zq3DnnyMWfbY8fPbxKPcS4aeYx1WtA57cjFmWbDj8xCS8qxaO9ZhReuwJw9jlj12fB22e5jsf0HfjnVY0TrsycGYZcGO/5wls3q9z5DbH/IvpjHl2eiwAjrM519weXqGcTvWYUXrsCf3YpYFO/77XB6e4TnHOqxoHfbkXcyyf50/fYu5rv2MCns5IediGtOenzET6DCfcyGeWXYTrgIlwphJ67An32KWPXb89bC1hycxc8ESccxahz25FrMs2PFjXqMnyduVoUQcs9ZhT17FLHvs+DpsxXw8JygRx6x12JNTMcuCHTfm5ZEpO57jmLUOe3IpZtljx9Vh9dKecdQLuRTTmPZsYgYd5nMpxKOwvrTnOGatw548iln22PH3JyX7X76W+D7HOoy0DnvyKGZZsOPfjSd79J7nOGatw548iln22PF1GMnOeLKeYx1GWoc9eRSzLNh5i1lqwISe45i1DntyKGbZY8dfD5M8lJ2HAG9VrMNI67Anh2KWBTtu35a8g10DGLdjHUZahz05FLPssePvS9aiPasSccxahz05FLMs2PFjFs9r/K4wbsc6jLQOe3IoZtljx88/k7yT7Rmec6zDSOswMjqMQIf53AmWGfvu41jXOGatw57ciVn22PF1mHiUGmArxTqMtA57cidmWbDzFvMt62LKcxyz1mFPnsQs+9f5Uzfm7blIDaBEGDNrHfbkSMyyYMdn8JZHa6PnMGbWOuzJj5hljx3/HOn2LK1doEQcs9ZhT27ELAt2/OfcHs+ZoUQcs9ZhTx7ELHvsuDpsj55VdgexRByz1mFPzsMsC3b8vVh9fy/DCZaQ8zCNKc9Gh2Hmk8952Dvfkj9YsUQcs9ZhT87DLAt2/L1YoWoks/8c8h2mMeXZ6DAGHebzHcTz3n+GvKGQ6zCNac8mZtBhAdeh7V3+5Rmec6zDWOuwJ89hlj12/H3J7bHY1o51GGsd9uQ4zLJgx495xyqxQ4k4Zq3DnvyGWfbYCfLDJEtr39cKJeKYtQ578htmWbDzFvPJaIEeFusw1jrsyW+YZY+d4D5e8Sx3lMJzjnUYax325DfMsmDHv49zZ6Qtz/CtinUYax325DfMssdOkB8mHpNt7ViHsdZhT27DLAt2/JillZ+5cdDqsR5jrcee3IZZ9tgJ7uOVEUUy1ORWXBhZYl3GWpc9uQyzLNjx7+Nd9zvJ7Rs7Zw7rHreB1mdPLsMs+9f5U/8u2nWzmKxmwKga8himMe35GXsFfRbwGOQMRJPYsa5hzFXrsyeHYZY9dvzznnL2RW4Yg/E85C9MY9qziRn0mc9f2B53DaC1Y31WtT578hdm2WPHv3dXTt1IHqjcsgRZXCGHYRrVNTCxg07zOQwn1znbVo91WtU67clXmGWPneD+3RVzkXsbC5SIY9Y67clVmGXBjp9js74oRWqAnuOYtU578hRm2WPHP9cpOZFFWht6WqzTqtZpT47CLAt23JglVrljXHmOY9Y67clPmGWPnSB/7JHrvJ839PFYr1Wt1578hFkW7Pixl8fzhj4e67Wq9dqTnzDLHjv+upnMu4q8ZeA51mtV67UnP2GWBTv+e51Ua2Oed8hPmMaUZ6PXKug1n59w+rjUADzHeq1qvfbkJ8yyYOf9vS5m5hfyE6Yx5dnotQp6zecnnB6W7HOO9VrVeu3JT5hlwc7b+qjcACu330pbqDaIdVvVuu3JUZhlj51gHW2v0EqNoETcBlqvPfkJsyzYebt/V9oA14hDbsI0hp6f3IRZ9q/zp/5dpEnFjCu1IS9hGtOenzE30GkBL2F7lptg0XMYc9M67clJmGWPHV+nSe6N3L8D+UYhH2Ea055NzKDTfD7C8Zhta8c6rWmd9uQjzLLHjq/T9m23RcWOM7mQkzCN6hqY2EGn+ZwEqYGsJeIaYshJmMaUZ6PTGrylASdhe943/kKJOGat0558hFkW7LzdtyvrpjfMQUM+wjSmPBud1jCC4L5deauc1o51WtM67clHmGXBjr8+zmplHlepQz7CNKY8G53WQKf5fATxzHKvGuR/h3yEaUx7NjGDPgv4CPfeC1ie4b2O9VnT+uzJR5hljx1fn22PybZ2rM+a1mdPPsIsC3b8PQHZC0g25lifNa3PnnyEWfbYCe7Tlee7awAl4pi1PnvyEWZZsOPnKSyNsu8ShtaO9VnT+uzJR5hljx1/X5P3rqL1HOuzpvXZk48wy4Idv2/rmHHPPuQjTGPKs9FjDfSYz0fYe7hyTyZkqoY8hGlMezYxgx7zeQiSnyCxq5hjPaZ5COnJQ5hl/zp/6t+Xmx6eC5SIYk6ah5AMDyEBDyH5PASJ+ZZ8QuGfnLlmirkISXMRkuEiJOAiJJ+LIFlA58ZmyU/BknEbJN0GT32WgI+QfD6C1EBysM59yRlKxm2QdBs8dVoCPkLy+QjnvuSiagI7KynmIyTNR0iGj5CAj5B8PsLOuds1YSgRx37p2J86LX3wKfo6bXmmnekInkOdljQXIRkuQgIuQvK5CLxvJTZ3Q6eYi5A0FyEZLkICLkLyuQgnq7NYz6FOS5qHkAwPIQEPIQU8hN2zJKsT+nio05LmICTDQUjAQUgBB2F7lnuxwXOo05LmHyTDP0jAP0gB/0DyDCUbX9U1jrnomJ86LX3wqfncAxnXZYTB1g51WtLcg2S4Bwm4ByngHuybtuVXagDjeqjXkuYfJMM/SMA/SD7/QM59nPuui61BqNuS5iAkw0FIwEFIAQeBdA2kRnD2JcU8hKR5CMnwEBLwEJLPQ5CTRnLzttRI1SDUcUnzEJLhISTgISSfhyA1uPfd3/sucCgZt0HVbfDUcwl4CMnnIchJ0XNuE7RNqOeS5iAkw0FIwEFIPgfh3PVtzm2mmH+QNP8gGf5BAv5BCvgHO2ZZS5Z7kAuUDGPX/INk+AcJ+AfJ5x/sk6PCPTj5ainmHiTNPUiGe5CAe5B87oHcb173He8MJeKYtY4zvIMEvIPk8w7k5Kh45rMSkGLOQdKcg2Q4Bwk4B8nnHFQ5nSHjfIaYY92m+QbJ8A0S8A2SzzcQj+eGbehhsW7TXINkuAYJuAbJ5xrsVt6tDj0s1m2aZ5AMzyABzyD5PAOJ+bQ6POdYt2mOQTIcgwQcg+RzDORU9HnOWCKOWes2wy9IwC9IPr/gvE1FjSiqj8f6TfMLkuEXJOAXJJ9fIK0tN2qrVo/1m+YVJMMrSMArSD6v4Nwaz7anxfpNcwqS4RQk4BQkn1Mg5+53zDJLwvc71nGaV5AMryABryAFvAJZN5eaNGj1WL9pXkEyvIIEvILk8wrOPeZy0wN4jnWb5hUkwytIwCtIPq9APEoNOMOYFus1zStIhleQgFeQAl6B3JQoeYqymp2hx8V6TfMKkuEVJOAVpIBXIDfoyV5RhlaPdZrmFSTDK0jAK0gBr2B7lpvUodVjnaZ5BcnwChLwClLAK9g3p6/81ARvV6zTNK8gGV5BAl5B8nkF4lFqgK0d8wqS5hUkwytIwCtIPq+gPO9Fgh4W8wmS5hMkwydIwCdIEZ9AboXftxRBiThmrc8MnyABnyD5fAK5I0juZIdb4VPMJ0iaT5AMnyABnyD5fAJp5VMD8BzrM80lSIZLkIBLkHwugdwGLzGfu6Ggp8U6TXMJkuESJOASJJ9LUGUOInuCcpoDxvOYS5A0lyAZLkECLkHyuQT7bpF9G7zc+IF1j9tA6zbDJUgX2vF1274jSu7d2PfSQ8m4DbR+M1yCBFyC5HMJzj0r0vpY5zh2rdsMjyABjyD5PIITa7Mxx7pNcwiS4RAk4BCkgEMgWaKS/Y9jXKzbNH8gGf5AAv5A8vkD504ZuZMb+nqs1zR3IBnuQALuQPK5A+Jx3wCSslODOHat2wx/IAF/IPn8gbI0qtxLLzWoOFLE+k1zCJLhECTgEKSAQ7BPz+9b4L81At0e8wiS5hEkwyNIwCNIPo9g31mQdA3g3oYUcwmS5hIkwyVIwCVIEZdA30N/bo6ANoj1nOYSJMMlSMAlSD6XQGpw7nGAHhjrOc0jSIZHkIBHkHwewfG83j7lOY5Z6znDIUjAIUgBh2DfgC83CjCUCGPW/IFk+AMJ+AMp4g/oW/+xtWPuQNLcgWS4Awm4AyngDlQ5tScnFzOUiGPWes7wBhLwBlLEG5Bb/uUUH9Y1jlnrOcMZSBntBPfWyg33crc+xBzrOc0XSIYvkIAvkHy+gLTyqQF6jmPWOs5wBRJwBZLPFTi3+hdVA7ghOcVcgaS5AslwBRJwBZLPFZDbgoUrIDXSNYjbQOs4wxVIwBVIPldAanDu8N2kAygZt4HWcYYrkIArkIQr8B9//79//Of/+6+///f//s9//fc//va3+/r5kxL93FyvO9/UR7v2h+6fxulOjcYJXKxMezHCPz2AcfvqWIBNsZGSXozUn3F5ZiojxbLkYaTrar5zK63cOHqU/GqlK4vWNQPxSAXpVqh2tXNfOfXWvcBKia1c7WcooHGPWS50/ym5W737F6Xc9MGVK+EXRFbaV9nW9mnpT7l+eg9rLXX1TpnRykvjDit1LAHMOVS30WNLNPP+cBUm00vbPmx8flobybuZbgKmSrfx0rL58zNW2++xndinyMMK9XqUNq47uDOBlZeW7Vbu0huhtyqNXOhuJTca13X11obcuSSUBNfK/fm5+gNNnOs4nnLzT+9qd776FKE3LVblpWG7EaZ2jZQ+Gsmy3Qp9Sn8ZiD4fqscIv7RsN/Jt2XFlUSt/buptO6Dan145HE74pWmfRq7yQzRbpPbhtMKnn1+atlvJw0r/YveGHEY+3UgXI7n3P3jI/NKwuf3wsMG9Gbs2fKvJS8uilfqpf+70M25pSOPe3huXaXp9X62U1kVa6t/lPjAMK32EyX1mUXs8GV7l+tZt28816kK9c3/67LlbKaMuXXunAheyJIE5+Fb45x5WCvWxqM/JxErvPKl9UCLVt9bln3H0oA/y41OThpVe9zSGuF5HQitvrUvf3tI/F1cq92rdPDKfxocF2qW9tS7/5DuVq/cPGom8vZ16g1w30V37c4Lu395al75Pugy2Zh/5R2uPuvT3qinF194al37GpQu1P9bueBrpw8M1gHOVlJJpb41bvlUhvj7jgMIYI0aRu8d0XQRdt7017rbSu28l6br3mND2ce4MLffnrXH7V/XqRXq/rYNu0P/H+zMusa19kKsZrbw17rPTXT88R5Ly+aSKRt4at/2Mc6l3Lv0zNMbK0Mj7sNAN9G/H4IteM57+FRvd+B6AygusvA8LZQ4L/fv16eHk+YB4wFYRQ9xfq19GBTRCP/2b0j/JfaC5gNLWjbwPCuNr8SmllyrTSp/rU+md7uoyBoz80rJl3Fg70tnyHPrrSAuuvceNu1fByrtI6Hqyv3bjBp0+JPQXKPeaUO1fJribIQk/wzdSf7hdNNY4+6RkWim1j9uFSxrQmmPlelMJVZqWyzho07/N16ePU/0x07jGFqy8tK2xkn5aLmNE6B/rC428CbDaH1CvOHVx3cf7IXt6TxuA9/6/9NcIrLy1bReDXZ/05izX56JhZWiC3mXryG3MYOWtcdNPvbvuGwNU7rq9tJ/+9ejatMtBnMnf+a1t08/VqA8aI80v0TDSdeFo3cQX7lD1sF+sLKHQVUr/jv4p/bH3qvU2ueB6iCRIj99N0PWnlJ97pOH1YbP/H0gsEvRHZKUPB13H9gbpw9wQyK3/09+gkYUC32bBgfhiXXRCvXKfKw8r/bveh4JuBxZ3e4Svgr9XovfRLkVHZt54xv2h83337yFuX933+7QhjcydPvG4x7x0yOzP56ojeXvsDIKVl7bt86BvPHcfsFuevXZ0rntcSYJpfvdvU7Jvqwwkj9jofbYrO0iK+f+svX3PJbWVt/tVkBgJHonnnu33tUY6fwDpBGaal6E7b6ORok5oCBMCDN0kYT79sfe+XHu5yq4b5hyiaLe7q1b9vKrK18+uKjue9shyu0Zzu4cuJV3vn+yKlNxmLa3/cI9y2iVLt2ulGo3avFw7MK1fF7xv7sl0HOJpl2wfJd5qVHss0tpuE+Ust/khl5rYetW2N+HbdXupV01rOPViL/6zHlk9QTczWI2o901JuCpp9quoaVXOOmStt1sbggoMrfhO12u/trytn1dbbDPYFM+6ZK27e71u62XmKtxblCCxnZ921szVf9Ypc43u7Vpx8WpXao0qkHJoVilcirluzzplNUq9ImuPqt6F7f3aGkXby7pt8fl4sW32WafMQebWRl/anXhrWXKbk7sGN9k965UNUSrKUs12bROaN61w8+b6P+uW3WpU+9rVPrbnRuma7dby1mvFfGRWozyW3XpaW7+5Ni4tShuRqE1l8BexV+5Zv+x6pqsbbMsP+is+Lm39tnrt1hM+VOj8yq3XrGqpp7k69iZFqxOrNqGmRpONcn7p3q9/dwVIujZQ9TTX5sZcdGcds34r5tZJDKWdoqahrWhQTa4zaTnrmB2aBbk1C1VGdWHWhJ11zGyU9g19ze5t6Kn2HKrzMUHOW9xra1lvnYsL8Z1ce9K+3VDtq/t6o5so521uTVs9zble87XlrlGuFcrl0v7WtJZn/bIbQ+rJqbdje7fiJMo5z1Io6fpy4C1I62a2QX1pq1ObIOcXbnNs9YzWLlW6pqUN79YWSu20kS6edcvqPVQ55qqnrTdedQo1SBumufb0LtWzmiiPOIXqRWN77TvUINVN1ZY/pzY/SjDjcemsV+ba7Rt8mxunttauRWmv0mtFRkqm9U9nnbLW+uc2jlav9no3vpNvTKy3kMtqP/VKZ72yw7Vio1xM65/OumWH6zZUF1PaIHJ1LbVvY6Kc5XZ3I9YoNzdbQ9hFeptX/ek3Yobyrl7E9S+DiXKW3VajNv4WNLcHuG0Q2NeT5rJLw4PftOiZ1XZIDsPaYTkinRZds3uYu5wKgBM58wT3ODbFLp0kZ9E/m8RpIyXrU7Xoodl69QvHy8mFs+ikmTRvl/Eln9wMi25ajzPcVOEsznme7R3e8ry6wxddtR7GtjZl19zEi41znuah7fPrti8temz3ajXrXrHdXFm+NsQ+NhNSg2i0es7TXHs5ucQkbbWh2t9qbAmuJF/1abFyzrNsEVU7S0tEpUXHbXX1mDgumzcc0qLrtrqaV/hOi87b4i5deYm06L2twqyMTVr04O7VMjZr7bLSogt3P1t3z3eRtedLi06cuUdrh79lOIuTq4+tDj1XC1qSE8PgRTfufhHe7bCPaz+cFj25+811N+dJ1+Y8LTpz9zj3roLXdVchLbpz9zj3jkvTs+q4pEWHbhbnrBuVFl26oV506mJZd+rSolNn87x1Mbce5uUi9axbNY+1zPfubnsGSXe3tkb1xjWPYdKiW3e/CutZyq5ezdX33Qaergu7135rBZfRs+jYTe8Ktx4KSIuu3e4mvQ5LtLtrMSyRFp27VZuxGiNJi+7dwiAsR2zSooO3a1Jv40d+PX6UFl28oYm/jWU5jesRsbTo5A3IYWRNyn5UzOp5jICVeJU4Nat6uY6L1Rvi0haBqU3hUK/HLuf7qGO72Rl1rKivGXMmz4u+nnEa9xHQ0EdAtbK+nnkz7pgWvT3i+MtD7ZG11Qrb87rrCE5t369DZbWRTlbPaZ6H0eEQ16PDadHnm8Vpj/nnI9Vp0efrUYZB8/WYeV70+u5hal3qpdNegKhdtjaAH0obItZLtO/85EXHr8cZHiesnybkRc/vHqYamtKeZKRK4RanNkHtIV/tNzmTnbzo+5k424OWBq7Fg5a86PxNwrRXbZdPffKi+3ePc38GVbm1fAaVFx3AHsc+ELvE9ROxfN4FHB7P1fQsH8/l8z7g8Kww5uWzwnzeBRyeW1bbs3xwmc+7gDaOV1k/Rc3nXcDxka5bP9LN513A4flyS8/i+XI+7wEOz7pvT5ivYdqbTvYaPO//hZrUem+2CQrVxRakdr5C6+xcZ5O8hznv/w2vEjQxq5cA8nn/z8apLF+/kpDP+3/DCxIlrV+QyOf9P/u2Rg21fFsjn/f/xldH3PrVkXze/xteZImyfpEln/f/qp42TBDbeEr7vJgXhVx7f7skew2e9/8O1+DqVaF83gE0rxz52j3ZvyxkbvXzDmCNU68c196hb8ui9deFakNUm1AxPYF83gMcXuoqJ69j5fMe4D7O8uWwfN4DHF5Uk7B8Uy2fdwCHt+ZEz+ScptnG8ZKXr/Dl8/7f8Dqhz8vXCfN59294tbE6wv5uY2zDT9G8UJ7Pu3/ji5Zu96KlSc55729467MZ5tVbn/m8/2ffQM0a1++g5vP+n4lTjXJevw+bz/t/vg3N1d5x7Xvm1OKE6hZK7eJoW1PefOOUz/t/w5vCSbY3hWN7+hKS1fNYx8S8t+z27y3b/Dw6NqfX0el6/YTrALpWr6vVwEiNZvQ80gE0r3R7TcsB9Lzq/10uqUZoneC2kojsX1t0J639qit4C9km3qjcrY5ux7Oy5tmqU3gJ/qHZr+pVcvuc2KKtDW9YtNW+ijXVi/5haiey3mjttmsfz+xF6l6kudIeeV2zrTsX6+17/RyxseHSXldpb5Zfso0yPyFFa/NYDUwbAgr1Cn9klDsMwuYnpIf04dKMWtqP4588D8injwzbSGdNcFs7pl58LUrV1MYeanfEBytsfhK09hmuXejaoWnv8N1Gvuu9ndtH120KkRqyjR009bUTaCbyKouuZNF6A7Q3d0M17fXs3Qblr2Pwsc1BUVr6qpWvTu7SCG1GnQu9SvsFyPUVoHduv3r7vc6wdn2Vht/EL9sltstsl9kus11mu8x2he0K2xW2K2xX2E7YTthO2E7YTthO2U7ZTtlO2U5v26XLbbvM39/mwLg+DuW3/z3bO8fvbbtAXgJ5CeQlkJdAXgJ5CeQlkJdAXgJ5CeQlkJdAXgJ5CeQlkJdAXgJ5CeQlkJdAXgJ5Cdrry/bkJ5CfQB4C+YnkJ5KXSF4ieYnkJZKXSF6iYzvHdo7tPNt5tvNs59nOs11gu8B2ge0C2wW2i2wX2c74Q7ve5O6LpPYpvPkiqRrWbcu32cDGkckdkch8IvOJzCcyn8h8IvOJjCcynsh46lceGc/9iiTjmYxnMp7JeCbjmYxnMp7JeCbjmYxnMp7JeCbjmYxnMp7JeCbjmYxnMp7JeCbjt/mhr70MftmOOyFzJ2TuhMydkLkTMndC5k7I3AmZOyFzJ2TuhMydkLkTMndC5nzkfj7IRyIfiXwk8pHIRyIfiXwk8pHIRyIfiXwk8pHIRyIfiXwk8pHIRyIfiXwk8pHIRyIfiXwk8pHIRyIfiXwk8pHIRyIfiXzYb2/tuqeHO0CGO4DRMnMHuIuJM2PC1ub1mvYr0Dxds+uf7hW48R50h3vQ9GaKm92DXUE/57bXa9c/PRx5rLs/1N2buvuzuverLlgo+3Wd/Vhnf6iz6W8XP61zv686AcxwuV3/9HDksc7hUOdg6hxmdb4fcZLtsK5zGOscDnU280zVfuS0zp2i/d4313hc1zmMdY6HOkdT53hW597aBPPuol3/dH/kONY5HupsORXP6nxv58x5Tus6x7HO6VDnZOqcptf2duTuYUy207rOaaxzOtTZ5i7N69yz3V2UucLyus5prHM+1DmbOuf5ee5HLMds53Wd81jnfKizeQW+5Gmd81bXkXPm2YFdB/WgYKx7OdS9mLqXad07YTfv2T2padPKOgdlzEE55MC8lVDKLAd5c79pUJDNoLNdF/WgYMyBHHIgJgcyvea3unf3YTTLuu4y1l0OdRcb56zuecu6qbOu6yxjnfVQZzV11rM6349srjhd11nHOuuhzuZZZ9H5Na/DkbO50uz6p4cjD3WWy77OdV8TZ36td1e661+Zusu63yBjv0EO/Qaz8m7987TuW09uVGJn/pe1b5PRt8nBt4nxbTL3bd1Bb0689ymN9rVvk9G3ycG32WfUMvVt975Az0U5Klj7Nxn9mxz8mxj/JnP/1n1b5/vWSzFX4trHyejj5ODj7JthMvVxW/+ou2jjpmTt42T0cXLwcWJ8nEx93DZW0HtM0R55XefRx8nBx4nxcTL1cb2PeB+lMNle+zgZfZwcfJwYHydzH9f9+qbAHnld59HHycHH2edRMvdx20hM7y+b+3zt42T0cXLwcWJ8nEx93L1H3hUYrWsfJ6OPk4OPM+vftskOpkfuYwLheOS1j5PRx8nBx4nxcTL1cffxrk2B2WNd59HHycHH2fm9Ze7jpGeb+3q7xs3dtfZxMvo4Ofg4MT5O5j5uG5HpY4HmSlv7Nxn9mxz8m9hWee7fZDzyNlbUz0YfbbS5WPs5Gf2cHPycGD8ncz/HKFsf58zDkde5GP2cHPyc2Ct57ud63fu4mT0Laz8no5+Tg58T4+dk6ud6tu9ju6aNW/s5Gf2cHPycGD8nUz+X+93GWOc9633s8J4DXfs7Gf2dHvydGn+nU393H8cOoyLZj2YmE2mZGx39nh78nl5snPn10I/cR9r7PWH2XPs9Hf2eHvyeGr+nc7+nOhz5PsLrzJ7rHIx+Tw9+T52tybRt1N0Ys3m2pmufp6PP04PPU+PzdO7z+pH7cwXzwqKu/Z2O/k4P/k6Nv9Opv+tPTvo4e7zcSaRrf6ejv9ODv1Pj73Q+TrcdcZLttb/T0d/pwd+pvWem/u7+dGh71nDfY+3vdPR3evB3avydzv3d9jQjHbO99nc6+js9+DuNtgbT+3t7ntKfkPXsmz3XPk9Hn6cHn6fG5+nc5/Vnav1ZXH9SZN7D0LXf09Hv6cHv2e+1der3tqd//dlUf+ZkXgDSte/T0ffpwfep8X06H7/rT7u25439OaS539f+T0f/pwf/p8b/6dT/5e2JZxoUZDOrvq79n47+Tw/+T43/06n/uz9r7U8C+6+5DtY+UEcfqAcfqMYH6tQHxu3ZY697fypsroO179PR9+nB96nxfTr1fdtT0X4v+JmCdQ5G/6cH/6fG/+nU/92fbI9KspkiRtc+UEcfqAcfqMYH6twHbk+K+7N1c/7XPlBHH6gHH6jWsUx94P1p/vbsuu/hL2vfp4Pvq1vu6tz2NXHmde5Z7+8R2COv6tyCjUfOhyPbONP7fns+H45HXvq6Fmw48t7XtX1NnOn93j1NZ9/d2/jL0s+1YOORD3V2tgbzOvfz29/mKPc9ln6uBRuOvPdzbV8TZ36e+3sh/chq9ljX2Y913vs5f7Fnbern+vsZ/chDtpd+rgUbjrz3c21fE2dW5/6GyP1dmP4mian70te1oKOCQ92Dqfvc121v3/R3V/o7K2bPpb9rQQcFe3/X9jVxptd6f/tie2smmD3WdY9j3ff+ru1r4pzVvb+3E4O51pe+rgUbjrz3dW1fE2de557lfs2b8730cy3YeORDnZOp89TP3Y9Yjtle+rgWbDjy3se1fU2c+XuGW11vRxZT56V/a8HGIx/qnE2dp/5tez+rv0Fos730bS3YcOS9b2v7mjhndd7eFBNzhS39Wgs2HvlQ52LqPPdr25H7253mPC99Wgs2HHnv09q+Js68zuPbctHeh0t/1oKNRz7UWWyc6XnejhiO2V76shZsOPLel7V9TZzzd2j7G4Im20tf1oKNRz7U2bbCU192fyfx8Jakd0tf1oLZI7uDL3PGl7nT94b7W5JmDWjv1r7Mjb7MHXyZu9gazOvcj1gO2XZrX+ZGX+YOvswZX+amvmx7I7S/s5wmdV/7Mzf6M3fwZ874Mzf1Z/e3skcl5t1A79Y+zY0+zR18mjM+zU192v297P5WZH8b0mhf+zU3+jV38GvO2zjT89/f1O5vbvf3Pp05C2vf5kbf5g6+zRnf5qa+rZ+FxDPm/oZmNPx1a9/mRt/mDr7NBRtn/o5yfye0Xw/lqGDt29zo29zBtznj29zUt93fTu3fC5grcO3b3Ojb3MG3OXsdzX1b/wKhv197X8HAu7Vvc6Nvcwff5oxvc1Pf1t/Q3b59SOaKW/s2N/o2d/Btzp61uW/r7wR3BfbIa9/mRt/mDr7NGd/m5r5t+75jU2D2WNd59G3u4Nuc8W1u7tv6+9DbFyWmnV/7Njf6Nnfwbc74Njf1bfcjpsmR13UefZs7+DZnfJub+ra0HXF7N/y+x9q3udG3uYNvc8a3ualvS9t5LjsFRvPav7nRv7mDf3Ni40zv6+3u6u/D9/fkzf299nFu9HHu4OOc8XFu6uO2N/R7C9PbNnvNr/2cG/2cO/g5Z/ycm/u53o5vX0ttirY9/drXudHX+YOv88bX+bmv277P6l8z9K8YktlzmQM/+jt/8Hf+YuPMc9C/n9i+GLvvsfZ3fvR3/uDvvPF3fj7utn2Ttikwe6zrPPo6f/B13tkazOvcv5LrV979vvdrP+dHP+cPfs4bP+enfu7+1YqbHHld59HH+YOP88bH+flz1O5du5ftXyDe3+Dyfu3j/Ojj/MHHeePj/Hz8rX/B0/tv27eHVsE6B6OP8wcf542P8/Pxt95/274t6grMWVj7OD/6OH/wcd74OD/3cdvXTf37S50oWOdg9HP+4Oe88XN+7ud0PPL23ZUZp/FrX+dHX+cPvs4bX+fn43G6HZFfU/e1r/Ojr/MHX+dtmzl/vroduX+9alqcta/zo6/zB1/nja/zc1/Xv1bsI8CGTX7t6/zo6/zB15mlAeqfp23ddsRwzPba1/nR1/mDr/PG1/m5r9uOXI51Xvs6P/o6f/B13hJq7uv6CH8fX7ctw9rX+dHX+YOv88bX+bmv275y7N8HdyX9e2qT/bW/86O/8wd/Z2bzrn+eX+u3I5ZL77+bVnbt6/zo6/zB13nj6/z8uen+yObZkl/7OT/6OX/wc95eP1M/tx0xHI8c1j7Ojz4uHHxcMD4uTH1c//69bN/B2yMv6xxG/xYO/i0Y/xbm/q0/Q+xvpZkshbV/C6N/Cwf/Fox/C1P/lnmG1M93Mk8vw9q/hdG/hYN/M7PvtGlQTq6w7Rtje+S1fwujfwsH/xaMfwtT/9bPb7+78taqOrPnuu6jjwsHH2dmjK1/Pqv7faYFc+S1fwujfwsH/xaMfwvz9+G2812O1/jat4XRt4WDbwumdQ7z8bdtFol+re+/NTcR1v4tjP4tHPxbMP4tzP1bV7J97d7nuTBX4Nq/hdG/hYN/C9HWZJqL7Xv73bisVbD2b2H0b+Hg34Lxb2E+LrfN3dHn8ujfrQez5zoHo48LBx9nvg2uf56PSY9fyt+/nDcK1n4ujH4uHPxcMH5uuTpqm/jrEi9tslWp3ezbjGJFg6gruWppM5OZKItlIdyDT9fJftvSRCHeJhTTS1vVqnUnyi7KYv4c9xDrlel8e2O8fW7cokTN7ZPwmGqbsouyWBYitjnH2jRNbYGZat7aNGCS2n1euydt2eshymohnviQitc2wbNcWlvfolzaxwcptLkid1pWC/GEh9ImLnOXi8YS8m1ms0tqcpLfV2i1Ds/lobbLbZ6j5pyL3ubo8xcfY2gad0EWuW0To4Z6X+aalnb/3lYoLeWS2xx94nZR5rmt+0hJbdrrUButrEzzV6+WVLRewH6Mspyl60Eu9b/q0qLU6+axKKu50EyUUOJtCsTSJgxrb125fZTVTGgPbVFILW3SzdBmlgr5ob0fUNU4H/fneTUXlzw0Kc7X83xpn2y32TOvNRKpp6zssruantk/SO021IupzVnn4yNRVpMz+4e2mEBqZ+jaC2lRkq8dp+rqNe1rtJqa2T+Ey/afu2lp05Om1uGtV/IYZJHcY5BQL7rrJVjaHGK7KIvkuoecxij+QeMyyiK57uH88Ks1UeuO1wO3KftSm6qxZeLaQuZY24dd27ZaE9W12aC96HVKQ1fS9TrLLUS6tFWJ3C7KMqFXLVr3u37Udp2Y7nqFpPZYPO6inF6tvopv944MUa6TVY9RFgmVh3pFXdrkvT61CbWuU5m2VSXTFWHjJbJaFrWt9XS9iWuNSvv4/XYX19PjSmxrNO6iLLJ7jKIPTi5tdYWSDlIWyT1WqDaRtc2sYi61T7ML8pNze9K2rdZFrVfL9YrXNu9Oe7/mPMpq0uU2N2hbb7pd7+lyo3KbEb1NL6eqaRdleeXutIwOYZeX1cKoo88oE5/h2hTptSnR9uWXeSy/XCV1NB1pYjpcm7o9iqs3e5sWwoRceIfHHUgLWa+O2Kb/vNyn7PTLBVSxI14qGJrnvNsRDe0qaw9yHy61NS9tRr77Bwp+uZjqaE38xJq0kDVtlzaztVNT79Xiqo/6FJcqFutt0JowMyW/Xy60+qhpaac7tgnoa15KsIlcnJvHHUwLWdrMiTHUVN47Eqs1WHd2pkxuM8dyRTVkjsXUezmr87CD34WsRvIk5MqiPBqyXmNt7letvqFNP29CruZtlRqyLXpbbt2QnxNyNYXroyHdsIW5KpczQA8+cXZ2lhF/gmf0aWIZx4jmElrOCj34Rz/xjy1k3aS9Zp7N6nh+tdjrzkzuXGCjc230risWS6k3o5pzs5wretgh7EImfxJyOW/0oyGXV9ByDmmpBqLULPnc1iP5WSFXZ+fRkG7cwoRcnJ3HTfo65NL3W8ce944930JWAtU/1zgWZKsJpx+17y1iuW9hIv7kDsHeTK9DLs7OaOzDxNhXqj2ENAu57CtMhalxKKs5qN3DxNqPu646tKO5jxNz3ypSLg2wlX/mGeVqldmd04+j03eOy6zdgXoJaWhXll3dYYe86zzcmqpVyCVHHgu5vGWXaxTRsJTqspov/Bkhl8sVPRrSDVtkE3LZ4bA2v0w6YuuQP7n7se9PtZBtRvzsXSzRhlyS5LHOVQsZr7irJ9DbXC57fTZkOPa0VhFXq9s+3u1aVXu11O3k5Bjj0NagXJ6c1bq3k0vo6G5WIZf3zmMhVxf6akXc9rnoNfdaOxxtuvafEXK5PtKjIZ3ZQk3An9SdnHruRcDVzPqP9nJbI179lHMXH7I3p2bViT9oPHR5Vxp/6omxAduTqFXA5XpKjwZcnun10kq2/y0/K+RymYnHQq46/adr7pou/b7T79ad/tPld+9d+n2n3+m603+yFO/Qp991+mM0vf424YW9JterMtk+fdn1+oOue/0nC/QOnfpdr/+mct7tP1mr1/bqw67bL3Hd7z9Zt3fo1e/6/SWt+/3rJXyHXl7e9QMvad2zXK/mO/bydv3AIOt+4Hph38H0l1234HrGF92C9SK/zaLvOgMprq37epVfAlmrLSfdivU6v1eHv7P+ktfWf73Sb23lp4qMg18v73vb2dr/w67LnFprLzvzf7uY5uZ/vbjv4HgOVvDEEp111++uLOydoDvxbevu+j6kdYIpnIU8cVljva0VTPGs4suzY9mfdu5A5MQdLBeFmoSs/ZkKhsuldtUOoDTN5nJ9qEcrvg75vz4965Anp+f8IlqHPDHBp1f6OuKJ1Tq/HZchl8+rZ43DOsrPa5/WcZZnYdFiriM9QoOfLukRGuyxsgy07qk/hrx1yP81mNchl2dgP9S9tw/rkCe+qS0lFy7tCQ4m53JdLritCHpa8RPfdG7FViFPliR+zDCuQ/6vbe065NLWdmtd287g9y8AnTRTp4sWn3cR1iFPeh1tSdT2Atrl1oGT2jnw7Slhe7y1jkhXfXiZzDONt2dJKM9U1p5pnT3TPHsmHvZMieuZqNazJJRnclbPlJmeKTQ900V6plD0TCfomdzPM9mfZ7o5z+RvnsngPBOgeaYj80wO5lkKyjNBlmeyKM+k/54p+D3T03smi28vbpmMhNVLcm3w1bwkl13cvSRnpkOrf86zzG4KqIGnBuZ13cwLvlMFeVSgBwV3497XTx4VMLWTycFEgV/nwI858IcceJMDP8/BqCCaF4WzX9fdj3X3h7p7U/dwVnemOfJmQQTfVzCeHTmMdQ6HOgdT53BW5+3I9ooL6zqHsc7hUOdg6hzn97Ibjhyt1riucxzrHA91jjbOrM5M6eSZ5si0KqbucV33ONY9HuoeTd3TvO7jkbsSO9FSX+p3piCNOUiHHJhRjJzmOejXeG9pekuazJ7rHKQxB+mQg2RykKfXfOxX3KjATkLUV+KdKchjDvIhB+bT9Jyn176MCroipsnxTFrjmU7FsxBke5RvIq9zlMcc5UOOsslRmeaocwOO8FK959V2z1KNnhfLPa97e/tydV9md6awjDkshxxaIpd5DjtpXc8Nv3bPdY7KmKNyyJEZ8OkL4s4VMPWIZ1lObybg930N3JkCGXMghxyYSXSyTO8ljsi0G8ZtWAXrHMiYAznkQEwOdJ4DHY7clTAhiGeKCh873TtbLWd0nSMdc6SHHJmPM7NOc9SZmncOzEx2lnWdIx1zpIccmaHgvkLsTkHZe76eEzV7LnPQviYyCspln4Nyn37Z98U1d2dpc5mchU7AYvdc5qAGHRXsc1D3vceZ+2cUxM6dsvles+c6B6PPLAefWUy7U6Y+sx8xltFpjwrWORh9Zjn4zGJ8Zpn7zIsbjhyLOf9rf1lGf1kO/rIYf1mm/rLXOXbiqT3yus6jvywHf1mMvyxzf7n1X7jizGf8Ze0vy+gvy8FfFuPZytRfxs6FfmSb7bW/LKO/LAd/WYy/LFN/GWXfZwvHuq99Zhl9Zjn4zGJ8Zpn7zK2XiIKuSHqZf6f1jr1FUht5naPRh5aDDy3Gh5apD42668/aI6/9Zxn9Zzn4z5JsnHludHfkZPZY13n0neXgO4vxnWXuO3udtffN+xVqrsy17yyj7ywH31mM7yxT33kfJXCjEtserH1lGX1lOfjKYnxlWfjKPj4R+pHxkebeWPvGMvrGcvCNxRJt6hu7k707W3vkdd1Hv1gOftE+Cy9Tv9jrnnqLZF6ALWufWEafWA4+sRifWOY+0XWXjovvZ8Gbuq99Yhl9Yjn4xGJ8Ypn6xNTHo3wf5en9BXP3rX1gGX1gOfjAYtuPqQ+8jy/1HHD+e266ov7v2ziUVbjO0egTy8EnFuMTZe4TOWLafnvOitlzmSMZfaIcfKIYnyhTn9iPmPqo0PZrFSxzIKNPlINPFOMTZeoTtzEZ38+Kmj3WdR/9oRz8oRh/KFN/2OuctlEhZ/ZY13n0hXLwhWJ8ocx9IUdMk/EoWftCGX2hHHyheBvnbDwqbQrsHus6j75QDr5QjC+UqS9M25H7+FM61n3tD2X0h3LwhzLEOR+HSoMSO/WNrH2ijD5RDj5RjE+UqU9kgiHPFEfbiJgdi5O1T5TRJ8rBJ4rxiTL3idt4kxsU2LcoZO0DZfSBcvCBYnygzH3gNnbSR8BQEM3dt/aDMvpBOfhBMX5Q5n4QBUxx5VPcRnPMnuscjL5QDr5QjC+UqS+8H7GP8pWjgrUvlNEXysEXivGFMveFjMqkPu7Yx+bNKI2sfaGMvlAOvlCML5SpL0x9pLO4QYGdwljWvlBGXygHXyjGF8rUF95HJvp1wN1pJpKWtT+U0R/KwR+K8Ycy94elX4nUvd8TZmRc1j5RRp8oB58oxifK1Cf2I6Z+V27jBlbBOgejT5SDTxTjE2XqE/sIRT+yneJS1v5QRn8oB38oxh/K1B/2Oqe0jROZPdZ1Hn2fHHyfGN+ni/FBHY9sxgl07fd09Ht68Htq/J5O/V4fI+lHTmbCaF37PB19nh58nhqfp1Ofl3obJ/sRClP3td/T0e/pwe+p8Xs6Hw/UXvc+BtJ753bPdQ5G36cH36fG9+nU96W874X3s6Bmz3UORv+nB/+nxv/p3P/1kUgUdEUp2z3XORh9oB58oBofqPPxwd7/p3eW8tZHNnuuczD6QD34QDU+UKc+8P5Ea1Ng9ljXffR/evB/avyfzv3fxe3qbLSufZ+Ovk8Pvk+jjTOt8zYO0BX0vrCp+9r36ej79OD71Pg+nfq++xH7yMREwdr36ej79OD71Pg+nfo+ltXyLCnmWcjN5/5EcxsH6DnqI1X9F8XdL3R685whld0Yq/Tt2b+3vbR8LBviU9+O/dL2tKg/QWM/nuWk3m5tz4qJ0+9p7jC7hJau/ayOflYPflaNn9W5n93GL3qGTXu29rE6+lg9+Fi1rdLUx/Yj38+h4dnav+roX/XgX9X4V537V9+vnm0ExeyxrvPoW/XgW9X4Vp361vsRyzHba7+qo1/Vg19V41d16le3UQPfrzCT7bVP1dGn6sGnqvGpOvWp93u199nNtb32pzr6Uz34UzX+VOfjmLsRk2zb7LU/1dGf6sGfqnUdU3/a26v7kU1LufanOvpTPfhTvfvTcJn609w5tY2QhH3dw2XpU1tQo6AWd3Vv+5o40/t6Gynp93dvA9XsucpBCzoq0IMCk4O5X+0+pbeq9zGacFn61BZsOPLep7Z9TZx53fuYTG/P7ZHXdXZjnff+tO17jzMfl9zeQupXnsn20pe2YMOR97607WviTOusO5YNR17X2Y913vvRtu89znxcMo7jUJ2qZvHFcFn60RZ0ULD3o21fE2da97gbj+q9ArV7rnMQxhzsfWnb9x5n/vy690tSH4MJRwVLf9qCDgr2/rTta+LMz38fg+njUf3X7rnOQRxzsPenbd97nLk/7Qq6C9tGg8x1sPSnLeigYO9Pg/naM1ym/nQbBYo7Pyjm/l/6uBZ0VHDIQTI5WIxLbkccHer9LcRwWfq5FnRQsPdzbV8TZ5qD7o23sZl+VsxZWPq6FnRUcMhBNjmY+7ptZKS7dFP3pa9rwYYj731d29fEOa37NkZj91jXuYx13vu6tu89ztzX9TpvRzZX3NLXtWDDkfe+ru1r4szH4Mp45GLa/aWva8HGIx/qLKbOc19Xxl5alMOIWLgs/V0LOijY+7u2r4kzH4vTod94H5cyV9zS57Wgo4JDDozPc1Oft/Vc8zgyZhYyDG7t89zo89zB5znj89zc522jQP3897603XOZAzf6PHfwec74PDf3eV3B1pvfxmjMnuscjH7PHfyeM37Pzf1eP+L2hnWaKFjnYPR97uD7nPF9bj4u2UeFei/6/p5qcGvf50bf5w6+zxnf5+a+z+3GWrK58ta+z42+zx18nzO+z819Xx+P2t5LMXVe+z03+j138HvO+D0393t+NwZns732eW70ee7g85zxeW41U8Pl4R0vw0Sh+R3mxnKhcj95e+etJmfYRclZ4zsp32au0nr9Jn9fLi641XwMLcp1ur/2skZybVLPd1K5fWws/josY+6A1RQMtyhXLSWWohJqlNuMRZV8udSoVsvi68Ea"} |  |  | - |  | - | -
[14 empty] | {"index":135,"total":402,"filename":"Advanced_Project.ifc","data":"zxLzOQebcY7c6rwyV5wyfRJVVh08tlOq9yxRLAEFvUeg92ir98o8G7xHGYwuyvUeeb1HQe/B2x4Lu73LWVYfn3ObgM253iOv9yjoPQK9R1u9d/fte2bBnHObvc6joPMI626r8+6+XUoYXZTrPPI6j4LOI9B5tNV5dy3zpoflOo+8zqOg8+Ctjv7zfv6eOdLd158vcp1HXudR0HkEOo+2Oq+s0SRxRqFct5HXbRR0G9x/1n/ej+vVvrTmtOeLXK+R12sU9BqBXqOtXrttXjlX6GG5TiOv0yjoNHirYxTFb+3Mq7YfbUK5PiOvzyjoMwJ9Rnt9do/njc25LiOvyyjoMnhJof+8n8PWDDKizbkeI6/HKOgxAj1Gez3Gr76NZc31GHk9RkGPwX04/eev6/Sav3HezvUYeT1GQY8R6LEtN+Es52vFwDks12Oel8CBl8Bwy5S3vITH1nPEmSTXY56TwIGTwMBJ4C0nAbTJamfoYbke8/wDDvwDBv4Bb/kHkGOJNud6zPMPOPAPGPgHvOUfQM/azCS5HvP8Aw78Awb+AW/5BzB7zlqH1S3nH7DnH3DgHzDwD3jLP3hyXCWAOSznH7DnH3DgHzDwD3jLP3hmkluHQc65DvP8Aw78Awb+AW/5BzZzvMYz5pzb7HVY4B8w8A94yz94anvtakEB5vwD9vwDDvwDBv4Bb/kHjzKocVTl/AP2/AMO/AM+safudVhbtb12eFDbuQ7z/AMO/AMG/gFv+QeQ86r1Bl/kNnsdFvgHDPwD3vMPnpzbx7Nb4y4n5yCw5yBw4CAwcBB4y0F4avv2m0Ct53rMcxA4cBAYOAi85SCYjX4nD96LnIPAnoPAgYPAwEHgLQfhaedV+2hzrsc8B4EDB4HxFCThICw9dvtPVh2s9bv5dVzumefn8z30zFy/eW4CB24CAzeBE27CWtvm6WVZkf1hfc/5Cez5CRz4CQynobzlJ6wc9e+iGFAsQa7nPEeBA0eBgaPACUdhMZ/W/N9WnXxah5e3c54QlI4ly+vG673AWWA4HectZ+Es09dcpt+9wKlIzllgz1ngwFlg4CzwlrNgkNeZ44xACD7mnLPAnrPAgbPAwFngLWfhsXmehpQBNud6z3MWOHAWGDgLvOUsPLSDNVqxnXO95zkLHDgLjGcUe87C3cPuHvfYnHMW2HMWOHAWGDgLvOUsPDnftY45pzZ7zgIHzgIDZ4H3nIUyxPUwbOecs8Ces8CBs8DAWeA9Z6GMVctrVEFZc73nOQscOAuMq/mes1BuqtyMyw5nRzlngT1ngQNngYGzwHvOwjODjNjOud7znAUOnAXGnUnCWVi1vMg8sP7nnAX2nAUOnAUGzgLvOQvL5rsEMJ5zzgJ7zgIHzgIDZ4H3nIW7b9+zKNic6zzPWeDAWWDgLPCes/CMqmUz9LBc53nOAgfOAgNngfecBT6KH1UDajvXeZ6zwIGzwMBZ4D1n4e7bo4S1KucssOcscOAsMPqy9pyF1b6PzVDbuW7zfAUOfAUGvgLv+QqrtpftzuZcr3m+Age+AuMJ356vwIuP0+5x/XyR6zTPV+DAV2DgK/CWr3Dn+JQAajvXYZ6vwIGvwMBX4D1f4dEiJa7PuQ7zfAUOfAUGvgLv+QprfeZ10o49LNdhnq/Aga/Abs3b6jCeHj+e3mzG1S3XYZ6vwIGvwMBX4D1fgedZIM8XawynFjlfgT1fgQNfgYGvwHu+Ar+4KcfzNpJzvgJ7vgIHvgIDX4H3fIXb1mX78z6Qc14Ce14CB14CAy+B97wEptXDpiqCFT3nJbDnJXDgJTDwEnjPS2C623eTc26z12GBl8DYU/e8BKZl6+LjQDvnOszzEjjwEhh4CbznJfDc8d+1fvc4LEFuu9djgZvArg73emzlvGzHnpbrMc9N4MBNYOAm8J6bcLfzbPe2ZpiHGcM5P4E9P4EDP4GBn8B7fsIzo6zxDTnnuszzEzjwExj4CbznJzx9/R5t8EVus9dlgZ/AwE/gPT/hzvEeZdDTcl3m+Qkc+AkM/ATe8xOeebzFds51mecncOAnMPATeM9PuNesm1YDOee6zHMTOHATGLgJ+s9f5/G7BFDWXJex12WBm8DATeCEm7AIPGt8rznuXlHmeJ8+SJ4nPDzPyXl+z3DukvMW2PMWOPAWGHgLvOct8PRF86JcwBlEzltgz1vgwFtg4C3wnrfA8rIZ7oLkvAX2vAUOvAUG3gLveQt3zrLmf5gHcj3neQsceAsMvAVOeAt3Ld9MkeeLXM953gIH3gIDb4H3vAWW4mzGu7Y5b4E9b4EDb4GBt8B73gLzal9att9f5LwF9rwFDrwFBt4C73kLd87zblera15o8GVqu+cucOAuMHAXeM9duHvaGt/1ae+cu8Ceu8CBu8DAXeCEu3D3MIm1nus6z13gwF1g4C7wnrtwzyiyae9c13nuAgfuAgN3gffchaeHjdjOuZ7z3AUO3AUG7gLvuQt3+675HNs513Oeu8CBu8DAXeA9d+Ee1/fKAWXNdZznLnDgLjBwF3jPXVjtfNy2g825jvM8BQ48BQaeAu95Csvmm6cC83fOUWDPUeDAUWDBnrrXcat91/qNtZTrOM9P4MBPYOAn8J6fwO/xDKeTOTeBPTeBAzeBBfvLXsfdc9iI4znXcZ6XwIGXwMBL4D0vgetrPKPNuY7znAQOnAQGTgLvOQl3zmXNntDDcj3m+Qgc+AgMfATe8xHunO+eBmXN9ZjnInDgIjBwEXjPRbgpJWs838rwXjXn3PZo05yTwJ6TwIGTwMBJ4D0ngee9GF50qkUv6ViCvE68XgucBAZOAu85CSvHVQJehC7wt+acBPacBA6cBAZOAu85CStHXnydm16CJcjrwOu3wEVg4CLwnouwclwl4EV0grOFnI/Ano/AgY/AwEfgPR9h5cgrIuixK0FaB56TwIGTwMBJ4ISTsPxy854Er8ig4DHKeQnseQkceAkMvATe8xJWjrzic970EixBXgde1wVuAgM3gRNuwtq7rvPxFTUTfFc5P4E9P4EDP4GBn6D/vK2DmSOvuJ3nrgR5HXidFzgKDBwFTjgKpy8Br2ia4B3PeQrseQoceAoMPAXe8xRWjjzvwfA6/ZqjVOjFVXEly+vG68HAW2DgLfCetyDLuzZPPwXOZ3LeAnveAgfeAgNvgfe8BZnellUCAb9ezltgz1vgwFtg4C3wnrcgx6r1+RdnklwPet4CB94CA2+B97wFmTOS0PqLOec2ez0YeAsMvAXe8xZ43dxY6wLcGcl5C+x5Cxx4Cwy8Bd7zFlZfl3Ueh/N/rgc9b4EDb4GBt8B73gLPGxt3e2M753rQ8xY48BYYeAu85y08trY17uGL3GavBwNvgYG3wHvegqyIsYufgjNArvs8b4EDb4GBt8B73sIaTfdMgmtcrvc8V4EDV4GBq8B7rgIPcu3McFsl5yew5ydw4Ccw8BN4z0+45/O7p0FZc33n+Qkc+AkM/ATe8xOeeXvNJI+6zvkJ7PkJHPgJDPwE3vMTnjVrtfOAL1KbPT+BAz+BgZ/Ae37CPXsea0Z5eljOT2DPT+DAT2DgJ/Cen/DkTGFU5fwE9vwEDvwEBn4C7/kJT/tSWDFyfgJ7fgIHfgIDP4H3/IRnXW5hfc75Cez5CRz4CQz8BN7zE54ZZM3b0Ldznea5CRy4CQzcBN5zE545LI7nnJvAnpvAgZvADftLosPktT5Dbec6zHMTOHATGLgJvOcmyM01XD3t1qbwZW6712OBn8DAT+A9P+EuweJknGB7rsc8P4EDP4GBn8B7fsKtw44Rx3Wuxzw/gQM/gYGfwAk/Ya7PMvcmMk965Wb7QR3k+szzFDjwFBh4CrznKawS3CXCWTXXZ56nwIGnwMBT4D1PQVaO02clsOvJeQrseQoceAoMPAXe8xRk9fXpERbwRec8BfY8BQ48BQaeAu95Cqt9n/Yusb1znea5Chy4CgxcBd5zFW6b7zqA9s51mucpcOApMPAUeM9TuG1efR5OenKOAnuOAgeOAgNHgfccBTnvdt7knNvsdVrgJzDwE3jPT6DpCVwMIKztnJvAnpvAgZvAwE3gPTfhtnXa3lcJYP3NuQnsuQkcuAkM3ATecxPuvl0l9PGcl8Cel8CBl8DAS+A9L0EKvWq9wBe5zV6vBU4CAyeB95yEZ0ZZrBj4ItdrnpPAgZPAwEngPSfh6eP3KIMvcpu9XgucBO7YX7Z67c7xHl1Q27le85wEDpwEBk4C7zkJzxw2Yt/O9ZrnJHDgJDBwEnjPSbjXrFJiO+d6zXMSOHASGDgJvOck3D3sLkGDL3KbvU4LnAQGTgLvOQmLxCO8/i4+DpQg12uel8CBl8DAS+A9L2HlKIucuMg8rgR5HXjdFrgJDNwETrgJi0O+dgizJALn6Dk/gT0/gQM/gYGfwAk/YXFwlldr3tgQuH2WcxTYcxQ4cBS4Y0/ex+1dO0JZJVg0GihBrt88T4EDT4GBp8B7nsLKUVY8btqVIK8Dr+MCV4GBq8AJV2HxcMiXRHCNy3Wc5ytw4Csw8BV4z1eQedYsK8btinlKWIK8DryeC3wFBr4C7/kKsiLA35wcWSV6vsx1necscOAsMHAWeM9ZkOVbnqdb0jDn3Hav6wJngYGzwHvOwsq5Ls/QE8eZc84Ce84CB84CA2eB95yFx+b5d2DOqc2es8CBs8DAWeA9Z0HmOarME115OAuccxbYcxY4cBYYOAu85yzUNdetEsBdgpyzwJ6zwIGzwMBZ4D1nQebJnSwfM3jyc84Ce84CB84CA2eB95wF6eXVzmBzruc8Z4EDZ4GBs8AJZ2HpuRW7FnbHOWeBPWeBA2eBgbPAe87C08NabOdcz3nOAgfOAgNngfechVXbi1JTweeYcxbYcxY4cBYYOAu85yzUtZpOdVXBz5pzFthzFjhwFhg4C7znLEhffVpi3851nOcscOAsMHAWOOEslLtPr54GX+Q2e/0WOAsMnAXecxZk6bY1h8H74pyzwJ6zwIGzwMBZ4D1n4a7les8o8EVus9drgbPAwFngPWdhzZ43gWmt2zgqcr3meQsceAsMvAXe8xZWH79XS+xpuU7zvAUOvAUG3gLveQsybyGtnoa3hnLeAnveAgfeAgNvgfe8hTV73n0ctEnOW2DPW+DAW2DgLfCet3DPKL3FnpbrMc9b4MBbYOAt8J63cK9ZK9I37E1z3gJ73gIH3gIDb4H3vIV7XPewTkvOW2DPW5DAWxDgLcietyDzht1d6xVzzmwWz1uQwFsQ4C3InrdQj9dqOSDnVI+J5y1I4C0I8BZkz1u4Z897NsWcc5vJ2/zWYwKcBdlzFm71O8JMIjlnQTxnQQJnQYCzIHvOwurba+2qzzmJ5JwF8ZwFCZwFAc6C7DkLaw672xvbOdVj4jkLEjgLApwF2XMWnhyD4pecmyCemyCBmyDATZA9N+FRQ2tUjeeLVI+J5yVI4CUI8BJkz0t49Nin1sdcNd24TnWZeF6CBF6CwBsu2fMS1rx9r5bY3qkuE89JkMBJEOAkyJ6T8OS4Zhao9VSXiecjSOAjCPARZM9HuPkYy5Pb7x293+Gvkq1Zl2AUpvpNPD9BAj9BgJ8ge37CKmGl9XfRLKB1Uh0nnqMggaMgwFGQPUdh5ViXt+smekAJUh0nnqcggacgwFOQhKew6N9juJJUwhLkddB8Hbz1nABXQfZchTpvJ9QVi/wmepTny1TXiecrSOArCPAVZM9XqPP08iF6rLqAsZLqO/GcBQmcBQHOguw5C3V6P+taiU7IOdV34jkLEjgLApwF2XMW7pznqWYt0O6pvhPPWZDAWRDgLMies/DYPP8+r4ok5yuI5ytI4CsI8BVkz1eo87ylzjNFuFMtOV9BPF9BAl9BgK8ge75CrSvHWYLnlbfkfAXxfAUJfAUBvoLs+Qp1ni3VebYAd6ol5yuI5ytI4CsI8BVkz1eoTL6dnzdckvMVxPMVJPAVBPgKkvAVzmXrijBa4IvcZq/vAl9BgK8ge77C08MktnOu7zxfQQJfQYCvIHu+wl3b8yyhVsw5t9nru8BXEMIxstV3ta5xXNaM8nyR6zvPV5DAVxDgK8ier1Cnwrj7OPbtXNd5voIEvoKQS2cfd3/1sFUCsDnXdZ6vIIGvIMBXkD1foUp7zWEwqnJd5/kKEvgKAnwF2fMV7lo+7xnl+SLXa56vIIGvIMBXkD1f4Z4974jwiz4Ftud6zXMWJHAWBE78Zc9ZuPv4Wi2xh+Q6zXMWJHAWBDgLsucs1HP4nlZhLsv1mecsSOAsCHAWZM9ZWLPnnTNok5yzIJ6zIIGzIMBZkD1n4Z7LIh9Hcs6CeM6CBM6CAGdB9pyFZ3SN2M65HvOcBQmcBQHOguw5C3cPY4mjK9djnrMggbMgwFmQPWehzjPfuwSwyuWcBfGcBQmcBQHOguw5C7W+VkvBnFObPWdBAmdBgLMge87CPXve7Q1f5HrMcxYkcBYEOAuy5yzc6lfiTJJzFsRzFiRwFgQ4C7LnLNSbf3TPps8XuR7znAUJnAUBzoLsOQv3HLbaG9s512OesyCBsyAn9tS9Hls5rjkM2znXY56zIIGzIMBZkD1n4VFDa1Q1+CK32euxwFmQ01nwXY9Nr9duXOe6zHMWJHAWBDgLsucs3HPYWi2xvXNd5jkLEjgLcuJY2eqyJ8c1s0Ct57rMcxYkcBYEOAuy5Sw8DIGljvje0fsd/irZoh888Vsl5zGI5zFI4DHIiXW8j9PbVo+cJVqxa0EJ5JwF8ZwFCZwFAc6CbDkLd4715iy0TQnyOvA6LnAWBDgLknEWhst5laTO2wp1eQbXHQJQDDl/QTx/QQJ/QYC/IFv+wh3btj6R/+GLvE68zgt8BTmxbvc6b9y2Xn/bAWMm13meryCBryDAV5A9X6Eu7/g6IRiYc26z13mBryAnttr+nemKJDz7g2vnXOd5voIEvoIAX0H2fIW7h316XDnWif6A1TjXe56zIIGzIMBZkD1noa0c5/kqvNaUnLMgnrMggbMgwFmQPWehzlHX1s0csDnnLIjnLEjgLEhxFmz7eF/jeva4Djnnes9zFiRwFgQ4C7LnLDyja4Q+nnMWxHMWJHAWBDgLsucs1DsKfpxRcs6CeM6CBM6CAGdB9pyFu4fdsyzUdq73PGdBAmdBgLMge87C08PWXAY253rPcxYkcBYEOAuy5yzcK8ZYo2qs2TTMMDl3QTx3QQJ3QYC7IHvuQn3is8ecc93nuQsSuAsC3AXZcxeePl7CSpJzF8RzFyRwFwS4C7LnLqzY9HXcK8rzRa77PHdBAndBgLsge+7Cs4ZtZpZcz3nuggTuggB3QfbchXtmiXwNybkL4rkLErgLAtwF2XMX7jVsjDjKcv3muQsSuAsC3AXZcxfWzLLGd4VbDDl3QTx3QQJ3QYC7IFvuAqwgI66auT7z3AUJ3AVB7bvnLqzV8rYZe1iuzzx3QQJ3QYC7IHvuwmPrmlUx59xmr88Cd0EKzkhbffbMnhRtzvWZ5y5I4C4IcBdkz114anvNZdC3c13muQsSuAtScEba67K5I2xzx9jgJD7nLojnLkjgLghwF2TPXbhzLCsmfYEvUps9d0ECd0GAuyB77sKTs0Sbc13muQsSuAsC3AXZcxfa3Ke3efuggY855y6I5y5I4C4IcBdkz11oK3bpivsCoyrnLojnLkjgLghwF2TPXbh72GIPELRzrss8b0ECb0EgvrvseQvt9LQD18NyXeZ5CxJ4CwK8BdnzFtrpaxvid0jOWRDPWZDAWRB26ez5GuVlM/SwXId5zoIEzoIAZ0H2nIV7HH9KUBbJpWHfzPWY5y1I4C0IRKCVPW/hHl033QJsz/WY5y1I4C0I8BZkz1t4xnNZcxp8kdvs9VjgLQjEdZY9b+Gey+5RBn0812OetyCBtyDAW5A9b+G2+W53KGuuxzxvQQJvwb6FdPZzGb3WLLA512OemyCBmyDATZA9N2HNom3eInPjOtdjnpsggZsgwE2QPTfhzrls+nauxzw3QQI3QYCbIHtuwtOn14wCK0euxzw3QQI3QYCbIHtuwh1v+57TVk9b7T5LNL3cbd4VaPP8pcHdn5yzIJ6zIIGzIMBZkD1nod1Ui8WWgB6Z6zfPWZDAWRDgLMies7BybvOsqcE955yzIJ6zIIGzIMBZkD1noc3T6rvW4dQj5yuI5ytI4CsIxMySPV/htvWu9ae2c76CeL6CBL6CAF9B9nyFNs9X2jzlgthUkvMVxPMVJPAVBKKyyZ6v0HjRLFYJwOZcv3m+ggS+ggBfQfZ8hVaHtxlOcHO+gni+ggS+gkCsDdnzFdo8tW6yehr0sFy/eb6CBL6CAF9B9nyFp0+vUQVlzfWb5ytI4CsI8BVkz1do89y0zVOrBjdvcr6CeL6CBL6CAF9B9nyF/4+zM1q2JcXN9Ot0RZzYsUgSCS47HL7wje3w9Ps/ywALwa+UlLu7K2a8qvocJESS5A8IPi4q5vyR8R6yCWPOQtGchWI4C6Xgu+LrN5IeJqMoPO9Yv2nOQjGchQKcheJzFvbbJX2c0HMcs9ZvhrNQgLNQAs5CfvRxyKCMOQtFcxaK4SwU4CwUn7NwxrL9fkOJOGat3wxnoRR8V3z9Ju81OSNKrN80Z6EYzkIBzkLxOQv7a2k5CyXmLBTNWSiGs1CAs1B8zsLRJsW+17F+0zyFYngKBXgKxecp7K/lHlGgtWP9pjkKxXAUCnAUis9ROKMn21E01mOan1AMP6EAP6H4/IQ9lolnyFeNuQlFcxOK4SYU4CYUn5twni+btyrmJRTNSyiGl1CAl1B8XsLu2/t73aBEGLPmJBTDSShw4rn4nIQzau6edkrEekzzEYrhIxTgIxSfj7A9774NdY31mOYiFMNFKMBFKD4XYc8xxDPMNWIeQtE8hGJ4CAV4CCXgIQgfRWY9MprKeL6/ZTILkjbKYDluG63byOg2zOjyeQnM0jZPjgrUINZvmpdQDC+hAC+hBLyEraLkV3gqDCXjNtA6znARCmb0+VwE8cjCzRCOCtYg1nOaj1AMH6EAH6H4fIR7v43rVzga+HbGek5zEorhJBTMIfU5CeKRhZvB2dYg1nWal1AML6EAL6H4vAQht7BkGcl967CDF3MTiuYmFMNNKJhj6HMTxCNXYck0W4NY52l+QjH8hAL8hBLwE/bzX7/CrYed25ijUDRHoRiOQiEcc329J9kJkiOwOSpQg1j3aZ5CMTyFAjyF4vMUxKPUgJvwVKDusf7TXIViuAoFuArF5yqIR1775nXtKVdhDG0SAFiKdaHmLRTDWyjAWyg+b6Gund2a5Be+YLEu1LyFYngLhVQEb1yN4xm+C7Eu1LyFYngLBXgLxectnJhXDSBXJOYtFM1bKIa3UDDzw+ct7Oed5Pmf1o55C0XzForhLRTgLRSftyA9jpvEnKFEGLPmLRTDWyiYi+DzFqRPnz4OMce6UPMWiuEtFOAtFJ+3IK29Y4bV8pi3UDRvoRjeQsE9Dp+3UFPWfRtbKdaFmrdQDG+hAG+h+LyF83yT6dsxb6Fo3kIxvIUCvIXi8xbqph4k+5xjnad5C8XwFgrwForPW6iyv7qfM3qOY9b6zvAWCu7r+LyFM3ax7WGxrtO8hWJ4CwV4C8XnLZzRUzxDXWM9pzkLxXAWCq5l+5wFae0zhsFIEus4zVkohrNQgLNQfM6CjCDiWfWwWL9pzkIxnIUCnIXicxbqh9UXgyF7OOYqFM1VKIarUICrUHyuwmntZp9zrNc0V6EYrkLBObLPVZD3uK79trpmmnXtMdfNW4A+H+s3zVsohrdQgLdQfN6C1GTXDBRDzFsomrdQDG+hAG+h+LyFHftay6pwoirmLBTNWSiGs1CAs1B8zsL2eMtTgJhjfaY5C8VwFgpwForPWaib8LC+ZTgyxPpMcxaK4SwU4CwUn7Mgnuva2a+QRxFzFormLBTDWSjAWSg+Z+H0adu3Y85C0ZyFYjgLBTgLxecsnLdL3roMJcKYNV+hGL5CQeUR8BVWnoyQHbC1Y75C0XyFYvgKBfgKxecr7D59rVyhKs8d6hzrNM1ZKIazUHCs9DkL5+0q5r2OOQtFcxaK4SwU4CwUn7NQc3q0OjzvWKdpzkIxnIWi2s7XafJ2bZIHeI51muYsFMNZKMBZKD5n4bzPMqJAT4t1muYsFMNZKMBZKD5nYT/n/ZZBzLFO05yFYjgLBTgLxecs7Jh3X4e6xjpNcxaK4SwUHI19zsL5YjQbc6zTNF+hGL5CAb5C8fkKMooepQB1jXWa5ioUw1UowFUoPldhe76dvh3rNM1TKIanUICnUHyewunT8j43KBHHrHWa4SgU4CgUn6MgHI16S2sLUwLGsliXaY5CMRyFAhyF4nMUxGMVhoRbg7gNtD4zHIUCHIXicxTKw7PUpEJ+TMxRKJqjUAxHoQBHoUQcBc3RqOu/VZ+N9ZrmKBTDUSjAUSgBR+F4XL/CkoCSsW7THIViOAoFOArF5yiIxypMCbcGcRto/WZ4CgV4CiXgKTw8S00q5FPEXIWiuQrFcBUKcBWKz1WoK5uhrv054WoA0aPEfIWi+QrF8BUK8BWKz1eocjP4owYV9t1izkLRnIViOAsFOAvF5yy0NT9vsjrS0HMcu9ZzhrNQgLNQfM5CXevrde30VMhyiDkLRXMWiuEsFOAsFJ+z0NZa477nVUgPMH7HvIWieQvF8BYK8BaKz1uoK9egyioYnPaNeQtF8xaK4S0U4C0Un7dQ1y5nZWl99BzHrHWd4S0U4C0Un7dQ107Ofu5w2jfmLRTNWyiGt1CAt1B83oL08bp2N1XfjHWd5i0Uw1sowFsoPm+hyp22a2e3rd2MBiu9MXehaO5CMdyFAtyF4nMXKktfX+857GLE3IWiuQvFcBcKcBeKz12oK8+iykwR3+9Y32nuQjHchQLcheJzFyo33dMqjGmxvtPchWK4C6Xh+ODqu/q4QbrBemvMWyiat1AMb6EAb6H4vIW2VvSbrEEyeo5j1nrO8BYK8BaKz1vYI4rsHcFJyJi3UDRvoRjeQgHeQvF5CzKO7xooz3HMWr8Z3kIB3kLxeQvnPU7Wc6zbNG+hGN5CAd5C8XkL+ztdne91rNc0b6EY3kIB3kLxeQvSw86Ist9ninkLRfMWyPAWCHgL5PMW9gjSjFKgmLdAmrdAhrdAwFsgn7dwWtm0NsW8BdK8BTK8BQLeAvm8BflWVck+qFDXUJeR5i2Q4S0Q8BbI5y1sj6JN0HOoy0jzFsjwFgh4C+TzFk5rN/ucQz1GmrdAhrdAwFsgn7dwxmvR43xKhHqMNG+BDG+BgLdAPm+hED88Q8yhHiPNWyDDWyDgLZDPWzjjtXw5oG+Heow0b4EMb4GAt0A+b+GMnqKKoLVDPUaas0CGs0DAWSCfsyAe5TsN6pdizgJpzgIZzgIBZ4F8zsJRBlsJQok45qJjfuowAs4C+ZwFUUNbGeAYFuow0vwEMvwEAn4C+fwE6WFbm+AXI9RhpLkJZLgJBNwE8rkJEuv+ZmHMoQ4jzUsgw0sg4CWQz0s43+dkR89Qh5HmJJDhJBBwEsjnJJwZncQOfTvUYaT5CGT4CAR8BPL5CGd+teeWUCKOueqYnzqMPth2vg5LegxT73Oow0hzEchwEQi4CBRwEZKsGchXco9lWiVtPS5/T1SUPCV4J0L9RpqnQIanQMBToICnsN+JVVO53xXG/ZirQJqrQIarQMBVIJ+rIB6b3H25WSJYg7ANNF+BDF+BgK9AAV9hs0SKqgms2FDMWSDNWSDDWSDgLJDPWWiXeNZUE+CpUMxbIM1bIMNbIOAtkM9baHLT6H7+0h+gBrHO09wFMtwFAu4C+dyFJiOUfJkKeo5j1zrPcBco4VP0dd5aY25r76Fl6HmxztPcBTLcBQLuAvnchSY673HrLl1Ygzh2rfcMf4GAv0A+f6Flued39fmzzk4xf4E0f4EMf4GAv0A+f6Gt3c2W5Xmj5zhmrfcMf4GAv0A+f0Fu2z3PHVo71nuav0CGv0DAXyCfv7D7+Nrxa2e1k2L+Amn+Ahn+AgF/gXz+QnvcHNxk7ZGh1WPdpzkMZDgMBBwG8jkMbe3cN/nGMbR6rPs0f4EMf4GAv0A+f6GtPIm29lfV+x3rPs1fIMNfIOAvkM9faGs3+/Q0GNNi3af5C2T4CwT8BfL5C23tIcrI0mDuGvMXSPMXyPAXCPgL5PMXGstzXp4zeo5j1rrP8BcI+Avk8xf2iCJ3l+NbEes+zV8gw18g4C+Qz1/Y4/jteY5j1vrN8BcI+Avk8xf2eyzPGTzH/AXS/AUy/AUC/gL5/IX9nb7t9zrmL5DmL5DhLxDwF8jnL+wetkeU8z7H/AXS/AUy/AUC/gL5/IU9ghSrFGL+Amn+Ahn+AgF/gXz+wmllp7VjXab5C2T4CwT8BfL5C/tbRfLtalAijlnrMsNfIOAvkM9f2B5Fm6DnWJdp/gIZ/gIBf4F8/sJubfGMzznWY5q/QIa/QMBfIJ+/cMZr0eNQItZjmrtAhrtAwF2ggLtwPT1DD4v1mOYukOEuEHAXyOcunPFa3mfwHOsxzV0gw10g4C6Qy10AFZSNGop5CqR5CmR4CnThKOzrMfEo32lQvzFHgTRHgQxHgYCjQD5HYXuUGsDacsxPIM1PIMNPIOAnkM9P2GpIlAGOYbEO03wEMnwEAj4C+XyE3cPY+WLEOkzzEcjwEQj4COTzEXas4hljjnWY5iOQ4SMQ8BHI5yOc73Oxo2eswzQfgQwfgYCPQD4fYc/oxHOFvh3rMM1HIMNHIOAjkM9H2POrsueWUCKOWesww0Ug4CKQz0U4ntm8zzEXgTQXgQwXgYCLQD4XYZNZZGZX9lj2UEnSD+RrKipKeDsNPIVtpXkKZHgKBDwFCngK31E3rZEo7bkpjL4xV4E0V4EMV4GAq0AuV0E8Juknh+SCNYjbQOs5w1cg4CtQwFcQZgyrmqStOKr8nvEi5i6Q5i6Q4S4QcBfI5y60tcPb1q52k72pKv+dwULcNlr3GQ4DAYeBfA5Dkx0iWT1v0DNj3ac5DGQ4DAQcBnI5DP1lSw/P0Pqx7tPcBTLcBQLuAvnchfW85fkn/CrH3AXS3AUy3AUC7gK53IXDkJHxQZjewt/A1o91oOYwkOEwEHAYyOcw7Fbfzx96XKwDNYeBDIeBgMNALofhPHehIsC6XMxhIM1hIMNhIOAwkM9hOM9dYgfPsQ7UHAYyHAYCDgO5HIa03u+01y4ajH2xDtQcBjIcBgIOA7kchhOrjDQYc6wDNYeBDIeBgMNAPodheUx7bMOYYx2oOQxkOAwEHAbyOQxnVGUbc6wDNYeBDIeBgMNALocBYi12ZIl1oOYwkOEwEHAYyOUwwFvl9O1YB2oOAxkOAwGHgXwOwx5B9lgGdY11oOYwkOEwEHAYyOUw7Jhl9MRvV8xhIM1hIMNhIOAwkM9hWB6hBug5jFlzGMhwGAg4DORzGNaoCc/7fDVjDgNpDgMZDgMBh4F8DgPJnUhyf8SFnuOYtX4zHAYCDgP5HIbted/XDp5jnaY5DGQ4DAQcBvI5DCdmuRMxQ4k4Zq3LDIeBgMNAPodhe5b7vCFzJ+YwkOYwkOEwEHAYyOcwLM99erSfN5SIY9a6zHAYCO4NJZ/DsD1/itTglIh1meYwkOEwEHAYyOcwSGt/PrsGUCKOWesww18g4C+Qz1/4CL1GVhBA+cf8BdL8BTL8BQL+Avn8hXuTe6wOi/kLpPkLZPgLBPwF8vkLErMoQMj2ppi/QJq/QIa/QMBfIJ+/sD3veRb07ViHaf5C/08TM2EE7zFvJXhKxDpM8xfI8BcI+Avk8he25vyskeSDI0mswzR/gQx/gYC/QC5/4XhOuwanRKzDNH+BDH+BgL9ALn/heL52DaBEHLPWYYa/QDf2VE+HQcxJanBKxDpM8xTI8BQIeArk8xSWR6lBwhldzFMgzVMgw1Mg4CmQz1PYnmV+BXsKMU+BNE+BDE+BgKdAPk9he2aJuUCJMGbNUyDDUyDgKZDPUzgxL6UPq9wxT4E0T4EMT4GAp0A+T+HEvGihoHpjngJpngIZngIBT4F8noL06byUPs5KYp4CaZ4CGZ4CAU+BfJ7C9rzGbZwbxDwF0jwFMjwFAp4C+TyFE/NmtJ4SsQ7TPAUyPAUCngL5PAWhwcp3GnVyzFMgzVMgw1Mg4CmQz1MQj3mTUqFErMM0T4EMT4GAp0A+T2HHvLJD7wv6dqzDNEeBDEeBgKNAPkdhe165mR9QvTFHgTRHgQxHgYCjQD5H4d78QqFGwugZ6zDNUSDDUSC4R4ACjoJ43qxliDnWYZqjQIajQMBRIJ+jcDwLwxHeqliHaY4CGY4Cwflx8jkKb7PYmKNAmqNAhqNAwFEgn6PwNouNOQqkOQpkOAoEHAXyOQpvs9iYo0Cao0CGo0DAUSCfo/A2i405CqQ5CmQ4ClTwy+Pui77NYmOOAmmOAhmOAgFHgXyOwtssNuYokOYokOEoUMFR2D9f8DKLjTkKpDkKZDgKBBwF8jkKb7PYmKNAmqNAhqNApCJ4G8O8WWzMUSDNUSDDUSDgKJDPUXibxcYcBdIcBTIcBQKOAvkchbdZbMxRIM1RIMNRIOAokM9ReJvFxnwE0nwEMnwEwswr8nTY6yw25iIMY8qz0WHARSCXi/A6i415CKR5CGR4CAQ8BHJ5CK+z2JiDQJqDQIaDQMBBIJeD8DqLjfkHpPkHZPgHBPwD8vkHb7PYmHtAmntAhntAwD0gn3vwNouNeQekeQdkeAcEvAPyeQdvs9iYc0Cac0CGc0DAOSCfc/A2i435BqT5BmT4BgR8A/L5Bm+z2JhrQJprQIZrQMA1IJ9r8DaLjXkGpHkGZHgGhPtePs/gbRYbcwtIcwvIcAsIuAXkcwveZrExt4A0t4AMt4AI287VYW+z2JhbQJpbQIZbQMAtIJ9b8DaLjbkFpLkFZLgFpO28xuzMYmNuAWluARluAQG3gHxuwdssNuYWkOYWkOEWEHALKOAWvMxiY24BaW4BGW4BAbeAfG7B2yw25haQ5haQ4RYQcAvI5xa8zWJjbgFpbgEZbgEBt4B8bkGVW4hXXiGub8TcAtLcAjLcAgJuAQXcArk3c9UggdKPuQWkuQVkuAUE3ALyuQVJTphfa14FSj/mFpDmFpDhFhBwC8jnFuw7Q+V2WmylWIdpbgEZbgEBt4B8bkGS3X6ZU4ImibkFpLkFZLgFxNhfXB12PH+fd4KzqjG3gDS3gAy3gIBbQD63QJ5zWidS8FxWzC0gzS0gwy0g4BaQzy1Ia+zankENxdwC0twCMtwCAm4B+dyC7XmpoQS5sTG3gDS3gAy3gIBbQD634HheMcOMLuYTkOYTkOETEPAJyOcTnNZeY1iGmGMdpvkEZPgEBHwC8vkE4rms89gFv8+xDtN8AjJ8AgI+Afl8gu15jSS4/xDzCUjzCcjwCQj4BOTzCeTeehnL1FsV6zDNJyDDJyDgE5DPJyj7dmlzYz7FfALSfAIyfAJiFcHruC23x8NzjvkEpPkEZPgEBHwCcvkE+ZPWN+p7w4NaiYv5BKT5BGT4BFSVHT8nbmWmpeUZ1gxiPgFpPgEZPgEBn4BcPoHEevG68QdXXGMuAWkuARkuAQGXgFwuwYlVYoe1oZhLQJpLQIZLQMAlIJdLIGu8Z8UV6xrrMM0lIMMlIFQYPpfgPGe2nmMdprkEZLgEBFwCcrkE+cSapadBiThmrcMMl4CAS0Aul0DW8s/K+u5xUINYj2k+ARk+AQGfgHw+Act7LbFjT4v1mOYTkOETENz5Ty6fIO/Vx4+sCUrPg5KxLtOcAjKcAgJOAbmcAhhR5P3OUCKOXesywykguPOdfE7B6ev7bTslYl2mOQVkOAUEnAJyOQVnHN9vGfS0WJdpTgEZTgEBp4BcTkF+vN/6Oce6TPMJyPAJCPgE5PIJzjcrJfucY12muQRkuASEd5K5XILTw3YNoESsyzSPgAyPgIBHQD6PgIULLc9776Dt1l9r/+up3Ov9z1Jj+W/42sZ6TvMLyPALCO+sc/kFee0J9N9VU/xixHpOcwvIcAsIuAXkcgt67M+Y4Z2I9ZzmFZDhFRDwCsjlFRzPWWI+PTPmFJDmFJDhFBBwCsjnFPD2uH7hWxXzCUjzCcjwCQjvoHT5BHn3uCw76Wfsi7kEpLkEZLgEBFwCcrkEee205Y+st1zoOY5Z6znDJSC4+51cLkHee3zr9OxHdqMOAYliPgFpPgEZPgEBn4BcPgH0tPUL3+eYS0CaS0CGS0B4y53PJdg97fS4UyLWdZpLQIZLQMAlIJdLcEaU7DzvWNdpLgEZLgE1fFd8XSc9bD93eM6xntNcAjJcAgIuAblcAni+2T7nWM9pLgEZLgE1Zef1vd6jKLR2rOM0j4AMj4CAR0Auj0Ce88W7j0NdYx2neQRkeASEtyG5PAKJWfr4+OqeErGO0zwCMjwCAh4BuTyCvEeSLCMJfDliHad5BGR4BAQ8AnJ5BPDFWL/Yt2Mdp3kEZHgEBDwCcnkEMIZl+z7HOk7zCMjwCAh4BOTyCMZbpD1jzLGO0zwCMjwCAh4BuTwC8XwdfQbPOdZjmkdAhkdAuCPv8ghOzHe2PSzWY5pHQIZHQMAjIJ9HwGvNeL/PWxlKW6wcDtgXizkFpDkFZDgFBJwC8jkFn7Uf9pHsv3Xanc96Ose8AtK8Aja8AgZeAfu8AvEoNfhUqQlDyagNWHML2HALGGZj7HMLxONn7UoyOzUI9RtrfgEbfgEDv4B9fgGzrsFHmPanH3DMMWDNMWDDMWCYnbHPMRCPn7XqzWt3WtUg1HGseQZseAYMPAP2eQbH49qJZ6hzqONY8wzY8AwYZlvs8wzEo9QgfeC5hzqONc+ADc+AgWfAPs/gZolVYoe3LtRxrHkGbHgGDDqBfZ6BPOf0Yes51HGseQZseAYMPAP2eQbi8dSgQYk45lvH/NRxDHqQfZ5BWuew08oFgFvAOeYZsOYZsOEZMPAM2OcZiEepwY2ja6jjWPMM2PAMGHgG7PMMpGdJT1OtHeo41jwDNjwDBp4B+zwDeavkeaePvGXwdoV6jjXXgA3XgIFrwD7XQDymj7xdzdYg1HWs+QZs+AYMfAP2+QbiUWqQJKu/waga6jvWnAM2nAP+4Bjp758uj2mtx/LasVc1CHUea94BG94BA++Afd6BeJQapEtqAnUP9R5r7gEb7gED94B97oF4TDJ/KzKTXOpr7aezfHWxZqEeZM1FYMNFYOAisMtFyB8SJbpmHARPJdR9rPkGbPgGrEY2f32OxOOqwWFocsw1YM01YMM1YOAasMs16K2/Wp3W7+GHcswzYM0zYMMzYOAZsMszGDGu571+CTzH+k5zDNhwDBg4BuxyDPKnZN3jzi14HPMLWPML2PALGPgF7PILTl8v63kXeM6xntPcAjbcAgZuAfvcgiQzyuI851jPaW4BG24BA7eAXW4BxJrkvT8lYj2nuQVsuAUM3AJ2uQXd48pi+MiIAjHHek7zCtjwChh4BezyCs7btEcSKBHrOc0rYMMrYOAVsM8rSLIut254TBlaO9ZzmlfAhlfAwCtgn1ewxnPoadDasZ7TvAI2vAIGXgG7vIIzasp7fTKxOOYVsOYVsOEVMPAK2OUVnBFExm9QkjGngDWngA2ngIFTwC6n4IyeJM8b6hrrOM0pYMMp4IQ91V+XE8+l2Lcq1m+aU8CGU8DAKWCXUwDPt9gvRqzbNKeADaeAgVPALqcAPCb7fY71muYUsOEUMHAK2OUUwAgi4zb07VinaU4BG04BA6eAXU4BeHTe51iHaU4BG04BA6eAXU7BeZv29xlaO9ZhmlPAhlPAkLnHLqdAtIhoT9Gioya7ZMwrYM0rYMMrYOAVsMsrgBo0qQmUCGPXvAI2vAIGXgG7vALQYdm81zGvgDWvgA2vgIFXwD6vQL7PSbQJr7etStZ4AgtxG2h9ZvgFDPwC9vkFqwZSIzWqxvwC1vwCNvwCBn4Bu/yCHuuKuSVpAygRx6z1meEXMPAL2OUXSJ56XmvP/Rd6XKzPNL+ADb+AgV/ALr9Anu953kK2xOcd6zTNMWDDMWDgGLDLMTgxSxsw9PlYp2mOARuOAQPHgF2OgcR8+jyMxzHHgDXHgA3HgIFjwD7HIMn3uzqeY52mOQZsOAYMHAP2OQb7/EnNtrVjnaY5Bmw4BnzhW+rrtCpnMeSUgDmbwTHPgDXPgA3PgIFnwC7PAPp2tn081muaZ8CGZ8DAM2CXZ3BOwEirwx5CzDNgzTNgwzNg4BmwyzOAEUVizlAijlnrNcMz4AvHRn+dbffx/ZadErFe0zwDNjwDBp4BuzyDM47vtwtaO9ZrmmfAhmfAF76lvl7b47jTt2O9pnkGbHgGDDwDdnkG55tVk33OsV7TPAM2PAMGngG7PIPTw3YNTomYZ8CaZ8CGZ8DAM2CfZyCn+faZK3m/D7+CYz4Baz4BGz4BA5+AfT6BeEyikopTg1i3aT4BGz4BA5+AXT7BVRcRQTxLTbruhZJxG2i9ZvgEDHwC9vkEVVZ4Vk2upSRR7cY8AtY8AjY8AgYeAfs8AqnBtXY3LmHmwogTcwhYcwjYcAgYOATscwjE4yV88NJsDWIdp3kEbHgEDDwCdnkEfbBKyrPU5EpYg7gNtI4zXAIGLgH7XIJr7atc8nWFsS/mErDmErDhEjBwCdjlElyVtkepAZSIY9Y6znAIGDgE7HMIrnWGoy4WV4U1iZhDwJpDwIZDwMAhYJdDsFv51AA9xzFrHWc4BAwcAvY5BGXFWnarQ4lYv2kOARsOAQOHgF0OwfYoNbgu6NuxftMcAjYcAs4qAv85s/Jc8BsX6zfNIWDDIWDgELDPIZCe1T47digRx6z1m+EQMHAI2OcQ7JirxAzvc6zfNIeADYeAgUPALocAPK8TrrCiG3MIWHMI2HAIOONTc/dFt+e1AlSwlWL9pjkEbDgEDBwC9jkEx/O6geIDMcf6TXMI2HAIGG5pYZdDsD3T6mE4Y485BKw5BGw4BAwcAvY5BOL5yvI+JygRxqw5BGw4BAwcAvY5BDJqbs/wnY45BKw5BGw4BAwcAvY5BNvzWuW6GGKOdZrmELDhEDDcTMM+h2B7Xnv71w2eY32mOQRsOAQMHAL2OQTb88rlvAg9xzFrXWY4BAwcAvY5BNuzKANYQ445BKw5BGw4BAwcAvY5BCfm9ZxhfzvmELDmELDhEPCNb6evw3YPkz5+RpKYQ8CaQ8CGQ8DAIWCfQ3Dequ/MP527IznmELDmELDhEDBwCNjnECzPw+Oai4LnWIdpDgEbDgEDh4B9DoF4/nz3CjLmH8QcAtYcAjYcAgYOAfscghOzrNzCc451mOYQsOEQMHAI+r+/x7yeM2SHxhyCYUx7NjGDtvE5BDvmlUFXYZc55hCw5hCw4RAwcAjY5RAMT0rpq29VrMM0h4ANh4Axp9flEMDcYtUAdqNiDgFrDgEbDgEDh4BdDsHxvLLAKijAmEPAmkPAhkPAwCFgl0NwPMtqFrZSrMM0h4ANh4CBQ8A+h2B7ZvmF1o51mOYQsOEQMHAI2OcQHM8sin+XiDkErDkEbDgEDBwC9jkEbzO6mEPAmkPAhkPAwCFgn0PwNqOLOQSsOQRsOAQMHAL2OQRvM7qYQ8CaQ8CGQ8DAIWCfQ/A2o4s5BKw5BGw4BAwcAvY5BG8zuphDwJpDwIZDwHAPEPscgrcZXcwhYM0hYMMhYOAQsM8heJvRxRwC1hwCNhwCBg4B+xyCtxldzCFgzSFgwyFg4BCwzyF4m9HFHALWHAI2HAKGe/rY5xC8zehiDgFrDgEbDgEDh4B9DsHbjC7mELDmELDhEDBwCNjnELzN6GIOAWsOARsOAQOHgH0OwduMLuYQsOYQsOEQsBqR3nSYO6OLOQSsOQRsOAQMHAL2OQRvM7qYQ8CaQ8CGQ8BqXAjWw+IZXcwhYM0hYMMhYOAQsM8heJvRxRwC1hwCNhwCVt+8YD0sntHFHALWHAI2HAIGDgH7HIK3GV3MIWDNIWDDIWDgELDPIXib0cUcAtYcAjYcAgYOAfscgrcZXcwhYM0hYMMhYOAQsM8heJvRxRwC1hwCNhwCBg4B+xyCtxldzCFgzSFgwyFgwqcW6LB4RhdzCFhzCNhwCBg4BOxzCN5mdDGHgDWHgA2HgIFDwC6H4HVGR7EO0xwCNhyCURbsvMbszOhiDgFrDgEbDgEDh4BdDsHrjC7mELDmELDhEDBwCNjlELzO6GIOAWsOARsOAQOHgH0OAa3dQVrjdzu3J3DMIWDNIWDDIWDgELDPIRCPUoOcoIfFOkxzCNhwCBg4BOxzCHLSnumG1o51mOYQsOEQMHAI2OcQtHUfqnAn6ELPccxahxkOAQOHgH0OwY553dtAGZ5zrMM0h4ANh4CBQ8A+h2B7XrehUIbnHOswzSFgwyFgwnHB1WHHs/xCa8c6THMI2HAIGDgE7HMIjufV2qB6Yw4Baw4BGw4BA4eAAw6BeF6qN4MOizkErDkEbDgEDBwC9jkE4jkvEhXmRMUcAtYcAjYcAgYOAQccgpXNsz1D3445BKw5BGw4BAwcAg44BOJ59W3MiYg5BKw5BGw4BAwcAvY5BNvzymjCzKOYQ8CaQ8CGQ8DAIWCfQ7A9r5PBmPsScwhYcwjYcAgYOATscwi251ta/bxVMYeANYeADYeAgUPAPofgPOfVx0FLxBwC1hwCNhwCZnxqrg47nqWPH00ScwhYcwjYcAgYOATscwjOW/XNVMXzdTGHgDWHgA2HgBnbztVhy/Pw+P3F9znWYZpDwIZDwMAhYJ9DsD2vW6wwEznmELDmELDhEDDjO+JzOXfMq7XhWxVzCFhzCNhwCBg4BOxzCE7Ma0YH6yQxh4A1h4ANh4AZ+4uvw8TzWidp+D7HOkxzCNhwCBg4BOxzCFreatd8q2IOAWsOARsOAQOHgH0OwVaAUgNQBjGHgDWHgA2HgIFDwD6H4GjP5Rn7ZKzDNIeADYeAgUPAPodge17jdsP3OdZhmkPAhkPAwCFgn0NwWltqAK0d6zDNIWDDIWDgELDPITgxy3OGtyrWYZpDwIZDwMAhYJdD0GXYWidZN/LhrTUxh4A1h4ANh4DxZg+XQ5DljpAkXwz4osccAtYcAjYcAgYOAfscAjlHv2M+dzlzzCFgzSFgwyFg4BCwzyFYq46y7tl/Tw+LOQSsOQRsOAQMHAL2OQSnlZN5zjGHgDWHgA2HgCs+NfdejCTjtjxvWA+LOQSsOQRsOAQMHAJ2OQRXXeds13qYWn2MOQSsOQRsOAQMHAJ2OQT5I2eM24odTk3EHALWHAI2HAIGDgEHHIImscpzhrrGOkxzCNhwCBg4BOxzCM5zll9o7ViHaf4AG/4AA3+AXf7AeZ/XHfwVdspi/gBr/gAb/gADf4B9/kCSWyV3q0OJWIdp7gAb7gADd4Bd7sAYOeRtMjsoMXeANXeADXeAgTvALncgyw1rldYv7KDE3AHW3AE23AEG7gD73IHlWdb01T5GzB1gzR1gwx1gzEvxuQMyap73GTzHOkxzB9hwBxi4A+xzB854vWsAJeKYtQ4z3AHGdXKfO7DHaxlJYC4ZcwdYcwfYcAcYuAPscgfObtHar9Ke45i1DjP8AAZ+APv8gHV7nIwkQyGcErEO0/wANvwABn4AB/yA9lBD+H2OdZjmB7DhB3DF/uLrsJQens/oGfMDWPMD2PADGPgB7PIDzk6ojGGwvh3zA1jzA9jwAxj4AezzA2T3N5092VMi1mGaH8CGH8DAD2CfH7BHz7bHMigRx6x1mOEHMPAD2OcHnO+z7L3Dc451mOYGsOEGMHADOOAG7Oe832soEcesdZjhBjBwA9jlBpyxa49lUCLWYZobwIYbwMANYJ8bIMpAbkS8qpyrg54W6zHND2DDD2DgB7DPD5A7OY9SgBKxHtP8ADb8AAZ+APv8gK3H5HuNMcd6TPMD2PADGNcgfH7AmdFJDWBEifWY5gew4Qcw8APY5wckoemRnUfH/ADW/AA2/AAGfgC7/IDjUWoA6jfmB7DmB7DhBzDwA9jlB1xtzWYrJ/3VXF9RUUtbHUsW31rt6IMgeIjbSOs3wxtg4A2wyxvYNb3kFPu6EbnBXDTmDrDmDrDhDjBwB9jlDmyP17pToF3ZqUHcBlrPGf4AA3+AXf5A91SUZ6lJxu99rOs0h4ANh4CBQ8Auh2B4Wh7XCu4lv1D3WN9pHgEbHgEDj4BdHsHepdjrbasGGb/Csc7TXAI2XAIGLgG7XIKc1i2hSd5auNEh5g+w5g+w4Q8w8AfY5Q9kuTclFbNbUWPuAGvuQDXcgQrcgepyB3JaNzi0xdBJMl6cTIoacweq5g5Uwx2owB2oLndA9oZkd+qC2ydqzBuomjdQDW+gAm+gurwBaO30fN415gxUzRmohjNQPyoCN+bF3tjP/ewd1JgvUDVfoBq+QAW+QPX5Ao3keUvM0NNCvVc1X6AavkAFvkB1+QL9Gyj7YbJXBDGHeq9qvkA1fIEKfIHq8gWO51tihrqGOq9qvkA1fIEKfIHq8gXgOcsvtHao86rmC1TDF6jAF6guXyAnWVfdsUNdQ51XNV+gGr5A/Sg7ft6KxLpau0CJUOdVzReohi9QgS9QXb7AeH9X3159nGAMC3Ve1XyBavgC9aMi8J+zfDHMnm+N+QJV8wWq4QtU4AtUly9wxq79VqHnOGbSMT91W4Wbk6vLFYBRc9fglAj1WtU8gWp4AhV4AtXlCZxRUzwXGLdDnVY1R6AajkCFux+ryxE4O+uyt4+eQ31WNT+gGn5ABX5AdfkBoEmyfKehRBxz1TE/dVmFm7uqyw04uRvyPmeIOdRjVXMBquECVOACVJ8LcFrb6LEacwGq5gJUwwWosE5bfS7A7tvb82ntmAtQNRegGi5ABS5A9bkAO19FWhvGsJgLUDUXoBouQIXVlepzAfboSSZ7pMZcgKq5ANVwASpwAarPBThfSck7hLrGOkxzAarhAtSk7Pjvs7T2fq9PiViHaS5ANVyAClyA6nIBzti1WxvqGuswzQWohgtQYSWp+lyArQxWpnom0d3Q02I9pvkA1fABKvABqs8HSJL1t5UC1DnWY5oPUA0foOIXyOcDnNmNPPczosR8gKr5ANXwASrwAarLBzjjd7Hzq5gPUDUfoBo+QFX9xl93WycF284Kg5hjPab5ANXwASrwAarLBzgedw2grrEe03yAavgAFRWlywe4iEQJSi6exJ61WhJ1fN6B8Zsaeoj1m+YJVMMTqMATqC5P4Cprxb985Pdbk3utSZV1nvdu8AWKdZ3mDFTDGajqXXPX46rcLic79h+heew7uo+FWOdp7kA13IEK3IHqcgfOHc3lQQGQu/lxtI51n+YQVMMhqMAhqC6HAGoidA9og1j3aQ5BNRyCChyCKhyC//j7//3jP//ff/39v//3f/7rv//xt7+V66fUMlJd+jxw3C2SrvbTeh+vtY67Rq4/d/sBK8W3kn+61ON23/2bx59rWqljefjOA071tMKRlbE+18Xc50N3F0fDyuCgtpLHBRj3w0pzrdD9MzhiKQ2QUs30p39Pf65SevVquzIXbWUpR8dKo9J6b+hTx8rdCP/0PjrWUDnf/KhK8xuXys9n/HOXq7W7j1PDSrnrPa5jbCPZUFvxG9exQj99GBk7vH2IaY/GbX7j9oBqyb32n94efN3TSpdXfZgZR5VNXcLGvVv/p5Yu9scuT1dB3+5CZTznpKwIKsFYydNKHcy7/hhJWeHWhwJtJWjd3OvfPr18Gzeol29EvWF7Q133eJm0laB182zdgYltfSCn1bq9LlzaRQ8bQdtaG+M5jzvWeu3u9LQStG366d+0Vu8eUiG6ZsfNdyl1PKDxkVFWUtC26adHn9N4GHmc706p/XCpd21p3Kl+PawEbfv5uWov1EaGA1/TSB+a+yt095fqKg8jQdN+frocoPG61DwyJUZAlcYNrfc19hcfVoLG/fTH8bnKXXpLtvvbLD20ccPsxak9Awoa9/NTxjMaV7r2OOYTGlfD1sEyGWJVGbmCtjVGRlfJ/UmXT2+sRzxX2LS5K/j+F1p/V7+99jMYIl0nzMNR2kjYtHNIYO5jJFP65T28ggG3zni6ic+n5Nm0r1b8pi3809/lror6oP0ZV2CPiAYiuv/TB6z0aNvst+2qS/8O9QlPb+D5hK5xeXt/pQbN+WEl+Jy1n09ueYzUlPJs3f4mXnmMWKWSsRJ8zoaV3HtdH1XWg64/fdzsX4T+f8dmlrYStu59zbXG/q6OWcl4iT6zddsYhB+jQg5at3umDw/MdGo187Ryj0/r6P/l84joDlq3t8KwcvUuM89FDStljnIt3fez/99B65afO7er1Np6D5njHFih5zh3B63bP619mLvuuwcxDiB9I2qfrh54hqitBK17/xTOdWTalTLu5/+2bq69VfoU6n62S9C6uff3cZVZj+j7CRkPun+dh/r5lIeREjTu3bvL3bX0RXelu81Od/dRsY/ZvU93Ga+tBI17fweXsQjeh5TT/8u4C6w+WqUEbTu0QlecZRwv7/OM+S72J9X6B5EK1fawEretrsrbsFD8pr3pp1fg6l21dQU1HxBYudqjbclv225lzAnGnaB9jOTv4NI/cL0Xtu9Sibbit+3dPZc+jvT3bijJb7PUcblqV2ITMq2t+I3brdQuCe/+OPr3a+jT2Vv6F7G/iPPknbbiN263QgN0f3UxnQfRa1jpfe3TX9D6GWl92krQuuWnN9mcR/X3+VuV+Sa2Pu4NYpUywn7j5jY+rfO2+P6Nvn4z4rdtrn34/3Qhlq/+vOk7WOaxANvVzGAOPqz4bdut9Mc8Ltzv7/K4/H62bRv3KN65ludnkf227Vb6m0jjuOu4F+L7mR9PuD/53qOfuoX9ts29zPzKd3Vw939mXb5zohHS52GlBo3LP/N6gz576dOI9B2gxs2jaaDDeyUfVsLWvYZU/iZLtO/wP+syxvEufB9Wgp5797col9Z77iC+Xb9ZCXpu7sNCHhDwe2jjHtHVn9o4it3V3T0uRddWgp6bf7oYvcZjLn1Y+87yBk+sP7WRCKZsBLOz+ztAjfWuPs7eetL66CrB3KxPfD9jfjteXhpboiMYmp2/a8j6nIMEc7P+Gvb54Gec3+jTkJvRSp/95McrFMzN7nt+hfp3OHW50b5WuvAfAY6WfRgJ2vUeI1qtY+bcx6RrGulCs/+/bqPeutfmYGrWAyp9gPz0pznG7VGVrr8/fdrbreabn1bC8XbwHVLXxKm38ddK13aNumYdM6KHlaBx+3SuS5GRbdPbtnyFQpfe3cDdhU7jh5WgcelnHAUds6GhJL8Toq4FGw/53V/zh5Wgdfnn0z91XdTf47qzr1Lo71MdSx59UNNvcw4mZ91KH/HnMe3enmOdZExDeqv0EPtI+ZiE52By1q3kAQXvc2i6ebZL1xv9Y9CF4mfcUv+wErRu90xdFA/ln9u3Ktf8PPfaUbofRgKlkHp36bM7nosRXH+zEqiwNPp/17J9cLy/n+cRYh83+yjTR8pHQMHsrL/R17iRYkjp/i/TSBeH/VPQn9nIkdRGgmEh//TXsPf93vHqOBs1R+3UX4BuqWveR0DB9GwKqPzpfa72vvLt/tT/rUugoREfL1E0O1tqu/SRf9yYNK3U78rE+P/1YSWcP/ShaCy19M9qfw1+sRLNzrpS6DNc7vXvGj2PETf11s5EYzGLHpPwHM/OxgZBGSc0cv8iTytdKfSBoX9Xr4dUyNHs7Prh3um61y4NrjXm5rlM2B/UWDfUVoLWvXrrdq2cx9eMxhpUt9KHhd4oAznxsBG07a+Lp/3jNF7N/pEa3IRKx2Q0Uft1JbWb7Mq6m/yMGe3nBpNhl57Lqt3sOFJ3n2XVe0it+2uRPzwX01rGSgarD78usfaeX4bX3hDdc7rAZLg8+b7eOi12cfehrqeKshis+Py6+NpNdq/jn94FPh+IO5jo/b4S+2IyWA36dVl2Bt6fUB8BemPDNmoO5oDva7RjIWKanDO8/jYm6EHBfDA1/Pv5uer7yS8W/Yfzu8X+/p227i/UMRnMFLtJkuWsPC6F+1dM+g/nd5M9bvwb0CuDOeRj6Zvt3PrFZLj6jOvgbNfBp8k6N1bGGjX0ymB2KQva3S6lkqSjr0Xx/g37mhy9bDjFNJ8czDUfa+Rs18hfTAbvjl4wz3bBfHyAfz5EffrVY7+hXwbT0Mfq+WVXz6fJcY1J/cxjnmDyn9occAIfC4s/qXfIPgD22NFkuFPwyxp/15M/fWZPE9hbPzBoBLPVbrJ04T+myfdV5zjUerfqr2f38hlHANQHMZitdivjiDMNRTkW5+cToT4Jngfk+lP60ycVPz2uXv3av7KMFQueSP9O91Ybn4HRaF/hnbrEHKziu3+6//Tvw1jG6P97f4MI8g9yMI/9dXOjt+oQfXd/icbSLVYy3F3oU4s+IKQxbF9rp6OLzv4xKyV/R/HuZMyr+rS3S/VjMtqA/HXbY5rsX4jeKHeGm9drjrYjf9sDmRbnt4NH54SWjLYmf9sQebEYPhvcHbns9sg0OVac+5xEd+1oz1LvlehdjrnbOE3Oj/ZUysfkHcyS+zuBBZ4bJ98PQ2Qy/Nb8YjL8fN3B/Ll3myRfmzYXJ/4Fk5ES+M3kWHzHvwEmwwnKL5tQsclgmv37jlQ3ec2V8v5udo0CgQdz7t+3p3YtB8iMsS2DCfjve1Xd5Kc3RZcKfUKbKwYeTGp+3bhaJvtMtn8yYay8o6m5bGL1L0OfSvHZxBrkx7FyOOMu3L9G9wgbTEbzdL2jRXZHa5ock/8+Qbvr5wKTwdPR21tsN6bmAx/T6f5NLRdDUwZT+DHmYoHHjtnNbybDl+cXk/H7GMzuu8l7hn6PlcP83Nd7NRlM9X832QNXfwNM/lP7hs/A55cnNPnvbiJ2k2V0tLEb1t9YGIGjFYFfdxSnyf46pJGidWMl/83dxTnz/gwJN9K5IeHsjpYHft1qnHXs7/vdJgb2BpP/1L7jZTcev2GPb1Pq01pI8bujHd5fdyHn827z+V1Ku9wv272PWtqvRFTL8N1RBdxvWWAyWCD43WT8OgYLBN1Qn0D0ZhmLW9+p2D9vMhrafjPZOxT+DRiAgxWCx2avO60NTYb7x7jze9md32mya9exj90uiDvaS/51F7hb7C9Yn092sTLWSMFkuNGBW8LVbglPk2n0+z4LAkpRveNdZtwfLnZ/eJrs38reOCNnG7648Zbz+2bxtDhwt5zquMwbLEbvjipQHia5vZgMFgh+Nxl39GCBoOuez5gh9dFyrFzTv2Qyend+M3kl/TfAZLBp/dsu/IvFYAP71y35bjL1yPvf6p8JPHV5R7vZen/+svvz02Svbp9SjSVA6JXx1vYvm/XTZP+W9UrT2MIBk0EWgd65z3bnvpu8+lRgzEfHaRZoy2Cx4PfAuzboo99Yrx/7xqhWg9WCRy2TrWVvwrGe0/qb8OmjKtQyWC3oJnur9Yr07+5nbLvNJz7Gz6sL/89j8/cOFghGykIfuMeFIr2ffb67eZX62NbGrs0YOPpn+zO36j9D8IPFMK3jHoXHJk+P9KtXuhrrn4U+lCUa709Oo/XudBHeHDiWZ/6ZvAp65lXw9xnPka7PBz5oMXxd4hyLsdP07Yg8ZqldveJBzhIuEKgC9yPhYkq/0GQ4mP1iMhzMSrhA0JUaJxpfl/7J+ddMRnOc30z2DwP+DQw8TGzA5JVsk1dik9E+vM5kYZvJ0k1SV3K9R5QeOxzQLNGm/C9pLdNg1+ljxsM3LACWaH/+Pcdlxjyk5hwNuYG9lycDBbTBT73eTIYq4BeTcf8JFgf6oIIbpuVfMhm9OL+ZDHdpS7S//2vy0DTZZ/n965r6FBAshmsD+Pe1Qf7OmAKD4ezm3WDcjuHCQBdo3UI3wONE8L9iMZzbvFucIvL8BXgLg2WBt3wseTChyX8zOWu+NmMSX/qLj2vcJVgW+D1Ta5rs8qR/HEvvodAhg3WBR9pWtWlbM+67jPSrTOmDJv+pHK76zOH6WryI7nFSscKXuwTLAr/nc80Z3UhMufpMP6tK/lPJXTa3a1ocVEnukwrcVCzBqoAkeqU8poApQ6LXZyxmzLivn9YnpuMa/ws2FUuwKvDI+rpt1tc0OU5P5gFtuuHjEKwK/J4CNk3O+896O+SSweS/mQ82LfYv7tiOogJ3CpUwbUAX0Cb7LP7NZPjF+cVkPAiFeQP3fJ974/Wv9V3/JZPhF+cXk300x78BY0awKvB7ot2LyTB3D7Pubpt1N032ka2PLKV/4OF1DJYFfk3Bm1+xuSedmD6wGlKCVYHf8/HmGmp/T/qgNpi38O4EqwK/JuetZb+xFd8HAFj2K8GiwCNT737k2LUG69t93sgZ4w71ABZ4pu3dbxZ/2yoILMbdPFgTmJuBn7mt2h9vfYb9ajF8cd4tzp2h8xfg0UQnk39Nf3wxGW6y/ZILOTfZ+qe6jBWdesGwFqwIPBIj2SZGTpNjjtRFau+T0MuDFYFHlmSzWZLzXbz6iDHv64RMlhKnzL+mTE6DfWgYmzxj0gQGwz02TGXMj2THmWYUJDuWYHVgmjy5jOWR7Jgx27GbvRLIlmB5YOaqQS7jI9uRWpztSHH+ACYzpke641zDCNIdKc4fwMzD8kx3zHFuIoXLA8YkpjvOkTI0+ZJJCMmMz3THHKc7UrA8MJP0ILntmf6W4vQ3CpYHpknIRHumv0GqWjebK1p8ySTUFlUSWJz8RsHyQLeIqW3P5Le5TRskv1G4QqBT2x5pZXMUCpLfKFoh6KPaz0jVGTdqtno/475eAg9WCOrQLfXq8+6r5kb5Wcv2UsvoSHYXV1349HGHRsrVN/etfwx6l+mTSVpNOe5JGRvJuaFF/+n0j34fCVPvHmOxjr77QiNX+RrZI+MimGnyGtsJ49pkeL+DBQIeH9Oxf94/MWOtc+WD5bHqPG4JnxZ72/J15dpnJheaDN8cleb2TISL8+AoXCJQWW7pmQe38qLGEtvQAzdcJ0XhGoHKcnukwc2JTpAGR8EawbR4ctLqIw+utDhrjYI1AsckJsLll9Q6ChYJpsmT5vZMhPuUOBGOgkWCmX9ykp74kRb1aXFaFAWLBDsf7Jv0xI+0KKpxWhQFqwTdJCY90SMt6mvST4uiYJVgmZSkJ50VNe7njrKiKE4dUDlPj6yo79RJ/kb/EsHFrBSnDqicJ50VdbcaZ0VRmDqgM2CeOTIpzpGhMHUAM2BuCVxyZHINc2QoXCRQKTD0SJK5a5wkQ+EigUqByc8kmStOkqF4keCZ2KGSZF7STyheJMAUmGeOTI5zZChYI5h5HTsfYm7XqYyJFGZMULBEMBdoTz6EyZi44owJesscOPkQ1yNj4mpxxgS9ZQ6cfIj6yJioHGdMUJw5gPvj93MHPd5ApzhxALfH62Mf+VPiDXQK1wjU9vj12EBPLd5Ap3CRQG+P661p+iYj+BvoFJ0sGPtefdQbOvTus6Nn4O0l8OiYQeGRI5P6FOwqdT1w2EDPb7UMMwfKAGynPkcfC2jfB96nyv0J93ey3l+T94An1DnSgcng8XS59nOPa3MGB7R8J3ljK6GPFGOSdy2T9zgb0br8hE4UrBOkz+ebzP65Ptc4DDi303vMvYHrvNXvu62ce0NeY/CEQSNYJ5hP/GyWP3fTw810ChYJ+suoNk4fW6vzNFKwtUrhMoHaOk16a3XcJBJurlK4TKD2bOpjU+e6410dCpcJ1J5NeezqfFf5/V0dDpcJ1J5NeezqUIt3dThcJtCbNo9dnfyyrcNxFgFu2pTntk6Kt3U4ziLAXZtb7euMPY94X4fDZQK9a/PY15k6Q/7GvKAJTIbLBGrXJj33dXK8r8PhOoHatbke+zrc4n0dDhcK1CK+OVwfr/JzuE6gFvGvxzL/TNwKlvk5zCTQi/iPZf6rxsv8HGcS4Cr+/Vjnn00ZrPNznEmg1nUfK7+V4pVfjo8Z4Lpueq78xgu//JZJcJZ1zfH4HC/88lsuwVnYzXrhl+YAHCz9cpxMQD+5vyZ9wOi1+o7pYxGxfb9mZvMAumWc"} |  |  | - |  | - | -
[14 empty] | {"index":134,"total":402,"filename":"Advanced_Project.ifc","data":"6W1XVe6zzwpJ1HWKkjiuRH0Jgu2gx7YcAlk3Tnmq31kCwbuvKYfgStSVIOiyij13z3+fGnSWYJVI8OVXyiG4EvUlCHUA+mzLIZD5akLWrXqmVSfQD3KdVr1Oe3MIrm8hnW0/GNPvvViK5+oPMAZyvVa9XntzCK5vn3T255dnwZxXSWSd+UwFWae2qY3X+cj67+e/x7kt13nV67w3t+D6FtLZ3h9mv1fFXXLKK7gS8zmHugKdt+cV8IxF0cqqM1j/c51Xvc57cwqubyGd/Z3pe18+/4LNuc6rXue9+QPXt086+/cAawfx6Q+Cd6VT/sCVmMs56Dx8G7XnD6zaXj3U9bBc51Wv8978gevbO509f6DNUdh49e0BX6Q2N6/z3vyB61tIZ9/OL8+A4Bepzc3rvDd/4Pr2SWf/HmD17bn+ozck5Q9cibmcg87DvdCeP9CY/IwC52Epf+BKzOccbAadt+cPtKk4wDcBX+Q2e5335g9c30I6W5tvz8+qdbA513nN67w3f+D69klnq/PuGWR5+kDzpPyBKzGXc9B5DXTenj9wtzPHOSzlD1yJ+ZyDzaDz9vyBNV+3816z4IvcZq/z3vyB61tIZ9/O6/5CizNJru+a13dv/sD17ZPO3t+24iWsOQx8Tyl/4ErM5Rx0nZuR9vExpvf6Wafxi9xmr+fe/IHr2yedfXyM8pq3QUWlvIErMZdz0HENdNyeN3ArgjWL4gyQ67fm9dubN3B9+6Sz1W/3aFq67IR2znVY8zrszRu4voV0vtm82hnVUMobuBLzOQebQYfteQN3DzvvswP4IrfZ67A3b+D6FtL52rdv26G2cx3WvA578waub590Eh02Xqsk5JzrsOZ12Js3cH0L6extXjMJxfGc67DmddibM3B9e6ez5wzcOd4ncQ2+SG3uXoe9+QLXt5DOfq1au5wRRlXKF7gS8zm/be6gw/Z8gdvWe5WEnHMd1r0Oe/MCrm8hnb3N8uph+EVus9dhb17A9e2TzlaH8dIkHM89U17AlZjLOeiwDrPwnhdwqyDe9LBch3Wvw968gOvbJ529DqPX+oztnOuw7nXYmxNwfQvpbG0+Xc5uR5dyAq7EfM7BZtBhe07Ava+6dTeUNddh3euwNyfg+hbS+b6vWqsk2JzrsO512JsPcH37pLN9B3Dvq864o0v5AFdiLuegw7pLZ6895bVKQg/LdVj3OuzNB7i+fdLZ6zC5z/KD0k/5AFdiLuegwzrosD0f4Nbb68y33Ge/8GVuu9djb07A9e2Tzl6PnfeoWiWBL3LbvR57cwKubyGdr+fcy29SMefcZq/H3pyA69snnb1fbN7Snnd2BHezKSfgSszlHPRYBz225QTIGs+83n/ADfWUE3Al5nMONoMe23ICVi0/JcCccz3WvR57cwKubyGdrV+sOZtXCaRVqPVcl3Wvy968gOvbO50tL8By+uS4an3GbMO7kik34EoUS/DmBlzfQjrbdl+2r54379gyxPRK+QFXor4E7zoYoNP2/ABuLudVEi1Zgy/zOvB67c0RuL6FdLb9YJ0dtTvnz184wUl5AleivgShDkC37XkCswSW4/w7WwHGbcoVuBJ1JQj6bZyYzrYf9GXz7IH3X/wyrwOv4958gevbJ539uekcA7R6ItzBTfkCV2Iu56DjBui4PV9g5UhrLMC5WcoXuBLzOQebQcdt+QKW04+zHV6epXyBKzGXc9BxA3Tcni+w2ldm9BqCl2cpX+BKzOccbAYdt+ULPDb3lTPYnOu44XXcmy9wfQvpbPv4Xdsz54Ff5DZ7HffmC1zfPuns76+tnMdcYcaAL3KbvY578wWubyGdLzZbjmt8wxe5zV6/vfkC17dPOvv7a/Mu/cq5H5Bzrt+G129vvsD1LaSzn8tk5fj5C97LlC9wJeZzDjaDftvyBZ6c1/01uM2f8gWuxFzOQb8NnIX3+u2u7blHwfGc67fh9dubL3B9+6Sz129zJlkapkE8+ZQvcCXmcg76beDo3N9fWznPyPZOMeS6bXjd9uYLXN+udGjLFwCb1zrd4IvMZvJ8AQp8AQK+AO35AnwrA3mPZ8r5AeT5ART4AQT8ANrzAx5FMEswoKypPiPPDaDADSDgBtCeG3DnvBilB9R2qsvI8wIo8AIIeAG05wV80SSUx/0nH/efQtx/grj/tI/7/0WTUB73n3zcfwpx/wni/tM27v83TUJ53H/ycf8pxP0niPtP+7j/XzQJ5XH/ycf9pxD3nyDuP23j/n/TJJTH/Scf959C3H+CV3u0jfv/TZNQHveffNx/CnH/CeL+0zbu/zdNQnncf/Jx/ynE/Sd4kUrbuP/fNAnlcf/Jx/2nEPefIO4/beP+f9MklMf9Jx/3n0Lcf4K4/7SN+/9Nk1Ae95983H8Kcf8J4v7TNu7/N01Cedx/8nH/KcT9J4j7T9u4/980CeVx/8nH/acQ958g7j9t4/5/0ySUx/0nH/efQtx/grj/tI37/02TUB73n3zcfwpx/wni/tM27v93TZLqMPJx/ynE/acDZ6S9H+2bJkl1GPm4/xTi/hPE/adt3P+vmiSP+08+7j+FuP8ELyFoH/f/mybJ4/6Tj/tPIe4/Qdx/2sf9X5zNm9xLkHOuw3zcfwpx/wneI9A+7v9N+FzU4ueFIeVx/8nH/acQ958g7j/t4/4/Oc/4ws/tbsrj/pOP+08h7j9B3H/ax/1/altWrcMXuc1eh4W4/wRx/2kf9//JeZGaobZzHebj/lOI+08Q95/2cf9nzjLqshl6WK7DfNx/CnH/CeL+0zbu/5Pjsv25X0Z53H/ycf8pxP0neFNFSdz/xS7hxW/DL3KbvQ4Lcf8J4v7TNu7/Y/O8HVIK9LBch/m4/xTi/hPE/adt3H/IedqMPSPXYT7uP4W4/wRx/2kb9x9ynj0Ndjd53H/ycf8pxP0niPtP27j/ltPs22P1cfgit9nrsBD3nyDuP23j/j85t7sE8EVus9dhIe4/Qdx/2sb9f3KebxwH6LA87j/5uP8U4v4TxP2nbdz/J8e51zhw9sx1mI/7TyHuP0Hcf9rG/V85W46zBDCH5TrMx/2nEPefIO4/beP+g82fE5XRoZ1zHebj/lOI+0+4M9zG/X9yntyWjrWU6zAf959C3H+CuP+0jft/13afMb86jKo87j/5uP8U4v4TxP2nbdz/J+c5o3QYVXncf/Jx/ynE/SeI+0/buP+Q87K9wRe5zV6Hhbj/BHH/aRv3H2r75p/DF7nNXoeFeP8E8f4pife/SOtztewMtZ3rMB/vn0K8f4J4/7SP93+vzzfrHWo712E+3j+FeP8E8f5pH+9/5djn/bLOkHOuw3y8fwrx/gni/dM23j/k3Nb8DV/kNnsdFuL9E8T7p328/7u2F0cXdFge7598vH8K8f4J4v3TNt4/tPObPm5f5DZ7HRbi/RPE+6dtvH/dsU8vxaTUNpzDch3m4/1TiPdPEO+ftvH+dS85bzjdJYDaznWYj/dPId4/Qbx/2sb7v3Ne+2f0VuTx/snH+6cQ758g3j9t4/3X+97JXCXbgNrOdZiP908h3j9BvH/axvt/arvdtQ5f5DZ7HRbi/RPE+6dtvH/NcfasJpucc5u9Dgvx/gni/dM23j94o9ZfKGuuw3y8fwrx/gni/dM23n+dN5zqul/kbM51mI/3TyHeP0G8f9rG+4faXjnDTJLrMB/vn0K8f4J4/7SN97/a1/r09LwuDzt+mdvu9ViI+08Q95+2cf/vWudBYUbJ4/6Tj/tPIe4/Qdx/2sb9h9lzzSgCX6Q2+7j/FOL+E8T9p23cf2hvCjNKHveffNx/CnH/CeL+0zbu/2Pz3e74RW6z12Mh7j9B3H/axv1/ZpJWos25HvNx/ynE/Sf0fmzj/t9e5mdmgR6W6zEf959C3H+CuP+0jfv/5LzuDcL+Ko/7Tz7uP4W4/4Tej23cf+jTI8yiedx/8nH/KcT9J4j7T/u4/884XrPpPaN8ZpjpL+sr1sCMgtBWDOa5vvd5l1rAf5pzA8hzAyhwAwi4AbTnBtwlmCXqB+ac15nXc4EbQMANoD03QObrG1l7lQP6Sa7nPDeAAjeAgBtAe25AW/vvRRnvYHOu5zw3gAI3gIAbQHtuwFPbtNodvsht9noucAMIuAG05was2u6LSYejMtdznhtAgRtAwA2gLTdA+/6q7dXDoKy5nvPcAArcACo4uvd6bp24rfNNtDnXc54bQIEbQMANoD034Knlttobvsht9noucAMIuAG05QaArfOuBpwB5dwA8twACtwAAm4AbbkBtS2S56p1rO1cz3luAAVuABVcrfd6brzGM9Z2ruM8N4ACN4CAG0BbbsA9jp+ZZMAXqc2eG0CBG0DADaA9N2COKv27bMacU5s9N4ACN4CAG0BbboCtEG48u5xzHee5ARS4AQTcANpyA+pcTet9O+R5bUU5N4A8N4ACN4CAG0BbbsC9YqzRJVjWXMd5bgAFbgABN4C23ADo23OvckJt5zrOcwMocAMIuAG05Qbc7fysVVDWXMd5bgAFbgABN4C23ADIeYTxnHMDyHMDKHADCLgBtOcGTJ0GaxaUNddhnhtAgRtAwA2gLTcAVsdlu8AXuc1ehwVuAAE3gLbcABjHcX3OuQHkuQEUuAEEEf30n/c2r7lrqWBo51yHsddhgRtAwA0g3uuwUV4rBoyqXIex12GBG0DADaAtN+BW+LfiB6WfcwPIcwMocAMIuAG05QbcOS9t4uawXId5bgAFbgDBWzjacgMevU0Ux3Ouwzw3gAI3gIAbQHtugPCar5cmWX8Je95aRaWD9yvnCpDnClDgChDjXLk9/+x15Th12jy9EMYS5HXj9VrgCxDwBWjPF5g5rhJIn74KEWidXLd5zgAFzgDhXa8tZ2DlqH/nTlDKpgR5HXj9FngDBLwB2vMGZo6rBLLOR+V510s5d4A8d4ACd4CAO0Bb7sDKUfrskTJPdHwJ0jrw/AEK/AEC/gDt+QPnHCMnr/Zv8EVuu9dzgT9AOL9s+QN3jrMEgie0OX+APH+AAn+AgD9Ae/7AU8tjlQC+yG32ei7wBwj4A7TnD/Tlc+5tk3Nus9dzgT9AwB+gPX9g5gglIPgit9nrucAfIOAP0J4/0Ifr41YC+CK32eu5wB8g4A/Qnj/w5LjG9YAvcpu9ngv8AQL+AG35A3fPmj3N13au5zx/gAJ/gIA/QFv+wMr5qfWp3wXOV3IOAXkOAQUOAQGHgPYcgpmj2jzrYPrffQnyOvD6LvAICHgEtOURrBxXCWQcqwTQ83Kd57kEFLgEBFwC2nMJZo4yjlX7bVOCvA683gt8AgI+Ae35BGPdrFp6r67WgBkn132eU0CBU0DAKaA9p2DmrCWZ+m/GIFo+iz5V2Xz5UPu82yntLjHkkNeV14mBa0DANaAt1+ApySoZzmm5DvRcAwpcAwKuAW25BmprcTZ3uE+Rcw3Icw0ocA0IuAa05xrMVtH/8m4d+CK32eu+wDUg4BrQlmugNhbf7rhq5nrPcw0ocA0IuAa05RpAO98lgC9Smz3XgALXgIBrQFuuwd3Ot+1PjCLKuQbkuQYUuAYEXAPacw2e9m2hnXOuAXmuAQWuAQHXgLZcg3p7UeZ7BGmYc26z13eBa0DANaA916Dfpx0t1nau7zzXgALXgIBrQHuuQZ/Rr3pZtuMXuc1e3wWuAQHXgPZcg8fWEW3O9Z3nGlDgGhBwDWjPNejlZTPWUq7vPNeAAteAgGtAe67BPY7LxuZc33muAQWuAQHXgPZcgzmq9O8aVZhzbrPXd4FnQMAzoC3PwNam13iGnHNd5zkGFDgGBBwD2nMM+oxeONvbbIcvcpu9ngv8AgJ+AW35Bc+omn0btUfOLSDPLaDALSDgFtCWWwB9u63VEr7Ibfb6LfAKCHgFtOcV3O18r1Uwe+a6zXMHKHAHqGLdbf11Tw+jOJ5zHea5AxS4AwTcAdpzB54+vWyHHpbrMM8doMAdIOAO0J47cOd8blbJXId57gAF7gABd4D23IFn7pK4YuQ6zHMHKHAHCLgDtOcOPON5xJkk12GeO0CBO0DAHaA9d2Ap/Uf5F/gitdlzByhwBwi4A7TnDtw5cwkzSc4dIM8doMAdIOAO0J47cM9htwKEnHMd5rkDFLgDBNwB2nMH6nHrL6+KlkqaBLu5lsmYcRX7+svr7QZBTnldef0WeAUEvALa8wq6uJv17h1DzisgzyugwCughnW+f8ew9qqrBIJf5DZ7/RZ4BQS8AtrzCvr0Sfa6dgoCX+Q2e/0WeAUEUaxpzyu4bV45g/895xWQ5xVQ4BUQ8Apozyu4bZYRc871m+cVUOAVUMP5ZH/eOqNajvUX+3au3zyvgAKvgIBXQFtewV3ba1S6UZXrN88roMAroIY9da/f1vuzul46rjqA0ZXrOM8toMAtIOAW0J5bcM8k9wzT4Ivcdq/jAreAgFtAe27B/TpINn0813GeW0CBW0DALaA9t2DlfL/JwnbKdZznFlDgFhDebt1zC+7Z857LoJ1zHee5BRS4BQTcAtpzC55xvRlduY7z3AIK3ALCOyh7bsFj84h9O9dxnltAgVtAwC2gPbfgmcNatDnXcZ5bQIFbQHhbfc8t6HWtlmudxi9ym72OC9wCAm4B7bkFd85z5ahwhzfnFpDnFlDgFhDeQdlzC+4+fa9ZDb5IbfbcAgrcAgJuAe25BX3eLu/LYwt3/nJuAXluAQVuAaHu33ML+v1ueObc8IvcZq/HAreAgFtAe27BY3NbtsMXuc1ejwVuAaEG3nML1vn4WCc5cEaccwvIcwsocAsIuAW05xYsW+vzmhe+yG32eixwCwjPFvbcgrtnrZfLcGaUcwvIcwsocAsIuAW05xasOyC1rL9Q1lyPeW4BBW4B4f5uzy24X6Z3iTbnesxzCyhwCwi4BbTnFhyHG1W+h+V6zHMLKHALCNf5PbfgWCcwy2Ycz7kO89wCCtwCAm4B7bkFd89aPQ3elebcAvLcAgrcAsKVZ88tWPcenhJgzrnNXocFXgEBr4D2vIKnb8+eBi+icl4BeV4BBV4BuVbb67B71hxxVOU6zPMKKPAKCHgFtOcVLJvv+RvOfnNeAXleAQVeAWHkii2v4BnH91oFK0auwzyvgAKvgIBXQFtewZ3jPa6xfXId5nkFFHgFBLwC2vMK7vX5VgZgc67DPKeAAqeAgFNAe07BWKPqrvUCX6Q2ez4BBT4BAZ+AtnyCJ67HPYcRfJHa7LkEFLgEBFwC2nMJ7p41o9rhvJ3zCMjzCCjwCAh4BLTnEdxxH/qtEOCL3GavwwKHgIBDQHsOwa1J5hzmcs51mOcPUOAPEPAHaMsfePp2bWH2zLkD5LkDFLgDBNwB2nMH1u3QO2fQ2zl3gDx3gAJ3gIA7QHvuQK0r1sXq2/Kqg6VNP//+gNPHnEtAnktAgUtAwCWgLZfgLtlxrr9zbYP1N+cTkOcTUOATEPAJaM8nmDlKneclpe5KkNeB122BU0DAKaDFKfiv/+V//+e//z///b/8z//1H//9f/7nv/2byO9p226LqkyGJyGiX93Jy9nqUaSdP+4XWlhIsmRJNuZxtt4skH3/JGmIXWOTaqHdD3RnBSlKlqLub6Ufp35v4WKJzt+z8HGc5aB2XoV8fkHg9R3S/pUkW0zyJOZf/Z5pNDmwkONfMXsEs68ETxFDAp9uVaj/tG2uJFuxF2dW01DImrTN+UutaHqn2S1Wk/Jr9MXWjA/f+4/7hcAJ3qhJ4/gkW0xSS9l+dTepRWy+KmvSOOdvuZPUf7qSHE3HdDWgJF2lLJAppJg0zvl7lMok3LRCz08hRc2zJe/UuQl/oLKHnxRb0jj2QWcLgdYslsCVosVmaedo/Rjnx+xh1021U524sra0cf4w+0qy3jWJSf5LjbNpbxX92m9FU5bzRH+b2vUPS0l0HL+H/r/GWkPthCTT1vmjlBbaQMeOtZ4OBIgSuhgVSYOz6HgeFpHhavDrRF3bQ43+lBLS+adtIq3+2jauab86MMyrLmn/SpK0qUCdPn51LtKuqRMuQWfsaZvYZKYp9pN7Oa8k+bTTo1M1/CE/VIv+RicOXRToGFiB+YjRBd+mAK3wY1xJ9lPLfHLTtebHnoj9MjduFrgEnJYLobFrZRMrV+D/9iljsxBhYtPjyT/+BxDMcCE29mazDjZRLVX5MwZ1AKqqUHv1X6jA0J5YtBvo7zrW5PinA4br8avD3uL2aTMJljJvnKr9y863mz0FsCR1kdHVpl395qdW/jUdUlVPaa5Yyn9pwGzm3KsLWU/Xf3nWZ849F+xjl+QhOmLpMLzAp5BsB1I6eel//kzig7V1dC/1NM65WCC7BC3sNFcTd212ILGQXqp4dBHTf1Har/6vLollDMYkcx2gS3MVqiaXtFdTu7qMiGivrOPH/QJO9TXJVAdoLbLW46HjpVhN1l/dQetgVCGmc8WP+8VJWMqkcVjNtHX/5FLsdWScMtwvOjQOJY3zZ5I2f//ae11daAQE5LmwJX8YLtHwKS6ajn/Rfj4gyX/UPG1KqrO1opOUPP1cU0xa50+7R61qh45u/cUJIRbPhUL5/11IHZfnr2qCU3/Vj+cJ2bnwKf+gV6pu06FlOtPmDKjJM28cS1PN6hY752qcoWNRhMSio/3of/trTxaPVi34FpYybRwhPg3Vrip1jKuUukZTPcR28PKDvxDgD2iS/7R17DKXrhG2DpHOVQRJpq1jF8FPewIvqnsvw02m61TYu71mVa3VbBpRja3iuEIfKmnzsC5Tdk5SBtnUaHXZdcnSBVslguahTaJTm3RbzeSEFJPW+XuA0/FrL2LtvEDFIAzwkraOBVVQm5h0Df8UsojJFe2E2jw/WoW/utIV0flehw7anc5sw1aXppMtt2vZ6b+nNbXqlPMY12T5/KJD45S0cf5I8RrgaqPOK9rRBUYjp41zVF2cDUleP6qs/TZVoyZnVI9ehXx+ATvaczFrNkna26WmlVS0G8tVSu6sH2v7Ds3D/YJcKdPWwSTpneSc2QoXe48Jz5M0xbRxwO4Wzb4SvPSX9dkCnZL/lca5etCrcew16W+3UF39HLiA564BbJsRC3kLfV01kGJ+Hrlr4I8kWy86OE15NZ0FcPbNfQN/2N26jledKatubwowRjTJtHFMoogOZR3hwndz69yo41knocH0q4rFYpSZ9sQk09b53t4WYeVXlVdthjZmGIy5c+CPkaPzya+czQ70zLUEKeZ+m9Z0Zmy6yyqzJnUo68Tauu6Zyw+P/mu9XldH1Z4N5qDMN6BzbzdQRDMvJn0GTjFklFajro/8Uw/SUnddbM3tVaEmM9+ALY12SDa6XTQeV5La0M0UUDO6jftFEejomXPg76Gj/2jT8WmvFqnAAp55B6wu2SI+2YrSedZl0d2STowW+/3a0V4tdQ6LCAFJps1jOxgdvjI0UVl1qauMyjZ7zGbBcHU4WtvxIagBM++AXAuZLvpqp4XkvEqppbF+bDFNVFyotrFgAqxCo8IslDkH5NKQuicoB/fZhWxDYXOr7v9/DJH2a/HXWfe3Z4N+nvkGWGvJCHs6x9g9zCtJunY5rbLt7N0vOkEhM9+A7rbY9JjFKbSY9DZ0zBOtdvfr7a/7xVmhvTM3gUuyj5jkJdB1MjktWgTc8dH/PmmcPw2/kmQ72uqlAi5Ak8zHjq0mw7aaFgLAkhxH6SYrih2M+F8MEC6Zm0DnVu2/fI6mU9gxZhey4auC2C5e+190MDzzE/yZ5GezoxWnA/7E7VPmJ/jD7umbbTaV2hR/wGSZ+QnEVmeVa4f00q9Cjl8dQ1MDnh919fwC14jMT6D6m0lMbveTZpIWF0mTqdfg8b9wSaYzG3xwzb+vJC/DdcVQGdMgNv5JmZvgT7s/GtCc1CpVAVZyUuYoMOewZl50zzWHI7ZO150J/uJ5zqIpJo3Tfs3howKi2fulUJPjx/9iYJJJ4zTzZujMWmxZuI4g3u0Nv7C0Icmkcf5MUqvy1Pm06/JZD7hte1LmJ/jT8CtJVZWqXVSwFYYk/6XWiY1zpUhNe5gFj4WJjTI3gYqppVx0NPNrYjNnvPvFgC6U+Qk0AbnI3Cr2ag1Txvhxv4AL5idlfgKfZI9JquGkckjKOFR2CVRl5ijwhte34fxJUm7VDymmjTOepe9SqiACLdS1+8WAfQRlfgLbZh6qk4s9Fhd5r2T8437RsAtlfgKfJMckP3aPUYc9PDswyXTsgOGN3uq3f7rlcS+OYHjmJ2i/2jCnbjHtGPAsm/0y/oIOGI6Zo6D96kAxp+xh2nazb3S/gLv/5pH7h0lehhsQ1jYBBRwklDkK1Kx2qjIhTdYuD32EpXV9sRiT9ZPksK1EFVPvkOS/0jz93Ox3NGk7obCaJFQFlHkKrJTaP3Q383lxcjWPDsbT7urRea7dKJ/mZ2sntHjmKbAk7ZK5bneOuTk5tXj10E2+kVjNetsaaKctreNSljkK/rRbk/k1N68dCAqgc829niWpFqkaOnS7Y5dErwavaqI56cS2FqctuBbjVVU13L0+KXMVmN1dq8mC5c7djuiYKSbJupVR95aXa2RoBgTNnXkK2nWuLTowdOU67p2j6NZksJ0mDFX9NvxVjZz4huKkzFPQzIFWbXtkW9C129G5+7Cdw9E0yWEHl9qH7DAGVCBlnoJmhyZ24t/4LGtPprOSarxxFlvbTiGdqi4PZB3YgzJPwZVk67pp1C50baCcM/n8cb8AjNlJmafAJ9miN/mjCs5rvrUohk+SmatAV5k+tGNqH2Jdzzb+SviFHCdol8xXoN1a51Xd6F2vcs7NsYn7xYC6zHwFfyZ5GW5FqkP/Y8FS5rLgu+GfNdyg9V3/NSqszFfg2pPeLa7No3Pwr6gQsn5U4PT7pMxX8GcpDbSkGz0dOObpgZ6euQr+bnAquo6Yt0N0PsXpN3MVqAy0gwJRGVqXF13FDw9diLodH9iJhNmsq5P+D5qdjh3bi+m2WWctneCuFMUEcWEd+OXqQs8vICzcSZmv4M/GMefbbz2HTS1NsJSZr0Ab02agYW+Ey316UJqpajaFdR1IiJ3vylGqSzJX1Hb7zHZRpvs+hnerSdOuJoh1gjNLLA8dOtA6ma/AG749grJbBwerCDi5wMaeMl9Bs1Nuiz/VVEIdchtuD5Z0OSo/dsKsbd3sLpNOyFjKffNU3bQP3UyQTsHzANh8WkXaRSs/f9wPcK5MPAVVV+ehu3XdjNj1os/5v26nDgNd2GbF/aC5FPdtcx3E200qqybpZxw57he1woyReAr+TtLE3q/5mahYr4R5LfEUvOw+g91XijowdQN+2HtaSPEfNo2myDoD2BtsFQWQ4pk4Cqp5u+xyyGHahWwOMoeWCqvGdk1m/PhfQJc8E0fB30lepaysA7YPiHCnKSZto8KFzZ8xbJoa1slP+zejqpayO6Q/7hfd2Z20jU+yxSRtL/1r9+DEzhNgWjsTR0Gtv61YSEAVtfQ5qqffpttQnX/6FSXP/eIExXYmjgIrpV0pHHbF5FhXC5vdDmG7j1p+3C9IoHUSR8HfSX4M15lct31ASdUUk9b5027beekmQKfJQ4c3LGNn4ijQkXOcpiJFzKNSry5UtPuUZtq58o/7xQCRcSaOgr+TvEbjaN2CndoNjSfJxFFQzShjHNqscV57He3W95ShjYM/KLAFPxNHgX5gDr6uuyPh2j+FlGIbRJt3dBlzvwAuoCaZtE7RBLquDqc5YWcZ1Ty7VHndz1az6689vbDDmdHQ7KRxvNk1mH2l2MxhWxw15TwzN8H4tV2M7t+t3q/rBHY+bacldkCk/8L/AlLMvATj1y7RldGbvbn9zEHaUdQmY13YSou/0N0OJJnoAVtGq23ghm48z2i2+wFuv8/MSfBXijpQdatcrMAHXAbUBBMxoDaVelhfME8xfbqP7j91oBe7Y/1J0Y5Dm517wZn6mbkIfNOUd9PQJ0mVhppLEzwxOTMXwV9m6zg8Tcay3d4vOF1kHoI/+w8dQ3Mddp7VzZkJSaZt84fdFgf8V+cNGwejYlVmLgJvdwt2t6Oq2pem+6TjBN7weWYegj/tbocdBNibBToKBEo/z8xH8FfjlF5+LfyFWswVj23PzEUwfi9lbuQB3SPwlAPm6x52TmD37OxQR/uPoVEPnMszF4EmqWtJEf5Em71SrKrzmk1hloVOZL92P2mY4oUpLXMQ/Nklu+2jNFNz0Ov2AVJMm+a0s3c6ereV81NGnYmqnYDTKT/jODVTXW747Ha48SSZ+Qf+LORxaodQRWWgiw6nY2fmHhi/ddilzsbcaSZoDmBWeal/PmPbPCbHcdpyASmmLWN3rUoTuyBcaC43zZAqTecI3Zjp+PtlnW+0Ngc8I7La+qcjUZc3nczZwu8NiIdznpl3wObJw1ZRuz7Pn8bRrmmnYabP7Uac3S7R5UE7kUpCqMrMO/Bn44jdbzHl1XRGh2t7Z+YdGL+sDVGGbV/HsaYLG3qHvYCwyyi1X14RXR8qXl87M++AJtlFZ2rtwlxnVVpcCVGr9V+ZC4Ntj6o7RS34OGGezNwDVpWqT1q/fvMppU3c1e57X8ej4xJaxRzfcsK5/5m5B7SU2t2sYnTbNZbhunUwFDrbpefjKNpzzftzyAm+8zNzD/w5UWp3/G06Pei8q2OhQF1m7gEtpYof3XjXWrl+GlxLrbOYucUuyfL8QOCg8cy8Azar6Q+buVZoTmumTw87aDL/kG4U7WaY6uirgjHJvHW0Z2gVqXb8vH7RttBxqaqH7Zb4jy7cv6I6aHTrZeAdODPvwGG9uBfSbZN1pB//IotU9eIv8E7cmfkH/kzSTjB+LQ5BtdkUThrPzEFw6ITQO9vrt35ei457kzV+3C8AuKlJJkJahZPOgbq71OHGNDdOz8Mx+vG/wJ1y5iDwSYa3aPQxXLcjXQeOtiAmmTbPH4ZfSTY79lVhDPGFz5LdJWi/zSTk6Nbn5kRkHdUuZepk2X/8L8DzWfK7BJhkj0l+nMg6Vseh/0owyWT0fG4Ld0ND2/+P8hx/gNeuSn6XQKetYhfvu7nbPynWQ66drSH1/C+wJlPHJ6ZYYoqfU8HTXjvbuwgwO7tK4M0uuz1E+T3sLbguvEKYYnpHSg5z5Reqp8yK9Jsx/AU+YijZVQKdGa/3LsO8sefY7MbwF/D2UJNML7Wr0NGdzFHtGt1mN+Z+0AVSTK9IfU/xus5kPi3djJcGL0xKdpFAjdIlxTzSh0oU3m7HrhuIOtuaS3lAkv9S4wQxdM7bZioa1A7VXGB3dpPgL7t1O3b8Djs21MUIMH729uIf9iD3qO8smVvg73RYdb4ddxymP0CWl8wv8JexzVS5/be6uVCpRJDiP20RS1L3NTzsaL/Aw4WS+QV8IeNUpmrrV1vY3vVr1uAYKJljQHuivSES2wK3Rs8eTMje0ooOF21j7dg6lTSVj2j3PxwuFhLr97C9iFYOgwwomV+ATZWzOSabCp61rbOoP50/G+ZzdF0xR9MdGL5IP0vmGGA7iLSzMzpLW0leHvla7J6E7sJIq8auSddhWUGS/3S4aGK/g3T/pTniJeSS+QWu77W32Tvc0WRtw5rF9tQlUealVHsBYIqSoHEyx4CqPDui0NWV7XrJ2oaptrxiY9kurNrlgc46pguchpXML/BnN7/aW6fuYXc1uEAhM8eATY+mtsmOYPstAlSvqr41fp0FUNfhXawLMLpYSuYY+LNxpIvd/TBkYwUwqKaYNs51F1j/l0e/fbzasnIdFp2fXRjrfGt+44HDO3MNaJL2tK5rNapRsnZhpHk0ug4WT66/xv6xC2uo0DLPgNXksFtBQ9MsdW3CzLF5mCPfNmG6M9dKtEviBHczS+Ya4Ouoy3by14O2exM2hm7zyA7xVJ7/drspph1KOwAkmd+U/j6d27zGOvuq4D0E7yiWzDdgZop5gav+vvLchGlbWHRDi2DrfqHDB5JMW8dOttUmHZLaC+cujC/SPeusobswlWiHHXifFjEAZqHMN2Bl0o2QVp2uVOWcu7DzapxmZxGq73XA6n+oFvQFTitL4hywQCZP1AvzBfgtU83iYmiK+9a5UoSwF6+9yHpougmMoUnuW+dK8gl7Ia+9SF33uWNgjLMkvgFNEmNUyM/rRfWZRrE4S+IbuJKE+A8/PkJEr2mEiLMkvoErySf+Q32fJZ9phAhNMmkearpAj2qvoy6e0StJ+ZZk0jyHirB3Bcq3Cty3CV/+/25P0I+zd34n2b4kmXgE2nnYrvewCU3V58daHeF02L2wU1aTFLYFsYIXsSQOAdXgdnHpI4xngrrk2nDR+jl4pXg5rc6BRUwaRMzXafOMDrcWX5fylwZJ3AG63xO7zXxevqo270nYq5/D0I+r29jEVJudaMDKkLkDdMTV69CTijXJu5QtLyUn7oDRbGlolVRG2Yy1bjWUK9CCxd+apawm0kygQpLZjYHzV7WOPSjUyaV+RrWuW7pYndqlxgpr0Lu9WFLNz5Bk0jy6xKoKsztKvX98Sq5TlrxTcuIP+EwUWkCd560+rySL3b00OdDarMvnF1jKdDrDcADh0smZBwzgxCEwJ907HMDrfh6PPGAAJx6Bz2LzxAN4X1viPGIAJx6BYVrR3m6yLSYzJAgYXr8Znk1nrV1XlcVeRp7hVln9VspkZut2imMrnsVYk/OdZP+SZOITsIezurm31tBldV7X0n+olkmnmWK9Oqk5/glSTF9N2ZVVQ00f7Tg+d+wPC/Wia3+dvjSVMEbhsPdhBZNMBo9qyF+xB5G6xJYxr76JMV+P63bUJ0kVxRaDCVz6nHgEjM2uIqp1nYUunPp9PU/nWt15rTJ2u6V4MgZK4MQ5oCvOr70k0wTMsDB02pcelDgHdBnQkWLHBHYX4rp9UU009246rKxS6qpxsJ0TYXMn3oFr6MBL+5/Xa4WSv8XnxDtwJXm/YefPIxp4WkDpK3dOvANXis8j9vBKo+TP3DnxDmjf/tVtnRhvul+Bb5zZ7YvZiXfgUivXI3YLOtFDIeuXQibeAV3hdJ9t0XMOrvo/7yT7tyT3jaMD8LdTtZgkmsqKamArRNeFpq8Zo1xxLXRkNVhvE/eATWi6mtrdW7szFrqQfKvLZNk5z9Mekascajo2ZheyKH/a+8eUvFrKavFa7JnqIzQ4j0LAOgvq+kp2HXE+VzC1avffzz77kNizjWIH3tAtE/8A6/7StnK687K7vSGORf9iePq2QHUF6U+buV/ncDSfhT0s1/3cvZLZdWz795jkvnlUodpUqb+27fK1RtgDNE3vsPhytCIUaord3rSBr4UTB4E96Pi1x2xc7BFEeOjOXwxPPAS689UydLuDpz8v7Wc9k2PrAryah65X6/bmBFo88RBc2uV5Kf2JbADPxc78LTUnHoIrSXgp/fN6S50/pebEQfARWOsJsrxfHH50//aRMif+gY++ep4g/7weKVP+SJkT/8CV5P24t4XnoJQ+/+Vv7oHnce/583qzupadzfNfzv0D+Mh1m+L+FSzn7gH3xvVtdslfwXLuHsBHrv3dOCN/Bsu5ewCfj5ZXD7oOp5MHppy7B+D56Dne3bynD0w58w4M9zCzvMYirxQ3Tzc58w4M9zAzrLdn/nSTE0fBleTz5LFslcv+USQnjoIryefJ4ydJeBR5v4nU6btb5DFIcd84OpH/6rJ82syhoqC87W5f7M5cBYd78TgXsvtNJI1VSjsmlAPDynDmKtD/5teu0Ng1yTKCdJFvpUxaZ7qDTK/YeyMLSiizSXS9tGtpplHudCTxD2j3+7XXt/bAxdaXj7V2Ztrt39Xb2qNcIWdg7pHEP2DvkX919NrNKgsU+knyci7opH60laK9emp2OQZSTN0Dh4XuHHYqdHmzr66oxSZ7ENRm79YZnO2WYgMnhiTugXbYltZC2ehCXeeotmtMXbc8dhCzSmlUSZ02wWMu2X0Bu/zRL5FnER/n6nXYrTwdH7LiBFQ7N7InH3A2K4l7oNttALs6dchn/VtyxULHXGfzn3lc5bBVx4BJVzL3gN3ut4tZ2tha1g5JmgZqFZK8eBYCSSYyuugKqsnpdlMsiOcc1vZo4fjgDj5LgzagvUA6IECNJO4BnfN+LQF73NrWo7N/7Sm6ZO6BevxagVTXmWr+SL/Lt22Xq0wSfUp52PU83aXC6aIk7oHPKvs8Gn17HNYyu34BwzFxD1wpPq8x+e0PWldtNu81JXMPDPcac+u02j/XlMQ/MHQ/0o3zqpv1a215md2+mJ3NZhbvV1d4u0r32SVHf3lSyMQ9oGuQdg/djpy6FxvStx6HLMlksenlV/qwV0rMPF/v2dMZe18on6dSl16xK552zwFGYx55QKeXol2yU5H68f+xTYxa7qMda922N5C6Qwf4kCaZ+aV1OGpPsbBYd/BV7c8WIta89HORYEus6RZjoOFJ8+iM+Ku9rxln/rp4aqWsdjWGjIE4G5xsCrE3Y4/klcQ/YL66cZ0W6Pjrx95Xt3+QLYl/wO7j65JN5XojfD5vK3Utv4b9XBx116R7abvmA0lmQ8e9IQx+zzN/ZSiZf2C4R4Tlx78y7Jw/M5TMPzDcK8Ly458ZXrIqeWcoiX/gSvJ58vfzehNY3m8CoQsl7gELkwLv886f1wu+M3/BJ4l74JPkevl2zPuY99u4axrav42TxDtgV3Tw5duPexvXLzWZvI2TzDsw3DO1z12e5yGb9Pwhm2TegeGegK1b+/cjsfyNmKTOAfcE7P3W5XK0JI/EJHcO4GOoXYr711KS+wbwLdT5vp5H+WspyZ0D+Baq+ysOU5bvX0tJ4hxQrfKr1dPtQsRB5Z3i+JZi0jZT6Lvqa3n1JQ6B2sydZ0pJR0jj912bzy42STFxpZVmLwv7ca0t53o4rGKwXE/up60qhTXfUdH/LplDQKdtldx2DUqnKnrXXvtSe5k/wFI0JWbBbNoZ+mHNzU7cATpG7aKFrojmOjn7ff/LzjYOuz5wpaj2XiGgKy6vmT+gXjOfUF/3vXwh5UshsxOcNnQ5FnPEzOhD8wYh2azJstrGbmV0e6EISe7bpnQL+aw9yGaUY9bkv/a0UHJ3wKEbw3qdl69SqhqytySjtmX38wsoZRaU8Dq50nnOpoTeP3eXi24RdOo9Dul1Gd7NF3tgoC3J/AHVpnx7uULmXh/vXlm/GZ40D1lsCd0tXWJpPuW67jcs7+ynlK1cYXiOgYYnQ0f7ok3Q2uWOT1CO65qaTh66HnJfo9HoLMMuIMAljJq9JBh2ceqwa2mqoNeTJhK7dGqPVOYcbhcBLFyYwGW6mrgGyvWQ316vXbHL33dlz5H29Jq4BpqFZbHxaLpu1Hlby+JpaKJ2jeuehSyySIPz85pdHLBTId0Q2zrCn72INk5RRWQHx/p/10KjA0e1D7mazPTzUEneLChWVcNmIYsdp9oRw7GGo91Q038QOMio6cUB98bmfF0pu7wsySucml4c8K9X3nfK5Cd931ITz8CV5PN6ZQtbSt631OziwHBPTe7XgOsxytwx7R6j1MQz8PF03s845iLxPPT4Sd951NwxgM849vJn/9Cj5p4BfM8QFvB5NrJ78VBzzwC+Z+hbSbV/8VCzqwPDvWfg7WS5f/FQE9+AVrjNlaoyLrrAe+H5kmDiGcgVVVJ9iTtA1/+LFmGTo+5zaSupsiT3LaKbtotpoWLCBOTaeHXritUuxc4WkWLBO+ysDpLM3AHnMDCOBdnWcdveLdK/VWAq0/pFi9C+ou09tqIqMTzzB9gKavuhy3src6057Xa6PX7vqyvaEl7M3QJrTeIPMBfZr82vbPKhh02NfCtl5ofu56+upfYOwy6Sg6wqdgFuPRGyu1q14uFSTdwB9j6/HwatJK1M2oqqpHHSxwTXkUCxe9t2FD8VUGPz8eoCwauMvRy2UEDU1pp6A+xk+DBHuN0cHUun0cV/Guc6O16/gLbJvAHaW3+vBbZoi7/H9FT6id2ZN4AsTnuxYyTh9XiE++XEttfTy+5ulwx1LOGynbkDtMau9wRGCznXK/F+BaHrxKt1dJ9uN87stQ4kmT+SMryMflD7elr3klRiSJJTx5haA42TeANK1XVE7NnG6Fekgp2kSrp54g64NFW3oGa6o5kvXOyQzTANFpfinoS0z5tehcUr8wbYZS07R7FIiMK0NNWlw7Vq17zWLgq9hZKEJLMtzlB9qlOi6m6aThDtknaOpcVcra1bUe0Smi8MxW9XBb5e0n/xMMHsb1cFvt7Sf1E7obm/3RX4ekv/hRaF5s7vCvxxS/+Fr4S6zC8L/HFL35EeGXxz9dtbgq+39D2+Eue1b28JviZpHMdxcZtUpCObo357S/C1Lv1jyppfEfgrHc+igwkyvyLwh7UXPUOH53XVFO+r1/yKgDXzaRgLu5P1aWbV8cW8LXZ6tQL5jOu6GoyY3CXwV1+0p3B2vGLn0djI2VOCMV8K2MPJUer0jotF6dTRYe5yldy/1Q52LukLjZx5BP6uycmabEP3IA03xplH4LLbbrlpTfG8H2seBZ0KtXLthp5uZX7tod11lkyY5LfGIbskpuVY0QctorE9Yjo/A+aws0W7qIbRhlriEFij2hx6JnA+KQ572qB1a+FidIzYFDnsngxhQPiW3RX4syrt2Nbe0IjF5SngXGnZZYFPVfIwMMYHh3S9yyC7vy7GsjEypD1bNH62sVQhyW/T2dkskK+W7XMOdFrTNntxYo+u7dVw6RaezDKCFL81zkyxD3IpGsTnxzTXGDaaLaINvFtr+VOCP14nvAiJUMpvTwm+vE7ob44jtE7qEfjrdcKLNomGf7s1+M1w46H+GldUu6k9HYYkv2mBb6W0gMSnhYe6nldC7O2WuwS+JmnzUO+X3DS07gk3T1vuEmCDvWrrGC/20zwANDyB62fKH87UWu4SuDyRzfTu5BQ8PMMy1s3/9QOCFP9p63iuH/hrWnZbwArZzUVssZt5Hpo/PMOH46iLkL1heFLMXAKWojVEpzZvxyLOUFeNbsGDD1ZBZbEe4XCp5W8J/uqVjuOIHf3bW4KudqpduqH9BPN+eIZWbN3t2Aaj8mE4Q0zyy2OCry8ePM8QXpy1zDvw54uHFyoQOnr2muDPJw8eaFhg4cm8A38aXvuFoK6GGD4wyHxLbwv8VUqv/Vp6ReDPdCbXTvSXOgzR2i9t8tVaTVK7K9kVO92H49qQOwWuZm529b1JvZt58vwAnFauUM2Q4pcm+Wr35BjqhGfwPXiN0dIrAn9WpW5Hftmm8eq4tC29ImBbOgvQrBMg8byaf/P87OzcrhaaVLGApa1gkl8aR7R8zfb8jX88z8+u28joFkOx2WxTIHRRS68IXCuD7uEtyB19Svnw/G421/0LTPKfDhjtjyrVrncT1oNg1s3vCFwxd3pVKS93XS6eX5Nr/8VXnDG7ow5Xq1t+S+CqS3tBxp9TSuT5qYS5KZNkowd0dPvqF7D3rmKhp9djjMXzs5Wciy3tusLaczR4d9S++QVMmdsT8SGfC5NA9Lte3JnSOszxa/xaSPKfvu944fcgxX/4vMOz9GC72HKvwB/PO1KsXcu9Al/fd7zZezAac6fAH887XsA4KGTuFPjjfYcHwGGK//B5R8pNa98eEHx93pHS3dq3BwRfn3e8EHQwvHP3wB/PO15IMihl7h/443nHC5wGwzv3D/zxvuNF+4Lmyf0Df7zv8EwyCErScv/AH+87PEcLkuy5gwCfb6yL4M/7jg8Vy4JiqvZt4DjuuX/gq90m0+zIzHiquoAO0AQ99w/g642f1/OOupxW5ouxqygDUvzSOMPu1ha7qTrfEjzMqw/7qcihZtsCjBX5pW2+mq3VabHl1WbbzkMZc++APQwxl9fQpfVz+/0hXumyNmwSsmi1h+31sCJz78D1QELryY5t5oX6h3l1TtSXbgJ0FJy41vbcO3BeDnGtpFbOW10t5pVt5avdFO9sz3SLS/LbxGaIFru92haI7WZekSV5/Nod4CvkcWdI8kvr2H512FPXmSQwr4qKjH7Ra8ZF7oLbVf0fvyTwNBpYbfs/fkqQ0qT6P31K8EJeod1fWuer3aqrzLV2DqtPdMH33DvwvZBDRaUF3jLetuC14J57B76naKzwX7t5Xgw/ByGte+4c0KXRLgCzhdJ9g5/MlXMDkA77H4EkvwydQxNTEXh8cLxIfjrXi5nnF5DkP2sc9gAkjMPTc+eAtuZ177DbnZIfR346Bz/EK74eRjwp5r4BrUrdFnXTV+ckXt3gJ5UdugCaFSo7dYR20EI99w381Skd8QpuWPfcN3DaaY1NMLp3PG+7P+An26GZo1vb2lzGuuBikl9eEnx9nJBSlXr+kuCPxwkv9hMk+e0lwdfHCZ5PBRuTnj8l+P444cVAggb/+pLg2+METyzCbpk/JfjjcULKAur5U4I/Xie8iEVgeP6U4I/XCS9yD5Ty21uCb68THOIGOWw9dRP89TohJff0b48Jvr1OeNFh0Owvbwm+Pk9wuBe4ytxzJ8EfrxNemB0wO3cS/JHkBXMp5gjX9afAgUHPvQTfa9L7PHvuGvgjGR19usSyFcw6LKT4Tx93LNqKndB2jKzVc9fA90K+kDDQa3LPwB+FXKQDXbfbibvunrsG5sV+naaPcT531MSWGD4vgEu5LmvZQQZOj7lvQJPUrbCdJtO8cms3N+yZwTHM/3Dak297kqybpwYBaHruG/hqeH0wIfaEAZfDb48JLNyV3fhauB6LC3W95zRqSLMoZrq0GjzjBM9Azz0Ddgf/tCekWqGfy1pCFjWE7UJY/VGx/0s0VGjoCndCFJaeewYOO7Ezz0xfSA/djl2ywCLfQePYXWZwBfXcM/C9U74QQFjIL23zYGTuFy4TNKNbRUeiAefkyP0C+E6AXtfeSs9fEozcMfDHhJExgEbuF7AZ/MKMWYTAzx013WbYA3Ftcf0X46jX3St7nnjAlZuROwb+mm8XZ6ZcEaTR7m/rjApRe1KlIu1TyqPaU2ybtz8BjnU+08FvevqZKEfuGfirkEYqsmuVxr3AU8WRewZswrAebpGYP0kW46oM3dlfECAj1xx2+qdyt4Jjf+SegUPHs/YX1Y1lDkaLWWnXs3Sp1uncEMHnNfc2hyoauWfg+L18+terqPXsyiK/W8w4u9B9XJEtq4kfXXqgdVLPwF+vMl64FTA89Qz89SrjBTJpkOSXhx5fXmWUN24F6jL3DPzxKsNDRAak+GXz+e1RhsdzNEwxHTp/PMp4QUdggOeegT8eZbzAFtA43+4NfH2U4UAVJ3gTR+4a+ONRxosRAh09dw38keTFoWAL36ENgsTukbsG/qhLLyVH7hD4Kx3jUFi4uKY9ER8Kj9wh8Ie1kxqhPdWitIErbeQOgT9K6dgWrufk9wb+KOWK2F4vcgEc8o/83sB8zlBsRVlvfE1MFttU1otEYVF7VRZZjH1I8ttjAu3eOlOZP2XqNLslPHSfbBGcDBthWsWgV9hv8msDf3XFxTowruIJ7rmRXxuwu+PXXfHjc7HKCqkTpMUiua5nqtI0wct2FQOPz0d+b8AeH9jDgH7jwuzyi4V41arjH4uqcmhN6iTMjLdvR35vQJPU/eQVqmq+Rimf+NaFjWBzNw7bc2Z4lzHyewN/9EoPM4GrJ+Nr4MGbhrHE5MRl8AUTuoEaqs2gdb7GHbyfSLzfpZaeP6IY3wIPfp8zPB8F+nnuELB5XFvvlHFO2AHbAZ+xwK8gYMOWXYsYJadhPZ4kc4/AXz39BmboGD1hHza+XRtoFo1t2DuJuW5rY9mFB74eUJuePC0YZTXaJyb5T1ebi7lieyZ7jAPemvHt3sCFWCt2ELDkpEW+LIaeOD8IDp1DWr0eFmNVfmmdatRLC1o/HjlpB2Lm51c5qaVmu6xUu+oYGDu5d0Aux3O52COL7WU3UVSYsRX7sPjuzfy/xl2BGT1xD3R7Z3fYSYU9muAQFl3eLzOgW2bugRsj4MIr+bcTqCkynwDZ60cV3nZwOqi+i8bfivY9pJ2d52r3uxaIyp+XIvbYul/OrieZxBEg53Vvbz4QqCGWVPtibOYJWPSAqyVnOzh6wCtJSDF5tm6vtobujoxd8lkObKdhbtajaA5XIcngkVVHJQqyzA2gqf0a36DWSxG7BOU4T0ywHhjdbGR+ALbo52SO36OPyUy4TiBte6qD7Woasbul2jAFzr3sZWFSkXah6+oC+s3xuRSr6uI0uJGthVeSza6TaWPraByQ5LcXN8MWl67JfjqiRYluZnWZHfG4QvIdFjq6QZLZGDGdZDcbjTDbwqMEed+kr5BkHjLNbinonHiYQHwfKbX3tXeGJLO4w2TuKQu4dx2Pv5OUL0lmroCTqk5Q1Y4yVwCtJ9r9VcZiGxeLVDbgUFIT/HLz6Yll//MKdn/++HD4HRJMwtjouGHWvnMBNz+xzZ5Q99fjNxMWw4J/HMTQfTIyodhVndMCHRq/6RXr/jJZaNiVCdHfdEwwbRZd1YeRtTTPOP3wl86TuQBURFhwNWNu2737n1ek+4/ZNl2edlG/QSEzD4CPUj5vrGCU8uzat52Z73v4fOlV7O7lB5v0ivju72hj22QuALv2am4jiwDONQR35XeS0H8yH4DOdro6FDu71IV/3lp+Ir5fpazG37K7MSc8sC9HxiFwwfPpfNdl+1KXWaDB1uyOsc2QdM4yPvHerwRrsbndIOyg6zXBLzdtn2ju69LTivfeLrOfiPBV0Oy0cSDsuYR47/zN7GzBWWHPVRRzCPdOnwlN96F2FIus4nJkvgDtKjZfGLy88bxn+0R7/6SoCdph6WnuZ0jxXwhzzyNcg+5fzM4YhSvMvR1d1DvI6x3t/fPw+LrPbHetSsck/4WAw3wt3a+Aw9l1QUM6fhnf61LcvA7swiJfl/vMZWVLxlFguUlcARi8WcYmdnNeyMwXsI+KLIaa0TFe7GwBAjZrOhku6gphbPs9bYBjdu4nKrJ8jB31urSv/xK6YuIA+ARa1nExzM8+Zx6IijwvR9pJg21KgFSnv0iCCZzjehpZDbt0TG4HhEW+SlmGPUCvdjKG62vmADDni9ERVUV24XWlb0VFPj+F1ELbUfyAhzbmVEoGtfmnDVauslTm6waIivzhMku1O/rNnNgw9WQOADJHra74FnullwfiMKMiXzfbzHVtl8oPuDOmKSax7Ko9nDM4q13pF4EUr6DI7U6xGBSn4qKd7f9Vd/2ah6kOY2ase4d3UOSrkGIPW+1cV4cddKFs/y+qAywMjt1+PAdv1sN0wGT7fwtarVOh9Ri7evbzCop8JakK04J92L1vLGQqnputsEdXidNae8vS+r7JCO2d7P/tmNXu67HdjNtsv+r73iEmmam0o//agmo3NrjSRqWlSWb7fxPPbOaP62X5zys6cP9cdzeHot37gzNtW8u+3Om7Y/9+7rbd0YHrZ+w88YMrw8qQ7P9VTf3a5T+L2NhrXVFy7+jAn3v+dkPbniGaNZBkJqF1m2izWNFdbZm4qCc68DVnaE2f9jiT7PoUpPhla2P393SBtWh1m61N2oey6wG6b/m1xdMcsKU9On9GB76SZEPEqiIylym0TuYV0P3q72GBJcvtyMYgSK87RDALfScPXG/m7Hj+7Tkb7xs/WMZ921jYz8Oea2nL9nWKBsGzXgnCDj5DFLo4orIJepWaTYlTwAKJapF00hnNTiLWIYN5y1nX28tsi5iu/cleSzVMMuNHfgKJ6tzKvdX6rsn+NpwgyX3jsL1Vu550GbZnXYI5DbSu7XldfrY3OLqI2Wm87kYbJJmoNB/3cxOh6ktdZhJaV1u7e3+Yq7Sty5Htkun2wOxTl+bkvCjaz/U7lTWZhq6nTTKGr+Y6YxbZ6YyQ7UBrn4bzcbEyzwJ1mbkFZkjNYrf2qIeYZO1L82SIwk6/F230Wvta8OC3L3WZ3Q+wwMxsF5C0iLyinFXrgzqDf1K06Bz2KErlpmCKSQxVH/4yNPj4UsjEN6A9UCdXNbtdLpB5iUFL17na67wrSXuUa1shOyXqkGSy+yzX0f1hfmydOlYoUTanNdladCWp48BwyrrnqdCHEueAuU+HERJV7fQV99MeHpmv2NaqH/eL9tytsQvRSV3q6mqvvNSs8nGK/GszG2WuAV0/7caumKSbZwzdrpVbLNA+J6FijgvShQdaJrsboCW5YtE2VWd13a01MuX1rkw+48bQBOd1e+M5ANIk0xVHtbKFMtFEWw+Bguv7ugGW8vt5wHuhSS4EaDrZQmMxjy2YrXbdFdkMmyNPMFtoILpiqbuFxtsKXSbxBlh0RZvEjL9r9zyehYas2T9nkTaFaB6mLEDlU3YzYEVX1OazKAGbhcYbDv0wcQfojGPP5nUvRBdjfi40qkvsYb7uka5Skp0TW+S5XmFEZ+4AFwoxxGuUL90muxigU4o9D71uMR7zsEu3raxtfy3Ln6ps5mi0qLfQ3tm9AAu2Z9HhzDFHK+yuhbY4zOlwyDJb64DsHiOsr39FGTT3IY2gAtqXxkkcAz7a3hF65fjSKxPHgO46fi1URrEQKPUMSbZvSWbBoG191RRsC93XZblmV3a1u89eyVSvUABtNJwdE8eAmALXHSLb1boVqtteJ9mFnlovrzZf02Ox478DVuwsymAhQzfamwgdjXUlaZfnLQbAx262BebQ1h9EMBoTx4DYlF1tj13sM9ksM+4X2NETz0CpxpWyOxYWeIVfEf3tKmM+s2WeAVu6hoo0817wWdZSo6rFHt70OXbKtaC3A8JK2uWObK0ZduigI5zKujRWzK3WjRPTPoPHcuBmVYpL9vQM/K//+B//7//4j//4X//2b/pvbaf18/nb5t8x/0JXmR6A//u//Nd//4//85///r//r//4P//zv/3bTPTn9z9/n1/W+5f/Nn8Avbj1bQlmjjr1f/4zxRL0Iy9BdyWYm3YoQT8gnX0dkC9BnXUyZsna+rv+/fyL80jP66j7OuqhjnCk920d1dk6Y5YQB/LI66b7uhmhbgbUzdjWTZ22j1UCzDm3eXibR7AZtvJqzi7nNnPsswRQSzrm85ydzefxtlm/hXS2Nq/2vdu7wRepzZqYz/lt83mgBXuby7J1luCZXlUW5Dl7mynYTGAzbW1etq6+3jHn3GbyNlOwmcBm2vft1cPK6uPPF2duM3mbz2DzCTaf+3ZetrZlO3yR23x6m89gMzgRdb+8re1XzljbJbf59DaXYHMBm8vW5v62GXPObS7e5hJshksCuv7EnHXYrb5dwkxycm5z8TZzsJnBZt7bTK/ahnbm3Gb2NnOwmcFm3rbz6mGfFeWER+iqxnOb2dsswWYBm+W7zWPmDLUtuc3ibZZgM5wY69Z2m7P4eRt7WM1tFm9zDTZXsLnubS5+lcQeVnObq7e5Bpsr2Fy/r1Ul1nbLba7e5hZsbmDzXr8N8eszKL4z122n121n0G0n6LZzr9vWirF6Gq6SuV47vV47g147Qa+de7126681uqC2cx12eh12Bh12osLY67B7jdrM27kOO70OO4MOO0GHnXsdtuauMeJMkuuw0+uwM+iwE3TYudNhltMax2sWvb8ouQ47vQ4rQYcV0GFlr8M+PetZOWA8l1yHFa/DStBhAH+3lzVf16o1h4HNuQ4rXoeVoMMK6LCy02EWa+xj8znbmTDn3Gavw0rQYQV0WNnpsCfHMmv9hNrOdVjxOqwEHVZAh5WdDoOcJdqc67DidVgJOqyADis7HWY2zhxnCZ7XhKXkOqx4HVaCDiugw8pOh9k7gNm3Z3vDDdiS67DidVgJOqyADit7HbZ6GM12JmjnXIcVr8NK0GEFdFjZ6TCr3VnLEntYrsOK12El6LACOqzsdNjTzqu2sZZyHVa8DitBhxXQYWWnwy7nlLcZeliuw4rXYSXosCJowdbmcrfv9Zfvvg5f5nqseD1Wgh4roMfKTo89tb5shztyJddjxeuxEvRYqWjB1vZ7PJc1pz1f5HqseD1Wgh4roMfKTo89c9k9yqCP53qseD1Wgh4DMo7dAvlm893u8EWux4rXYyXosQJ6rOz0GKwYI9qc67Hi9VgJeqx0tGDfx1ef3ozrXI8Vr8dK0GMF9FjZ6bEn57Lp27keK16PlaDHIEyHxTz4NqpWznC0z7keK16PcdBjDHqMd3oM5jLyqybNf1/mf+b5t86/sv77BjmkdcRev3HQbwz6jff6rc464hJzzvUbe/3GQb8x6Dfe67eV87IZxi3n+o29fuOg35gwna3NLL72C/SLXL+x128c9BuDfuO9flu21k1t5/qNvX7joN/wUj7v9Zus2p7j/3njZXTiPGdvc9BvDPqN9/pN5hhoqwRQ27l+Y6/fOOg3eHGq/7y1uYm3GVZDzvUbe/3GQb8x6Dfe67dKK8dZggJf5DZ7/cZBvzGjBfu+vWaWNaqgnXP9xl6/cdBvDPqN9/qtrXZetQ3tnOs39vqNg35j0G+812/ibebV4+DyJ+f6jb1+46DfGPQb7/VbXTavnKHWc/3GXr9x0G+MPXav35atq4836Gm5fmOv3zjoNwb9xnv9tlaM1cfhGSHn+o29fuOg3xjXgb1+k1fOAjnn+o29fuOg3xj0G+/12z2uNzNKrt/Y6zcO+g1vMPBev9WXzfC0lHP9xl6/cdBvDPqN9/ptzShrfOO4zvUbe/3GQb8x6Dfe67dbGay+/XwhuX5jr98k6DcB/SZ7/XbPniXMopLrMfF6TIIekwMt+DqXrZxhxpdcj4nXYxL0mIAek70ea+91usEXuc1ej0nQY0Jowde+vdZrGFWS6zHxekyCHhPQY5LoseZzBu+l5HpMvB6ToMfkRAv27dxefRt6WK7HxOsxCXpMQI/JXo+tvcbKGdZXyfWYeD0mQY9BPAN7E7TLud+ro18tb226/vNaz2cJ4Q6H5LpNvG6ToNsEdJvsdds6leqrP8ySwOmF5PpNvH6ToN8ER/Nev905zhKMWSdwEiu5jhOv4yToOAEdJ3sdt3Icqy7apgR5HXg9J0HPCfa3vZ5bOa4SrJMcODeTXM+J13MS9JyAnpO9nps50rHqQjYlyOvA6zoJuk5whtvqOpr+V7uufv2dPmjCFSTXd+L1nQR9J6DvZKvv7hynV5SOsilBXgde50nQeYKr+Vbn3TmuEtCqC2iFXO+J13sS9J6A3pOt3rtzPFddyKYEeR143SdB90HAMf3nbR2sHFcJpreUcIXJ9Z94/SdB/wnoP9nqvyfHWRfTd0W8SlY2JcrrxOtCCboQiET6z9s6mesHyfr7fFFzXSheF9agCyvowrrVhTR9mXfOELKh5rqwel1Ygy4EWLH+83ebZ62D/q+5LqxeF9agCyvowrrVhXd7z1WaYA2ruS6sXhfWoAsrYTpbm+8eJ6vnPV/kurB6XViDLqygC+tWF959evXxArWd68LqdWENurDCGKlbXXjX9rIZfBg114XV68IadGEFXVi3upB4vPo2wRe5zV4X1qALK+jCutWFT/u22LdzvVe93qtB71XQe3Wr926b57mMa+dc51Wv82rQeRXHyFbn0dS2t+04h+X6rnp9V4O+q6Dv6lbfPbNmiT0s13XV67oadF11FuzbuficwQddcz1XvZ6rQc9V0HN1q+fu2l4540yS67jqdVwNOq6Cjqt7HbdmkDtn6GG5fqtev9Wg3yrot7rXb1z8ioHjMNdt1eu2GnRbbZjO1769csZ2zvVa9XqtBr1WQa/VvV5b43juIGnupmjueamvEkGfz/Vb9fqtBv0GVFj9521dyGuGWTPOWs9XK8FJUM31XPV6rgY9V0HP1b2eW3Uyd+ME/rya67bqdVsNuq2Cbqt73bZynLtsfPHSct1WvW5rQbc10G1tr9umf4emp4ngZl7LdVvzuq0F3Yavcttet62cp3cNqMkWUC3P2dscdFsD3db2uq2/bIY+33Ld1rxua0G3NdBtba/bVg9bfR9myZbrtuZ1Wwu6rYFua3vdVlctt1jbuW5rXre1oNvaiRbs+3ZZtl5/Za3rcCrScv3WvH5rQb810G9tr9/u0dXCuG65fmtev7Wg3yCCtf7zvr3Lq9bhi1y/Na/fWtBvDfRb2+u3e3Qtm6G9c/3WvH5rQb81Rgv2Nq+eJmtOe77I9Vvz+q0F/dZAv7W9flvt3DajK9dvzeu3FvRbE0znq813X4e+neu35vVbC/qtgX5re/22crzXLChrrt+a128t6Lfm0tmP6zWOR1w5cv3WvH5rQb810G9tr99Wzn3Tt3P91rx+a0G/NRyde/3WXjmD97vl+q15/daCfmug39pev02PL01/K41ZgoElyG33eq0FvdZAr7W9XrtzXO09Yglyfda8PmtBnzXQZ22rz86DXjl//p7wUqblOq15ndaCTmug09pWp53z9toqyTn9sCfc3Ou5Xmter/Wg1zrotb7Va08JPq1xTg/wSQRfpnXQvW7rQbd10G19q9ueHFdJRixBrt+612896LcO+q1v9ds5b2o+Oc+S0IAv8zrwOq4HHddBx/Wtjjun9/s8V11A++c6rnsd14OO66Dj+lbHnfMe9JMz2JzruO51XA86roOO61sdd05v9zn97fhCtef6rXv91oN+66Df+la/3bbetkNPy/Vb9/qtB/3WC1qwtXkqiVPW32em6bl+616/9aDfOui3vtVv5/RFndM7gpGyeq7futdvPeg3QNrqP29tnqvrnTPcSuy5futev/Wg3zrot77Vb+f0ap9T02Aor57rt+71Ww/6rYN+61v9dvLKWaLNuX7rXr/1oN866Le+1W/n9IKdvGobyprrt+71Ww/6rVdMZ2vzvGdxzv3YCSqq5/qte/3Wg37roN/6Vr+dc1d0Tk/PCTc8eq7futdvPeg3DAfbt/rtLKuWKY6qXL91r9960G8d9Fvf6rez3rV8/a1LQYB3q+f6rXv91oN+66Df+la/PeN55gze7Z7rtu51Ww+6rYNu63vdtvo2jzi6cr3WvV7rQa910Gt9r9fm3uScu+AT9mUj12nd67QRdNoAnTb2Om3uFO6+DuN65PpseH02gj4bB6azt1lWz1q2P1/kumx4XTaCLhugy8Zel92r5D2nwRe5zV6PjaDHBuixsddjq7ZXzhCFY+R6bHg9NoIeG6DHxl6PrVl0jmt85z9yPTa8HhtBj40T0/k6nrlFm3M9NrweG0GPDdBjY6/H2tImLdqc67Hh9dgIemwUTOdr316jClaOkeux4fXYCHpsgB4bez221uk1o+BMkuux4fXYCHoM+D8G6diuWa85DFaMkeux4fXYCHpsgB4bez22bGWJc1iux4bXYyPoseHS2esxerUzfJHrseH12Ah6bIAeG3s9tnKsI9qc67Hh9dgIemzgGNnrsXut2swkuR4bXo+NoMcG6LGR6LHVt5cygFGV67Hh9dgIemxgq+312MqxbebtXI8Nr8dG0GMD9Nj4rsduZYA55zZ7HTaCDsMIY2Ovw2p7jWfIOddhw+uwEXTYAB029jrsru01rmEmyXXY8DpsBB02QIeNvQ5byqCFUcVHrsOG02F8vHWYfQvpbG2entp7Z/fcS+Mj1WGWmM+5hpzRgv0+euVMa1f7fJHqMEvM5fzWYfYtpPPd5msmsUDL790OH6kes0R9CYLtBLbv9djSJqvWn7MBPlI9Zom5nN96zL6FdLa2l5ffxOWc23x6m996jAHqoP+8b+/Vzi32tFSPWWIu57ces28hnX17L2/k8D1u7bfu/dea5++Z5/N3QL9I9Ztl7ksa6qhAHe31W79znH9nSQZ8meo4S9SV4K3j7FtIZ1tXd46rJGVTgrwO2NfBW88xvErSf97VQVk7/zvnT0nKAfNDqussUVeCt66zbyGdXR2UeWpRjpVzm3+hH6T6zhL1JQh1gLP7Vt+VeYO+zNOMpwQwZlKdZ4m6Erx1nn0L6WzrYO7XyhwbpcA8keo8S8znHGyvYPtW55Xpbytzf15wNk11niXmcn7rPPsW0tnavHKcSrM0aO9U51liPudgc0ML9u09a7muEsAXqc6zxFzOb51n30I6+3YevrYZRlmq8ywxn3OwuaMFW5vnbFzOlTPUdqrzLDGX81vn2beQztbmud4XWX+hb6c6"} |  |  | - |  | - | -
[14 empty] | {"index":133,"total":402,"filename":"Advanced_Project.ifc","data":"8WGBr7tp9Q/eh9NbPpDiX95NM5f2cGqIzwp8JyhiT/prlhqQFX2FcyFnfFTgsxrTW+3F5wN+KZnM1z/SZ3SXSvepnxTjGMBvJSuibDViKG5J+zok+dEeWd3o6IvzCZ2kj0UXXTLlS+3pWUmFbxw5QZIfLaLzunhT3Skc97OkxEdKGryUGWKoPZnL9eVVGdXQa+IgwHdVqjZLekxZ4+OMYyUOAvxSlbLWGDfdxIPri9VgdxwG0EtI9Riveetx/vEM0zh7oaez1wWg+y9g/MVxgDn+dCe8P9dNxWuJb2yydu3iOmUGLKd5dFZS/GicqnfDuKm0GTV56h0oKlKBInvGTCneMl/oI0zyb8eLpKzPYhelazRAwev1va9S9qIR0XZepZT1A+s9GIVX/FESDpOelMga+YNRHYcBih5VFJGsPrBea5BrQ642DZgOvadv1Iy30xom+dE6X/5Ws9NHg/Weil7jghQ/WkcPYxxHlwXWFbnWQXM0faux/Rn3SPVRMH1fo0Js6vx6NeDzVpq5CtewvT/fDYgvfI0kn0tmGMzOcRTglxtf5iocQTg7x1GAXwxPpz5c3uuILjCcQcyfLwd8lVLGlCyVukaSkp5rhCQ/VMBnkuOckj5hrOcUGyyNcxwRKD+jc+grl2Xc0NLXvbteSBBXxlfssOtVFg1awhyb45CA7m6dSndRATUufTV9cqrrRs45r3/DX0CSf9s8NekikRVNIx0Lgqb56wUBWRrJ6jzpKah1nUoVWtbTciN2eI5r7OMKF9RlHBPQfieaTi+45WF4vm60nGMn5Y8o559TDMgK/WHwQzkOCvzWL2WsyypRgzUiNuFQdf56QUBbUlyrLOTLNJxYrxhJNnrkpB1D5pMs+QhOYOY4KPDLdSpzhyvDplqOowKf16lOTfJQetIxLotDyCbHYYHv61TmOlzBPhRHBb5T1OMHTV2bRt4ZNFuOgwK/1KRVk/mLf/6RjsYOM+v2mi7GVKRAkn95G006vYzBMg5g6CP3kOJHg2gba8BEt3u0jcXnHAq8OGS99CcdGmzX/xO5SYxJfrTId0/sbdxBGCS+ju4sDgao/Czjhd3E47qWyCe9yKFj8rp3iX8BozoOBugltEOPElW9EKJJ6g6DqLyqO59J0teTu6dunYICynEs4Je20dauo7X1iVuoyDgUoNem9JB3auNQfpN5JTVWvIReQhFxobuWjbRDlvyQrCXJr9FyVZO4/YIVqbtIaQxAjfRyUqUFWys5jgVoRY67uimN219Zj9OTPvUj8+qf2sZ+QGssIq5gL49DAd81qb5Rw2F6tlPWKeBv41iA1qRKMt1s5asms+rnixQl/0Hkq544GZslsAzLcTSga+hHpKQeZrv2oGWG0gCazC0aIZca+cnjxV35Oxw4cTTgSbK2jkl2PcfyZ1xWkAHD41gDwcD5Cgd83CcbN6ueS2ymdb7iAR+Xv67LWveNM7zXkaPHBD9xtcrtsve/GjRP9JqggerSC3KocbXwAlgOogPmetc8Y/IctC35df8LZ8MgOmCRtReB0vDp7P0viKLlEEhIeuBHnaKKphcDo9M7RRg6UWzgusJrznj1j+tzOXwz4GRdSTc913eWN3SofTVIFBFQXGsl3Vgh3Zy4Dqto6npzSQToaBHth+LwZBjB4itHjIGLrarelan3881aihskiAcY/mt16B1yNYllDFpE7y7rcVnWMyDHOCZYai4yTycRz+kyW/pgkllAH3iAuSsICFgkaHo3Dn+WMoKr6ok9ZQhLzfcT6KpdO9BZr8bRW8Iqy+GxQ1k4xQBPRUfoBoO082jvsZkgzX/qKSdNMo3Lg7KI0ePAkOS+eVjjeUpuEzcrruU9Xt43MLHBg4AAnSNIrPww8bplYc/EKYyLylenlKbRtaNuJsJ+X44iAlJBGvHTeyJnf59lbK6QMKijgECpSVSfrAX1eTCajkcvg6iqU5iKFlIPdYySA1xLUdihwx1aSTdnxjtryL5No23uP9B3vyDF6Kq6vg4vWkRWA6nleTnmlAGtaKx2pShqKtWx7wlXgspXOODzupbe/xJ9pdG6g/CicYnCAZad/D4NWz/cWokeErhHjsaE+1VIfVK36SfHdc9YmVNF+WAF5HOJXhO0HNS3VzvjW0Yl5gsgrDW9Ya30vmUEZgfBgBdS9nXL6MztfcsIelAQDLDQ0na+1Y+7ZYSlDKhDlgfa3rfp8/uWEXShIBjwgpa+bxnx+5JRhRT/lt35umSESQatA3eIxFr24sdeMoIE/yl2p8N5uztG0CmjUMBJrMNXYYm9vf0kfST49azgW/u4yoNOE0UC8nim79DziH3OCS/tEycZuDIFV44D86SyemqfoQcS6en80SBZn1hMCrYEyVyCUMDkTBZ9/1yfuHPaJ66+iNAFJMza32bTl9lRIKBWXabrgyV6nfW6rq0uRhqmSmXUYXZKRU/V6iVecI5BIMDCEZ0w5c9SRg/WHGMxqXj10i4O/CTLa0ekq5RZ4Vn6DjDu+pUgFqAwQ303X2Z5vel3GS5+UKHdsgir5TL8kIlBJt+OZyJLEAuQv/sZSBlZ0Ik8Zq99wgYPQgH6tFHWuKp4/HEg50pR0tS4Spv9XKMN48RkhnhuiWIBsqT86YoSFdP6G/naPgsZejJVxhpN1rN7bJGdVUUA/gVBoLREsYCigVBdeki/0U54KRV9g1P59ZfZiq2VihDRBU/LlCgUIH+sSxuFwtZGbd35Jz1NIf/vuiaq2kgf7qh4RaLEoYBfrgLpadWuzCB9pxEvapUoFGBBsm0jfsKhE4UC7qEjbqOvUkp3Oo7xHt28zUr6BIUiWk2S/xQX8k2SPeP7KyVCD+LtlHqxaZ/7K+lor/srcLitROhBi9isb8Rmet1ggYBkCWIBL4hjf0Mc+/sKC5YyQhEbQOL7Dsu1kNjeYSkRetDcUJFpy1Ec7V+gXwvCAr/RDEt8h6X8c+hB8ujB1x0W6JVRYMDcUHkj/dr7BgvMY/8UeJDfD1xmd4MFk/xbtF14g6VEYQEL4Mvv10z7+wYLOPSILmAuqBzv/TlK9gpLwlVddE7g6O1HtbBiHmt7v9GnAjo0PIgL6HumGoPSlQZR5lcpr0cUoJRwrq9EcQFxNbISPFgP4aV3io3fKWJVRgo6jV0QpTL08YadIdG1+dKD3jiRsSgrqaef16/rAg9nrlkSXb8uNTysugInYmoQGGijz0g1KkdJ35m3JLoyLjWQAppFN+jmzQlJRhFoUdMyMJqGREZoyZDorm4pNS0y6dDbFw1SjBrnUI1XVDRcT0WYXTCOe1CNjgmIpNDpVZ9vrPW6ogYcunSZ3TX+KU0kS2QoZBQYeO6TiHrJ+f3e/vm6cQLruvoRGfgivNX3jRMwPI4MAIeuvPgKSkewN04qlnLfOjfzTO8Y9nmWEx45768kG9bl5yOcpgLfF3ZguEQnA25OXNag5pv+RK9ydUwxCHHe27f63uUFf0IW23UFSLvmmHYPeAmnBsEAA0473Av+16XByO5ouCDezdHd3glCC0fBALHsJ6sOkerLF2IRWGxXOKkoylImcG6m0wThgK7v9+tLBoceUSn0Bhd8mR1EBtTvyMpYVlt5PBP/YrFdc5e+O6aPC5Mer4YkgwC0dG3S4+3idPQ40YvFVq7pUJ/eVMdUH+K0HmEPYg26MtCHMUWCLYTGg2KrBVKU6RVPnNbojIButMg0JY6AlHNvUWz1GtKyJqFG4xQhnEirQWhA/k7ljT6lT0M3GhJbGY0jklIaX/cDzdQVRAZkxaZMenFjolDoeDMbOb2dBNgdIQdlDSazjCRY22xuALHVMRY1BKuLWdJrLZDiP4NNq+nNTXtfD8F+HgQG7O2P9Ea7dXs9BHVFDQIDLypZex3vz+/bIdDaQVzAXP44+H095PJqcD0EToTUKDBggV/dA79e90MIkgwJqoglK55TFd4PqRFhwKCvzk2K9noI9MkYMAB0rgumhXiu/L4fgkmGfC5kiJU3Qyy/7odgVUaBAUuVqm+qVLE3RBJsD9T4jACyr97oq/N1RSRDF4qPCAC2iRy2qb6uiEAZoyMChi3VXkJldEp7RQQKGSEHLREpvxVae98RyZBkeIADuU381pHpfUkEulAQGJiUoFNPUafdVBsn+KnPTPV9VF50ZWBylbTbdS4vQtW8TBUULIgEoECTGe8NLyqjOfQwvoIGDox41SAUYEFD6SUi0/lldijPkIb0luD0WZOhQCvjBW4R7HpWzKKLGg9Pphdjuk7qMuShGwaRAPmrH2Um6HUNEadvEFv6KmVIGtQzzeIWqt62qfmFLmqjdRQPK5pFywjHvGp0QkB6kIwykdsabrScIVIxqEkW3U09B4DJGB4qNJJpQN9SbUe//C2gi0p9kpQMM3ahKBLQul4z0eleViTXiH7IRa1fKSr2dlyUzs/E1YJAwNBnp+7UyIxP89ryAy66Zi7S8ZVpvAaXIMlIoCmmWFy+vm9wlrfb+RiLLYgDqD6TxZ70TcmzZMstOo9htVK0joFzKfBWTQviAC9uEXlu0es6B0OSMaHzmwhkr3M8rd1i3OAv2KLXbQ5o7hA00EWA6WWf3BTS8IpOcY6vsbQgDsD6XLTIBUlQn7+ld1SO3qXEJMMQmu7cqMws53h4ykRpiL+S/Iihjecz1PVdsUNA+FS+tM/RdT01tmefJL+uCzyAnjfC5xgN/kB+CA5wtCAq0MYkI/WoL8vxemPlRvjwcJUi8pUDQXr5vUKSkQhIena/KsC6HsUSfM40GjzpOQw9xqlnYSDFsHX0HfNDL2vpGH/HTPmjD4VnBFivOkqT6s2Ka7n0EHz6dUFWFoT6qttpLya2ICzwYuO8MVA6eMzNC3RsUVgA71WM57Tx5oW06fvmBRgehAUsZ6jymzOU3lcvoA8FcQHd7u26hSINfs06lkDTvpL8FGl2XL+vrmAFxucE9ChI0xsM7R171ehenGB0sLazzDUyder5I72MqFAb0oAxZd0gHS2iz17qAfKCAcMWxAKkj/4kESZ6jFqSpesGQtUltR5q6+1KUo/j6YSGDzu0IBig01cRP6HHw47xyIol5fBHiwTBgJZlEdR1e/A800CyjqPzYqZqmNxGv5GlzaGv75VikoxuDIhHUSyivn5/PSBo4TvuFhAmGc02euyy6nJVj3KM/TS9cKDH0VRDlauUp27PnuMcHiQZnLDJeot6HFzJsrC+7gxIEcduXC/panFdbxQ9f2ycbhQOOPHeS3tPs2f66JdROEBrSv9PViS64Tw6UZHxLANSNG2Zdbn+IsFeSPsADgLW5n1n4DqND3cG4M2jFscDkEHT36fm+H1nAFIMwwFwvp/dEbfyR/6rXlPQB2S7gg4gyTAcAKfx0/tE2nxOWiGz41osaqA4HPBLikVfLtbTwCJ7G5wVbPGNgV/MflFUoJBROGAcwy668aAHFudZJdIorL5j1i7yh15o1ntHDSsyigbYuxfsC2nJDViTQTTg15oMSS8tCAfMQ7QqRfVdsusEa9VLUUlBGGlwP2S9Io5Nyo0XY1oQGhjXP5qitfSETZ33Q8QFiZ6iEZIcdJKkT/eJ4Xj6qQWhgX+iuS0MAksZNk7Sq3waWpeavA7R607qqYsa6Qd/8qlL3KpnmvUQOzROdEzANo4/XvwC3EAPik4J6AsXIkWVZq5vPF/Hi8eJZ13V1PoQbvSqGvrJ6JDArzUpC5kfFoWl140rPprVotCAAquyPhao10uvU191vIih59uzvhmb08/YyhcZUlLHJP/Wq4kSzj85J90vl66LhoeNo6t4VkBZ6tetJcVJywKfNDYiHX2cCyoDlcF4FrEFsYEBSdFHWjTRfpE18vCKVd/0lDykL6pQJ12Dith8hEuPbw+cZTxqoQdUrqOiTYPDeidFF4R/xIOPgGAedkM4vwfBgd+d7/RrXU/GZdi86dEhgaIBKj3IwHoT4+rnRNq4RfcVxVXK6lkf9zj0KYgOS/keRQf0CoNOouOgCi22j0Y/iraX3jUeR1FYI9oNLzn0KDqgek0xD6e+cjFxL3oiuoxQ9oXO1QMTetRX73FDKePwwC9VGZGcenRKwJ5QP98dPcv0rccEpA+dyriCq1s9OiVgD5T7Y3721nYPIgK/J6MwCF3zaJAywUmvHgQEfj+NH/IlekQeHMeHdRU1LrDSPWnLoNYH0yYToY8nBvSJUujcf31n4PWePZbyr1ok3RQMfS5Vd6eh38S3BnT5L8uGfF7I5XHNpOuI0cjixUQ49dEvffIUj0H3ICKgSdbOI74j6/56TdsiI8YmrC7DZNrWuHJXFgDjTmKPIgK/t3j0RH6PIgIKomERS/k89A3UOW3rkcGse1Y6bZNuLXMe75XDKdYeRQS+b2Cci/4h4iTpFUtMMWwdkVA6ELjr2xZz2tZzzEnZZQ/8Q7eaOo6dIB7we002fRi269ULPaEGu349CA1oTcq8J4ulpGeFLi7UuHk8nnI40pi2xZORRuP1yBok+bdjR3c1frSpmvTzAzpldINAB7gMNr03rn1iztpJHfYQkDJrK01En8vvek4IGic6KKDsiKQyRJbz+bpOl8frTgoDkPWzzNoa3FakqvasA+3+GDqD6aaHFdasLZJMnzLRyyg6a+shtTHczwzH5np0UuBX97scW9OXGGDt2aOTAqyTvKrjs8g0W59ZW2uvnWPWrj+iTIvu4hScvT6uEJThqlkqkOfNiRG1SXqqSptbN351fZERJtKjwAD/6FX6Y7TndXcSp+x8UTp07ayYGwR/9CguYOuxed97I25kgOuRqCfJKC7w62lgVtJL1l0wfc8OFmE9iguYo7vvI6xFH3w6f0j3B3VVhh4oCguYBD3zXR8p0ufKZfmgtJqKbROFBQYJUSeoqgcL2L7sLlnc75vrI7z4omKPwgJdJ72BetKdxPZ62J3HabfnL7CMUVjANs0mBP163hw8bxQW0PfvZYyIn9RAVLXvup8JH7SXrDJcF+lRXECs0r2U0dHpYPuuex0vpmuERRmmsgY/4Chwj+ICvxpuHrRPpi7D1tF3R/TdaL0j3F/vusto73qRRh9OlYlMY71PklFkwBxgpdPtxys5Ro/i6WtQ5cSqjAID9uCuP2/xErtRMMAWrL0LVv5IafQUs7SLvv6DvjEKBvxWMvsoN8S8enxlQF/w0uFbeByigufNdfs0Kxtc118ytmH+j68LKAegs95LL2UdPZxPm+uTYffz2XocoaE4iyIBphr766Bgut5010LXMXgYzvb3KBJgq/H0J7PtM/HQr6NAgPoxjbmLz090ncF73jbnNI5cPn9h3E4UCLhOcnd9cpvmOeDnbXP130Uj3noEt0gXBzIbRXEA9d9HlgEsvU1b175t3jq8Oy/LjgzRSIriAN8d8ny/8d0gxXiSEZ1XLn7qfKz4ftucB1xKxLhM5CK2JFM4B0xRHEBcY9FH8E59n68V+7a5vtAoou9HX5A/9AxFzVjKsHG+B6J90x0SjC8LJKWA6sWrvsy+nzZPeqLjGK0lbrAcGR/upSgMYM+NdV/IRsoV1pvmMuHiw7MUhQHMgbn+PgPkXCNFcYBfi1b0qmJXPplUHxNaG57bwKJtzvLZF2yB3kNRIEB86bi0qmcKy/F6DHg85a5UzaZPaenjbeBuKQoE1HFOfiwsmK6Dls9jwDT9o743K8sJfQEcDA9PBpi6bJvpSp2ZvsMpf6FENEgybJ7fmtk8rAxDMIoDjMWP3sZWsCR1+xiwXjsxf4F4aIriAPMcpWSpocyHvjIeAz516VHOKi2ec+3j3jQkGbZOUbamngTgY95BuF8D1nj+/VRzG2xmgiT/esREr+JSFAjQUp4a2NNjc9dc87wGTJqkuLGfY9yXVs4FJhk3z6n35/X53sLv14B5OEi9JTEur6HCpSgQ8Kvdr1eQEyQZtk6W2V1fPGF9r8e8BtwGDuLQh3f0GIzOibA9R1EkwJ4fO9/nx3TVJcr+LIOtos+PQpJh0PmX0176HNJ4nXs8O4c9PYoE2CTfFyaHDtculOs4+nyCTqMoEiADQ6tIH5WRdX5+vYrb+H4cVv3dgY9zUxQK0FCREkd0szXl/HoVl8YRpecvTjhWQ1EowDZP8cf7Xo/DYpLh4JGVpmg6Gm/y3HcR56u4Usr7OeBzHJSFIR5fGkj6zrY4hNIGngNfxT0H/5QVyK2AVtaH/Z4k41MCaHjdnGs0zwHD6RWKTwloQ1bd5bveTodXcUUV5j/6gqayMTSslA54AJrC5wTM2SzedHV9MTWNF1MVXwJ1GcUDzEGq9j5jU5zAiKIAtmjv04xSNH25lsbLtXo1BraLKQoD6HmhpE+udLFKj6/qISW9LaGRTF1FvIoWrf2tiXljoj6OykPf6gtv4HOitb9NMvkk56OeouvHZho422jtL9ZquymJXTvFOPqiLz/rtJfGZeXx8ui4H5T16iMkGbbJIUJTrwhJh73O3clko+Pk0KORp6z9k8bdi3Jp9aLRk2S09h9tIjO8NuJ4Wq9JArnpvV19c1V3NvOAOqro00cjIMmweX7r1OZhYXQQUSDg1BPEGp6ufIzQjL5HoCfH23gULF1PzZ66OMiG2UhRHODXQmqDt/GKq0L5UAJEgYBx3kqD/fqgRZ0nsvT0lcwAGsX8Iz7h1LeyFGB6NpwKZzDgP//xH//vP/7xj//8t3+T/6p79X+uX75+Zc4fvzVfv2X+e5n/e6vz76GRZkzgf/23//Hv//i///Xv/+e//+P//u//+W8z0z8///Xz/GW5//Lf5h+AU+S2K2GdObZZUqx5pjjnZnNml/PTJ/jY1k2bNveVM8MXoc16kQNyFtf9ypkhnsLH1uaVc5k5QyRCOmecc7M5v21mcO6ctjbXmWOb7Q9745xim5O1OTmb4QqHzF2fNq9fsDnFNidrc3I2w806Prc2l9nDSnY9jM/Y5tPafDqbYUeBz33fXrVcvc1nbPNpbT6dzRA/5by1ub/GN5xu5xzbnK3N2dkMxxTEw+1yzmzHMxxZF6Ud52xtzs5mOLbDZd+3p81tY3OJbS7W5uJsBmHHZWtzr9Z7QlxfptY4Z2tzcTZD5J3r3uZla/fjucY2V2tzdTbDiSauW5vvUbU8CthcY5urtbk6m2E9z21r85rD7naGsrbY5mZtbs7mhuns2zlZTwILZm6xzc3a3JzN8HYh90+/nVcfh7L22OZube7O5o7pfPbtvulhPba5W5u7sxk0G9On3749CeRMsc1kbSZnM7wLJer8U5OM9tYwo/dlFNtO1nZytsNzabzXbavWK/v2jvUYWz3GTo8xYzpb28/V3vMXmAsc6zG2eoydHuNHj+l6basQup0tn9rWsE+QsyYGOSvkw+as30I6n+P69qYMX0Q2a2I2Z3Y5g817PXbP08uLQs6hHtPETM5vPdbhLrESkrejK/8xtheo7VCPaWI2Z2dzApv3euzW3ZvaDvWYJmZyfuuxDrRw3Qvf2jxzXLWOtR3qMU3M5uxsPsHmbz12K0Go7VCPaWIm57ce028hnb3ufo3nZ2UnX8Q2Z2vzW4/pt086ez12q6Jhux7nfXsU+TK2vVjb37pMv4V09n78tcLD9g51mSZmc3a2F7B9r8vuHFd7Q86hLtPETM5vXabfQjpbm2nmSLMENPs84Zex7dXa/tZn+u2Tzl6f0ap1fpUA+nyo0zRRU4K3TtNvIZ1tHXB6lWD+Mn4Z10GzdfDWax3wLHq4fluCOd555Txb47nPoId8wxJ0Wwdv3YYUWt192pbgylkc8sy5rpLAl3EddFsHb/2m3z7p7PXbzHGVQLrO9TtjUrqJcv37VVc9rxKDbaHO00xNCd86T7+FdHZ11GdUrKdZwgKtE+o7Tczm7OqGoG62+q7P2bdPxdFx7gr1nSZmcn7rO/0W0tnavHI+l83gjUN9p4nZnJ3NoO/SVt/1uW7rebY/zF0p1nfJ6rvk9F06MJ1vm/PqefBFaHOy+i45fQebKXo+f5dzWj2sr1qHL2Kbrb5LTt8Bwlz+ed+3V47sbY71XbL6Ljl9l0Dfpa2+e3rWXQL4IrbZ6rvk9F2CMZK2+k5fCJ3jeI1r+CK22eq75PRdAn2Xtvruru1cvc2xvktW3yWn7xKOka2+6zOeenvPCjbH+i5ZfZecvoPHsvVc0tbmaes9rqGssa5LVtclp+tSwXT2fTvZvg1+O8W6Llldl5yuS6Dr0lbX3XPY3c4dvohttrouOV2XQNelra7rMxryeBIYz7GeS1bPJafnEui5tNVzd/seq4+DzbGOS1bHJafjEui4tNVxd9+umx4W67dk9Vty+g1YIVKd+/l5eRD2fjvWbcnqtuR0WwLdlra67e7TVw9rac2W6Mti3ZasbktOtyXQbWmr2x6Pkn17x3osWT2WnB5LoMfSXo8dy38vJQheNNZjyeqx5PRYAj2W9npszRxp41FiPZasHktOjyXQYynQY8uTVN/HYz2WrB5LTo8l0GPnXo/d8/OarzN8Edp8Wj12Oj12HpjOfp7uf6ztCb4IbT6tHjudHjtBj517PbaUYPG1fcZ67LR67HR67EyYzr6d36sehi9im60eO50eO0GPnXs9tnJcJcB2jvXYafXY6fTYeWI6W5uXJil+ZXfGeuy0eux0egzuj4ik//Zh/Yo9zf0T9ChnrMtOq8tOp8tO7Dd7XZZfKzys9ViXnVaXnU6XnaDLzr0uu2fLNXdBzrEuO60uO50uO9GCvS6ra76ePe65tClfxDZbXXY6XQYX7fQk8C7nuRf45AztHOuy0+qy0+myE3TZuddlbbXz/G3gy2JddlpddjpddoIuO/e6bNl62w5ljXXZaXXZ6XTZ2TCdvc31ZfP6hfaO9dlp9dnp9NkJ+uzc67O5V9RnXL3PvYT+XJfR92jCEliddjqddoJOO/c67c55tQKvksCXcR1YnXY6nQZn2vq512kzxvzkPEvSoe/Heu20eu10eu0EvXbu9dqM7N4lmfHWbr6M68DqttPpthN027nXbasENFuDVgmgJ8b67bT67XT67QT9du7128qRV0nqpgRxHVgddzodd4KOy1sdRzN6SXN9RjDH5VjHZavjstNxGWbrvNdxM8J7lyDhF6HN2eq47HRcBh2X9zpuRrdpahs4VCpfxDZbHZedjstowVbH0Vwh0IwE0FLPEFfPsZ7LVs9lp+cy6Lm81XN3O9+1DjnHei5bPZednsugE/JWz9Fx57hqH76IbbZ6Ljs9B1er9Vj3Nudq2xtWDDnWcdnquOx0XAYdl7c6jo7V0/KqdfgittnquOx0XAYdl7c67ulZ1fewWMdlq+Oy03EZdFze6ri7fa/2Vt7q/Hf8Mrbd6rns9FwGPZe3em7VeufsPUus57LVc9npOXipS/75u4+vWgdvGuu5bPVcdnoug57LWz139+17dEFPi/VctnouOz2XQc/lrZ57PEr37RzruGx1XHY6LoOOy1sdt/r48mWdwaPE+i1b/ZadfgMsrvzzvo+nP7YEmHNss9Vt2em2DLot73Xb6tPLs9zz9vzvMxJEM1ZBcy1LMxJIZflAsDHWednqvOx0XiZMZ1tXc0VJ9S4RfBHXldV32em7DPoub/XdnfOqA/Rdsa7LVtdlp+syYzp7m1+1XaF/xHouWz2XnZ7LoOfKXs/NVfRd27CjU2I9V6yeK07PFRjVZavnaEaI6Fwl6PBFaHOxeq44PVdAz5WtnrvbuS2bGb6IbbZ6rjg9V2DeKHs9t2ye0RKCHZ0S67hidVxxOq6Ajit7HTf3kO6cIeZcYh1XrI4rTscV8Atlr+PKy9NkzDm22eq44nRcAR1X9jpu7qs8NkNtxzquWB1XnI4roOPKXsetPn1m37djHVesjitOxxXQcWWv42p9eU+o7VjHFavjitNxBXxh2eu4865l37dj/VasfitOvxXQb2Wv39Y4Xn0cx3Os34rVb8XpN+CRyD/v/XZ+zZaYc2yz1W/F6bcC+q3s9ds9V2U/qmL9Vqx+K06/FdBvZa/flq33jFHhi9hmq9+K028F9FvZ67d6+65VAvgittnqt+L0W+mYzrfNSy2BzbF+K1a/Faff4LH3Xrb67ckxeR8W67BidVhxOqyADit7HbbGce2+nWMdVqwOK06HFdBhZa/DbhW0PAmUNdZhxeqw4nRYYUxnP57ZehL0nrEOK1aHFafDCuiwutdhtw+bv23NXRW+DG2vVo9Vp8cq6LG612N3Ca51+LliTxm/DOugWl1WnS4DfH2ve11267HkfFqNdVm1uqw6XVZBl9W9Lmv3nGUVw+oHd2us1mFIMa4Tq9uq021Aaux1r9tmvJ360qyrRB2+jOvG6rfq9Bu8VCn/vK+baksw4+/UoWfGOq5aHVedjqug4+pex905rrrIvgSxnqtWz1Wn5yr28L2eu3OcJVgxKsIv4zqwuq46XVdB19W9rrtznHUx9yJMCWJ9V62+q07f1YLpbOtgRRJWHH6eMic4ZV5jnVetzqtO51XQeXWv8+4cVyuwL0Gs96rVe9XpvQp6ou713p3j9cszUszoXWPdV63uq073VdB9dav7nhz7/E2+BLH+q1b/Vaf/asN0dnVw5zxj1JxWCaAVYh1YrQ6sTgdW0IF1qwOfnGddTK/M02vz9OKcV13xKimkHNeR1YvV6cUKerFu9SJPtcblLhl8EdeN1YvV6UV4oLnXrV68c151gb4t1ovV6sXq9GJFP7PVizzX93yunKG2Y71YrV6sTi9W0It1qxd5xuvu2gbVVmO9WK1erE4vVtCLdasXOa+xsEoAs3KsF6vVi9XpxQp6sW314t3OddnM8EVoc7M6sTmdCO+zyj/vbX6NPtgda7E+bFYfNqcPG+jDttWHPM8GPz2swxexzVYfNqcPAQkr/7wfzy+PAuu/Fuu/ZvVfc/oPoOe9bfXf3cOWzbD/2mLd16zua073NdB9bav77j59+L7dYr3XrN5rTu810Httq/e41Jf3hB4W67xmdV5zOg+wJ/LPnzbf4xpsjvVds/quOX3XQN+1rb67x/HyojieY13XrK5rTtcB5lD+ed+3lwepto/fsyiWJK4Dq++a03cN9F3b6rtn7sres8S6rlld15yugzc75J/3dXDPWavnwRexzVbPNafn4L3Q3vZ67q715H1arOOa1XHN6Th4w0H++XPuWr4NfVqs35rVb83ptwb6re312+1Fl4aFHhbrsmZ1WXO6rIEua4EuYzvK0LPEuqxZXdacLmugy9pel93je/7WNZdBrcf6rFl91pw+wxvXba/P7hLM+A6tEuCXcR1YndacTmug09pep91aJfnxHeu0ZnVaczoNb1q3vU5Lr1l0tf/dCqtV5t/NeBCvOoLYZ4t1XbO6rjld10DX9b2um5EGnnEfeDe+91jXdavrutN1eBq+73XdjHHdJYDoSo91Xbe6rjtd10HX9b2uo2Wzr+0e67pudV13uq6Drut7Xbfa927vvClBbLvVd93puw76ru/13d3Oq9YZvohtt/quO32H5/D7Xt+1O8f52+GL2Gar77rTdx30Xd/ru5XjfKsjrwgCnKfusc7rVud1p/Pwnk3f67w1zvs93uGL2Har87rTeR10Xt/rvPbKGfx2j3VetzqvO52HNz76Xuf1Nb7r6nHwRWyz1XXd6boOuq7vdd3KubL3LLGu61bXdafr8A5C3+u6u4/35d/hi9hmq+u603UddF3f67qV4z26oKyxrutW13Wn63rDdPY2s80ZR1Ws67rVdd3pug66ru913fKe9xwGc1es67rVdd3puo51t9d1K8e7BNDOsa7rVtd1p+s66Lq+13VXXL4d1ypZfqG2Yz3XrZ7rTs/hrYa+03PtSGnluEoAX8Q2Wx3XnY7roOP6TsdBzpf/xve/eqzjutVx3em4zpjOfr6efZqX94R2jnVZt7qsO13WQZfRXpfN3Q/mWdsQGaBYl5HVZeR0GZ5+pb0uu2xtx3HXOnwR2kxWl5HTZQS6jPa67M45u9qmWJeR1WXkdBmer6adLpParWizlCTBF7HNVo+R02MEeox2euyp5bsEUNZYj5HVY+T0GJ5hoJ0e0x41c+xuVFGsx8jqMXJ6jECP0U6PPeM5ZSyBPvHufBrFuoysLiOny/AkAe11GS3bk/NpFOsysrqMnC4j0GW012XUXz4Nelysy8jqMnK6DM8Q016X8cpx2Q61HesysrqMnC4j0GW002XQ3tn7tFiXkdVl5HQZnsuinS5bo0vH9cz56ml5RQYYU4jrwOo0cjqNQKfRTqeB7Ru/Hus0sjqNnE4j0Gm002kwztdog3aPdRpZnUZOpxHoNNrptHbMWwiPdqmv8X6X6Pp39F2xjiOr48jpOOqYzrZOZmzqOGernLOOIEpGsZ4jq+fI6TkCPUc7PbdyfBgGuxLEuo6sriOn6/C8Bu3fAz5nK6zfeR7raLMkZbZKnv97We8Gz1cAIaZJsQ4kqwPJ6UACHbjlPbSDZs5llgRWVzHHoVuOQ3cch044+nc6UHLsNmecWWIdaDkO3XEcOnAc+pbjsGr5eaV5vQsOtR7zHLrlOXTHc+h4jmPLc4D+wKtfwBeh7Zbn0B3PoQPPoW95Dk9PWz0P7orEPIdueQ7d8Rw68Bz6lufQjvU2dr3bHb6IbbZ60PEcOvAc+pbnIO182zpru8IXsc1WDzqeQ8eo+5bnoDnNHGePg52hmOfQLc+hO55DB55D3/IcJKeZ8xplMLpinkO3PIfueA6dTTpbm/vMedEVYO8x5jl0y3PojufQgefQtzyHx5PcngXKGus/y3PojufQ2aSzH89s/Tp40Zjn0C3PoTueQweeQ9/yHCSnir6s4TuvMc+hW55DdzyHDjyHvuU5KBZp9enVx+GL2Gar9xzPoQPPoW95Do8PW+MZIv0xz6FbnkN3PIfOaMFe762Zo+xyjm22es/xHDrwHPqW5/CMqr7JOdZzlufQHc+hY0xzy3N4/HW9Zw74IrbZ6jjHc+jAc+hbnsPjNe+ZA3KO9ZvlOXTHc+gYr9/yHNRz2Jxxror1mOU4dMdx6MBx6FuOwzOq7pyhrLEesxyH7jgOHVdjW44DjKbNeI71mOU4dMdx6MBxoC3H4bF1tffjPSnmOJDlOJDjOBDEfWjLcXjm51sZ4BeRzWQ5DuQ4DgQcB9pyHB6/vXJ+9gwp5jiQ5TiQ4zgQRJxoy3F41FBf4xq/iG1O1ua3DiPgONCW4yBrjdm+95qjwhexzae1+a3DCNa2tOU4PDmv9VeD2g51GFmOAzmOAwHHgbYcB8j5qvWyIv0ZyhzqMbI8B3I8B7Lp7Nt79TBHSaGY50CW50CO50DAc6CA57CUwZ0z1Hqox8hyHMhxHAh8Im05DtDH63u2pJjjQJbjQI7jQMBxoC3H4VFDa3Q1yDnUY2Q5DuQ4DmRG6V6P3QqB/bgO9RhZfgM5fgMBv4G2/IbH1pUz2hzqMbLcBnLcBjLeeK/HluJfHoXwi9jmZm1+6zECXgNteQ1PjvdqFmwO9RhZTgM5TgOBfqctp0E9h42boM2hHiPLZyDHZyDgM9CWz/B4z+XT0OZQj5HlLpDjLpCxYK/HVpTzZpSsXyxBbDtZ29+6jIC/QFv+guT8IoOsvQYCbxrqM7IcBnIcBgIOA+05DDchhFa7z99nX41iHgNZHgM5HgMBj4G2PAbNaeb4ZpVk+DKsA8tlIMdlIOAy0JbLsHKWX0sKac+bSxTzGcjyGcjxGQj4DBTwGdbe4oqrz/3VNEdlmrteac7z6Vj/+3rRtkIOcV1Zned4DgQ8B9ryHJ6SzGgI0BAo5jmQ5TmQ4zkQ8Bxoy3NQjvysi1VH0DqxzrM8B3I8BzIWbHXerOXnDfT16j7Weqz3LNeBHNeBgOtAW64D9If1GjuUOdZ5lutAjutANp2t7aunrZ737IJRzHUgy3Ugx3Ug4DrQlusgPevuYavd4YvYZqvzHNeBgOtAW66D9O3b1lnbCb6IbbY6z3EdCLgOtOU6aE7T5tnj0HfFOs9yHchxHQi4DrTlOrS03thbO784umKdZ7kO5LgOBFwH2nIdWior50WIgbLGOs9yHchxHQi4DrTlOtye5PYsB9gc6zzLdSDHdSDgOtCW6wCjKXkvGus8y3Ugx3Ug4DrQluvQ0txHnb5MfRt8EdtsdZ7jORDwHGjLc5Cc19yVVx+HL2Kbrc5zPAcCngNteQ6PD1vj+YTxHOs7y3Mgx3Mg4DnQlufwzBzHJudY11meAzmeAyXURtu42z2q8i7n2Gar5xzPgYDnQFueA/jre+aAL0KbLc+BHM+BgOdAW57D4zXvmQNzDm22PAdyPAcCngNteQ7qOWzOMFfFPAeyPAdyPAcCngNteQ7PqFo5gw+LeQ5keQ7keA4EPAfa8hxgNPnxHPMcyPIcyPEcCHgOtOU5QPuy854xz4Esz4Ecz4GA50BbnsMzP9+2g82xDrMcB3IcBwKOA205Do/fXjnDKjnmOJDlOJDjOBBwHGjLcXjUUFnjGmyOdZjlOJDjOBBwHGjLcZAc2a41npN3FHMcyHIcyHEcCDgOtOU4PDmv9VeG2o51mOU4kOM4EHAcaMtxgJyvWi9rFwP0WMxzIMtzIMdzIOA50Jbn8MwYnl5HMc+BLM+BHM+BgOdAAc/hXluunPGL2GarxxzHgYDjQFuOA/Tx5GbLmN9Alt9Ajt9AwG+gLb/hUUNrdGXMObbZ6jHHbSDgNtCW2/DYeq92oIfFeszyGsjxGgh4DbTlNTy2rpzR5liPWU4DOU4DAaeBtpwG8CTVzxyxHrN8BnJ8BgI+A235DE+OqwQFajvWY5bLQI7LQMBloC2XQT2HtRlyjrkMZLkM5LgMBFwG2nIZHu+5fBp4kpjLQJbLQI7LQMBloC2XoaW5/5keGs71W8H2WJdZPgM5PgMBn4G2fAbJefFYTAkarsRjPgNZPgM5PgMBn4H2fIabTTP3v2eJ5LfDl3EdWJ3mOA0EnAbacho0p5njIsM4Pg/FvAayvAZyvAYCXgNteQ0r55ZW+99sGih7rNsst4Ect4GA20B7bsPNopn7aGn1g4ZfxnVg9ZvjNxDwG2jPb7iZNH3VxewPsJ8WcxzIchzIcRwIOA605zjMEmiO83f2TILRGOs5y3Egx3Eg4DjQluOwcpTfNyUHShDrOstzIMdzoIyjeq/rVh2sViDwhbGeszwHcjwHAp4DBTyHm54xSwC7WzHPgSzPgRzPgTL24IDnsGgK02bGL2KbrZ5zPAcCngNteQ5i42zveUoB42Ixz4Esz4Ecz4GySefDZrG1rlqHL2KbrZ5zPAcCngNteQ6S06rl5HOO9ZzlMpDjMlA26Wz79typv2sdR1Ws5yyXgRyXgYDLQFsug46i1ae9zbGes1wGclwGythT93ruru2Zc4c5LdZzlstAjstAwGWgLZfhad95arSuHvfcnaeYz0CWz0COz0DAZ6Atn2HV+iKFGI8S8xnI8hnI8RkI+Ay05TOA98yrr8MXsc1Wzzk+AwGfgbZ8hqe9b8+CX8Q2Wx3n+AwEfAba8hkem3nTzrF+s3wGcnwGAj4DbfkM4EnY2xzrNstnIMdnIOAz0JbPoDPFGlVrlMEXsc1Wrzk+AwGfgbZ8hifn9ZbtAT0s1mmWz0COz0DAZ6AtnwH6dHVeNOYzkOUzkOMzEPAZKOAz3ON49bDV3rMkc/f5nLHmc8Ygz7mLdc7o95kXywhaK9Z1lu9Aju9AwHegLd/hKcEqEfbpWM9ZvgM5vgMB30H+ef/u/23rsh2+iG22es7xHfTbJ519fG6dBZiq6sTajvWc5TuQ4zsQ8B1oy3do54zPnTPujjsyMd+BLN+BHN+BgO9AW74DtHNePQ6+iG22es7xHaigRwv4DtPmGcs4IYYR8x3I8h3I8R0I+A605TtA+3bfzrGes3wHcnwHAr4DbfkOUrszx3n32tgc6znLdyDHdyDgO9CW7/DU8vIoOC/Hes7yHcjxHQj4DrTlOzy2LgoazhSxnrN8B3J8BwK+A235DjqK/thaT/BFaLPlOpDjOhBwHWjLdWjn+RrPCb8IbbY8B3I8BwKeA215Ds84Pn0Pi3kOZHkO5HgOVNGCvY5bo+pYtmPOsc1WxzleAwGvgba8Bp2bXuMZco51nOU0kOM0EHAaaMtpkNqtK8dlO3wR22x1nOMzEPAZaMtneGaMmxgCOcc6znIZyHEZCLgMtOUyQN++Z0v4IrbZ6jjHYyDgMdCWx/C08z1XVfgittnqOMdhIOAw0JbDAD0s+fEc6zDLXyDHXyDgL9CWvwB9etne4YvYZqvDHHeBgLtAW+7Ck3Pys2TMWyDLW5B/dTaDDqtbHfb4rqWCoayxDqtWhznOAgFngbacBRjP7D1JrMMsX4EcX4GAr0BbvsJS+KD4oayxDrPcBHLcBAJuAm25CU/Oi7ODniTWYZabQI6bQMBNoC034fFhtwKEssY6zHITyHETCLgJtOcm3ISf/FIISzHcPW+VEPp+rNMsV4EcV4GAq0BbroLmNHNc/J3FIAIvG+s1y1cgx1cg4CvQnq8wc1wlkN9FAALPE+s2y1kgx1kg4CzQlrOwcmzn4q91X4KYt0CWt0COt0DAW6A9b2HmuEogv3NsQDwu5i6Q5S6Q4y4QcBdoy11YOcrvm0EEJYj1nOUvkOMvEPAXaM9fmMwhKcHsB4vQy9AKsa6zHAZyHAYCDgNtOQwrx3YuNhlvShDrO8tjIMdjIOAx0J7HQGxKIL/zVT5QHjGXgSyXgRyXgYDLQFsuw8pRft8MIihBrPcsn4Ecn4GAz0BbPsPKWX5fDKIDWiHWfZbTQI7TQMBpoC2nYeUsv7M1ZqT4XKO0rX+frbTejVwvnmFfj3Wi5TqQ4zoQcB1oy3WAkqySQivFOtFyHMhxHAg4DhRwHNb7YmvmAj8fcxzIchzIcRwIOA605Tg8rdLWG/fQL2KdaDkO5DgOBBwH2nIcxMZq2x3i9zHHgSzHgRzHgYDjQFuOA7TzXQL4IrbZ6kTHcSDgOFDAcVgrkNt2KGusEy3HgRzHgZpJZ2/zal/27RzrRMtxIMdxIOA40JbjsKgJUoJFEoCyxjrR8hvI8RsI+A205TdIjhVztrUd60DLbSDHbSDgNtCW26A5zXZetkPfjvWf5TaQ4zYQ3v3cchseW1eto82x7rMcBnIcBgIOA205DJLjy2YYzzGHgSyHgRyHgYDDQFsOwzOO2dsccxjIchjIcRgIOAy05TA8o2qeHcIznjGHgSyHgRyHgfCE75bDoHPTazzjF7HNVtc5/gIBf4G2/AWp3b5yXLbDF7HNVs85/gIBf4G2/IVnVN0clgRfxDZbHef4CwT8BdryFx5b6Z4t4YvYZqvfHHeBgLtAW+7C086rj8MZwZi7QJa7QI67QMBdoC13AXpY9uM51mGWu0COu0DAXaAtdwH69LKd4YvYZqvDHHeBgLtAW+7Ck3P3s2TMXSDLXSDHXSDgLtCWuwC+q7sZI+YukOUukOMuEHAXaMtdeHJcJUBPEuswy10gx12gjn5hr8N49axbFcEXsc1WhznuAgF3gbbchSdndkRGirkLZLkL5LgLhOdnt9wFUAbVj6pYh1nuAjnuAgF3gQLuwloBrlj0UgpLJd09b5Xw+vc84/X5WOwZGI2xfrO8BnK8BurYz7b6Lc9oap673BnWrDGvgSyvgRyvgYDXQFtew8PZWSWAfbiY10CW10CO10DAa6Atr0FymrbOlQLeJoh5DWR5DeR4DQS8Bgp4DcvmO2eGL0KbLa+BHK+BgNdAW17DY/Pcq7A5hzZbXgM5XgMBr4G2vIa7b6++fsJuWMxrIMtrIMdrIOA10JbX8HB2anejKuY1kOU1kOM1EPAaaM9rWLV8zuhYu9s7wZex7VbHOW4DAbeB9tyGx5Os3wpfxLZbHee4DQTcBtpzG/KxanvTx2MdZzkN5DgNhKcitpyGlbOyhZxHiTkNZDkN5DgNBJwG2nIawHsuX9bhi9hmq+Mcp4GA00BbTgOM6+xHV6zjLKeBHKeBgNNAe07DbfPtUaC2Yx1nOQ3kOA0EnAbacxruHO9IHtgc6zjLZSDHZSDgMtCey5AXEeK4/Th8EdtsdZzjMhBwGWjPZbhzXlFM80Vss9VxjstAwGWgPZfh7tPLh6EniXWc5S6Q4y4QcBdoz12Y3A35XZQj/CK22eo4x1sg4C3Qnrcwc2x57n5muLcWcxbIchbIcRYIOAu05SxIjnNUlfWLOcc2Wz3muAkE3ATacxNuW9dL0Is6DefcY34CWX4COX4CEbbeXpedqwSzx8H7MDE/gSw/gRw/gYCfQHt+Qq5rPM+c4XXNmJtAlptAjptAwE2gPTchzzO8ua6+zvBFaLPlJpDjJhBwE2jPTbhtXT0OXlGNuQlkuQnkuAmEe0l7bsIzurrr4zE3gSw3gRw3gYCbQHtuQl5c67UmhT4ZcxPIchPIcRMI4+17bsLTw9baA2yO9ZjlJpDjJhBwE2jPTXh62N3T4IvYZqvHHDeBgJtAe25CnudmcmXnRWNuAlluAjluAgE3gfbchLuHrRkEyxrrMctNIMdNIOAm0J6b8PRpP3PE3ASy3ARy3AQCbgJtuQk3sSuXVQLwYbEes9wEctwEAm4C7bkJz5zVvSeJ9ZjlJpDjJhBwE2jPTXjaufvxHOsxy00gx00gVFd7bkLObOcqHFWxHrPcBHLcBAJuAu25CfeoWiWAdwVibgJZbgI5bgIBN4H23ITbhy1PAucdY24CWW4COW4CATeB9tyEZ67qfn6O9ZjlJpDjJhBwE2jPTbjn5bqZJWM9ZrkJ5LgJBNwE2nMTHlu7b+dYh1luAjluApkxstdht9/u3nvGOsxyE8hxEwi4CbznJjwzRXrXNsfcBLbcBHbcBAZuAu+5CU87O+3JMTeBLTeBHTeBgZvAATfhtAzXW/kvr3pr0qUgZqs8+2Mc8xXY8hXY8RUY+Aoc8BWWLp87sXlRLU5onVC3seUssOMsMHAWeM9ZeHJc/Dv2JQj1G1veAjveAgNvgQPewuKbrdZYMaZ5ziXT+p11NfcS84z4lwNLGtfVaevqrfcY+Ay85zPkub+WV39i6Ceh3mPLZWDHZWDgMvCey5CnAikrOvLsNXHMZWDLZWDHZWDgMvCWywA2p1kCGL2h3mPLZWDHZWDgMvCey7Da92lvzDm2uVib33qPgcvAey5DWXHWVQKC2g71HlsuAzsuAwNlgfdchrIiQrT6NvSwUO+x5TKw4zIwcBl4z2XIdNfybG+o7VDvseUysOMyMHAZOOAyrOjIok9nqO1Q77HlMrDjMjBwGXjPZXh6GPt2DvUeWy4DOy4DA5eB91yGVduL8GJ8WKj32HIZ2HEZGLgMvOcy5LlbfY/rBu0c6j22XAZ2XAYGLgPvuQz3OF5+HL1nqPfY8hjY8RgYeAwc8BjuHrb6NtR2qPfYchjYcRgYOAy85TC0TK/a7mBzqPfY8hfY8RcY+Au85y88niQvjwJfhDZb7gI77gLD2+W85y6sebscaZNzaLPlLbDjLTDwFnjLW7j99s1NWsTU51YRxxwFthwFdhwFBo4C7zkKa5a8PcpzPoJjjgJbjgI7jgIDR4H3HIVHGSyVBGWN9ZvlKLDjKDC8pch7jsLdx5cqel644JifwJafwI6fwMBP4D0/4bb1zhnaOdZjlp/Ajp/AwE/gPT/hmSWXKsIvYputHnP8BAZ+Au/5CXc799unwRexzVaPOX4CAz+B9/yENT/fXhR7WKzHLD+BHT+BgZ/Ae37CrU0WrxzbJ9Zjlp/Ajp/A8Goj7/kJq2c9owt6WKzHLD+BHT+BgZ/Ae37CmjFuLwrzdMxPYMtPYMdPYHihkPf8hKd92fftWI9ZfgI7fgIDP4H3/ITVzmu+Lgd4z1iPWX4CO34CJ+ypgR5bObJv51iPWX4CO34CAz+B9/yEp53v9oYvYputHnP8BIY303jPTyjzFElZbJCbUgW1Husyy1Fgx1Fg4CjwnqNQFvPnplT1VSL4Mq4Dq88cT4HhZULe8xRuStVqhVmikkCzxDrNchXYcRUYuAq85yqUtGxehK5FaknwZVgHlq/Ajq/AcH+d93yFlXM537Qq/DKsA8tZYMdZYOAs8J6zsHJcJSgzKlbmHkSZ8fgyI0Vl+YcVuwI9H3MZ2HIZ2HEZGO6A857LUGYEscyYZimYc1xHVt85LgMDl4H3XIYyd0NKXb/QP2J9Z7kM7LgMDG9r8Z7LcNs896DKc7abYy4DWy4DOy4DA5eB91yGu53vdoecY31nuQzsuAwM7xvwnsuwetZdggK1Hes7y2Vgx2Vg4DLwnstQWrV9v4LNsb6zXAZ2XAYGLgPvuQyl3LU8c4a+Hes7y2Vgx2Vg4DLwnsuw3jIvdRGboLZjfWe5DOy4DAxcBt5zGZ4eVn07x/rO8hjY8RgYeAy85zHctd3WL5Q11neWx8COx8CnSWdr89zluMf1CT0s1neWx8COx8DAY+A9j+EZx+y9Z6zvLI+BHY+B4cYc73kMTw/rq6fBF7HNVt85HgMDj4H3PIaS37UNNsf6zvIY2PEYGO658J7HcHuSu7bxi9hmq+scj4GBx8B7HsM9f9fqc471nOUxsOMx8ImKZKvnbr+93mPPN3kTvoxtt3rOcRkYuAy85zLcs+TyKBB7irkMbLkM7LgMDDcpeM9luJXBUgoPxYhjLgNbLgM7LgMDl4H3XIa7j9+qqMIXsc1WjzkeAwOPgfc8hkcVLc/S4YvYZqvHHIeBgcPAWw4DzBjLdqjtWI9Z/gI7/gIDf4H3/IW7nc/bp8EXsc1WjznuAgN3gffchTU/314Ue1isxyxvgR1vgeEUBG95C6C7/ZwVcxbYchbYcRYYOAu85Sw88/Rid0O8LeYrsOUrsOMrMPAVeMtXePp09bNlzFVgy1Vgx1Vg4Crwnqtwt++tBMHmWI9ZngI7ngIDT4H3PIVV2/d8DScxYp4CW54CO54CA0+BtzyFZ5a89TfUdqzHLE+BHU+BgafAW57C07fb3cfhi9hmq8ccT4GBp8B7nkJZOzVznyQt/Q1ry5irwJarwI6rwBgh3nIVWlkkh5tis+Zv6HGxPrN8BXZ8BQa+Agd8hZtmM2t/lqhg2WOdZjkL7DgLDJwF3nMWyozkl/Uu96LboF+P9ZrlLbDjLTDwFnjPW1g5l/Uu+001glaIdZvlLrDjLjBwFzjgLtz0mmRKUjqWIK4Dq9scf4GBv8ABf+Gm2KzWmP4A9pRi/gJb/gI7/gJjFD3gL6zxP/fTys3X6fBlWAeWw8COw8DAYeA9h2HlWBZ3Y/kFLEGs5yyPgR2PgTGuu+cxlOX3V0SQMefYdqvnHI+BgcfAEY9h2j5LUCEGEfMY2PIY2PEYGHgMvOcxlBn1rscqAX4R22z1nOMxMPAYeM9jqGu/nBdzZBECwPZY11kuAzsuAwOXgfdchqedV61X+CK23eo6x2Vg4DLwnstQ6M5x1T58EdtsdZ3jMjCudbdcBqjtu9bhi9hmq+scV4GBq8B7rkLh1dPSqnX4IrbZ6jrHVWCMppStrnt6VvY9LNZ1xeq64nRdAV235yqs9l3t3dvyMFCCWN9ZvgI7vgJj3G7PV1i1vrgbxrPE+s7yFdjxFRj4CrznKzx9fPl18KaxrrN8BXZ8BUZttOUrQN+uvqfFes7yFdjxFRj4CrznKyyP8uQMtR3rOMtXYMdXYOAr8J6vsPr48mW46xzzFdjyFdjxFRj4CrznKzzek70vi3Wb5Suw4yuwmYn2uq3f8/Rr3r48TJ17zHXelKt5/fdZ0vsdd+iZsc6zXAZ2XAYGLgPvuQx1RvxrvksEX4R1ZbkM7LgMjHW+5zI8Od91Al+ENlsuAzsuAwOXgfdchpptbVeIksVcBrZcBnZcBgYuA++5DHWu55/axi9im62ec1wGBi4D77kMdVHk19iAWycxl4Etl4Edl4GBy8B7LsPdznNdX2FPKeYysOUysOMyMHAZeM9lWDZXT4TgmMvAlsvAjsvAptW2Oq7OUwwrZ1NLsY6zXAZ2XAYGLgPvuQy3Z1meBvtkrOMsl4Edl4GBy8B7LkOduxyPzdDDYh1nuQzsuAwMXAbecxnSTd7svm/HOs5yGdhxGRi4DLznMtTc7XjGdo51nOUysOMyMHAZeM9luMfxTamCvh3rN8tlkH91NoN+23MZ7nG8+jiO51i/WS4DOy4DA5eB91yGu5bXbIlzVazfLJeBHZeBgcvAey7D7cPu0YVfxDZb/ea4DAxcBt5zGR5bq5+rYv1muQzsuAwMXAbechmeueq8FQJ8Edts9ZvjLjBwF3jPXXhsXl4UbI71m+UtsOMtMPAWeMtbgByz92GxDrOcBXacBQbOAu85C/dcldm1c8xXYMtXYMdXYOAr8JavACro9qLwRWiz5Sqw4yowcBV4z1W4e9g9W0JZYx1meQrseAoMPAXe8hTAhy1NkldJ4MvYdqvHHE+BgafAe57CU4Ir577mrufNI455Cmx5Cux4CtywLve6rNwa1Pm0mKPAlqPAjqPAwFHggKOwuCrH8jCvfnC3xmodaJVYt1m+Aju+AgNfgfd8hVpWCRb5Z3FXoFVi/Wb5Cuz4Cgx8BQ74CtmWoC7aBWiamJvAlpvAjpvAwE3gPTdh5VgX7aLsShDXgdVzjp/AwE/gLT/hznGVoC7qBZY91nWWo8COo8DAUeA9R2HlWBftouxKENeB1XeOp8DAU+CAp7B64tz9qutt8gKtEOs8y1Vgx1Vg4CrwnquwcqzrBdm6K0FcB1bvOb4CA1+Bt3yFO8dVgrretsX2i3Wf5Syw4ywwcBZ4z1lYOdbFmKi7EsR1YPWf4y0w8BZ4z1tYOdf1vu/NXwGPFOtAy11gx11g4C7wnruwcq5zJ7jO3bC6YlpzZ7AuEky9Swopx3Vk9aLjMzDwGXjPZ6hrB4HvksEXcd1Yvej4DAx8Bt7zGZ6c77qBL2KbrV50fAYGPgPv+Qx17ghXWjln+CK02fIZ2PEZGPgMvOcztDVr37WNX4Q2Wz4DOz4DA5+B93yG+rzXP3Nm+CK22epFx2dg4DPwns+w2rnNKHqD1XbMZ2DLZ2DHZ2DgM/Cez3CPtjX6wGfFfAa2fAZ2fAYGPgPv+Qx17n4/PQxqO9aHls/Ajs/AwGfgPZ+hsvUoFVYkMZ+BLZ+BHZ+Bgc/Aez7D6mH1ptzgF7HNVvc5PgMDn4EDPsOa39d8j3071nuWz8COz8DAZ+A9n6Gulccaz+hJYp1n+Qzs+AwMfAYO+Azt7lm+tmN9Z/kM7PgMDHwG3vMZ1jheXtSM51jXWT4DOz4DA5+B93yGx2t228fXLApzV8xrYMtrYMdr4I51udd3a+66PQx+EdeB1XWO18DAa+A9r+GeQeiet+GL2Gar5xyvgTtasNdzd61n79NiHWd5Dex4DQy8Bt7yGh7Psnwb+rRYv1nuAjvuAnccrXv9dnvRpcvA5liXWe4CO+4CA3eBt9yFp51vrQJljXWZ5S6w4y5wR8Wx1WXP+F7zdV4lgS9j260+c/wFBv4Cb/kLUIIrZ1rxPXgBI+YwsOUwsOMwMHAYeM9huEuwxnnHL0LbLYeBHYeBgcPAew7DYo7cyuH2svnVKvO/zxhYW5RrGBsxt4Ett4Edt4GB28BbboPkPKkJM9LUEuYc15HVdY7bwMBt4D234eY1rBI877tzzGtgy2tgx2tg4DXwntewXrRbJTC1Hes6y2tgx2tg4DXwntew2vdp700JYn1nuQ3suA0M3Abecxuedl61DqMx1neW28CO28DAbeA9t6Edd47zF8oa6zvLbWDHbWDgNvCe23DnOEtAM6rWEvS4WOdZfgM7fgMDv4H3/IZ7nJ8rZyhzrPMsv4Edv4GB38B7fsPT0+4eB1/ENlud5/gNDPwG3vMbWlo2p9Xj4IvYZqvrHL+Bgd/Ae35DeygZ3rPEus7yG9jxGxj4DbznNzx9fK2WYVzHus7yG9jxG5hw5trquqd9q6/tWNdZfgM7fgMDv4H3/Ibbo9w5Q23Hus7yG9jxGxj4DbznNyzvuXwZsEk45jew5Tew4zcw8Bt4z294vCd7XxbrOsttYMdtYOA28J7b0GYcvs0dogZ7EjG3gS23gR23gYHbwHtuQ5v7MW3uz+AeQsxtYMttYMdtYOA28J7bcNs89+kaxN9jbgNbbgM7bgMDt4EDbsN6cXyNLjjpEXMb2HIb2HEbGLgNvOc2tBnlbvNsYIM1S8xtYMttYMdtYOA28J7bcOd81zrkHOsyy21gx21g4DbwntvQSrc9DNs51mWW28CO28DAbeA9t6HVVctrVHX4IrbZ6jHHbWDgNvCe27ByXi9NN9jViLkNbLkN7LgNDNwG3nMbbg8y9xpNO8d6zHIb2HEbGLgNHHAblidZRAHQoDG3gS23gR23gYHbwFtuw5PjXQIYz7EOs9wGdtwGZvSFex1W7j69fBl8EdtsdZjjNjBwG3jPbXhG1erbUNuxDrPcBnbcBgZuA++5DW3uFd6jCm6RxtwGttwGdtwGBm4D77kNT9+ufq6KdZjlNrDjNjBwG3jPbbjbt94lgC9im60Oc9wGBm4D77kNd20v29HmWIdZbgM7bgMDt4H33Ib2MCpWCeCL2Garwxy3gYHbwAG3YeV4lwD8dqzDLLeBHbeBgdvAe27Do0Wqn59jHWa5Dey4DfxwG9qx5zbc83PlVw/TLwKbR2JPzvqv1ubxLaSzf8f3PVetmWP5tuVpZp3cd/U1xaBORma2ZOxKBnWy1Wltlqwt5uv9CyWI9NpI1JQgubpJUDd7vXbnON+XudkF+GVcB8nWQXJ1kKAOAm5DxxLUGWuq97psRvzb3EdtvFpp/s4d/NahP0V6bxTClPh0dXaC5Xu9tyKAi+fQobUivTcSszm7ujqhrvbvlqzIwHpH9n5dQL+Ibc7W5uxszmDzXu/NVmorItwx59jmbG3OzuYMNu/13tX+qz/URwfoF7HNxdpcnM0FbN7fb71frO2+h0V6byRmc3Y2F7B5r/fm3kO/2xt6WKT3RmIm5+psrmDzVu/1dU5inh3q6F0jvTcSszk7myvYvNV7fcYaVwlMzpHeG4mZnJuzGT3ZXu+tMyK3R+nwRWxzszY3Z3MDm/d6b+6z9Bl/6wnaOdJ7IzGTc3c2d7B5q/f6sWxetQ42R3pvJGZzdjZ3sHmv95YHofULniTSeyMxkzM5mwls3uu91c688WGR3huJ2ZydzQQ27+Nu01+3fs9Z8EVsM1ub2dnMYPNW7/WUzHg2niTSeyMxm7OzGfTelttQl5p6fFiGL0Kbk9V7b27D+BbS2bbz3LF/5ukKX4Q2J6vn3tyG8e2Tzl7P0ctvgzIIeQ0jMZOz03EJdNye19BuDotXQyGvYSRmc3Y2g37b8xru0bR0GfiekNcwEjM5Ox2WTkzny+bVzqiGQl7DSMzm7GwGHbbnNdw9rK/fDl/ENlsd9uY1jG8hnc++fduOX8Q2Wx325jWMb5909jps6ey2yTnWYcnqsDevYXwL6ez99lL+2Y/nWIclq8PevIbx7ZPOXoetHFc7w1wV8hpGYiZnp8MS6LA9r+EZTcmPqliHJavD3ryG8e2Tzj7utmy9Z0nIOdZhyeqwN69hfAvp7G3urx4G7RzrsGR12JvXML590tnzGpqdMXBFF/IaRmImZ6fDEtbdPu62VBBvelisw5LVYW9ew/j2SSfQYek1V0FZYx2WrA578xrGt5DO3maTs1nRhZyGkZjN2dkMOmzPaXjWFpu+HeuwZHXYm88wvoV0PtdVdOsx+CK22eqwN5dhfHuns+cy3Dn35T0TfBHafFod9uYxjG8hnb3N/TVL4hehzafVYW8Ow/j2SWerw+6cm1f6IVdhJGZydjrsBB225yosvT1XdHXG12rL+GVsu9Vjb77C+PZJZ6/H6B5VqyTwRWy71WNvvsL4FtLZs6QWh2WxSCp8Edts9dibrzC+fdLZx8XSopVN28EHhXyFkZjJ2emxE1ttp8dqu1mua5XT4YvYZqvH3nyF8e2TzlaPHSsGSMnNWSFfYSRmcnZ67AQ9tuUr3Dbfcxeo35CvMBKzOTubQY9t+QpPzv0e3/BFbLPVY2++wvgW0vm0+Y6X4BexzVaPvfkK49snnZ0eq8+aMruZI+QrjMRMzk6PnaDHtnwFsNlHp0K+wkjM5uxsBj225Ss8NqfkvWesx06rx958hfEtpPNhc537ZBXXGiFfYSRmc3Y2gx7b8hXqXNE9OVfo27EeO60ee/MVxreQzt7munKcv9DOsR47rR578xXGt086Oz0GOc92Rt8T67HT6rE3X2F8C+l82lxmbcNuZMhVGInZnJ3NoMe2XAXIebU3wxehzdnqsTdXYXwL6XzaPN8Lwd2AkKswErM5v23OoMe2XIWVs+Z4/cKMEXIVRmImZ6fHMuixLVfhybkvJjPmHNtsddibqzC+fdLZ6bAn57nLfFRo51iHZavD3lyF8S2k82nz3GnHna6QqzASszk7m0GHbbkKT87zLMdRoLZjHZatDntzFca3kM6nzeXN3tYvYputDntzFca3Tzp7HbbILGt0wYwRchVGYiZnp8Mytto2LnbcPWwqQdi3CrkKIzGbs7MZdNieq3Brz0VShXk15CqMxEzOTodl9EjbuNid802NxS9im60Oe3MVxrdPOtu42GPz4lAn+CK22eqwN1dhfAvp/KvrqpCrMBKzOTubQYcFXIWPdVXIUxiJmZydDjP95UuHbddVIUdhJGZzdjaDDttzFL7WVSE/YSRmcnY6LGPdBTosXleF3ISRmM3Z2Qw6bMtN+FxXhbyEkZjJ2ekwMzoDHRavq0JOwkjM5uxsBh225SR8rqtCPsJIDHN+8xHGt5DOv7quCrkIIzGb89vmAjpsy0X4XFeFPISRmMnZ6bCSMJ1/dV0V8hBGYjZnZzPosC0P4XNdFfIQRmImZ6fDCuiwLQ/hc10V8hBGYjZnZzPosC0P4XNdFXIQRmImZ6fDCvaXLx22XVeFHISRmM3Z2Qw6bMtB+FxXhRyEkZjJ2emwgnUXxMPidVXIQRiJ2ZydzaDDthyEz3VVyEEYiZmcnQ4raEEQD4vXVSEHYSRmc3Y2gw7bchA+11Uh/2AkZnJ2OqyADtvyDz7XVSH/YCRmc3Y2gw7b8g8+11Uh/2AkZnJ2OqyADtvyDz7XVSH/YCRmc3Y2gw7b8w++1lUh/2AkZnJ2OqyADtvzD77WVSH/YCRmc3Y2gw7b8w++1lUh/2AkZnJ2OqwwpvOvrqtCjsFIzObsbAYdtucYfK2rQo7BSAxzfnMMxreQzic/uC1yGuYc2lytDntzDMa3Tzp7PtXi1c2z7h00ScgxGImZnJ0Oq6DDthwDzQlzbh3Gc8gxGInZnJ3NoMP2HIP0kE1XCeCL2Garw94cg/EtpPNlc187oifYHOuwanXYm2Mwvn3S2eqwO+d5l6EnyDnWYdXqsDfHYHwL6XzaPG+5d+zbsQ6rVoe9OQbj2yedrQ67c57t3RO0c6zDqtVhb47B+BbS+bZ5lYDhi9hmq8PeHIPx7ZPOVoc9Nl+7/niaOuQYjMRMzk6HVdBhW47ByrnOEw/V2BzrsGp12JtjML590tnqMLD1+s3Qw2IdVq0Oe3MMxreQzt5mXjlevzieYx1WrQ57cwzGt086Wx125zzvopi+HeuwanXYm2MwvoV0Pm1Os7YTtHOsw6rVYW+Owfj2SWe7L/nkvH6hrLEOq1aHvTkG41tI59vmyVpDm2MdVq0Oe3MMxrdPOtt4WF/k0vleBp5RDTkGIzGTs9NhlTGdD5s1x+sXVUysw6rVYW+Owfj2TmfLMXhynvGwBKMq5BiMxDDnN8dgfAvpfNo8Z8kEJ5ZCjsFIzOb8trmBDttyDMDm1d5Q1liHNavD3hyD8S2k82nz6ttHgi9im60Oe/MLxrdPOnsddiwmbnIzRsgtGImZnJ0Oa6DD9tyCpQBXCTDKEHILRmI2Z2cz6LA9t+DWnovKfILNsQ5rVoe9uQTjW0jny+abcV8w59hmq8PePILx7ZPOdl/yznne7C8QoQk5BCMxk7PTYRhL3HIInljv4v/OPl4gzh1yCP4/Z++2Y8GuY1f+Tj0kEsEQqcuj264GDBguw11+6P//kSZjSRGTQXHl"} |  |  | - |  | - | -
[14 empty] | {"index":132,"total":402,"filename":"Advanced_Project.ifc","data":"4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPww+GHww+CHwQ+DHwY/DH4Y/DD4YfDD4IfBD4MfBj8Mfhj8MPhh8MPgh8EPgx8GPwx+GPww+GHww+CHwQ+DHwY/DH4Y/DD4YfDD4IfBD4MfBj8Mfhj8MPhh8MPgh8EPgx8GPwx+GPww+GHww+CHwQ+DHwY/DH4Y/DD4YfDD4IfBD4MfBj8Mfhj8MPhh8MPgh8EPgx8GPwx+GPww+GHww+CHwQ+DHwY/DH4Y/DD4YfDD4IfBD4MfBj8Mfhj8MPhh8MPgh8EPgx8GPwx+GPww+GHww+CHwQ+DHwY/DH4Y/DD4YfDD4IfBD4MfBj8Mfhj8MPhh8MPgh8EPgx8GPwx+GPww+GHww+CHwQ+DHwY/DH4Y/DD4YfDD4IfBD4MfBj8Mfhj8MPhh8MPgh8EPgx8GPwx+GPww+GHww+CHwQ+DHwY/DH4Y/DD4YfDD4IfBD4MfBj8Mfhj8MPhh8MPgh8EPgx8GPwx+GPww+GHww+CHwQ+DHwY/DH4Y/DD4YfDD4IfBD4MfBj8Mfhj8MPhh8MPgh8EPa/lRzFCrr2gXk56sXNceT1au646UlbJSNspGOVFOlDPlvCi3KOFI2VF2lD1lTzlQDpQjZfQZ+gx9hj5Dn6HP0GfoM/QZ+gx9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9eaEvNwt97ZGyo+woe8qecqAcKEfKkbJQFspKWSkbZaOcKCfKmTL6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+jz6PPo8+jz6PPo8+jz6PPo8+jz6PPo8+jz6PPo8+jz6PPo8+jz6PPoC+gL6AvoC+gL6AvoC+gL6AvoC+gL6AvoC+gL6AvoC+gL6AvoC+gL6Ivoi+iL6Ivoi+iL6Ivoi+iL6Ivoi+iL6Ivoi+iL6Ivoi+iL6Ivoi+gR9gj5Bn6BP0CfoE/QJ+gR9gj5Bn6BP0CfoE/QJ+gR9gj5Bn6BP0afoU/Qp+hR9ij5Fn6JP0Qc/MvzI8CPDjww/MvzI8CPDjww/MvzI8CPDjww/MvzI8CPDjww/MvzI8CPDjww/MvzI8CPDjww/MvzI8CPDjww/MvzI8CPDjww/MvzI8CPDjww/MvzI8CPDjww/MvzI8CPDjww/MvzI8CPDjww/MvzI8CPDjww/MvzI8CPDjww/MvzI8CPDjww/MvzI8CPDjww/MvzI8CPDjww/MvzIC35Is+BHd6TsKDvKnrKnHCgHypFypCyUhbJSVspG2Sgnyolypow+hz6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+hz6HPo8+jz6PPo8+jz6PPo8+jz6PPo8+jz6PPo8+jz6PPo8+jz6PPo8+j76AvoC+gL6AvoC+gL6AvoC+gL6AvoC+gL6AvoC+gL6AvoC+gL6AvoC+iL6Ivog+dlxtIvoi+iL6Ivoi+iL6IvrYtbiJ6GPP2Caij71Cm4g+duxsIvrYM6gR9LFzTyPoE/QJ+thnpxH0CfoEfewI1wj62C2hEfSxb1cj6GPvqkbQx84xjaCP/R4aRR+r8DeKPnbhaBR97IHTKPoUfYo+RZ+iT9Gn6FP0KfoUfYo+RZ+iT9Fn6DP0GfoMfYY+Q5+hz9Bn6DP0GfoMfYY+Q5+hz9Bn6DP0GfoMfQl9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfQl9CX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZffDDwQ8HPxz8cPDDwQ8HPxz8cPDDwQ8HPxz8cPDDwQ8HPxz8cPDDwQ8HPxz8cPDDwQ8HPxz8cPDDwQ8HPxz8cPDDwQ8HPxz8cPDDwY/2WKw0H+orzXdTMPLJGezI2R4pC2WhrJSVslE2yolyopwp50WZffjaI2VH2VH2lD3lQBl9ij5Fn6JP0afoU/Qp+hR9ij5Fn6JP0WfoM/QZ+gx9hj5Dn6HP0GfoM/QZ+gx9hj5Dn6HP0GfoM/QZ+gx9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9eaHPNwt97ZGyo+woe8qecqAcKEfKkbJQFspKWSkbZaOcKCfKmTL6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+jz6PPo8+jz6PPo8+jz6PPo8+jz6PPo8+jz6PPo8+rwVO/7E+g4X3WQtf25xtMUxUo6UhbJQVspK2Sgb5UQ5Uc6U86LMXkd+sc5Ae3SUHWVP2VNGn6JP0afoU/Qp+hR9ij5Fn6JP0afoU/Qp+gx9hj5Dn6HP0GfoM/QZ+gx9hj5Dn6HP0GfoM/QZ+gx9hj5Dn6EvoS+hL6EvoS+hL6EvoS+hL6EvoS+hL6EvoS+hL6EvoS+hL6EvoS+hL6Mvoy+jL6Mvoy+jL6Mvoy+jL6Mvoy+jL6Mvoy+jL6Mvoy+jL6Nvsc6AhIa9thbrDLRHdrpfrDPQLfNO2VNm58vFOgPtMVKOlNm7bbHOQHtUylp81x7rO8K0zx977dJHBPqIQB8R6CMCfUSgjwj0EYE+ItBHBPqIQB8R6CMCfUSgj2iPlNnb1SfK7IPnF31YCOgL6AvoC+gL6AvoC+gL6AvoC+gL6AvoC+gL6AvoC+gL6AvoC+gL6Ivoi+iL5V5jsb6iQDfxU07OUPaY10iZfbdVKLMrtipldkNe7FXWTRylnCj3O0bmRdnYWW6xV5kEY4e5xV5l3VL/lD1ldlk19Bn6DH2GPkOfoc/QZ+gz9Bn6DH2GPkNfQl9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfQl9CX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZfXujrFi3hSNlRdlK0RFvuiXd++87OxTt3b3f/fWPv4s5uv0mecVpeHBfDmkjXEwmqOqAXZhfDlDsHD3d3Ll492LnxL1c79+9/+C5F7f/z3N/LX7O56zoRJ29DT3YLW12EHV7HF2m7vpMYIsbBNTZX1FMhT4VCUSGZr5B0FeqWP23Ka+nm+gTqE4r66Hx91C+cplEHF9lcochFYnmR+Yood6YNRMqLsB3rnSvb+zu3d/Zvt73UzYPtg6t7N//9j26NmX/Of3z+859z/9w5/vLiybPDGx+fH77759zyZvf3o/dVXx8uuVLFJq7bD67e8fu7XTXa64SL//6Hnvu7lLPoN4dKbmzv/4uRc4henaAnJ9y/evPi3v3dqzev3ry8f3uvrcvB1Z07//7jrt/4+nD357d84eeLy9/S3Rcfbpy/c/ef1oxrq7a9u33zzl+XXv84fP7XndcfXr47/Ov+6w/PP37/H/7p4Pb2/v6Vu3f+x3K3pcI/ndbx/62kWCHlxP3//hPefn3o3r4MX7a/v7x5/sHfX+7fvrP368zXX1y4vX9yMmJrD10qwi/mNHcHWRxscVj8pH+MF9mOSNY5MkaIZJ/5jk+6hU7+kxtr8p/n/sknLP7n3NbNvYOLO5eu3ty5uDUqXDr5/6UD0iLgv7F9sHP76vbu7tU7HfC67e+6YMfz4qNb+zeeFE/40h0T/9zNxOjKyrHxg+NJ/+x5f9MdO6J3WaKO0J73SN3v3OJ3J/13eT5/Pxltd8dF/30yMasrarE9XwrUZX+/fIq6nrnjnK5+KKd7gG48+fTp8Pntw09fDo8OP3x98vX1xw/9g5SKmR79jr239y7evbDw9dXO2skF/l00g8V1i3PIGW3fPti5c3X75v7e1Zut67slOFzY6vjmTl4uh24xhLDlT1L03fyxZmtlJC/u3sWrt9uIpZP/7381W2183C0x1npQTz4caLZaeKV2uNuysxvCDQyEyiO+kNjeKrrd7E7Ocd2uTmnx/O7uXdjeXZ707+LfOiwufiSri0jxkE2f7zd//Hyf6ans63COW3fun95QG+g3W+daTzdbzfJ/YVWNVHtU+nFgKJ+UvuWXu7k69hymu3t4p+36dnfube/ebfudG08+HLf99dfjL4dfulp1Lt4+33LjnzvfDj8cvX3y16X/feD/t2ku6f8+aP73w9HX9ncFF1zjhsbb2PUf9zB+jY+ufj44718eHB/vfP719ejxVZy9f3T49XF52YOfnw6vfnjx8ct72jott9Vd1CFML9M8+nDnw/HR21/n3flwdOe+y58eyefyMnufDj+0N2bn3eH79lG68PH9+95+2+SLTYcdmyLPuujCk6+HLz9++Tl0z+JOHw19oVOR/q1defLivf/WfHlhH788u/Pt/fVvT0qR+18+Pj9+9vX24efj119OhB4VPpBCZJqaDxfv5Rv6/tKDncf7e4fXnt648/XC9k5p/tbxkw9fX3/9efDk7eHeixez1XdrWkh3e248+fJ2WP3oBjV3rm7gztePXw5/3nzy/hATBzsPWuW7h98O3/3PX+6v/2ofoS9HX/+69O7jx2Hb6reCnrf65Ovx0YWPbYv80nqPhrMSePPw+1+Dfx0YDnXDNw+/bn85fIK17ds72zd2ttuQaudfH7faCFy6eXDdbOOBwVg3eOXw9ctXX3t1OzcvH1xZWmz7zK2BnTXt8P7r519fzZuJYzNaN3P74/HLV2tsdT3RwJatqVrbNr68e/3h7eDOvvr69dP//Pd/f//+feto0Ym8+HjScWwdHQ5vw0yD9u7b/Xh4t2Xyt1uXn7169XL/g+z3HfWF46OvH98/7tp1S8p/TgKdZjHI6hoxR8fRcwwcI8f+94Q5xQJ/zjeElbuL4OXO+YdllNjsP750tPvy5pfo9x4f2gN3/bM9+L4QtyJubqMi+saV4bjWsEtPD55dPNi54m69ennn6ZPzb/XheasbDivDtt7w09fvY/7w+culw31/rXmzvbN79/H9uuFlvOLCeleET69+3r3nr4j7vn/n2s308YW79fVR3XBaGQ5rDfv86een9ML9SvduPdp+dN67r0c7oWrYFYYXrf7W3e2bB1e7sLpr16vn75+ukS6euOUZNnsGT8fihDg4IQ1O6HqHf/9ZdBf/PGkPf70/fHLUQu35X68//PXy8OP7w68LcIz7jqXBRUS2s3sSz/R2Wy+EF9c/PGyeuOb4/Levby8c3doO12728cqTo0O69deHR/+s3MILRTZVPtG7atuk2ast5fDa7Ue++fxL3ffvv26ED1d27t78WfV7yCvDazq/83uPt599bB/b18/+unr08d2Toqde9BZBnp8f9ApxTR94Yu7r8ZN3f11+9+To6K/7Zd/a3ozdf31jW6n72GRgck1/2Jqs2QrDnjCu6QlbK7sH//1yUDML/y02rFpaa+Hu98H5bmsIWVIp62ux/enTu9fPnjx9/a5l/sDc5d3tO3f+unrnrzYo3b16Yfv87s7AvKwJAs5ORFkTEbRir3446cNnACRDp8uaGODex3fHy6ji3t7u3Rs7vZVmy4WTT7y6dTc1NjqwuQb/RaizcJvX4V2Qtah/8vyvs/BeZCakO/r+/OK3v78c6J3zv/Le21svn978rD0BT0KaJ6+XQWLbP3VZwu7Asx+LwE420OHl0fV73559u7LzbP/v54/uPH1+8YFP1WdelsMrp80Muvfl4e3P395cTE/S3fh5X2+9T3efDISvIrUO3Sdf2HSHkzyE+CLeJ3FWFb73eP/q9/tP3oSfLy9fTQffD2/u/r1XFa7NyvCMx5tfL/Xxu6fyTQ5e3f375beb75+4i48RfvHJ1yereDwSRESCiNg7nQ43Fh2urne+//vdt4+Hf+9+aa6k7RcH2/euH935+rxeh5Xzbcb57tOFu+9v/Dzc1Tt57+Hjo135lpfAuPi6HVYctZ4vRhZCuCSES7JKajjb4P3jdH/f/Xosl+7tXd+9/f77hbfbb4+qym3lfZvxvrvx+tPDnUuvXsTLt940N54cH+y/vncb5VefH56MXv4a3gYJhdj1bm7+vrUXd2+//Bae3g528WBv/83z5nNd7MrNacbN4ebLvHfFf/gVPh/ffvr6er62/2O3d/Pe11eLUfRJ4/YnubaTdxHdwS0OYXGIiwOtSFZvhFxa7/vm0t6NZ2+2713Z2f325vKvL88fub3316rVSSvfpxnf+4c3Ln1tHjT7eTe/f/NIXb7xYf9iP3x89eSoHT0vKtS2icLnab3Pw+6965evxseuufDiWTz48ePquy/XHtZFrnyeZ3ze+Ou2/+7+YRtqvnr2Kt9/6i7d/UrU/c+910evV7A7cfwi8yllCiRvaNB6L+24x/o0392/8/7jI/073t2/UtWbV07Na4KVP86t5Jl8gjs+Pn7w6t7HL/nh4dNbN242v27uHZw9t5KLvEJeE5WcPvmR88ydu3T+xtP3N867cJC/79x4+frh0aslyjYnP/KqM/VzeSYfj4/eXT68/mU7fMtX/fePv3Zevb52xuSHn0stucOnD/wVu+T80fHf3788Ozh8uP19r7S8cMEgpXTyIeDY+Jr2cZrMih/nlH4zs9CGxf8XmQU/zkH9QWah9dP/r8yCHye0Thrjzd2L/t3+xQcXru4d5Xjh45cPOw9sLrNA+/O8LmXafVxsXSAsZHhSgdWN9jJ9D9BNp9TRewDv9Y/fA/ji3af3yzuy9j1Ae93VOYztp+8BuikBW21HZ92r7eDFcrOVTzZ37r6qTk2RxvfB/9l7AB9qr/oWEpfvAdor9e8B2v+svgfwJ1s3LH4kq4uU7/0q7wEOTv0ewMmNv/ZvX723fbCzeBWQTvkqoDjxn14krcon3ga0tlzs3ga4ytsAT7bgT94G+LhmYPanxPLRz4RMry989/ff3n56Kf64/PzZtUc3dq/s21mJ5YtJBX5dxuHUxPLjRMMJUl6F5z+fb9/91rx+8TjvtY/Iu4/3Lp6WWN1Mg5V5mzH//PvD408fbz7VtH9h2784/Phu7+b+RmJ1PYlZYXqGtcOWvf1gt2zZVWSdfIs+sr5u6D7PLBkya92Y/bffBvh1o/Y/eRvg143o628DbKsbsea2FbnQuBYFpcU11F8DbRdGtJU18K+D1o2hLWvYvwHabgxtWRMA3Hn97t2a6lnOW7n438Ds/79YYC5V4d7vH+f8+f6DtPtt93Pz6PD67l5+W33LsHgqztG4OTIbYjFbsLvnHOnWmeSyWOXlpIarJ2xDdsNfvffh+vl331/kD3n32oPL8eLHj28vjoYjLdkWw5G2010Z1vXjnEfvn917uXP/Yn5w+3Z48eLW/a9fwvu64RVGmSxUHZXeeJk+2A/5Je/z7cd37Km/cf71OB9TGLal4U2phi/x16+r997suk/f3x5/On9xb/va8YO64bwyLGsNh2/fvjdHj/euXHp+fP3KjZvv39/8+Gr8KmdleJVB8jZ8BzD7mmHxJC/PyBtfM7jyNYMn83D21wyTTmlp0c2/ZwjvnuT3at92Lz26te8f3bj26s6na183vWdYLE10UrNzCF417rT+/U643Ny/cvjkYD/tfIvp9c03L1+9+f6i6vjkVobXZ/HP+J7Bp/Xp/A3vGSRuubZzTAOL69P7p3vN4NP6NP/m1wx+nEQ502sGn9dn7v/wNYPP64KDFiDr8ufrCJLXhAe/gfC8/qXWad9f+HUJorXvL5puIe3GdZOTXbd0xcDomidh5gWGH96AdS/0N73AcKPQYpw7mkai+e9fZSRae4GxaHkcV6no0Kx/DT261rvyWjO9SU4rw3Npn6G1xzPKT/sGIzTr+TO61Nv1wsNqEBjmpgGNrH0/KIUPUud8wx8X+yAKuyKcdDu4qKiDO5PzXx5sqMPK+eMJOHPOfzqow/QNxmIdvJNHlaMUys/m/afrlbuV9+fmrIyVvyiVz7/BaB/hldgNs07GYl9sELtys5+bNSdHL88/u/vLxYfH7y+9Prjx8fr+zxdr32AsxoiL9dG6Y14cT75i7o5ExNmKKm2Ivq6/euOffPmZ5XB796Y7vHl1+/y7ccJ9VSW/8r8/hf+vDIa+1bcYYcMUl7Hfr6z3u1/5PWxu3j8+lCJP9RYjhDM16lcf1usNK6eGfpZpkbxsG333KdkgeRlIQP1J8jIUc1LCKhm1NnnZXrc4J8wnL7v1HmTLdZlO61ZYCdqGC36r268phe6D9EH6MpD9+e30ZSC/M5u+PFlTk/RlYBh1kvRTV09fdu5e/KhZXSRvTF+GR6dPXzaD9KU2zWnTl80kfblYk6C7hSfpyxNbpC+bQfpyGcAH8kJ/kr4M65I1f5q+DHPTMVxzeOHek8fffl08PrwUbsXzT8PhzXdnTV+G4hVvWJePOXX6MowzMSdiH7178ub85asP5PKtg3D08vKb8/dfu9OmL1thK5FzaZNw0HzZebl9fv98fLV9+OZS0Gd3ftzbmL7sduVOpemZLPFc+nLZstemLyfW17SQSvpyECCH8RSR/5P0ZdA1MfufpC+DrmlN9fSlbPlux8PcbSPdWBMHFteMY8+Qvgy6ZiRbTzmO3lyG8WyXs2Qvm2Zka9089d/OXgZbM6b9s+xlsLkQ7sjy1Zevfrzxaf/J/SfXf30/+vbz0rrsJd8wd22bo3I0jokjzFp8YRpZaaur4eoB25BZc7sXnz36duBfXNo7PLzw1vz2pVcvno7CkBZshCGrSWXBNiQZjx/e/Pbygj3QHz/83u7h3qedqxe+1A2v4rENc2rCjTsPsru1/a25mO79fenW7tOD46RVwwWe0wZXPDp8vhu2X37bvnT46VlzqXn44OGF63XDfmU4rTd8eD81T17cy/7Vi51Lr998+Xw5XB9nL1eGbRXqkd05ffYykLBZl73Mg9+H30xeTrqkpcVYSV7+Oi9Pnl07/tLsHOcb7tO1O3+fv/N0U/KS1eG6inEshgR5fQI97F26cG3vh/8ir5K8/SQfbnw8juNxy8rvuajD+qzeGZOXcd03XZuTlyFuWTNMXsbxBJvfSl7GZk1PeKrkZRznZc6UvIzN+rTdHyYv47rpPH+QvIzrZvmcHeBx3WSfMyQv47rZPuuTl6HbtsmnJnerIpobGF3zJMwkL+PgBqz7Uu2sycs4/mqtlrxcxqFrkpes8tE1kf9cXWD9q5C55GUYf0Oz7E1auSvDczMDZ5KXI+WnTV5GtwE/M8nLdcKXCYToN7v8JHm5FD7ImrGkStf9cXQcPcdVVx79mZz/8mB9HfzK+f4Uzn86qMM0eclSpN2jyjEVys/m/acblK+8HzZ7/yR5uVQ+n7yMxcS3uOFzrrnk5RqxYeXmMOfm57+23dGX/TfNpXzrzoeHRz/eHT/8sil52S2E0m2WcHLMi2O35OLJkZZT5BhiWO//oL/u/7CXH365S+cf2Os3+fPtdHE8cb+o0sr/47lXteTlauBbTV7GeDa/X1nv97jy+/hjqVrycinyVMnLGM/UqF992KB35VTpV5PYsAJDlFMuYbImedlebFWjVSpqbfIyFl9WRGb0zCQvnbctl5y1zEzxXDsQy03Y6pbuTqFbx7TIPEYyP7+duozkdmZTlyeLGpO6jIyhutULROorMJwszrf4kawu4jenLh/+1goM2rhT5i1HKzCwIHJ360hauk0rMETtJ/b+ftIyrkvR/GnSMo6zNSfzDH/devj6lrgXO5+/X3tw/ke6cfjxTTxr0jIWC/PE2Y+O9t/lu8+2f72wwywXPhxddM9/3PxaXua0KzDEdSmUU+dE41y2xL+8uPP93ps7Vy48O37/6P6N3ecfrl3ZP21ONBaZjzj7+dKtC8cvb187PpBPt74dXf9188qFy/tXN+ZEx9Vf00JO851AtHXz8n43aRltTaz+J0nLOP626k9XYIhpzfD1DN9JxLSmHZ7+O4mY1oxiz/idREzrvjj9o+xinPsmzD3VZ/d/Xmv2m/cv9v4+fv/33SvPftSzi6sVGKIRyzI7LDI7LCai9US0noi5UuC4ejcSN3xZ5n5cPny89+L7B/fouLGbeTdes8vPRmFCix7CBF3mAGNe//l72H3dvL/07fHTaIf7r18d/Lxw/ZsfvzxdGV590xjz+qUdwuvPlx4+PH/41H7sbT/2T/2ll2/T5brhFXnyBlfsPn986W/Z/nb+wv721Xzr5q/Pny5L3fCSzLJpTo3de5vefnu2H/a3b7x6lC5+zC91nMBdGU6F4WHqb/MKDEK+5tQrMAgZmP+zFRiE1Mskueg+55u/7j169Gvn7fGnp+HzlZ1f95/c3ZRcFBZJE9IBUqQDpNkwrviY31w4fnbx2yXd/vL90/l7x39feztOQy/9LqvIVtYtv3P25KKsW3fn91ZgkHUr7pw6uyjrltk5VXZR1i2wszG7KOvW1fnz7KKsW2rnzESU8Uyl30wCilsTA/zmCgzi1y5JNskBysBN4xzSn6zAIH7mXbTPd258u/5T29ayd3Ac3+29vffg+49Tr8DQNpPVM79h4Z/mx4Xdn7s/buzK5+Nf7777zz9/3Ypvq8+89yvDM58XNc3ju4/zpZsf/MF+kAeH1z68vP/25W+lAMWvfxnn3r1u+8ufb96kp7d/3n/QPrrp2f0LdeHLGf8S5jz+48brjzeaK98u7b18tPv5MN/afnr31lwKkL1xuk6KIx0uyztJsaathA3OP9x79OPb1TdX8pXbdy8fXH/oH+jHX9U6hJXzw4zzXbjw4sDd/tulV7e33xz/uPX9/v0vH+opQGE53cU+sycPWqF8w6vQ8y9epe+vmn2N+xeP3t/4mK7/fLVbV77y/twXeq6xt9fSPflw6eL3y7eufk752F26tDYFOGgqccPiVnfs2avdJ28f2OVvL7af77555Pa+jz9nWYldfc4is5/Q7d17feXN1Ye/9N6PK/ffHXzZDe77zz9cgaHtU4rqrPd92H5lH65cefPmov7Y/3b93u7n16/evKxXZ+X78XdxJ4/sV3sdvv96+jR/Pz5/5eWj1492P26/2pj+E9nQtG/vHl379e1Kvnjl+/W/d5ub98LT50+qImXl8/HkpJN5P9+u33j/+Obeg0sH3y/txS/nb9+483L/LOk/kQ0NeufNE7l8/vaXC+/33t/+ce3Hccjv3tX1rpyq/aSyVfovpMUEh0H6TzT8cfpPipVfZTVNaG36r71ucY5V0n/Op7jV5CZb7lZNDxaDy1u+8d6HbmPowdxFYWJNPQHY7Zg1SgAOV3EVZsLMpgBP9s4gBdheq08BdhvG1VKAcrI30+JHq9iadMzaFOCDU6cA/Xj2oj9lFtCPZy92NaF2QiLQL2cv5uF72lVl9I8TgbIuS/OniUAZJ2tOessX32+c15d3P+z49PXdS719/8a98PqsicBW96oO6zItp87UyTjPctLNPLr74cPd3XcP0qXbjb6Wl48/uI+fT5upa4UVIuOM+RxfXtCL957ag+zS/a9HT65/3ruyefaiai5HcePP0KqzFx+UpquzF8fW17SQyuzFZujYtSm730wEyrpPyv4kESjrvjarJwLzVrfZeLcRrnkX1A0srpuMd/rZi7Lug7I1Uw7HA4x1H5JtygSOpi/Kuo/JNkxfTGNT69aV+aOkoow/MDsJc3Ye7vx48frCgby/9fnL0RX30V178XHdlEXhwyS2nuuaIEcGAEzfEj4DYmu6zkkci1FY3hB9/Pr58vv1b+/3/c9Xl95fuX10Y//m66uj6KOlGdGHLaGgzfq3sM3rCztPL+0d7PrjV4evDt9de/r2ydHfVcPJrwxvmIj26/z7719TO+S/vf/y+NOj3R8vXnhXNxxXhje4Iv96d+X57ss3F+/8iNcfPvr18dH2wXj51cLwMr5St+FL7p3vsvP4vey2g+rnr9ue4XH6fmE82FoZzrYyPEz5bZ6yqG5+JdjBB9d5cMJwIdjTZxUnHdHSYppPKzbvrvvH+/nhl/hw7/6rj1m+379+329KKyopdnZc7QQvG7duWrT41dEj9/X4qcjNbbu9c+/io3a0Nx4rLh2vq8/HdPz52J+lFdVvWid2bVrRwlY7oBtkFdWvz+adLquo4/k8Z84q6jgXc6asoo4/afu/zSqqXxcQbJizOKKGhrOvEbsG1Tqej/SbKUodp5ROP09Ru014c25bku+WZBoYPdsqsTpweviTVWJH8xQ1zL2lm5un+GBDjnLR2jiusk0aNrxpmpunOF6EY9WDhOULIY1zkwbm5ik++K0kpcYNzJmbp1gXHpuV4c0uX8xTfDCXpFQ2qWL7266j4kj37YvuO57J+S8PNtRh5fzxgs7VeYoP6klKXWxVFtnSu3vUVsrlbN5/ul65rLw/+x3e3DzFB2uTlO0jXIg9k5vfvtggduXm2Q/l7t64s3Pl7SMJze27/jC9untbHsW1SUrGgt07hJOjccyLo/b3YfWuXDctI/T5x4un/u3DK+cfHb67cvehHj3+9OR2tUqrz1p0bpHk2XmKDzYmKnXDKsiz8xTrfl+tgqyzE5Lm5ik+OEuiUjctSDQ3T7GudzVPQJk8NM79SVhMOzvZA7Tbr9v5tJUth5SddV8yn3Mxhq2k3TZ+2Zoy8rP5dOKsyRRPlq1OjTRuYTLMmpzfImrWpLai2gbarRIZFiadaMqx2056lTBSEkabTbo2VvBeXfeJlbRdZfsfsUtrNq7brEwLi/OfgM9Y1C3r1lZse4Lc7QneWgxb1vU1OYWmWDBC02nvjus+vEi5yd1Hcd53JmXLus04Y/aptHjam+PCVg7dJmfWpG7j7sXNyd2H7OFkpuvK5GlvTmvSt0PIttvwyUlamGxboDTtDS5WItN86nvjJ40yboWuqVuyYl96zae+NxOL7W9afrX1dr784l/zqe/NpNrSivQx5m4X26Y0+fs3pzXZNk+zbvvV4qtuzae+OZMWpH7Ld117t4RBsXy/Nae+O7bVbbXZdBuAdztNtybj1skuy9plFaQweerbM3kYtX102kg+WbcRXanyDB3bqMtofZm6ZWa69xSNL0yeoWPr9h/slikM3SuIxR3PMbUxtMXiyz5rztCxjdtl3HJBcm79m4st+MzN3x6Xo5VGxyZdvUc3N397NplcJ3L+7sxaXDIidn84aemzJufvzqzJ5Q3vNuCu33A3f3emJofNck2r9Ke9OUNGhMWz4yW0j5Mb5ObNn/bmDJ5wp2uecH/auzPsh0K9HzJ/2rsz7C19vbc0f+q748cNvdKnWzj17ZmYnAePhVPfnUm95+Fo4fdvToXgFk59cyZNaD7MsHDqezNghFvEQidPc+j2vShaUDz1vRk/jPPxmlWW7DlNh1EJKi2eoVtbEoJb3YhL3UanTSmRFN7e7sPdvb39xb7JbJjexXIcF+8ilHcQyrsHNlLvwgqOi98Z3ycas0LZYL3jG0fsGeczg1qZOa3MmNay92V6SrfF897dg53b5/fu3ly8t28rcW7rYJnVNhIA3S//5QdF6+5nowxqbGQu2Oq96004UiPyAMa21WwB3zVsjvwu8jt2nmZr+I6ZHPm76//O+Uw7sGJCjjHXZa7Gbasb1FjGNS57Rpm7x0tFsb8HxcMldV/L0Nc68XXZk+icr/u7vrpyEQhovc46rLNO6qxFnXW2XdPO+rvTtrfijHqddVhnm9RZCzs2276WV+wVFN62ep1tWGeb1Lnsv2z+WXaDZ2vVMouWZvW627DuaVL30odpvu5u8IxoMWHBUr3uaVj3NKl78f2EpXV1X1256E9Svc5pWOc8qXMq6pxn23gKg/5BS3Tlep3zsM55Uudc1DnPPtfLK/YKSq31OudBnVMzqXNe2UnNfJ2XdR31jVKcWa17a3SoYFz39tzCznzd+yuHIbeKdbJSU/VBa3SgwI19kIrgMLl5H+SBgp4bLTmLM+s+cEMfuIkPXOEDN9vml2x2AwXmS+11H7ihD/zEB8V03eTnWdqzrI8K+ighFGfWfeCHPvATH/jCB37eB2OKL+OU4sy6D/zQB2Hig9KXYbYd5D5iGiooU8Qp1H0Qhj4IEx8U+fAUZp+FZUTTt8BSc73uYVj3OKl70Z+kuK7u/ZXbaLA4o17nOKxznNS52GUkzcaty7izj6aKdTFSPX5Mw/gxTeLHVMSPaT5+dKPIt4jjUj2OS8M4Lk3iuFTEcWk+jlvG1mFY9yK9kurxXBrGc2kSz6Uinkuz8dwqhu2VFP19PZ5Lw3guTeK5VMRzaTaeW9Z9eeWizvV4Lg3juTSJ51IRz6X5eK4fyfTxfEmGejyXhvFcmsRzqYjn0mw8t7ri0uvFGfU6D+O4NInjUhHHpdk4bhm3N3lYd1e09Xo8l4bxXJrEc6mI51LlLULL160OJKH9j+BcGicE4znv2pFwYWc+TdBGw1sut5ROKYT2dxvtVF4YqLUj97GdIp2YJ3bmUwKdnS5HEXwj3UK+46Sxm9iZzwOo5i31GqQ5+dE4VTGtVsXNrZnGcupGNtGHSbbQJnZqbnZbTfs0ZW+tX9uIZPQSYGQmVxL/nXdalot2e9F1o/1R5kkndmpebqvVntCtbpHdiXsGObGpnYqXWzttTJmdtNF1OrHj17WeXMnra+oaXdsL5JxU2+djo52Km9unQsVScI1aSG5cr4mdSga/s9O61bV3ybWP6yTDN/FPJW3fNpCtttW2NcqhHSxtvO2VXH3bbrYsqdMYvOtWMBrl8qbVqri5tdPEJnjx5hZuHjwVYWKn4ubcbLX3pVvayLqNDjY9pLmSi+/cbN19kfZO+zZKGr3OmeipJOA3d4Yuxlzaqfi5u+1jO4NObGyn5udN/hnbqfl50/0a2akk1Ts7kloDqbUVgk17sbGd32zOYzNr3Lzm6Zq4p5I03/y0j+3Ueo1Nvc/ITiU/vrk3HNv53d55bKfWO2+ixdhOxc+b4DU2U3Gztg9TasS52EjbEKe92MiOVNy8Ce1jM78baYzt1L3c3mJpo6g29pGZTmxsp+blTZHY2E6eiU0z2exMTJoZEWTGJplRUWZMmshVJfI1iWxJInuSyCAkxu+JMW1mfJcZbWVGIJloPBfjgMymBzOxcDe9rYiFM+OqVSzcnlvYiXM1Jnvetl6OKGTDvsxGfZkJsJmN+TJ5gUxGIvv+75xPviiTwcrk1DLZvEwuNZPVbZ+FQqlWa6xxWGOb1FgLO3P3eHmv0qgmxfL92eo+16HPbeJzK3xusz7vfYhPU5EHzlavuw3rbpO6W1F3W1f35ZWLfGJO9TrbsM5pUudU2pmrc/9k9O0pFVm8nOp1TsM6p0mdU1HnNPtML6/YK1iNdHOu1zkN65wndS59l+fr3Hs5jJ6l8sx63fOw7nlS9+IbrZzn6+4GT3Vazdlru9d63XNZ9/aXo7p35xZ21tV9dWUrzqjVuTM2vLJNrqyFndk2nvuebNnnrs5wtTp3xgZXdpM6u6LObr4v7a+47EuLM+p1dsM6u0mdXVFnN3ufm547eVD3HIv77et1d8O6+0ndfVF3v54jPdH6Y3lm3Qd+6AM/8YEvfODnfRCGCnqyNIUPQt0HfuiDMPFBKGoSZn2wpLcMFYSiHYS6D8LQB2Hig1D4IMz6oKdqWMYRfVyxOjPWfRCGPogTH8TCB3HeByMFPffLpyfWfRCHPogTH8TCB3E+hutjNzdUsPqcQRqp+yAOfSATH0hRE5n1wTLmWUaTxRn1usuw7jKpuxR1r8Sv4ysXbb8aR3bGBlcex5HduYWd2Tr3kXIf/7mixVXjuc7Y8MqTOmtR59l4bnXF/j4XWqtxXGdscOVxHNedW9iZr/OyrsO6+6Lu1XiuMzpUMKm7FXWfjedWUXf/lBU9TTWe64wNrjyO57pzCztr676M/8sz6nVOwzqP47nu3MLOfJ3dIG5PqfB2NZ7rjA2uPI7nunMLO7N1Xo55egXF01WN4zpjwytP6pyLOldS4K4daG+lloLW0lnjeApzS5xBsk9cJQfugmu2JLQPmnfaTebZaKcy+bCz04zsrJJ9KU/sVGYchqbLPwRRCSc5leEcRjcxU5kBGppuwZ6sKVjqXv0P0xrjFHhrp+bm1k5sK5dcG4PIONeX0thObRJ7aPxW9G0Uoa5bnmg8I3VSr9rM9RM3a9t4rXVtk0ZJqGgTOzU3t3ZC9M66XR27yaaDpNiMnZqfndtqo0HfhRTBj5N90+ZTm5neNefgfNOy0rfji412avPROzvtSMxpt6uFjZOYcWqn5mfvtrz5bqF9OZkwvMHPtZnnoXucuv2w1Wty42Tf5LbXZpuH4LZa33VD+u6d6ijZN1OtmptD6+Zujntqn4Jm82NRm1feuafrucxaL2vc+JjWZpN3dtpgou0fvDkZzi/23YB3bKfq5g294SDb19qp+bnVE0Z2Br3Y2E61OW/wz8hObY74xvs1tlPzc2sn+7YVutaWTroxm9j5zeY8NrPGzWueLj+xs6bXWPu0j+xUcuCbe5+xnWrvvKE3HNv53d55bKfaO2+gxdhOlYIb6DWyo1UKNlvehdQtzJ3CTDc2tlPz8ya6j+38ZrAxNrPGzW3/ldp+q23NadqLje3U3LwpFhvZ6fffLKPSDmnnQBJH45jP0adzXPyuyfy94e8N5zec33B+w+8cv3P8zvE7x+8cvytGAI6lC2ei4W5v6SIadsUsJ+pjobCjczUWrixcWVGoKFQUKr/T3hP8PfD3wN8j50fOj/wu8rvI74TfCb9bZZJbpaleYx3WOE9qnFZ20uw95l4t711fk9UMs/bMus/T0Odp4vNU+DzN+rz3Ye/TIq/nUr3uaVj3NKl7Kuqe19V9deVCa67XOQ/rnCd1zqWd2To3o/ZUZBJdrtc5D+ucJ3VefYklvpmt8/KKvQIrzqjWuTVWXtk34zr7wne+ma9z72UZPUvlmdW6t0aHCsZ1901Rdzdf9zB8qovcpXf1urth3d2k7kUWzru1dV9eORdn1OvshnV2kzq7os5+vo33Pcyyzy3OqNfZD+vsJ3X2RZ39fF/a02DZlxZn1Ovsh3X2kzr7os5hts5Lnrhh3aW436Fe9zCse5jUvcj3+rCeIz3R+mN5Zt0HYeiDMPFBKHwQ530gQwU9WYrsqY91H8ShD+LEB7GoSZz1QU/vnuZLthXtINZ9EIc+iBMfxMIHMuuDnqpxGUf0cUVxZt0HMvSBTHwghQ9k1gd+pKDnfvn0SN0HMvSBTHwghQ90PobrY7cwVFC8v/Na94EOfaATH5S9t876YBnzLKPJ4ox63XVYd53UXYu6V+LX8ZWLtl+PI/0wjvSTONIXcaSfjyP7SLmP/3zR4urxnB/Gc34Sz/kinvPz8dzyir2CQms9jvPDOM5P4jifSjuzdQ7Lug7rXryj9PV4zg/jOT+J53wRz/n5eK6PupdReNHT1OM5P4zn/CSe80U85+fjueVIqL9yeUa9zsN4zk/iOV/Ec2E+nmPs1cftTTEnIdTjuTCM58IkngtFPBfm47nlmKdXYMUZ1TqHYRwXJnFcKOK4UF3JJchgNYFMdsQsN7l73d3GZHGxWnz3PUgxpAjVlVxGJl2TBjbXmaytebDJpJYGm9XnY63J2noUmyq+xuTMO6/Ow+dwC0fhWNzN+vyOMJzfESbzO0Ixdg9EkTNrQ8T1fhIZVKpomn5+31bR0uAZTabfNNmODMJ8A+EDzbNXfI1JP2tSB82jm0F++mYc5m/PZpOjNieFybmeIyxW3+xuHsd0DjcVZ9Z7kGF0HObmq6zac/AcY9++V9co5quU5odNejJVJQTkFlNWQjyl787wvM5G1YFoevmc9vUanFn33TCqDpOoOhRRdahN9N5YqXobq+W7x0/CjMnak1BJfU+e17OYrCxzttHkqFfxhcnqckAbKl7vqGYD/mUDiTQM6Tv4on5FwF+0jWGsH+Zm43Q3ELO0P0a6QYq4oz4rJwxn5YTJrJxAjiYUs3PC3Oycrrc4N1SU6U2KJ6E+SycMZ+mEySydUMzSCXOzdFb9WH/l3hfFjMJQn6UThrN0wmSWTrDSzqwP+pvc9wJ9b1eMsUN9tk4YztYJk9k6IZV25n2go3YgfZ9enFn3wXDWTpjM2gnFrJ0wN2tn1cD7ui8jmUJ7ffZOGM7eCZPZOyGXduZ9kEbPRJjyrD6LJwxn8YTJLJ5QzOIJtVk848DQTt0nx9qEnrHJlE5v8pRB9sRkFYexNs1nY8XXmJz5fr3z8DncwjFwlOLM2nfsndHybsbxGi1SLODX/ut8FDehwsRPVSpENx+JTNh1FpOnDLJnGkiFsNHNB9mbK1436eeD7Em0coZm7E8ZZG9qxkXLmZvj3rWDc9w8jsoxFWdWe5A4nOMe59acWbVn33D0ffsurrFq16X5YZMeLzfTScNk0bRPO0A5w/M6Nze+ey6Hz2lfr9WK+O1/1303nBsfJ3PjYzE3Pta+VN1YqXobqy/qGDd16LUnoTJ3Z/K8nsXkKYPsiclqRBxrU3o2VrzeUc1N2181kNA3DMK1IlUWZW4oGIcz9uPcyjrdDTyH1zlyuWiF+dqqI53R4TVk3P6Ib6IUT8LcSjtdb3FuqMjoRQqvV1fa6YwOlIxX2unOXdmZW2ln1Y/1V+594Qrt1RV3OqNDBRNfaGln1gf9Te57gb63C6X2ug906IPxyjvduSs7cyvvrPrwZTsIfZ9enFn3gQ19MF6Bpzu3sDPvgzysOz3/oMFXV+LpjA4UjFfi6c5d2ZlbiWfFr+Uz4aY8q67E0xkdKpj4IBU+qKzEM1pxVldT6BYdiZ4TXwNNZVGeqclhJmydyVMt6D/Jra21eJoV4+0s1e63MRzey8SznGhVmXtZvBWJxZhlfC/bHry8l8XbEOwX329KU02UbriXLbl0Wa3CXjW+3nAja/bmIpBW9TmuNvRUKs+sRiAy/DJVJl+mFushdy94fq8dVSo0O1Gmr4g0o1u++py8e99TrdBwwoxMJsxIMQ1CaoOLTc24VqE0W6FFRaTvl3LoK7Y6s1hJclKhNKhQ8T4E+6u9r7rJGXMKuHLfVpZPVfEUSbGS5FiBD0MFOlEghZ15HzTnhkpy32pXZ4a6D/zQB2HigyLbIadb811H2U6p3tXTrfiuo4HYGnunZMbEXrXzlNOt9z5T5brJ2Zk9wvtW4f2r8M5ZighH6jN7ZDizRyYze6QIqCWe7uE8rdtj5dXaJnN1F/V7qY1chGsiTT2m3lXFmb7qImkGLiqmCGFfikem9vphVKfTtvTaq4dN5ta4aG5QtHQNOUshfyvF+x+pf9crw+96ZfJdrxSz/WT2TcLyysv2nHslxZl1ag7fJMjkTYIUbxBk9g3C8soyai6h6EvrbxBk+AZBJm8QpHiDILNvEJZ1DjZsqKUP6m8QZPgGQSZvEKR4gyCVHcQmHZSdsqVWtg+b2NNTdg6VzcM226s3/crmYZurvMbk3IhLjPu4WM+9qwvHoiVV13PvjA7u43g99+7clZ08H9OOe4jTuj1X8sWbzNVdNDtFaumaTGy52Ba8c1VxZvXFtQynSslkqpQUU6X0VPtzjbN0VRfpqfbmmjFXdZE2cyOt3jXKeF3JaEouz6yOtFqjpYu0GY+0tJjvrm4OnP2VV+1ZeiXFmVVwtkYHCtwYnFpkovrtw+efpKWSvrkUbyLV1X3ghj5wEx8U85r6DbrHDVWGzzANdeADX/eBH/rAT3zgCx9UPvaVuNWtqNWGYklTN/pS69aya8yc5OAWE4Nkqx1otY2vdXORWtLKh78iW5YsaTdlK2dru9G8ZbHR9p7FsPioPm551+WpNZWpX61vMrU6YWgthbTGXn2HqbJGMqxzE/2aOleGG60bc8hNTC6E2M10a0363E2zVfM+ubww2WiTu++JtJhNrZURR2vSnzzcsXGxW+2iNRl9+8z7kw9iY1qYtJMPGqVYQ0y0PuboNpBqGv//ODuTZd11HDu/Tg1O7BDFDhi6KY8qnBWO8sDv/yIGKFJaEAjtzFNhx3/vzS2SYAMugs0nfy5l0xQ1pSw9qXY9pnCl+PwFJBk2DVrVrd29ftkdbUec1H9S56Z3yqi8GqeVj8aJbhKLSxz+s0rbKNHEFpI+C/lxqVhKJIOuyyL9nWT/TDJondSUatbpyGk8TaKtI59KFvoue5q9sjcZU1LrBa4EtOi9zX78kNh85IN6uxoc6pK+6jI6kdXTz0lSje0snXJ5dfQPs6PzWNJbf7LerE1n02Pptoz1ywFFV5EHa0+0TTqPRJU0Sb0cInVbzuNcZnfWm+76LhgmuW+c3PJPkiTEy/AhTuA9vr/sDsJoSXo509FOYr24pK3NZxefWQacbJaxF33WPuPDLi26qTzcGvejN5JerSlqclqHyvydXfL5A0wx9GpNGlpWPEdW8PIoZElVXxqQJHlWZJZBUPIpIxbUQ3B9WXzNjxggVvfcxZu9mpu/umR4lZnlg3acR9ayjiSlcyeZkruST/uVZNM3CQ7iXDDJfeNQSSKwTqXo6Hu3l+/VW9viLrPW7UhRJptTNRkQSKSq9o1DWUpQTvl7cYq9zw5Uzp4U/3nec450UWKRJCjhejBypIv/FJEZYhS3ywdppxf/kUWdHHcXyl2hhnjOLSJRS5f+OfRSuHSQzJen1IOa0jp6j76vJPnko9PZ4KJESKLWx2jUQmkhvYyvSYqjzudYufflz7t08yYusBVMMhg6kgKPl0XE9jINl6GekgynKp1Rkzy1Dyjqmk441BSSqKXLSG84xyOZureofUimXda3nM90DZ5zFLwXfdIRpsYIRS36XuY4GVtjn+ztMs5rC/zICn5vpVRMMVxM4gdtO9lGSYaSAK1q1u6D6cvuUBKYuretI1743TqQZISWOH5kbkin+J1StDFkXkskWqt2feEhj6PmIgt1cpf0KuweRzBq8Yv4Adkkz16+kgyegT5kYJD0YfEbMm2nl+7lK0WdkkhFAzqNiD0hKWYqTWQAnzJitJCaiN7PkxE+XmDSJOWfZcRn0zrx6T3zgU1STwCESUYs6ivJ26z8svv8MDxkUYtjk4EoM5cWKe1XJcePdkhWyFqFFMOxA39feKv5gxQDx8Y/rM/liR6Q+TvvJb/oznqIyhjvYUCSgWOTWtIJu2f1r0d6S/52JSkSUfqDTMqwWv8gUWsnkilHH2Nsb8m/Urz/AAoZg6iNVVsvFNgdXV86NQ6fWFfCRTvlS/N/NHd0e+mR/GdRHu9O8keFDB/uEalT9EWlqnS9neIPUowe/koqhsSpiTSR8ZIuxa/TtSwi29Sp0jgibejUlUCDJKMn7ceqMVMShdfeiyf6qMgIiCEJioStMpZPWWbQRu9HRgctI+r5R0Z1l6WcSN9zq/eDIgYNIxroR6WFKrN+KQx9cUNWKacIHzrXqJGlUx3x+yfJIEKQh4Qs0tgibCWNl9XHV2NHEQJ99km8QlY8Wb7WtUPwn9qx9OHP2dgqEqUP8AlJfvk0kubpsuI4z0vxn0pClfVhuR58w7/IkGTo1EQqnIfSDqWleCp+SavIcjH12eA5ac0mxSJBkvvmESfzQ3pgU6bWJOr3rfg/Gjx8YYxVkvROuhl92Z2PsSgWwZ/msFFAhHhFJrgjEWGoZV34Q3qcUrq4qoBL73NrhyzGzuUtxG2Q0jSYsIz7tiFd1Z76apVUnm66XHpflgei8KWsy2rpDCI7GafZKD4gSy4RGKmVep0eu+R+VRmuC7TVf0RaJ2k+OD3Wg/DAqVAY6ZEkimWg64baF3vFRnFDa3SL0NeTXYwbbT0ID8gc8iOSXNYXsu6WrjzVfjsuBsmaFGXmkRREEMKZhB5ROvSMZtX1xymjr10LiEPWzXp/YRzgkhGk5zQVZidrvIxJBk4t/+jjKlIw6dU6Y2kHkh6ksldKNuab3H4UtKvvbOHbxz1id+QfqURNVVVse8dFhuGSZNczbaQHm6F5wgtb5gPaTbRRkmGIQD44dR1R9KHsUUr5Z3GaRWbfYwgM8xfQ0aN3zdhU/vlqnq/WCUIE4i9kCUpdEcBdy6TSXFznqVFJfQNOk5TqFqkto//omGJ4lxn+/uRXiudXilFk7eccM46oVBnAV1T6VN5n1qtmTb15PmU0ak8fzyk+SQYRgjbjQUWNZhpmSwFFRhNJ+YcTkiTp0BoXI+DiVY8iBGw+eKV4mR2lGN6BQavyy+6jf9kdjJyhqsQ/pKQtfklUWVLodkgpZ573iGUYnhrwryeWMhw55gOb5BXGiJIMAgRSyqSYsiaim/RMgvRSmSvEfUhjy4if5+5FdxVZ7Iu/gpETbjebD4pNUjL5SjIYOkWnBEUFiTsoMlKaDr3lMmTwX6NRnLm0vi4SYWqMMJPlR6bFrI9VSk3xMDypVxRxLX116Ba9F6WhsarvWmIpv26Q3R8Um+TFHoySDCIEI8nHrGoNF+X3YXh0ulXGoy7+zqzb5NovtS1kcMp8KFrobFccQ/6JVWrDFe0eBAgkRSkP68K9XbpFjCQV6l23y1ZkRLq8pD/WypBkoNfoJ8lMLRKii2fU/Rff4CX9iBwQ16v/BVRlGCEwH6R3VdY4SQojBNasl+GpxYZTeL/P1L1tnJz43TgJUty3jjhy3X4Rl6OjJ7/HzkFfdker0C6ToQihJp+PkLwpZaOwC1EQISjKS1QsxFlUpr075XHGKQYBAvFOP11nevmm6DkAbZtT5TofI3S8wnWqbHrDF+goiBBIP1fElD6OTPpm6rhnNVRuI/m/PAsp+kI3Ywo+lkTh2996qSmJaByctTF0ig7pXDSJcyYpZZTxLSod5h2KQgSieX+SeANZMVUpyXUb7BgtrtPE7EJF/Km+tH/AgQIKQgTytzLCRTNK0Y6ezlcXukoZdKEgRiAtq49NZ5alVlEx1MYmwamTVtVA0TT8VCGbdbsLkgyb59B5TCzXGVHGTtZOKqszmWp6WTFf1klHRDLeKaToyXAdjax2H+nQAxWSZK/jZaaSlUIxk7z/Ag0PPFvX8PnJIiP0mMsY4ed5apeSJU5ahh9Zl1DipmBxS0GgQIP8InOaKDyZIkRhSSkVNyS9Uld+ZSYpvvTQ9XeGa7gUHyXAD4pNUvrqV5Ifnu0x67SGH7l9GB4FCs7C+kR4l9HXRa69klzNs0/yI8BmmzkdrpnB/QTRgV4PpUafSVzaOQSlKRr3j6JF4YEV+xM3lsvVGZVM0qi0NG49XW1yHKWPMQOljE4QVG4/uuMha/+kFA7bv+nL8CBAUA7pKTkdUkBSzI+tyvMrwWDAnO2nqY4Xod10u1fNlhlBJmV95rHNflP15fqiVEqsyUAKnEy62y+6XPRnKS+z+cvs6Nly9boinvopS8QxJUo1SLEVRMLHtf+gjUMaVGNd9kOSQeMk6d3y0SmriKRbViNJ8WMyIXZRRzNJ6YF0qmOG/V8KAgSk8SMi7UMa4GuYpMbhs0nyYGN4cILgpHGq5exJJ52rlPriq0yQw1VcSYoaTTnpBIGGR82jy3exWI8Q6BayOvKi4UhdTNVluBS39LFdBC0eBQgq1x/VqFJ1upv+Go41fwzHKEAgc8wP6QNASWOpo1/qdHjodjCVJf5KGQxowqdyKYgQiOotRXREFQ0pbm0YTk3SLlXFUJ+qd7w5LNKvY4qhjpZ2qLrOljXHkFWnbvzpHvtR+9R+yt/Wfa2MU2L0MDqbD8oryVQ/kgwiBCPJx6iX1enD6iA+IBOi1Ld0a5lW6nBBhx4OYZFZ/doCVWkh3elIsmLCAobtkrKs+i5+XL9mQ+lFrNuwcydQ9Y+oSHEn4kAwyXCDGj94JUn9K8WP/enbqMIvs5fr3ZkdHx6QkmkbNpVhMofJOC7PTv+cw6RKtHeZ0D5Fhwc0/txFusqwlqVi1SSllUpj8UrK9pnOPJ260aPhGkjyQ6PBBzbJo3+l+HF44LEqWbv7mnH2dgcSrWqEaqxuNHhYbePkOhqn6NEt+d9FYaMvj+69imA+C+nhPzH0fNXkSrF0fV5d1qJQxigwIKI+ydwgI1lEXqJtcxdZ4CaZNWUsw2leCiID10sEzwfbmoyS/Hjc4LHq1drX1B2Y/XEKFyr+NW6uHY1903B0Sr781Fvjj90m9GgyR11ng8o92xRIMjyyppFjUT0yL8v4Nf5CyjGPE2qct4u+IEgwbBr485dHq2ec3McZXDDoZfKXweGIOdZcKFMfvddJs6H5nhWersNBSECP/Z18yPL0UJf6ng3zOvan+yVHBxax7pTEVt9/rz4XUyxXTClI8WPEPEa9V0mNvswOz61z0X4jPfpoub8k+apJmbv1AIBUDzROEBCoeuxQtxFrGjrtveKcriI3UeMaV4Z9ZI4ODbD54L3gbF8pfr2I+Fj1Xrx/mB2FA86qW5vSFBqryW7dcH4l+bnetIvDr0YOYgBd1gplrDaP8xg7+3YJSx9Fi2IAuN4cB4Gy+tUshnPW/zSbRAZ01WdlYM+ToxhA1YVXkj+XxcFYHdoF+5fhQQxA1pk/nZRl3DSS315+In0mGa049SioyAWpvENjzcM5ynq6q7Tv5+yL4kd0jSSzD/TF6D6B7knrKQE9Ac/1Vcpr7y8qZRQOkKWCHjmWptCz1mNY63vYiZseeMp1zoQyQmVNzgxnWjkKB+iKc7yjqNuulxIXv5XpHHG0c3oK3cSR2dC8ysXReQFRsbplKr2GzxVBm0k23X/HJDsTXPjkICCQz/YjM8Kpe8UqVq7l4aHYOtYZevZLpRnpifBkDP9acUrzii5OY09EF7FZlJkeYKrHTHKEERVs9exIcxQPEHN+8jhsqMcm366CvpxuFA/QBWeSlZziLBpdSwZVJLqPVtKaGkTbky62GY7JcnTFusoKVm9rn+Ij6rWYw72g6SPl/xfFHRaIwnLEOWPzQXnvDbSvJIPZpmhEQvl4YlXXfbXNZpCIlXbokQxqB9RlEA9QPa5ntURS6dRI7y2rWUrV6gp9g9vqHJ4XwL/Xay52L6h8pPil0G6j8nbDKjJ73zh8ygJQrxNIVR7jkJpp74+miaIB8uWP6jlZzjXK772l/FHEIBggy8MfHkfe9EZBbdu9hijJfdPoVpCGaEhGiV4i0CTFS7aux336PLmtCp9PDY2JnoEkw4Gj0Q0ZdKwq99q3kZVazlpV9ZZpWa/ypQNpBhxFBHJuenxHXG/KepBq7Nuc4inVF5e23JqicU7JGl5i4CgkoFMEiXMgmQMKjz5ZFSCoZ9wG/2skSWMfIGsU+UkyiAmU62UJVeXqtvKrB6WvPhTEBPohpRL/Jb68jXdl5oaVTGEadzhmkkXvwekWR4fmCWICVbq5uguZdsdDyLoTT6ynT/SMrFSoJtm1akRf9gMfmuMgKCBJDjKicu/HCVFJUpy7FHSc+eIJVWY9VVbYMJY4CgqcP/ku5dl569euc2ZXKSHJ8LyA+aBvfUaU5MfrAUwDnqj3GsZxDlGaRy5dlmdt8mXhLyDJj9cDnsp/NU+ij9YJogI0WKhJgUWiJM7XOQleTOe93ZFrG8rcdJwriLYtmqjP6DR0TzoTyCCUUfZuEg4LpteKvgsmXqL1xnoClVbvG0IL4IeSSjRE2o8MWmkuyldwz1h6xo0gSQYeTAWKnivUCA/pgsE0K8ejTpIMh8ihuz66RV/EM2qSetLsaLqRn/JMUtykTL9Zj7Q8SUYHAzS+o4cAZAbQi2qapJZH3cKlJ68kizo43UkukGTUIpzHSW19+W9cL3uSFG9+5leSz5sikmR011MmLTFIr7nm8XpE02N0A+Kjez19JVn0UOsBDxxIklHzNN1f4NHLFAGhdSnNI6sk6QiUp2/Qy13jsNWBSX68fEJJvJ9eb2jjxNOp0TzpIiLR75F8/wU0TxAHUGUmU5M0unRu3Wi2d6J4SlKRbVKvrOsxSPJLmt0ftPc1K/5KMpz/+ykNIbpdqrXQ+wbTur2vx6JlfqMCdRlFAth8kN83mPpXkn/1wMDzoIFuWoHRf/m+QPljXl2oBCWMDwX8cnVfnwsQ6TIOnPfnYS1J8UM1f97cN28aPCeJJMWP0OZnitKT0o80S1Krywmj++t5gc+XGuR/O36edOInjn9Lp+g6lPUIqkzwDVokigH8am0/xNnpTmvXPVmcsKJHBX4tZT/03IJ0AD0pmTu0cvzE8S+lzLowYSI9hFDgXKQk+dEmesVENH2al5b4HKM8aWBE+o0CxamrS+vARtAo6EeKMvtpCKFdB931VFjTALSIkvxnHERoGgGQGaw3GIIx5eW3vijl/REtco7nFZ7XonUS/SqlUrZJhtl1dl7cIunNOT0n+kd3635EIsg010tiNPyjdfTJErE7peucslSrvq3QVO2WP3wkvYh0avCxJWjvGPLym93iV39SkvlSt4WfBD8fFZDyiQ+gnOclBD2yIl/ruY8/dC3gq16E7+gd4wBA/dFj1GJ1ui7GZPGqooOaLJSkQ+k7C+qBpWWSCjVI8WvcNF3y5ETXFQTVslIoGXyDia539xLpJooqJIYkP1rmcyjquNG3NXPXJXKCcRMfCFC79RwGt3Pe1pIpR1fa4iH6mBUy6wHYQ2/sPwnGxwF0e0Gfd9Al+eg944J1a3QOivGZzF9AHw8vDHybna9hU6q+1SHFBDcZXhjQIkh/Ec0pCnw2t3iFph5E72LIQEl6AbWI7FPcMyT51/OMeF3pk6Lgqr6OgEl+zTNFz/OUPq+96eVE3Q2SH5leNYLxo6c2RZTi7BA/TafOQrfSZenah7PQC9THOKSnB8j0CpsskGmcYoCWid+mUwFAGtUUWT8SlF4kvnZEsmXNUEiWySyFZ417oCP/6+cEzBMGhTDJv3tOoP8xDy3UAwb3Xz4nUP6Y5yDqAfNsfFngl7v/5sGBExdLX88JfF6rN3f54XVy7ccfScbX6umPeXCgV3C98ZmAXy7Bm4v3J3rz+FTA1/1y1hRPEd6nDm+9THmnmOLLAr/cL8eb9zKdMST5t1fW9SS5LvN1ZSPju0CSf/uegFWmKT4P8Fs6oh7lPzVVGjqjQZIfTfJpbT9kRZuKjqFTb8s8SX69IvBZSk3y0L1ukTHSdTDJv20TWdP/iATQo4uGtaZnGz/6ol5K0kFR+iNNM+txe/E+GsWVf9c7J6IVMiT50Txdp1SZsVsqU5ommUkOTeFUaapeknSgynwB/TuOBfzWGSk1sUMmChntBHGVFJ8JGK9CHIdukqyn4jTOrMGxg5pK06SngzU0rK/sQJIfzSPaibsem7re+RqHh0gjFKLVRJrq7KFXFjWq8oRxJcmP5vkwnFSbio+TKUe8B8MbkpLk1+gZx1kPxehdSeoNztJpXLuWleZPGhB5ccLNlPKjeXRzInVdDuapT89xYF+mA30fPrGutYvui8AMluJwgBZSJhYxa1w0ueRp4abHpEQJ6uVm6WX90MNdx7O1K0l+tM7neMyiBkR/SKFlImOCqvx8TICTvnpw6PXTS56SjMBGerZxzA0yS2sk+JDCQ0+PAwJ6DV8v+ZBeBtoKVPMXkORX63y6S5LVg5RbL6Hnjs0TxwYOXVSzkqh1GTcVKo3wnI4dmWdk5pXhf+qjK9CF4tDAbx29UtFgbNN39BhiKykODYjdespeb1IQTYFK+kaW/N+p+lRWD7qzr4cnEhby07PJYM2qcnkqVPFkVd//OqS1WJylhgX0tAbQaCTJLy0gOlG+EkdDl0ZNonn0pJc+LlqkkDK76qEGWVM2aJwwNPDbHXhz8f4EEZTC0MD3HfjrSJDITd1k09UcpPgBBvy6Am+eMAAZncK4wPd99RGSfu7IA/dekgzv3H5fBcfr5yiiU/yUwOdN8OsFhPuOfIcFSYqfEvi8tj02pO+74moMJBk2zecd63FG4rnY3Sp0yfgxgc/by+POxHNl2sirMDTw2+1lc7G7Evjer7sCn7d4zdVh0dOQ5MfFtI9bvPWPueAMu+SS5MeZ9K9bvPYSNkO3/Lwv8GW3KB69MCBT3CE9DfzF132BsIzlD+vI0SdppGpKz9CB4tjAR4KyDhdf3qWERc+AdkaXFgcHxoOnpz5EME4pS8voS1ZF3NqhJ57E94wXbU59SzRjl/y6LVDU6dLYg7w6tSzhRGtJKdcbi/AXkOTfNU37Iy5Smjuph1OtBB7jKziQxnuX4iJavg5u6A1uSVdGtei/rncajnEKT7om9PL4ZICYpcdm9JUAmteC1X/p/rEeVZYZ90eFsHgofeoFJu/4ZMBvfVJmBekS+hii7mVikh/NoyHirE9zHaPFm56J0W1LnYZk2Sh6Les5dH27E+3+uszxdYVXr7lIp+xMMs8fJ3T0ODbweTk2/zE3cttzY0n+w0frfFyOHdGg594wPScvVXv/TZIjnJj0kL1GBjVEiaX8u+vQr9jAGccGvkrWiizrurrcqsdopE4Jkvxoks+SyT/8aKequpiFJdgZhwakkVUkijStV4pFN5RK1+tTogJlKS6Trp7gJN1qaZDkR4vo1HTKmC3zDoeYqC+bSd/rkuSpE4OeYq0Z3iDTEfA3NSmLOpnBflT8yVJPX+SDmowjA981KYpVVGDRO6j6YHeGFD/aRvpX0T0pfQFaUuRajnEcj6jO+3jPXzwq4IwDA9cIlAVWH2+KXyOwF13p6aOFvWeNiOhF6FRRBZxxYEBnLxljXe+IXGe+ZQQndV7iZP+M/11fkDj7iHZCin85WsSf/+jcKiqr6OFFSPGjbUhpjvrMcL4KqVfpsozYMs6A96TPSej10aZhP0jyo3GKvgUnPltJqnqYuqlG14VEEdWX9KG7EeXWA9IF7P56O+BzLEp3l0wkUz3TAzPs+fV0AGkwPEs5znnd5JoM9QTon+seez5O3Qtrpoxh23zeYu1/zM3Zht08jgp83WIdwhRu9zKa/fViTXhHVIPQeDEVol9nHBP45Y6ovTqLvTwOCnxfvzRXPhusbc44JvDL9UtzMZWN3V9E5K97iObyIyVwQXFQ4Ose4vnH3M+EO+rSgB83oD4uIo4kn1uk9QAN8HVcILzkl//YW4WgIs+vwwIf1/zMzccOO7Pn11GBjxt0o4zPrb1EWMaPlomv0PU/5mohdRiI"} |  |  | - |  | - | -
[14 empty] | {"index":131,"total":402,"filename":"Advanced_Project.ifc","data":"wue0JjntzpuwyoIc+wyQ3xLmF53B2j6nNclpd56EVRbkvJ71nhY8Nbt5EpYwrPnOk7DKgpy3N6RZZzzTcfMkLGGy5lvn/kE5ts4cu8HWhhI+j3XJY3eehFUW5LzFq7DuQmefx7rksTtPwioLct7ezX5qhn72eaxLHrvzI6yyIOdN50D8l9cygpK+7pLL7vwIqyzIeYvJ4nez+R1tvK3s5kdYQkULFJ914DM7P8KJgONXbc6r1QFK+jaQnHbnSVhlQY79ZnQRNZ/YPNh7cPMlLKGiBYrTOnCanS/hiYDklkCbfU7rktPuPAmrLMixdef3sTnuFEr4nNYlp935EVZZkGPrzP3M/Q7W9jmtS0678yKssiDnPcY26Zp9TuuS0+58CKssyLHfRydRM0Y0u/kQljBZs9IZOM3Jh3Bq5heYoWaf07rktDsfwioLckydz2vkHK0PbfU5rUtOu/MhrLIg5+2eQD4rDOjsc1qXnHbnQ1hlQY6ts3z/nO9KFFzXfV7rktfufAirLMh5u//zvDqedAt8buuS2+58CKssyLFtIFtw7gVh//v81iW/3fkQVlmQ83bvi99Bz0m3wM2HsIRiC+58CKssyHm783bu7Z7eICjp2oAkz935EFZZkGPfWb5u0UIcm5sHYQkTNSueI+A5Ow/C8+I634HDmn2dJc/d+Q9WWZBjvwHNt2j5LIFfZn64zs1/sISKFiiuI+A6O//Bc4+XXyUG3X2eI8lzd96DVRbk2LrvHV2efUAAbr6DJUzUrDiOgOPsfAc18TnZtjrq7PMbSX678xyssiDH1lnWnGF/zc1vsISJmhW3EXCbnd/g6MrzWtTs6yy57c5rsMqCHPsMIV1jvOkx7vMbSX678xqssiDH1H3PsscGoLvPbyT57c5jsMqCnLe76vXMc6jZ5zeS/HbnMVhlQc7bXXW2doHdLjePwRIma1Y6A785eQzOGOcWQM0+v5Hktzt/wSoLcl7n9bE2tNXnN5L8ducvWGVBjjnGzwhrup99fiPJb3f+glUW5Nj9fDImiPktdPf5jSS/3XkMVlmQY/c368xv+0N/+9xGktvuPAarLMh5f8/+vGsPJXydJa/deQxWWZDz9u4Gt6A8Z0TBzWOwhEHNQeUxCJDHIDh5DCq/ZsOvyPNYD1DS0z3IfAZB5TMIkM8g2PkMuAX8ok9+bs0HP39BkPkLgspfECB/QXDyF9RT4/dvBau7nBZk/oKg8hcEyF8QnPwF5wV9fqELanb5LMj8BUHlLwiQvyA4+Qv4teCatLVdPgsyb0FQeQsC5C0ITt4C4igTfqELanb5LMh8BUHlKwiQryB4+QoK18gtgBK+zknqfPNZgDwFwc5TwG9FPW/zQwmXz4LMTxBUfoIA+QmCnZ+Arfy0AGv2dc5S55vPAuQlCHZegpMVoDbRAnitKvh5CYLMSxBUXoIAeQmCnZegMhlyBrzGNsAW+DYo0gY3pwXISxDsvAT8xsyTFeC83PWUdHktyLwEQeUlCJCXINh5Cbjm56Wfk58ASvo2qNIGN7eFD44nO57tvLfDGRJAd5fbgsxLEFReggB5CYKdl+DRtWmdXW4LMi9BUHkJwkfIeX2jv/F7afAVdbktyLwEQeUlCJCXINh5Cc57O/wtazDWXV4LMi9BUHkJAuQlCHZegvPODuch5Vy72AKX24LMSxBUXoIAeQmCl5eA3yRJogWFYMS5/BZkXoKg8hIEyEsQvLwE8nWUk5/giZgNfl6CIPMSBJWXIEBegmDnJeC3K3KXLYC7FMHPSxBkXoKg8hIEyEsQ7LwETzaA+wWRZw74eQmCzEsQVF6CAHkJgp2XgFtw3rboYH2f52Q+gqDyEQTIRxC8fAR8e5PzU0DNPs/JPARB5SEIkIcg2HkInkwIfO8/QQlfZ8lzKv9AgPwDwc4/wDVyC4S1fZ6TeQeCyjsQIO9AcPIOsId4brBizb7OkudUvoEA+QaCl2+AXw5hnZ8Vxs8zEGSegaDyDATIMxDsPAN8Z/bJsQCzyuc5mV8gqPwCAfILBCe/wBnbRdfsc5zMLxBUfoEA+QWCnV/gye6QRAvgpezg5xkIMs9AUHkGAuQZCE6eAf6W8beNjBb4HCfzDQSVbyBAvoHg5Bvg3Gr8Ctbpfxh5PsfJvANB5R0IkHcgcN6B//k//u9//6//95//47/+z//+z//67//4jxx//oTUflY28hxpPpzwp+YfamMkU53xoDU+Ujbb2VL6T8mtljYf8htGfZESX6TQzww2j7V9wky4OaTMYOacaHzuUgch+VXIUKXUWmiF+Q4htceac0yhV8ogpfpSyuenzUPCUa72+qeknyEiUiy5DmhGfV5sO4RQbcMA8zrhmG4l/vRQZjrq1GrKIKW/2LaEn5nh8DNzAxPVKaWUFoaRhqnG6AcpL7ZVUkbbqLeeUh0+JK4W/cW4Q8pYblMJNPPI0ZRSR0uGqetMngzrdX8zbvjJLcZPze0TP3FKScNQ8xbtp5Cwy4t1a/iJObU4s4APs/7JbVh7OLpxpsxpCeYRvVh3SGmdZj73z3qbfUip8yJxrHUmaYO20It1a9zW7XMfO/zJ9Wemm59HrC2FiFJerHtLieVnDONplEmcBSYAvVh3aJSXlM8YsGNpHVLmDapILVEn8Fw4Z4Mt5fPTp5QeVrpktymcxuFdSPysFFl5DMK5LHzmIWp/HrMcUt6MOwdZKmNdGEWGQkNKrjGNZaJ3Sp8MUt6MOwbZbEsbQ3P8w5RSZltiowD3TgPnfLBH7ljnppBaQm+RjpB59tKJIkh5Wxf6z+TieU0mzG3xISX1FOY6F3tIoFB4Wxf6d7SU9VrEtu1YZgrVMa9RyNuy0H9SjWNO9896OH6snsMcMdea+we26IeUt2Whffu5zLy5Y3GZa/BsS6XxXfvA9isnl/CkzJPDmZN6dHSbUspYdGes/7xNBaMlvBm3ftvSyrDnnNCf1ZaxrIxBA09uB05M8auUMQd45I7hUlsdBgYpb9YdH9c8Rgql8aEI8c/4j3ksnGPsz7vqH5TyZt170MWfNjQa35XZ/wkGXXxbFj4/c5d16DNWpDnofCnvy0IuYw0YA6yO9XJKGZ+zsc5M/zDhNErv60Jd60JJNObxn5xWH7W+glKe64lDyi/rgpBSx8dp3pyrfT7LX0HK+7qQS8rjS/9J83GUIaWMb9oAorFqQVBZ4IQZnpR5Z6tkim3Gf+Y5fsZy28ewGx0Ooy69A8OAhXmXYAzXz9BozKM02jL+PX4aTOn8YtxRaCwiY6gPr2Bu1o5/L32s3aWtrW2YjPnFuKPUNu7QYig0mhZnNrH5bcJXiIaUF+MqKeGHhoZjXUh9fFlg0OUX4w4pueQxcAf2DhycBDQJenwOJkWhkBfbTls2qnGQQRnWmULGkKtj8PTwESO3vBl3INyggjmdw9yPLvQzviDzGlocvYwjt7wZN/6kwdOTKfoQNKUM3p3mHXxcK4zc8mbcjQuDVEaHD6TrA2XGelMHAs3EryDlzbgoZXzpS/kZ37M5cgbx1gCDrrxZd3wIcxoOzGjIWLQnMNNM/V5ymJ4DDLr6Zl3mhVHzqHpKSWms9lPOvAINUt7diDHUx/Qbjs3oktXTcXgl41NbaFA/SHn3I8LopLkq9M8aLivJ9ow7HV0PZqkvxh1+0Veh4XsMzFwjd3xGxvxtrX0yNuXdRytfswx35OsBLClj6A5yBccovvpo7SfM9PJjZRlL0ppFdfBUGw7NbBEsUa8+WvsOl+HshRmOOqRMT2/MqAlS4EfEVyftlpK/GqWBUaMkfOrfnLQhpVKfG71zoZ4jdyY5ynMkD98G1oU3J2100ZcL03wMq86mpNWUyWLYkjcfbQip8+XvNnl/NmUM/7HUTy923oYDq7z5aNP/nQO3r17qS0rqefZPHk4X9PObj5bnh34qNIB/kPdUaCyeNQ3x4z9kGLlvPtqQMpaAmYF14NfwxYcUmqdDY9VNY7VDKW/LAn+iaUB3Dby4jC/I8Isj+CLxzUeTUsZoGfNhLAsTVMe4QzB889GWRsNZnCkyw+yjwc+Th8Y6Pnoto5TfrDtwbu5r9LqkzG/SWC1TnJMapLyN3NnT41M0ffYZvD8+AJ/5cvkYvZTGVwqkvA/d9ZZ/HwvUDPAYbaEWJz0M29BzByCkNydNToAppKwlKuV5o6+DkPdlYU3FNt3FFGcXjSbMJ/biTEmPTfkny0L/Lgs9Lzcf2/K+LBwpM3HjMO53M2o6fpDIN6Q3J42XyxrrzF4x3ccxm9ucnWNqPz2U3ny0vXKP+Ts91T6lLIXWDtcHXNf05qTtr0hcr+vGdkvBtrx/0Aa5j8bQmESfsjQaC/dwKYatYoEuenPSpoM48y4NW8wbddOrSBN8xrd2fNHAtm8+2vzOj2/PGGRxvuIzpcxdG8oDCucsf6S8+WhDyvg8j2/6mPbDK/uzNoQGPc3LPC3BJl1689GGQjlMGh3MMe/LDSl9LHiUBy8XwtHy5qPNqdjH+prmbudA1Pr9LI5ZFHDPMb15aHKwNCnjA754evPQ7nGbfuYm5fAbB7cA/Kc3/+yeh0PIHHBpbq3PZEwg5S9RYc7Duj/yoxlhEh1IeV8Thrsa5ykazUcN56bwcOOHTQatwkhxvLOYxyJybXP3lw3q5PhnjxxojdsYxz97hDzm/dCLYRwPzZATWnnpJsdHQ6V4yAzXyB0zjpP2iHnGrzsDHB+NZeA8qs2V4vhoLAXn9DSwO6cdL23LkStMvFYY6G/HTXvEPMvdHDXucuc4ao9afe6TD9ZI9F17h8ixRo7WgS+dHEftkRIGMdQ+0H/eNZ5fk+HolOGZhWF5kOO4ak9XPV+lQC/fNsdZs4cNSAkFbeM4a94Ydr/Xjr/mzM0LHmAyOB6bJ8dFGcdne+Q8YBXzC1g5XtvTWw/lTX/WxTzHb3vkzEOWsf7N2Ny4yDXNhzbGrC1isXA8t2cUPgQ8UU8ScAE5r3YWPF6Sz+PJ8d8eOY93EJPvHSTHg3vkPL7KbI/nqyTHhzPlkO85JceLQ72OHxd8Py45fhzamb3KuQe3vcrPvCrdcUl1PDns9+PjhuPjtlxqLkLOb+N5JvGLszVxjsMhp33mojqwFA5Fk+PMGdNiHn973n9yvLlrlq6diDm7vK2I5Phz3qrh7Ytkx6NzyMDdpcmOU3etqmvPKFd/zyg7bp1c4787WL37+2DZcezkN2fvpwV/Jyw7rh0AQhl00OpYNvfuXp8Hvmku0BnkON7dI+fZapyzfW81DloZixgcwmXHvwNCOBufA/33xifNm1XzvBLkvK8a4afRZKXP0Ct+99XWruw8fv1EbM/7qoGbwvFlUzg7bp4l5xP8LersOHqPnGfD/JP9DfPsuHqPnPlIXZ1n/eNDvLbvR0e1PITlBl/T7Dh7LAcPE0L2DxOy4/A9csayl2ILs+yaXzGOJZ6GNzE5D+S82xnPWebXyztnyY7bZ8jpRZ36wDh0HL9HznMGNb5e7hlUdly/LQcPxEYj7gMxGD/v7p84nhv2uY7nYL6/u3/ysNA/K8zvDqA4uQz9PrmE5rw7gChnOCn+OWp+dwDFqe4MpfFOdfO7ByjPmP0j5vzuBMoD73DkzJinwYowet7dwMFec3kYX746OXfKCWm4R2mUbB80z7sbKEMKXoIB8rsfiHLaYF43NCG/+4EiUKKSHyiR3z1BEbYxvspu2EZ+9wRFEEkufhBJfvcERURLjn5IS373BWd8zQxQW+lBC3HA0BhMw8EtcI6S331BNQ6dkKH87gpi5NGM87yChqA5767gnO1j/RowSGleuN9hQ2WeQwzTw3B+dwVFaFeLd1QWfEzfXcFbjhsjlt9dQRGw1pofsJbfXUERPtfTS3veXUGUM/P6uMF8+d0VlKGFfmRhfvcERZzjYEOOc8xzHyrht/3dE8Soy5k20o26zO+eoIwBjX4MaH73BEVE6vQJvIjU/O4Jgpxa4x0ei2J+Q40+HeXxKaW+/MmZNGd04Ey+Bh5cfvcEReBwiSdyePRgaZBROuRfPEEMYw7FD2Muv3iCw2MK6zM1Vui4dqzn/srg6OlswA2Y8osniBHenfwN9OJ4gnOD4Wda4TOPrAb0XMv9SwRjcZxCFjm+WH3S0x2IGP0vWnH8w9LqmLQTxsrciW+3yPwi0nEVx2gaE38d67aJHkvxwY9jbI2Vc4yVKXJeguhT9VEn2PKX0M0ZkzMYZDgZtEI36+SKuVs1exikOD0yPIyfwTPjMx3Wo+FT5PjX0YYwp2H6szZ9ZgDD8CVriKir0yPD4RgihnHS0DDX23xv1rM7ZDbnp8+w2OEFRNrWGwN67u7O1Opfvef/GOd+KMRaFMenHNNptrGtZw7mLcFrJPaXkei4l/M+87eVKbf5BuYSOWw6/czYWp2mTJ1m7pq5Ewc7HsXxNIe3MjcTapwO4sz0/stpBE5Bx+lkkeMLR3m+jnAdWwbvuKU43ueMlRuWG/8njm/a8MvXIXOesmeke1wnL+OLF+aeyIBe2IYvr+eP/YfmmfRY09vQbDZrEercLIrDIQEpTn+0wdotzbVqfDlT+Z56fOZB2PxUzZP48ZmIQ2KZQcIddjSK45GOr9TPAIexhM/vQ2lfkWPQzfs/dd6Wq2sziuZO5ifjB5VTGuIVoBXy9Wf9bZ/9N+6/ef+t++/+Xd+/6/t3ff+u79/1/Tvav6P9O9q/o/07+v4ufT77b9x/8/5b99/9u7B/F/bvwv5d2L8L+3dx/y5+fzd6eP/7/n3cv4/79/y/py03fX8Xtl3CtkvYdgnbLmHbJWy7hG2XsO0Stl3CtkvYdgnbLmHbJWy7hG2XsO0St13itkvcdonbLnHbJW67xG2Xsv/GbZ+47RO3feK2T9z2idsucdslbrvEbZe47RK3XQb377/7d3n/Lu/f5f27vH+X9+/K/l3Zvyv7d2X/ruzf1f27un9X9+8qzrfvQmBcSZvbV3Albcyr88v/2D94CJxTbcoZkbfl87Z83pbP2/J5Wz5vy+dt8bwtnrfF87Z43hbP2+J5Wzxvi+dt8bwtnrfF87Z43hbP2+J5Wzxvi+dt8bwtnrfF87Z43hbP2+J5Wzxvi+dt8bwtnrfFx6K+/+7f7ZmQ90zIeybkPRPyngl5z4S8Z0LeMyHvmZD3TMh7JuQ9E/KeCXnPhLxnQtn9UXiF2PZI2x5p2yNte6Rtj7TtkbY90rZH2vZI2x5p2yNte6Rtj7TtkbY90rZH2vZI2x5p2yNte6Rtj7TtkbY90rZH2vZI2x5p2yNte6Rtj7TtkbY9EuHITe4MyEHMgL3nBjMALnFzylc5A86ax5pui48egJL+HMxyDmY1B+Fog1O/2i3gPoeU1oHTwVo1F6l7UbrDpi+nfvVqPus+lPB1LlLnonQGz59Tv9418zzgLw/gQPV1rlLnqnRGvq2Wzk+NhrWrr3OVOlelM2xKcurXW2f+ivLcxxK+zk3q3JTOsD3LqV9tnXm1wYh8Tgdr1ix1bkrnBhr0N52fdQ76ufs6d6lzVzrDtXFO/erVzAyDbfV17lLnrnSGswJO+XrXzNZmOoIRRr7OJHUmpTOBzmT3M3Nb19YmX2eSOpPSGUYqp3i9dD4keL5zUMLVeb61AzXXz61zhXssnOLV1pm/sKFjza7OQ5is+da5wl1BTvFq63y+7Uy94L1y+lerBUHqHpTu8Lgap3q9dD+8zX+ZPrDtvg2CtEFQNoAgJU75etugixZkuAPIaWCtmqPUPSrdYeeDU7vauufje2BbfZ2j1DkqneFoklO72jqfmuFZJU73atWcpM5J6ZxAZ9N/DWekcT/DWPf9hCr9hKr8hAp+QrX9hMO3x6ODEr7Oks+q4rMKfFZNPuOaHx8SrO1zWZVcVhWXVeCyanPZ8Val7rlhSV93yWdV8VkFPqs2n7GXwOs5EwRcV6k+p1XJaVVxWgVOqyanPf4O26LrFvi8ViWvVcVrFXitmrzGewNc8+OJwQj0ua1KbquK2ypwWzW57fEBeZcCRqDPbVVyW1XcVoHbqsltz34Ijzys2ddZcltV3FZxBJvcxn7wsxMD1va5rUpuq4rbKnBbNbnteN6nBVizr7Pktqq4DWM8qsltz27T2ROAEr7Oktuq4rYK3FZtbuNdh3paACV8nSW3VcVtFbitmdz27HucHTco4ercJLc1xW14/7iZ3Hb29D6nBVDC1blJbmuK2xpwWzO5jWvmPaCy+7vwbiE8j9d8fmuS35ritwb81mx+O7tPPM+x7b4NJLc1xW0NuK2Z3FZ4x/jZUYUSvs6S25ritgbc1kxuK7xzuHeeimirr7Pktqa4rQG3NZPbuOajO8yy5nNbk9zWFLc14LZmctup+awsYG2f25rktqa4DS/ENJPbyp5dZe/PFog1aT63NcltTXFbA25rNrfxTmuxavZ1ltzWFLdhqHAzuY1PA/h0oOCs8nmtSV5ritca8FozeY3PJ56VBPrZ57QmOa0pTmvAac3ktNPPH7Y2rGE+nzXJZ03xWQM+ayafPTVGo2ZfZ8llTXFZAy5rJpfx2vWcAoG1fS5rksua4rIGXNbs/bSzdhnz2eeyJrmsKS5rwGXN5LJnPhurp89lTXJZU1zWgMuayWUlyJUkw4OLzeeyJrmsKS5rwGXN5LKzegZjbPtc1iSXNcVlDbismVzG8/ghBOhnn8ua5LKmuKwBl3WTy07NUY/t7nNZl1zWFZd14LJuctkZWYcQMpRwde6Sy7riMnx7q9tcdk5vs1zLzpi/zvLgzlH3Oa1LTuuK0zpwWrc57Zwi8jkzn0djC3zbSF7ritfwMmA3ee2cZPPsgyvL3ee1LnmtK17rwGvd3mc7J6l8hv6BEr7Okte64rUOvNZNXmOdnzNdqNnntS55rSte68Br3Y4TOTWf+AEo4essea0rXuvAa93kNY5U4HPtCBeIus9rXfJaV7zWgde6zWunRsPaPq91yWtd8VoHXus2r51oDD7bxxK+zpLXuuK1DrzWTV470QMcvwHRUt3ntS55rSte68Br3d5XO/ELHJHSdQt8buuS27riNrzA1u1zUI5h4dgXjsyA54q6z29d8ltX/NaB37rJb0+0zR3jASPP57guOa4rjuvAcd3mOI4u4fieE/cD893nuS55riue68Bz3d5nOxFGVbQg40rhc12XXNcV13Xgum5y3YltOpE3/BfGgc93XfJdV3zXge+6ve/GsT5Hd46ugnHgc16XnNcV53XgvG7vv50opDu+C1vg20DyXle8hw9OkMl7TySZbEmOWNK1AUnuI8V9BNxH9jkqz39ejWEdIJ/7SHIfKe4j4D6yue9Ez51YMSjh6yy5jhTXEXAd2VzH8YD87ctYs6+z5DlSPEfAc2Ty3BMPl3XNPs+R5DlSPEfAc2Ty3IlN5G8fsA35PEeS50jxHOFINXnuiQXk2YUlfJ0lz5HiOQKeI5PnTo0nHvMDJXydJc+R4jmCVZrsc1PmdmZYtLbPcyR5jhTPEfAc2TzHPsqJPeUWgO4+15HkOlJcR9h7NtedaFeOFeVYUhjrPt+R5DtSfEfAd2Tvx7HfdqJUYU3z+Y4k35HiO7zZRibfPTWz9bGEr7PkOlJcR8B1ZJ+XsnfMu2KwT0M+z5HkOVI8h5duyT4n5RpPC8DaPseR5DhSHEfAcWSfk574aY5SBp19fiPJb6T4jYDfyOa3Ew/90db2uY0kt5HiNgJuI5vbqqw543fW5zWSvEaK1wh4jWxe45r5BA9O7sjnNJKcRorTCDiNTE7j+HiOTsc4efL5jCSfkeIzuBEcP/Y56akx39aOH5fLpjCoeT4fJWueZUHO650VPql9Tmjjx+WyKUzWTKpm0MDksucOAN9KwBK+zkHqfHPZLAty3nTmWwnxiXuIH5fLpjBZs9I5gAY2l3GNpwUZSvg6R6nzzWWzLMgxv9fnBsZ9Nwl0d/lsCpUtULpH0N3ebzu3oGRLEs4Ol9OmUNGCm9NmWZBj2eC5B8W3EPiWAox5l9emUNkCZYMEmpi89tyMuu9ZQC+43DaFihbc3DbLghxz7PPNCr4zxnfIGtjA5bYpVLZA2SCDDUxue+5g8HjougUut02hogU3t82yIMccB+c2CM8BbLOve5G639w2yz5ybG7jG398n+WJc4wfl9umMFHzzW0R7t3Gj8ltfCPmuWsII87ltilM1qx0xlXb5LbnDs5H1+xy2xQmar65bZYFOeZYP/cpTwughK9zkzrf3DbLPnJMbjv3j/gGZ4d13uW2KUzUfHPbLAtyzH4+NVajZl/nLnW+uW2WfeSY3JZOjecuFpTwdSap881tsyzIsXXmfu5XC2BFcfltCpUtULrDFyrY+2tnbPM9Nb6XFqGka4MgOS4ojgvAccHkuOdG3H1X+AMlXRsEyXNB8VwAngsmz/Edved28mkRlPRtILkuKK4LwHXB5rpzH5pvD/LtwgolfRtIvguK7wLwXTD57rmveG5oQwlfd8l3QfEdvNQQg73vxned6bQASvg6S64LiusCcF0wue7c2WSyxNni81yQPBcUzwXguWDz3LklGo2afZ0lxwXFcQE4Ltgcx+x67quem/dQ0tddclxQHBeA44LJcadGZthz1x9b4NtAclxQHBeA44LNcUzT5y4vtwBL+jaQHBcUx8HTwzHYHHduE/M7Bh+jBb4NJM8FxXMBeC6YPPe8oHDfc4Y1z+e6ILkuKK4LwHXB5rpwavz+FW32dZdcFxTXBeC6YHMd18x3vQOsOD7XBcl1QXEdPAcYg8l1570Kvm0eYJX1uS5IrguK6+AOZww2150as7a2z3VBcl1QXBeA64LNdafmrnX2uS5IrguK6+Be23zT2qw5y5oL1OxzXZBcFxTXBeC6YHPdeVVgx4qdd0f4/RJsu28DyXdB8V2A70Y0+S6deDl+GSVCCdcGUXJdVFwXgeuizXXn7RXWfUevPcnXY/S5Lkqui4rr4E5AjCbXsc4lnZZACV93yXNR8VwEnosmzz3W/sj+L2B9n+ei5LmoeA4e7Y/Ruccg37soCWr2eS5KnouK5yLwXDR57rywkbtRs6+z5LmoeC4Cz0X7HkPiaFR+3Qf62+e5KHkuKp6LwHPR5rlyzTLsZ5/nouS5qHgOnhEfXWHrHIXOYoz7HBclx0XFcRE4Lpoc99TIO4HYVl9nyW9R8VtEOSa/PfM66zXN57YouS0qbovAbdHmtmdkyZHGr8s80Qox+vwWJb9FxW9wKjrmhb2uc838l22BJX1bSH6Lit8i8Fu0+e28sHPtDIsW+DaQHBcVx+GpSrQ57ow8fr2LX6qBOeDzXJQ8FxXPReC5aPPcqXHfP65WC3wbSK6LiutwfzdurlOv1H1+Wv3k9aj9fPp7PRo7H5yFkskuGX7iivL+9Lmux/W+aw+DyFvO83XNS0rxpOTyWTHfFOZbgFPKukqbh4tX4yWk2ULyfEi2x/m0Sqcxr+dTqr2Npfkz/m8Nd1PIk1JapJm+o38m5a8HWeej1nXeVstBSiHHoOmnzddow+dDuc0H++ZztTPZQMzzUcxySXGM+/mZz/FXSnOozzcTZ6ql0U2lrCco6yXFMe589H6MplKHYeZM+2ag7/NNxFTD94VikGJbdz7q2cp8DHB8mFpt+/3mmRS3jhEzllMpxbZuGFLW+4qxr9eZ36Wkj21dIWXuOq1HNIeQPlP0zkeFpRTbumG+3RlnAphEY/5/n1sd02Ue86Sh6SXENm7o68HIeYucZkrf9Sr6UogqfcZ/uaTYxg3xp4+VIrU0VpAQ829SHOPGlVe6zA6aC8+SMsZayfOJzH4N3RQc48af9Dn/J3ylrLQUAzXifPZASnGMK6XMCZBnrpX58vhnxkFcUhzrhp9aHinTLulnTitHimPd8PNb9Y5Bw34NdHwlyph1yxSrV9p87vYj16UUHYOOJZLGckNl5hpZ3dJ+2mesDaWXOGM8pRTXoKstVDOt/e4pZbVlLHUzrlgKeR2tcSy2c+pUISR1JcWxZ/9JwwObeRkGAFH+vt2b54vZJfUZ7yulOMadr9HPOTwUarWmPYlnQrFSx2otl+uUHOMqKfWb42PmlOu1lEuKY1yl0ZAy5s1nJq6v6R7z6a+s+9viltzRuoY8hfn1aL9Kcaz7+ZmPj3eaKYHK8MTXs/Rjtn7m1bxIUkh2Ry42pWosSNn9ciFQhF2SZqKbmdtjRm0HAjEuFyBdGHBBMwVP7vOOBN7wHBIdSPiVNKbEOQbm0+0fOD9M2QWGhR2xf75P8T7YMV+aHmw9RJaJEPNq6Fx2H5HFoYffGWSKzLF9Sp4v1zcQ6XTI70Ay1qefWD9pLlUYRpCKyxVAJz0YdDL7e74bn4ZpGvDs+Lz+DaoEA1WmyDamwlB8GBMVt7vn4hYyphPtzJNDZM3A66na3TP6FAvES+TA5xeRdvf8hcgxzObj/TQIYVgIRdrdM+hqiFwfq7au9/4TkXb3/IVIkr8AkX8DhCVY3eOJbH9Bh5EfqBd0KEXCIGp/g4qpa1ScEtv8DzMdRkeJ/4ob02pkWN/m3sZ8JJg8ze0dLJAukTm9ibR75y9EumPIcTWHyLZxss7ccv9IpDd5fhVJ8hcg0ume34HcF+kyPtK5AedT4ve/jBUAv2WOq/oXpD5FwmB0vFVD0E3LtyBnnkheDwavj/9vsBZIcsnfbAUBezie6rfoDepXURf4EdUNUp/NX/9lDKvypLganz3XtC/Ynj+7j9Z/+KSCS0d2/NY13J8C9fIE0qtI91vxm0hvUmbHpT1LRxsw1ZYD+Pcif1mNfJEkfvFspGbP2X1ziPK7xL9yJYLhHE2RY3xRjfPBPRTpfit+85SmyLy+Z6P/4Mgiey6xFFkNt8kX6fpzl+LKh3IV9zxn0Tt0wQGV+NI9jhutx5CBMJ5Id/L8JtId6Y6HPUR+kYWGY9HphtZ3ke7k+U0kwS9gZfM879/9VE+gM3N+dVnnGv5ZqbrXBw4kuh8Ry3/1mvXXffEm5K+tP4W4neg45GMmoAPdfxXjTQJTjOedZ8c7X6m0wPmW7nml4rvn2XHPl8jH+06Xex6S759nxz8fIoX3ffnnqYN/3gIlHFeOf75Egvd9+edrQXb88+z45+N/EN735Z8vf8Dxz7Pjn69efrzvdPnnrfv+eXb88yUSvO/LP6/k++fZ8c8vn/Layx9uh+8AZtc/l87Y5a19P8G2u5Zd/1yw+U3vKfn0nn3/fMDlxexZoXb2ffFvccHIuvTLerR2gQSfKzzPjo89ypMC9Auys+NMc1kg9EZZFXathgDeJaL373BxEP3Nb36wpFzEFvMLuLz5zQ883cQW3/DK95svkYLYcnsT+cJCQnFBbN+x6Cju+M2rb59PdLm+4T2+fMQdv9kUGetMGjlc9LUZKr5/+DV2HOe/UNwV6bjQf9E9vsiX7nkfRL7IF1R9H+q+yBc8epmQr7Z0u8dcIDw5xfG9nUXKF+P2g71W+oJ+WfH/ukG/LP33l8MX5Br6t6+aK9JxqP/i2+uLdO0vdmsNQvBFvqDRKJvSZ8yn8uWYdfdtvohC74q/oNE7bfkiXXJ9ZcI3kY5H/Rfk6ot0yZXp+TPc/3iF3XxelqnietS/egG+yBfHYizvPax3lJZECnlmXB3ftfSyPJftUIuorRn482eH7uy/Zf9t+y/92SEs+2/af8v+2/bf/buwfxf278L+Xdi/C/t3cf8u7t/F/bu4fxf379L+Xdq/S/t3af8u7d/lrUfnv1ufvvXpW58OFtk7AkY02jAWRqNxPtMnGm2UBTnZsuxpwdYgbw2eFNqRM5BaLUhZtqCpFlSQY/Vtyu2ygdGC7NsgSRtkZYMMNsi2DWQLUgbrZ1/3LHXPSndAOM6mZ+s+auQWPCWKr3OWOhelcwGdy5vOT82gc/F1LlLnonSGGxucTe+umUTNCdtafZ2L1LkqnSvKsXSe6bO/f3kVCVr36utepe5V6Q5vO3BWvXsdkzVzS1KBfm++Daq0QVM2aGCDZttgj/HCKyevpAlK+jZo0gZN2QDuv3KWvbsFdK3dp0VPye7boEkbdGWDDjbo5tgn2QJuUaq7V+rulbpbVvfvKoyT7tuoSxt1ZSO4K85Z+S4bne/GtwV5f4cyrufk26hLG5GyEaEcy0Y5cs1t/yXZErhVwhn8rJaQtAUpW8CtZc7Wd9niw99+7qX9F8Y6Z/IzWyBsUT+3LUZZkGPOGaaKxn+ZLhKUdG0whMoW3Dao8A4SZ++7WsA1NuaZolsQXBsMoaIFQdkAwqQ4e99tgyZr5pa0/d/b7hXmCP6KwxeNM/9ZLQzSRkHZCI6GOLvf1UL+eveL9T7PusKZ/8wWSBtFZaMINoqmjfpFl9yCji3wbRClDaKyAezfVJOTH57lXtgtgPlefZ6skier4smaUI5pA24Bf+HoEDaU9G0gebIqnqzAk9XmSa6RbqaHFvg8WSVPVsWTFXiymjx5vAeuGU4kqs+TVfJkVTxZgSerzZOsM3/ZINqq+jxZJU9WxZMVGK2aPHk8JdadCEr4OkuerIonK/BkNXky8Xfh1Aw6+zxZJU9WxZMVeLKaPJk/t3cYtO4+T1bJk1XxZAWerCZPPv7otwXcovzhf99f8b16570iZVzvfd6skjer4s2K32CTN3OQnrOs2beN5MyqOLMCZ1abM4+PzjXDt9Lnyyr5siq+rMCX1eRL1jnzrgLvEkQYmT4/VsmPVfFjBX6sDj8GUTO3JON64PNjlfxYFT9W/J6Y/PjshASuef+FueFzY5XcWBU3VuDGanIjk+phaKi5+bxYJS82xYsNeLHZvJi4/3l3qEAJV+cmObEpTmzAic3kxMzWPpQOOvt82CQfNsWHDWZts/lweyynBaf/sQW+7pL/muI/DA1qJv9l3nPL3O/ELXlK+vzXJP81xX8N+K+Z/PfsobEN9sg7ttkt4v/97LVhC30bST5sig8b8GGz+XDXmM9fthmMUJ8Pm+TDpviwAR82kw+5xnx2vprRAt8Gkg+b4sMGfNic/UYSNY+WPCV8LmySC5viwgZc2EwuzKfGswMGJXydJRc2xYV4VNycfUaSNQPPNZ8Lm+TCpriwCTlve25ccxYlfJ0lFzbFhQ24sJlcmLnms8eWtO4+HzbJh03xYaso532vLYmWZNjtaz4fNsmHTfFhAz5sJh/m3YJceKeL/0ILfP5rkv+a4r8G/Nfs/UbeU+M9tt2CDLt9zefAJjmwKQ5swIHN5kDeteF9o8otgNnn82CTPNgUDzbgwWbyILcgbxvkevaRoKRvA8mDTfFgAx5sJg8+NfJuTdEt8HmwSR5sigcb8GCzeXDvB2XeW+VdGtgfaj4PNsmDTfFgAx5sNg/ybm4n0YIM72Z0nwub5MKuuLADF3abC0nuynCLcm1Q0rVBl3zYFR924MNu7yPuFmSeAzwnYPe/+5zYJSd2xYkdOLGbnMg1Zp6VZ8cCW+DbQHJiV5zYgRO7vU/IeyO7Zrww2H0+7JIPu+LDDnzYTT5knXM7O1RQwtdZcl9X3NeB+7rNfVvnp+Zn7es+73XJe13xXgfe6/Z+IJGoOTfQ2ee8LjmvK87rwHnd5LzceO9D7o0I3X3e65L3uuK9DrzXbd7j3ZbGvi/7hVjSt4Hkvq64rwP3dZP7crv9f+4FWHF8/uuS/7rivw4s1U3+e/x+nm27RR1L+jaQHNgVB3bgwG5zILdge2e5H+/8KelzYJcc2BUHduDAbu8T8u5cPC2AEr7ukv+64r8O/Ndt/gskdcY1yue+LrmvK+7rDeWYOp+dCG4B+8Kgu899XXJfV9zXgfu6yX1Pjex9Gy3wua9L7uuK+zqOYJP7yu7vsvu/7J3IwmeqZ5+AbcRnrfx3t5h5gb/e+4Qj0727u/+dV/u99pa98pW9Epb9u7LLlXNOxZS4y+1TpMJ7uOc8fMvZc7rsGVZwRvk82yXPdsWzHXi22zx79i/YwrCe+RzbJcd2xbEdOLbb5+I5XX0I3zOfX7vk1674tQO/dptfM4+es4NySpDPrV1yKyluJeBWMrn1qbEoa5PPqyR5lRSvEvAq2fuZZ9+ise5PCZ9TSXIqKU4l+AKTyanPXOWRRlDC11nyKSk+JeBTsvcxrx2TAms2+XxKkk9J8SkJOW/r1VNzghK+zpJPSfEpAZ+SyaeFv1NnhyRo3X1OJcmppDiVEsox5/XZKeG1jddAGOs+r5LkVVK8SsCrZPLqs4pyS2Cs+5xKklNJcSoBp5LNqWdPhtdzrNnXWfIpKT4l4FOy9yVPpBXvkIC1fS4lyaWkuJSAS8nkUrYyt0DW7OsseZQUjxLwKDn7knIfir+qBc4nyedRkjxKikcJeJRsHq1yP4q/7wVXRZ9LSXIpKS4l4FKyz605Wog9oxp0C3w+JcmnpPiUGsox+599s7MfxX+xpG8Dyaek+JSAT8nkU24BU9izGwTjwOdTknxKik8JNbHPqaus+eFBmP8+x5HkOFIcR8Bx5OxLnhoFoWaItCSf50jyHCmeI+A5MnmO2fjszVTuFegFn+tIch0priPgOrK57uyMMN0f3dPH5zoSXDd+eek+y4KcV93PHg2W8HSewmTNTdVcQc6rzqfm8pRwuW4KEzXfXDfLghx7D67Imp9oofRxuW4KkzUrnQPobHMdXV7aR+2IpY/Ld1OoaMHNd7MsyLH3o9gv5L2YExUEJX0bRGmDm/NmWZBj24B1vnbGCGzgct4UKlpwc94sC3JMG/AuELfg+NJY0rdBkja4OW+WBTn2vgTPOt4NOns0T0mX96ZQ0YKb92ZZkGPbgGO5OcY7GS3wbZClDW7um2VBjh2bwy3gvTmYhS73TWGi5pv7ZlmQY+/FXXstHUaey31TmKxZ6VxAZ5v7zn4Ux6WAzi7vTWGi5pv3ZlmQY+/FXXtwaG2X86YwWbPSuYLO3ouDn58/Zfy//TLXzGLTJnk+Bb13BXdBvpdMgxFmIAMUdB+2mQXXy2Iz5c9gzPqHb0n3GcNSK+jvvRj4lbJq7vNL08aAKd8Xkj6t19Yhp8yQ4jz8NKXkb6FPLfMieXmT8mLD+lPTUGH4VDnPVxVr+sltfENCovkJjo8U50mDKaXOJ5ZTanUKqcPdr+XblrVPFHAuOK8YTCm9/sy3FCvV+drPWEhfpPjWHVKGPqWMfp23n+ufmsd/qLX0OjeusY+8N/6+Ur59VEOO8z7ssMv3PzT6wMMg6eM966eFhJcu8t70m1LS982hPryP/i7kxba3kPx9EbL2Xgdwo5BX0176+FL+2rThT6avQos+C34wvQf+5sQv4WfMwjgTHYQy6Cunn9TLGH5teCj52dBLwXvUb0mJc7iXXGcUysDAHH9azrG2Fdj/OFspeO/PLynp508OP3PK1HmcneDqzSjpW3SVjHVdWm55PpIASTPm20avLQ/rm1sCzeuTsfykMjMI5mGQ/DwckoL30PyS8vlp89Gf+bZbKd97/fOxhsHwoUFAcAre23tTSq57Leop57be2R6OzhBYUp0hTiDlxYpKynegz6d0+yd3sIv3xN6SkvZz7zOL8vC+X6S8WFdJyd/5E0cHBdj2S8F7SG9KSXuqptFPY4F9keK9nWdKietBtNB6H6s0QR95r86bGvlS/tK6bb7l9/3+5nnZLON08V6dX0LGpBv/X6hlpvAe/6n0+YZXKxkzpKbgvTm/ZOxX/UNvY7FvU8pT0Hvsbn7w5it/jSrND3iYz8yKgq/f/tHMQSt9JgyK9dvuulK1zj8EUrwHEeg3agnu83V0NyHNh1/8JniPUdBtg/HtlzZwX60jZfe8iq7x0Gg9YgJivIcm6B4Caxy5g8B9to7UqB5fAXc8uk/VmWL8yeG+T0dqqs7HMl057qN0thx34XBforP18uX8IzP7i6r75hypJb72Ww7a59XOSo784MDwcV+XI/X5y/nl8+c+KUf7Yzzm5XxTekypslJn1EHR8x2S+f2FaeG+I0e/44D7iNwp60OI+4Qctx8wKLxgkPuUHCkoE0w2PIwOTOK+KkcXIQ64eSHE4D4wZ8pxeTW4r8rRDc8xvYl5s7IS44F8cF+Ps7Xy5fytlYdj5Ls4wX0mjm5/q5UXfyu4b8PR7f3NF8dc7y+4D8LR7YuW/OKLBvcVuPWRHEvKmEU9zFtKY4L8qfEnTV97DO55HRn0cp9+o9tPL+nFTw/ue2+kdg0+z67BaFAM4KgH9403urcwhrH9LYzgPuzGGOPuoZgZaOeWzJ+9w7L/lv237b/0Z+807L/7d33/ru/f9f072r+j/Tvav6P9u+9e/HQA99+0/5b9t+2/+3dh/y7s34X9u7B/F/bv4v5d3L+L+3dx/y7u36X9u7Tb95w+JT/jbpIZd5PKuJsg424yM+5OAt017xal3aK8W5R3y/P+Xd6/y/t3Zf+u7N+V/buyf1f27+r+Xd2/q/t3df+u7t/tng+758Pu+bB7PuyeD7vnw+75sHs+7J4Pu+fD7vmwez7sng+75wOhpb2si0lmFk4qs3CCzMLJzCz8jGnWlC2PLXAzDCeZYTipDMMJMgwnM8PwaUHg0c6jv2FJ3wZB2uDOMJwgw3AyMwyD1Xk+Fyjh6x6l7neG4QQZhpOZYRh0LVpnN8NwkhmGk8ownCDDcDIzDMOaxf0NOrsZhpPMMJxUhuEEGYaTmWEYxjqvog1K+DonqfOdYThBhuFkZhg+Oj+zLkAJX+csdb4zDCfIMJzMDMNQM39BYHa5GYaTzDCcVIbhBBmGk5lh+HyTeOX5dNDZzTCcZIbhpDIMJ8gwnMwMw0+NjbS13YzCSWYUTiqjcIKMwsnMKAzf3SBXXTjf8TMKJ5lROKmMwgkyCiczo/BpwbPuMwHALHMzCieZUTipjMIJMgonM6MwfHnYFk23wM0onGRG4aQyCqeIK5WVUfihnGMDtgmMAzejcJIZhZPKKJyQ8Dmj8NWCw1H8tea/0Pbu26BLG3Rlg45yTBvwfO8XH+D8774NurRBVzaAnQtOAny3gNny1MzkAiV9G5C0ASkbAP9Hsm3AVMvsxMwEI5F8G5C0ASkb0GODZHM7MW9zzdySACVdGyTJs0nxLLw2Nv7ZtsHFkfWQPZR0bZAk5yXFeQk4L5mcd2pksj2+BLTA57wkOS8pzkvAecnkvMdrSbIltUBJ3waS85LivAScl2zO4xYcyoc2+5yXJOclxXkpopxX3dnPeN5eGyV8nSXnJcV5uLuWTM47PiJ7OhDTlHzOS5LzkuK8BJyXbM47NTZtbZ/zkuS8pDgvAeclk/OOH/y5vLwCuvu8lyTvJcV78C7J+GdT9+OBn5rZ/4SSvg0k9yXFfQm4L5nc9/j+7AGz5wuzzee/JPkvKf5LwH/J5r+z68C+N//Fkr4NJAcmxYEJODCZHPjsa/BuAe8SgA18DkySA5PiwIQj2uTAs+PCtjj7EbDq+hyYJAcmxYEJODDZHMh7PeHaGckwF3wOTJIDk+JAeClh7lmaLeBdplMz9waU9G0gOTApDkzAgcnkwDMOzm4Rtwha4HNgkhyYFAcm4MBkcuCzX8U7b2B9n/+S5L+k+C8B/yWT/x5dSevsc1+S3JcU98G7BOOf7T28IGuG+Mvk816SvJcU7yXgvWzy3rFyOvuYUMLVOUvOy4rzMnBedvYt75p5/xJLurpnyXlZcV4Gzss2550ay7WvBy3wOS9LzsuK8+C1wPHPXxvcG+ziEK/k/j3aS3BGnzfnqZLz2G7mbJt7Ki3XfbA3N39qLfMwREiJH1vKOrXr8dNamzHd31O9T46h1D7zzUgh0RaSf+Zp0KfX9qlzIyZkPsAYjYoDXqWUbEpJ9aek/mljbNXSZg71dym2QbWUxPlB11um+ZLiGDcvKfSJkT4TMd6lJMe44ihzAOoVDncJsY0rDiBnzr53IbZttRARIzjgT0qxbStPs2K7pfRLim1bLUUoFK+2ZNu28gBzcJM84uxXW7JtXDy/nInCxQln+sRLiG1ceeg44AGPN8O8lySl2Ma9pHRxuNnms/1Sim1cPLicDx6Ko825vSCEFNu2Vw/lO/74Gv3FGbh4ZjmzHV2x0HdbnJGLR5aF2h2XfUtxRi6eXk7Pch5pyoK2PUX0VphR4HfBattQhGvNZ9hEQNcEfSnFtuEdxVaHFa6Cttk4bPbzGUvE6IIVNisL2pYS7Z6P967PygDReXRS271S1L8xW8/GZ605a6b5QVw5ROv4QI9ygWAXJDfnkyS/jl1/HefF259Y8rxqMqYXfKqbbdJfP5Ur3+cM1GgUZx+DROfjL7+bRX/xVlbSNm9fhLl9CETTbMOv3E5PgXaJnGFPrshu98jvIkW/drtD5p3Un1wDxTIWgEHav0ix++B3KWOQil+AyL8Bho8BLy8i7U7QIm968EWS1wm34kJkeZP4tx1ySRT9QV5/zOxkdSboam3uGb8LsXvgVyHf3LzPD0DiX+HbrVvLvsjy+SuWSwrD5oMBPyDGs/r4lQzratRUYdfaVmG0cfl4Ns5lL8khTLC5pPRLire6/CZlfDbwF88wLMFhDUmmRdPgi8i/IuaiMfVFpGf5W3EUOROVv4j82x6RIq9+dbzA+XzR117fMN9fpDhe4O9S5hMg+AsQ+U5/hyGtTvBEOiioRBpDxRPpdsKluDGgPZF/2yOvM81xHcfntqqpTldRb4kxi87nY7Cw48tIt+pe5qKW43gz0rEqyrEaYsoA+XmCMPkogETHs/nVy1oiHzme43jLUX7WLcdxHX/xtCZhjq9OHa7aPElusPlbHEfyGuBB+13+aHS8Si3ydsIekfO4GeK2i+NiyiDS2x9bS0X8/qfQZkKCR6DnbkrnbLVxSknQCY6POd9S+zF/767j+/diJjle48q2+x38eaw33SjorQFGwZXo/fmP0HeeCyl9z/SbFNeFfHVEdx73OQ17+xTc/CwvzqXySgcWoWV891L7pXdRx6cUnum8/yM803DrAQPP8TVtL9W3sONrqt7+TYw3Ni0xYrg5fuRKlft4x4a3XXx30SjpetvFdxGFL3152yn53nZx/UXhTF/e9syk7HnbxfUd5RdH3mag5Tt63yTHdxwiv6xJeaZTv75JOfb7W+I4jEqO+CbN90UuOa6XKL848pvU11Tzvkmum3jhzHXH4Q0NXadRfHHSfd3hjeNcF1J+c66v0ss3yfEgVyb6Zy2JctX8rBHtrJrV8SD1fczpfF+LX3X9RlIr59qakIXdlUU09d7Te1k6q+tP/iYyiYZ5Vja1EkUdv9GxpizqrtevfZsvKe4ofhly9eL86nuB1/S654KU8pc+h5qkQorrBc6Nq5lOtdfP0ggfDIn1EuJ6H69L2dVFjqv3+8IqpbjL8y8rvpTifiPfvkSXbV1/7rcvpJQSjfPqnOv/p+1Me+PWmbT9Vw4wBzhngIxHXKqKnG9O4qxO7CTOigGCLM6+O87261/JfambWthtJ/M+g4EOnVbpZoniVSxR5Dne/Zzj9Q1HzzFy5HfC75TfKb9Tfqf8Tvmdo+woe87znOc5z/M7z+8Cvwv8LvC7wO8Cv4v8LvK7WPQzxay50Xv21hnle3bli/vVe3Yt+ys+qh96TqmRUiOlRkqNlBoJNRFqJq4/8u9Nf6SGuT9So9Qf++tw3d6ucb5xXey1/eM5OjuOCzvCnRTubDcEpDcpapzrnrOB5xgRl55bobXfpXTU5tyobRj3sPgIUWP93sXhvYuTe1e2gTh376L1ra4Zts6BgroP4tAHMvFBEZr3u5aOFCzbf193FBXfSqvUfSBDH8jEB1L4QGZ9QHtatS8UpP5J7H3ke2UcU2G57iMZ+kgnPipmg/a7nI59NFLSKytmXanWfaRDH+nER1r4SGd91PdGfnllns1m+Iwun1l+l0uFdR/p0Ec28VHxxWe/y+lIYd9P9kozvUvTFGfWfWRDH9nER1b4yGZ9tOyhm/7KHP2gX1v1c33/Vyqs+8iGPkoTHxXfcvS7oo4Z17OEK9OepO+h+565rwE1kpIBqe7DNPRhmvgwlXbmfdjTzfe+4Vj0R6nuozT0UZ74KBU+yvPtqOdq7K/MsS/rkF6+p1qhMNd9lIc+yhMf5cJHed5HfWTQ3zXf383izLqP8sBH1kx8VHxx2++uOm5HfYzRtxN8U6ytaU3VB63RoYKxD8oxZL/L6lCBLKOeOIh6hgqqPui++i8VuLEPrPg6od9ttRYv9nWnPcSmOLPuAzf0gZv4wBU+cLPtAAXS34XlXUnFmXUfuKEP/MQHRWqg3211dBd6r/d3oY+ZSwW+7gM/9IGf+KBo0f1uqiMfLKPz3gflGfW6+2Hdw6Tuxbxomx0v9HWWvh2IL86o13kYb9sk3rair7XZeHt1xThz5Xqdh/GqTeJVK+JVm49XZVhnKe9zPU61YZxqkzjVyrs2G6cKozJZjsqWPijOrNd9GKfaJE61Ik612Ti1HyWsRg0o6sd//Xhw+e+0yPLu1ONYG8axNoljrazpfBw7UiTLEWnRI9XjVBvGqTaJU62IU202Tu2vKMsx8IyCepxqwzjVJnGqFXGqzcepoyv3SqRYCdfqcagN41CbxKFWxKE2H4cux/3LK3MsnpV6HGrDONQmcagVcajNxqHSjyL7zMOsgroPhnGmTeJMK+JMm48z+/EsCnpFYn4wQl+N2PtRZ9FO6nGmDeNMm8SZ5YtWm48zl4pQmKYjb6vHmTaMM20SZ1oRZ9psnNlfUfpR53LcWyiox5E2jCNtEkdaEUfafBy5HMfGkZKindTjSBvGkWkSR1oRR6b5OLIfRS7Hs/3osSnOrPogDePINIkjUxFHpvk4sunHr/2osR+b+eLMqg/SMI5MkzgyFXFkmo0jV+OLfrTYjwoL7fU4Mg3jyDSJI9PAzqwPlqPAfhzRj2i0OLPug2EcmSZxZCriyDQfRy7HDyhI0/FEqseRaRhHpkkcmYo4Ms3Gkcsrpj5XmWYU1H0wjCfTJJ5MRTyZKvFkM7xyr6TI8aR6XJmGcWWaxJWpiCtTJa7seyQU5OW4ojiz7oNhfJkm8WUq4ss0G18ur5iH44qBgnqcmYZxZprEmamIM1MlztThlXN55Xrdh/FlmsSXqYgv03x82dc5L2Ps4ox6nYdxY5rEjamIG9Ns3Lisc55G9akeL6ZhvJgm8WIq4sU0Hy8ur9grKLTW48Q0jBPTJE5MWtqZrXN/ZenfBTTTutfjxDSME9MkTkxFnJhm48RllN5H7X2+slj6N9XjxDSME9MkTkxFnJjm40SuqH2echmxlgrqPhjGiWkSJ6YiTkyzceIqNo4DJVrStx4HpmEcmCZxYCriwDQbB/YKlByt9jnaIlZO9TgwDePANIkDUxEHptk4cHnFZWzcTBXU48A0jAPTJA5M5TM1GwcuY2DiweX7tFREYfU4MA3jwDyJA1MRB+bZOLC/Yv9Gr49ESwW5HgfmYRyYJ3FgLuLAPBsHRhteuVcSBwqqPsjDODBP4sBcxIF5Pp/Yv0lZvn3q36j44sy6D4ZxYJ7EgbmIA/N8HNj0V+zf3fTvK8oz6z4YxoF5EgfmIg7M83Fgn2PvY+D+TUnxRjbX48A8jAPzJA7MRRyY5+PA5ZuQ/r1Dn+VPxZl1HwzjwDyJA3MRB+b5OHD5zqV/Jvo4sNBejwPzMA7Mkzgwh9LO7Pt8rti/v19FouWZdR8M48A8iQNzEQfm+TgwDWPg1UyC4lmox4F5GAfmSRyYizgwz8eBqZ/T0PcHRT9QjwPzMA7MkzgwF3Fgno8Dl1fuY+HiyvU4MA/jwDyJA3MRB+b5ODD38yP6iKTwdj0OzMM4ME/iwFzEgXk2DlxdsZl6ux4H5mEcmCdxYC7iwFyJA5dxPnUvepp6/JeH8V+exH+5iP/ybPy3nDXTv08svV2P+/Iw7suTuC8XcV+uxH3D+S5S7KaQ6/FeHsZ7eRLv5SLey7Px3uqK05k2uR7n5WGclydxXi57pvk4b5m970dZ2vugOLNe92GclydxXi7ivDyf7+vj+z7el15Bcd/rcV4exnl5EuflIs7Ls3Hecv5TH+/38f9AQd0HgzgvNpM4L6/ivNjMx3nLKLvvaXpFqTiz5oPO6FDByAfduYWdWR8sFfRjnz7+L8+s+aAzOlAwjvO6c1d2ZuO8/oqrHLifKqjGeZ3RoYKJD1xphwXs927e3LlwsHOx+9mdnYPul92yh93KPO3xJBPdHSlnynlRtqbhSNlRdpQ9ZU85UA6UI+VIWSgLZaWslI0y+gx9hj5Dn6EvoS+hL63m08R+p9d5D6STFWG7ZXk9x0U5N54jZUfZUfaUPeVAOVCOlCNloSyUlbJSNspGOVFGX0ZfXujzzUKfbxrKjrKjvIqTYr9j7awH/GI90ODdySi0O1J2lB1lT9lTDpQD5Ug5UhbKQlkpK2WjbJQT5UQ5U0afR59Hn0efR59Hn0dfsYdC64GwxgN+cY9O1iI4OaLML3zeHhd/D/g84POAzwM+DwOfy5orhsVz4YNwVCwt2nl75O+Z8qKd+7ho5+xP3K0GXrRzv+ZJZ//YbrEOz3HhpcUMktB9+c5RC4trnhx24W6PJ+PmwG6t3cLgXAGvFe9RYr9v8LxFWfQmXriTEgLHxRUkUo4FK8KaOxubxR2NzeLpiou1z7ulyygnypnyQnPrVs+RsqPsKHvKnnKgHChHypGyUBbKShl9Dn0OfQ59Dn0OfQ59Hn0efR59Hn0efR59Hn0efR59tPzo0efR59HHExE9+jz6PPo8+nhSIk9K5EmJPCmRJyXypHTPFEfK6AvoC+gL6AvoC+jjeWmPlNEX0BfQF9AX0BfQF9EX0RfRF9EX0RfRx1MTI/oi+iL6Ivoi+iL6Ivoi+iL6Ivp4ZiLPTOSZiYI+QZ+gT9An6BP0CfoEfYI+QZ+gT9An6BP0CfoEfYI+QZ+gT9Cn6FP0KfoUfYo+RZ+iT9Gn6FP0KfoUfYo+RZ+iT9Gn6FP0KfoUfYY+Q5+hz9Bn6DP0GfoMfYY+Q5+hz9Bn6DP0GfoMfYY+Q5+hz9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfQR/QTiX4i0U8k+olEP5HoJxL9RKKfSPQTiX4i0U8k+olEP5HoJxL9RKKfSPQTiX4i0U8k+olEP5HoJxL9CNGPEP0I0Y8Q/bSPD2VPOVAOlCPlSFkoC2WlrJSNslFOlBPlTBl98EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfBj8Mfhj8MPhh8MPgh8EPgx8GPwx+GPww+GHww+CHwQ+DHwY/DH4Y/DD4YfDD4IfBD4MfBj8Mfhj8MPhh8MPgh8EPgx8GPwx+GPww+GHww+CHwQ+DHwY/DH4Y/DD4YfDD4IfBD4MfBj8Mfhj8MPhh8MPgh8EPgx8GPwx+GPww+GHww+CHwQ+DHwY/DH4Y/DD4YfDD4IfBD4MfBj8Mfhj8MPhh8MPgh8EPgx8GPwx+GPww+GHww+CHwQ+DHwY/DH4Y/DD4YfDD4IfBD4MfBj8Mfhj8MPhh8MPgh8EPgx8GPwx+GPww+GHww+CHwQ+DHwY/DH4Y/DD4YfDD4IfBD4MfBj8Mfhj8MPhh8MPgh8EPgx8GPwx+GPww+GHww+CHwQ+DHwY/DH4Y/DD4YfDD4IfBD4MfBj8Mfhj8MPhh8MPgh8EPgx8GPwx+GPww+GHww+CHwQ+DHwY/DH4Y/DD4YfDD4IfBD4MfBj8Mfhj8MPhh8MPgh8EPgx8GPwx+GPww+GHww+CHwQ+DHwY/DH4Y/DD4YfDD4IfBD4MfBj8Mfhj8MPhh8MPgh8EPgx8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHhh8ZfmT4keFHXvCjm7jrOVJ2lB1lT9lTDpQD5Ug5UhbKQlkpK2WjbJQT5UQ5U0afQ59Dn0OfQ59Dn0OfQ59Dn0OfQ59Dn0OfQ59Dn0OfQ59Dn0OfQ59Dn0efR59Hn0efR59Hn0efR59Hn0efR59Hn0efR59Hn0efR59Hn0efR19AX0BfQF/Lj2LmXH2GYtuPn3yD0q3JGjguyqkJHCk7yo6yp+wpB8qBcqQcKQtloayUlbJRNsqJMvoS+hL6Mvoy+jL6Mvoy+jL6Mvoy+jL6Mvoy+jL6Mvoy+jL6Mvoy+jL6MvryQp9vFvraI2VH2VH2lD3lQDlQjpQjZaEslJWyUjbKRjlRTpQzZfQ59Dn0OfQ59Dn0OfQ59Dn0OfQ59Dn0OfQ59Dn0OfQ59Dn0OfQ59Dn0efR59Hn0efR59Hn0efR59Hn0efR59Hn0efR59Hn0efR59Hn0efR59AX0BfQF9AX0BfQF9AX0BfQF9AX0BfQF9AX0BfQF9AX0BfQF9AX0BfRF9EX0RfRF9EX0RfRF9EX0RfRF9EX0RfRF9EX0RfRF9EX0RfRF9EX0CfoEfYI+QZ+gT9An6BP0CfoEfYI+QZ+gT9An6BP0CfoEfYI+QZ+iT9Gn6FP0KfoUfYo+RZ+iT9Gn6FP0KfoUfYo+RZ+iT9Gn6FP0GfoMfYY+Q5+hz9Bn6DP0GfoMfYY+Q5+hz9Bn6DP0Gfrgh4cfHn54+OHhh4cfHn54+OHhh4cfHn54+OHhh4cfHn54+OHhh4cfHn54+OHhh4cfHn54+OHhh4cfHn54+OHhh4cfHn54+OHhh4cfHn54+OHhh4cfHn54+OHhh4cfHn4E+BHgR4AfAX4E+BHgR4AfAX4E+BHgR4AfAX4E+BHgR4AfAX4E+BHgR4AfAX4E+BHgR4AfAX4E+BHgR4AfAX6wR3x3pIw++BHgR4AfAX4E+BHgR4AfAX4E+BHgR4AfAX4E+BHgR4AfAX4E+BHgR4AfAX4E+BHgR4AfAX4E+BHgR4AfAX4E+BHgR4AfAX4E+BHgR4AfAX4E+BHgR4AfAX4E+BHgR4AfAX4E+BHgR4AfAX4E+BHgR4AfAX6wangM8IM1mLsp95TRBz9YY/9kyjpHyuiDHwF+sDrDyRRojpTRBz8C/GD9gBjgB1/xxwA/WOe4m9JJGX3wg9UmT6ZEcqSMPvgR4AcraJxMseNIGX3wI8APvj6MAX7wLXAM8IPVJ7opQ5TRBz8C/AjwI8CPAD8C/AjwI8CPAD8C/AjwI8CPAD8C/AjwI8CPAD8C/AjwI8CPAD8C/AjwI8CPAD8C/AjwI8CPAD8C/AjwI8CPAD8C/AjwI8CPAD8C/AjwI8CPAD8C/AjwI8CPAD8C/AjwI8CPAD8C/AjwI8CPAD8C/AjwI8CPAD8C/AjwI8CPAD8C/AjwI8CPAD8C/AjwI8CPAD8C/AjwI8CPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KP7j84UkYf/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/IjwI8KPCD8i/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD"} |  |  | - |  | - | -
[14 empty] | {"index":130,"total":402,"filename":"Advanced_Project.ifc","data":"Emh0CTS5BAougZYuwa+ZOO09Ao0egSaPQMEj0NIj+DUTp71DoNEh0OQQKDgEWjoEP2fien9Aoz+gyR9Q8Ae09Ad+zsT17oBGd0CTO6DgDmjpDvycieu9AY3egCZvQMEb0NIb+DkT1zsDGp0BTc6AgjOgpTPwcyau9wU0+gKafAHF+7PSF/g5E9f7Ahp9AU2+gIIvoKUv8HMmrncFNLoCmlwBxTvD0hX4ORPXuwIaXQFNroCCK6ClK/BzJq53BTS6AppcAR14dtbzYT9m4npXQKMroMkVUHAFtHQFfs7E9a6ARldAkyugA8+R3/NhxUxc7wpodAU0uQIKroCWrsDPmbjeFdDoCmhyBRRcAS1dgZ8zcb0roNEV0OQKKLgCWroCP2fieldAoyugyRVQcAW0dAV+zsT1roBGV0CTK6DgCmjpCvycietdAY2ugCZXQAceL7W7vhW29a03vKL3OSy6AppcAQVXQBtX4AgO3KEwN9S7AhpdAU2ugIIroKUr8LSELZ8Kd3S9K6DRFdDkCii4Alq7Au6CbQsNju3eFdDoCmhyBRRcAS1dgV2zqv+FlvscFl0BTa6AgiugpSsALf/tZ5wz6F0Bja6AJldAwRXQ0hXwlo81Z3AoQct9DouugCZXQMEV0NIVeFqKLb+/FNbeFdDoCmhyBRRcAS1dgd2y/p1dB87E9a6ARldAkyug4Apo6QpAzd7ruK19zTGHJVdA4f1/LV0BaHnZtHiE9TksugKaXAEFV0BLV2C3fN/utOK29jXHHJZcAcW7pNIVeFveHi+cz30Oi66AJldAwRXQ0hV4WvIrRT6r+hwWXQFNroDifXjtCniLvgV0Qct9DouugCZXQMEV0NoV2OO2G8SG29rXHHNYcgUUXAGtXQGfUddzz+3DEn3NMYclV0DBFdDaFVhn0+kjCbjL2rsCGl0BTa6Ahr6rf0fpzy9On9PHJfqaYw5LroCCK6ClK3C4iuu9jU8TeldAoyugyRVQwnGhzGFvrfd6agQt9zksugKaXAEFV0BLV8BrPlxBDuN2n8OiK6DJFVBwBbR2Bdax7fPc4QjrXQGNroAmV0DBFdDaFRjn9zM6gSXamqMroMkVUJzFrF2B96zy/U2wRF9zzGHJFVBwBeY/VzW/Ld5Fy33NMYclV0Bxzrh2Bd4W151dWKKvOeaw5AoouAJauwJr7Hq34P1CovaugEZXQJMroOAKaO0KjPXduvd8xiX6mmMOS66AgiugtSuwa/YRBY/tPodFV0CTK6DgCiiXv5/0s8lbDmdVn8M45rDkCii4AvOf62vV17gdWu5rjjksuQIKroDWrsDb2/kq2bsCGl0BTa6AgiugtSvwtrwTAizR1xxzWHIFFFwBrV2Bt0V/Jgs19zksugKaXAEFV0BrV2CccfT0xL+uXYebZur/f+u7WLq+n+T3ogOef/QegUaPQJNHoOARaO0RqG/R8HMD+qrPb9ET0OQJKHgCWnsCyt7yWbTc1xzzW3IEFBwBLR2Bdy+Qn5W4RF9zzG/JD1DwA7T2A3Yvr+/eKJ6/fX6LboAmN0DBDdDaDVDyltd7Rwy93ee36AVo8gIUvACtvQBdX1TU9dV+xWO7z2/RCdDkBCg4AVo7AfvsWl/c0/drktr7ABp9AE0+gIIPoLUPsGv1I+z9Oqz2PoBGH0CTD6DwpS+tfQA/ssb6HhbOWvY+gEYfQJMPoOADaO0DqKxn9evOf7ms82zDLehrjzkuOQEKX6fU2gnwmsceWaDlPsdFJ0CTE6DgBGjtBOzzeZ/fsL/7HBedAE1OgIIToLUTsK8cewug5j7HRSdAkxOg4ARo7QS8I4qPpnB29TkuOgGanAAFJ0BrJ2Bfs2hfu2CJvuaY45IToOAEaO0E+Oj5tgz7uc9x0QnQ5AQofJ9caydgn8++n7GX+hwXnQBNToCCE6C1E/Du370FsERfc8xxyQlQ+Iaz1k7AW7Ola1bvBGh0AjQ5AQpOgJZOgI9hPn4fjPu5z2PRCdDkBCg4AVo7ATsVnXc+tvs8Fp0ATU6AghOgtRPwZlK/TsN+7vNYdAI0OQEK3/jS2gnYY5hfp/Fs6PNYdAI0OQEKToDWTsCu1WsnOML6PBadAE1OgMJ37LR2Anbq9f0N71r1ToBGJ0CTE6DgBGjtBLz7txg9+zwWnQBNToDivFztBLw5zNJ+7p0AjU6AJidAwQnQ2gnQ79ETkmDvBGh0AjQ5AYozv7UT8B7TlHq7dwI0OgGanAAFJ0BrJ+Bt2Y80qLnPYdEJ0OQEKN4t1U7ATr/ix/YJS/Q1xxyWnAAFJ0BrJ2CfVXsLsOW+5pjDkhOgYa/VOWwnfcq93eew6ARocgIUnACtnQCVE3s75O3eCdDoBGhyAhQTRu0E7P3rV0lIBr0ToNEJ0OQEKDgBWjsB5DO1fox7LhvfV0/vm30v8vcXZsF6V0CjK6DJFdAwgpXPQZeWeLhqT/5WCbwd1vsCGn0BTb6Agi+gtS+wWvQtOFwOJHh21DsDGp0BTc6AgjOgpTPgLR5uF9JRbEGf56I3oMkbUPAGtPYG6AhbcPhXoAne3u/dAY3ugCZ3QMEd0NId8BYPN3JozU2GLejzXfQHNPkDCv6A1v7AbnHNBN8wJ9H7Axr9AU3+gII/oLU/sFr0LThA0dPeH9DoD2jyBxT8AS39gafGVeveAliirznmu+QPKPgDWvoDvp8P94FCy32+i/6AJn9AwR/Q0h/wFmELcFv7mmO+S/6Agj+gpT9wLEPlWN9kP8Af0N4f0OgPaPIHFPwBLf0BaPH2/Q1LtDVHf0CTP6DgD2jpD/iRtY807O3eH9DoD2jyBxT8Aa39AT+P9/7eZ5nAkn3tMeclh0ANKynfX5O9BT6yWN6CPu9Fj0CTR6DgEWjtEZDvdx9Zhp9tNyzZ90HMfcklUHAJtHYJVouHCxj+df+wBX3+i76AJl9AwRfQ2hfwr/uvLTjcZiC4x+l9AY2+gCZfQMEX0NoXWC0ebjLosjjI9wZuSZ8LozOgyRlQcAa0dgbI7yyXjEGQhXs/QKMfoMkPUPADtPYDvFavXRVq7vNddAM0uQEKboDWboCq7+/d67BEX3PMdckNUHADtHQDfH8fLlhpWKKvOea55AYouAFauwGqZ9jPobf7HBfdAE1ugIIboLUbsPbvWzO23Oe36AZocgMU3AAt3YDDBbpV+wHGjvZugEY3QJMboOAGaO0G7N5ekklouc9v0QvQ5AUoeAFaewH7fFa/n4fzuc9v0QvQ5AUoeAFaegHPyPFX67pvU/+CgPq/r7ENvtvQOwIaHQFNjoCCI6ClI7C3hPx9deyLPtdFR0CTI6DgCGjtCOzaLz8OcIm25ugIaHIEFBwBrR2B9U7+3AJ/g5pgibbm6AhocgQUHAGtHYHdsv8eAfZz7whodAQ0OQIKjoCWjsDh39revQ1fT+gdAY2OgCZHQMER0NoRUPNa/dcf0HKf46IjoMkRUHAEtHQEvGb/PUL49UfvCGh0BDQ5AgqOgNaOwLt/Le/nPrdFR0CTI6DgCGjtCOwWdf/aB5boa455LTkCir8vrR2Bdwzz2qHlPp9FP0CTH6DgB2jtB6yRxMeyeD73+Sz6AZr8AAU/QGs/gOz8Greh5T6fRT9Akx+g4Ado7Qfobnn3OizR1xzzWXIDFH87XbsB5ON28Wuu3g3Q6AZocgMU3ACt3YC35nWEwe8FezdAoxugyQ3QC688dT7z38zZnfdzn8+iG6DJDVBwA7R2A/ZZ5eM21tzns+gGaHIDFNwArd2A3dtXcZXs81l0AzS5AQpugNZuwNvyvmbBEn3NMZ8lN0Dxd8S1G7Bb9CMMj4w+h0U3QJMboOAGaO0GrN+F7l/v+dNMhtns3g/Q6Ado8gMU/AAt/QBv8fCnHevrKGELekdAoyOgyRFQcAS0dgTWd3e8Zd+SA58Z9Z6ARk9Akyeg4Alo7QnwmnPyLwCtd0QOfGuhdwU0ugKaXAEFV0BrV2BtwbGerx7+jBm/y9P7Ahp9AU2+gIIvoKUv4C0e/iSfT8lb0Oe26AxocgYUnAGtnYH1RSBv2bfkwLcZem9AozegyRtQ8Aa09gbW89bDZwLw1x69N6DRG9DkDSh4A1p6A7Ol3aJvASzR1xzzW/IG9MZzqP496Zpj4jXXyDDX2HsDGr0BTd6AgjegtTewevndgtByX3PMb8kbUPAGtPQGzmONsoePefB1yt4b0OgNaPIGFLwBLb2B3eLhoy7M+PTegEZvQJM3oOANaO0N+KzHrh3uinpvQKM3oMkbUPAGtPQG3iOLvddxW/uaY35L3oCCN6C1N7BrXvffB47nfX6L3oAmb0DBG9DaG9gtr5m9A5Jj7w1o9AY0eQMK3oDW3sBueeX1A94e7r0Bjd6AJm9AwRvQ2hvYLa93PA/IrL03oNEb0OQNKP7OvPYGdsuXbwEu0dcc81vyBhS8Aa29gbfmdWzDW6W9N6DRG9DkDSh4A1Z7A+8RtkbRd67Bem/AojdgyRsw8Aas9gZ85tbn0WCm3npvwKI3YMkbMPgai9XegM+X75bfb9ZY7w1Y9AYseQMG3oDV3sBueb3zAc/srfcGLHoDlrwBA2/Aam9gt3x57bhEX/OINX/nMQNvwGpv4O3tv792QG+3OcyiN2DJGzAY/632BrxlO7y3CZboa6ZY83cOM/AGrPYG3t5ex/j7bpf13oBFb8CSN2AwIlntDbwtr/NZoeU2h1n0Bix5AwbegNXewG55zR3aCb3d5jCL3oAlb8DAG7DaG/DkZ/5L1hvGsDaHWfQGLHkDBt6A1d7AfrLqc8Q39Habwyx6A5a8ATtwLKxz2G7ZZ7PgrGpzmEVvwJI3YOANWO0N7JbXF0XC6NnmMIvegCVvwMAbsNobeGv+a9kOOMLaHGbRG7DkDRh4A1Z7A/sIW2/K8cCW+5ot1vydw+zAUbicR+PhLRZXyTaHWfQGLHkDBt6A1d7Aztu+BQL7uc1hFr0BS96AHXjNK+fRdsvrXV426O02h1n0Bix5AwbegNXewG55pV7G8bbNYRa9AUvegIE3YLU3sFteCZDf72Ja7w1Y9AYseQMG3oDV3sBuWX0LsOW25ugNWPIGDLwBq72Bt+b1F67PvTdg0Ruw5A0YeANWewO75cv3M7bc1xxzWPIGDLwBq72Bt2byu1lYoq855rDkDRh4A1Z7Az9mK6z3Bix6A5a8AQNvwGpv4MdshfXegEVvwJI3YOANWO0N/JitsN4bsOgNWPIGDLwBK72BX7MV1nsDFr0BS96AgTdgtTfwY7bCem/AojdgyRuwE4/UOof1sxXWewMWvQFL3oCBN2C1N/BjtsJ6b8CiN2DJGzDwBqz2Bn7MVljvDVj0Bix5AwbegNXewI/ZCuu9AYvegCVvwMAbsNob+DFbYb03YNEbsOQNGHgDVnsDv2Yrem/AojdgyRsw8Aas9gZ+zVb03oBFb8CSN2DgDVjtDfyarei9AYvegCVvwMAbsNob+DVb0XsDFr0BS96AgTdgtTfwa7ai9wYsegOWvAEDb8Bqb+DXbEXvDVj0Bix5AwbegNXewK/Zit4bsOgNWPIGDLwBq72BX7MVvTdg0Ruw5A0YeANWewO/Zit6b8CiN2DJGzD4cpjV3sCv2YreG7DoDVjyBgy8Aau9gV+zFb03YNEbsOQNGHgDVnsDv2Yrem/AojdgyRsw8Aas9gZ+zVb03oBFb8CSN2DgDVjtDfyarei9AYvegCVvwMAbsNob+DVb0XsDFr0BS96AgTdgtTfwa7ai9wYsegOWvAEDb8BKb+DnbEXvDVj0Bix5AzZwPeV7Zb9mK3pvwKI3YMkbMPAGrPQGfs5W9N6ARW/Akjdg4A1Y6Q38nK3ovQGL3oAlb8DAG7DSG/g5W9F7Axa9AUvegIE3YKU38HO2ovcGLHoDlrwBA2/ASm/g52xF7w1Y9AYseQMG3oDV3sCv2YreG7DoDVjyBgy8AWu8gR+zFb03YNEbsOQNGHgDVnoD57l+TX+sKwbDtar3Bix6A5a8AQNvwBpvYLW4tuCA3xxZ7w1Y9AYseQMG3oDV3oCtcdtrPwlq7nNY9AYseQMG3oCV3sDTu58W/beK5/slAOu9AYvegCVvwMAbsNob2DWvXxKd7+80rfcGLHoDlrwBA2/Aam9gt7zeUMP5jd4bsOgNWPIGDLwBq72B3TL7/ob93Oew6A1Y8gYMvAGrvYH3CFu9jcd2n8OiN2DJGzDwBqz2BnbLu9fhCOtzWPQGLHkDBt6A1d7Au5/XWQVpqPcGLHoDlrwBIzxeyhy2W16/gjWYfey9AYvegCVvwMAbsNobML+XXH6ICfR2n8OiN2DJGzDC46WcD7P1VZPdMtxL9t6ARW/Akjdg4A1Y6Q28La97Sbug5j6HRW/Akjdg4A1Y6Q1Ay+svzEr13oBFb8CSN2DgDVjpDbwtr7khw6tkn8OiN2DJGzDwBqz0Bt6Wl1xiYYm+5pjDkjdg4A1Y7Q28Na9jHHJY7w1Y9AYseQMG3oCV3gDsZz+foeU+h0VvwJI3YOANWO0NvGfVXw4zmNPvvQGL3oAlb8DAG7DSG/CWnxb//r6/17HeG7DoDVjyBgy8ASu9gbfl9esZI2y5rTl6A5a8AQNvwEpv4G15zekbQ8t9DovegCVvwMAbsNIbgN5eLcO43XsDFr0BS96AwRvoVnoDb8vrr0AC7L0Bi96AJW/AwBuw2huQlXbZRxKsuc9h0Ruw5A0YeANWewM79fqX0eG+qvcGLHoDlrwBA2/Aam9gt7zuq0Sw5b7mmMOSN2A4A8D1c0lveX19CL57ZL038KwstJxyGHgDVnsDu+WVtwVSL/c5LHoDlryBZ9l3PeV7+u9+9i2AI6zPYdEbsOQNGHgDVnsDb82n31/BEn3NMYclb8DAG7DaG7DT5wB9fht6u89h0Ruw5A0YeANWewM+6/jOe2LLfc0xhyU3wMANsNoN2E9OdCUDPJ/7HBbdAEtugIEbYLUbYGvWcc3ph+cYvRtg0Q2w5AYYuAFWugGz5TWjflvu7T6HRTfAkhtg4AZY7Qas3j5t+F84q/ocFt0AS26AgRtgtRtgh1+fV6/jFb3PYdENsOQGGLgB1rgB+ynCXbTc1xxzWHIDDNwAa9yAy3vZ97fAEm3N0Q2w5AYYuAFWuwG25jv97MKzqncDLLoBltwAAzfAGjdgfXXC9zM+f+7dAItugCU3wMANsNoN8GN7PZd8jjhYoq855rDkBRh8ic1qL2Af2+uNJYMrRu8FWPQCLHkBBl6A1V7APrL8SMP90+ew6AVY8gIMvACrvQCv2Xs77Oc+h0UvwJIXYOAFWO0F+BdQeY/f/m4c9Hqfx6IbYMkNMHADrHYD9nXafzuMvdXnsegGWHIDDNwAq92Afc1ac/z4BLx3Ayy6AZbcAAM3wGo34L1WmZ/fsERfc8xjyQ0wcAOsdgP22eUtY2/3eSy6AZbcAAM3wGo34M1h+Wlw7wZYdAMsuQEGboCVbgC06FuA29rXHPNYcgMM3ACr3QBPgu9ZBTX3eSy6AZbcAAM3wGo34D2rvGYYv/s8Ft0AS26AgRtgtRvgb3X4WYVvd/RugEU3wJIbYOAGWO0GeM3s337AMazPY9ENsOQGmOBoXOcxP8LOouU+j0U3wJIbYOAGWOMGeEI4fQy7YYm+5pjHkhtg4AZY7Qb4keVjmb7fN7HeDbDoBlhyAwzcAKvdgH1MH3sLYIm25ugGWHIDDNwAa9yA+4xXDNjPvRtg0Q2w5AYYuAFWuwHvvYa3DL3d57HoBlhyAwzcAKvdAE+/bxKEmvs8Ft0AS26AgRtgpRvgd7F+nQ73lL0bYNENsOQGGLgB1rgB/pbW3t+4RF9zzGPJDTBwA6x2A970K7m3+xwW3QBLboDBN2CsdgPeu1hL43bvBlh0Ayy5AQZugNVuwL6XHDsVwRJ9zTGHJQfAwAGw0gF4Z2jGHlFgib7mmMPS9/8Nvv9v9ff/dwIc+T66/+6/xe/+W/ruv+H7ZuV3/+FssnyE9Tksfu/f0vf+Db73b+X3/o91F3v4VxwN3lzqv/Nv8Tv/lr7zb/CVKSu/8//2tt9H47Wqz2Hx+/6Wvu9v8H1/q7/vv97fhpkaqLnPYfH7/pa+72/4Pnj9ff9lXOw05AlB95csLY7r67vB6s+t4WlT7wFY9AAseQAGHoCVHoBv6bGeNh3+pI1xBOrzW3QBLLkAhnfTtQuwWpxb4O9aUd6CPsdFH8CSD2DgA1jpA5yucKyWfUsOwzGsz3PRCbDkBBhmpNoJsPXdKhOvfWVZmGfrvQCLXoAlL8DAC7DaC/Anb7zfeNtbBEu2fRDdAEtugOEYW7oB5366vPoA31fp3QCLboAlN8DADbDaDcjPPaHmPt9FL8CSF2B4r1t6AVDrfv4JS/Q1x3yXnAADJ8BqJ8DW18H22QdvE/Q+gEUfwJIPYJjWSh9g1rrGxPX+WejtPt9FF8CSC2DgAljpAhyXvwnltQtua19zzHfJAzDwAKz0AGatq0WvHcb3/vv/Fr//b+n7/wbf/7f6+/+75fWWtr3fWrX++/8Wv/9v6fv/hmNj/f3//f7C3t9Qc5/v4vf/LX3/3+D7/1Z//3+9m/PWDL8Q7L//b/H7/5a+/2/heKnzHfv57Nd1XKKvOea79P1/g+//W/39f796rnexntphib7mmO/S9/8Nvv9v9ff/jby39xbAEn3NMd+l7/8bfP/fyu//v+/m+DGOZ1Wf7+L3/y19/9/wbbL6+/+i+z2VMH6D72O9A2DRAbDkABg4AFY7AO/V0t9ngNr7vBYdAEsOgIEDYLUD8F6r/FiHmvucFr/3b+l7/wbf+7fye/9+zTr2FlzYcl9zzGfpe/8G3/u3+nv/u7f97gl+39N/79/i9/4tfe/f4Hv/Vn/v39/iXW93vuc51N5/99/id/8tffff4Lv/Vn73/+3t3fvQcp/L4nf/LX333+C7/1Z+9//NZe/ZBkv0Ncdclr77b/Ddf6u/++/721U8PK/77/5b/O6/pe/+G3z338rv/r9n194CbLmvOeay9N1/g+/+W/3d/33tEr9uwzHe57L43X9L3/03+O6/1d/932eVJ0KGmvtcFr/7b+m7/wbf/bf6u//v+exJAZfoa465LH333+C7/1Z/93/fa2hOwf13/y1+99/Sd//twgrqXOa9vHPZDUv0Ncdclr77b/Ddf6u/+79TEVct9zXHXJa++2/w3X+rv/v/1nznI6zPZfG7/5a++2/w3X+rv/v/5m+/A4Ca+1wWv/tv6bv/Bt/9t/q7/+s9cUiGUHOfy+J3/y1999/gu/9Wf/f/rXkd44bb2tccc1n67r9duJ76+SeHa1Vsuc9j8bv/lr77b/Ddf6u/+//eX/n5DPu5z2Pxu/+Wvvtv8N1/q7/7/74b7zkcxu0+j8Xv/lv67r/Bd/+t/u7/Ppss3+303/u3+L1/S9/7N/jev5Xf+4e7nHxs99/5t/idf0vf+Tf4zr/V3/l/f33xN29yDWy5rTl+39/S9/0Nvu9v9ff93yRIueU+h8Xv+lv6rr/Bd/2t/q7/PrYlZ8/+e/4Wv+dv6Xv+Bt/zt/J7/uf5lcN2NvGssu89v9OxjwM+i/mXXQn7rM9x0QGw5AAYOABWOgDHvX6NddvydtfvhW64O+4dAIsOgCUHwMABsNIB2L4PrRRN63pPq4/ITUrXMcltyhvW3PdRzH3JCzDwAqz0Al5JbpuF0Dd97otegCUvwMALsNoL2C27HAi/de69AItegCUvwMALMPcC/l//+//3//5////+j//9//y//j//x//5f/9v/5uMfzITyzX0eD6ecP7PPLr/3TMl3/fzAfNh/8P3P1iL1Wuhf8dcy/3ssPt5cP2s5eLZ6XLKOcb1tZa7W8u4x33MQeKRKq7PWvQ++NDznvcUd1yLnOValP/ZYef5PMK9nlQ+N+nfmCPkHNROeb4cFddC3VrueSTQ8cDs17y0nHT9m7ctc5Q+b32uNXEtde+q/Due/2OZ/clrLfKAKjwP9EH8tZa6d4u12D++Bh8H0fMN0a+11L07K5oxecwFznOmpvFZyznmQaIy78RnR4W1aNu7fM//mwH80vOY+4j073h5fsam59e2aNO79FnLTHc6N+bmsJZzHONrLU3v0r/zmH15P3oAE/9V9HzJbh7Mz2+Fv9bS9C59epfmsT6vEWst/GzLNYf6Jx7EtTS9m9fy7Ol5Bn2+tHV+HXXW9O75bw5ds+FZlKiOz7FL+hz+z3/lr6POmt49/43ZH+c8/eb4ORc6+fj3THk9O07mXdrXWprePf6NeXfD95MDnxetnrVcc8XHXO84x3dFTe8e/06eh8HndxVzPZ+K5l9inmPDIP1aS9O7xz/WYwiL8vk5XO5/zw/GPhfjeX7GlVxN5x7/5NlH4zlwz3UyPq/oznHuZP7akqvp27yS52h5jpR5xJzf9Vxt39I8zPWai9zPDcqzluOe58/czfPo/V5L27efYeF5qHib/sepeDWD7vUpaK7hmBeemd5/r+Wu+1bs3zydh85Nn7nmuQDMguZBM69pPMb3mHvXfbs2ZV6K5tE1rr9zaDwnxH0/g+PXSpoL2v3voHkVPuzpTVsn4ty987C9Zmd/raS5nj0robkMz7zyiAPPATfzmjxvo7KktbRdOwfX65jH+bwczZD4nEHHp2vneDUHcFzLNfdBt5ZDZ8KfBT/DgH7Wws+19fnl4vOb87iWpm9tjkbH8y7e86Uw5s9aPsfs9fzCXc+vtTSdK/+YZhq85m2SfkY5XMvM7l9raXp3Xlvncf50gX1e9VoVqczdT3PI+lpL07v8T54fql8Pxfh8+POvd5mfZG3McSVn07k0L/NzaJoXoXlJ/pyIz46eWf+5qMRr4uXKRbElcxGZx4fy9aBfzyE3x7fzOX3o6zp0uYZR1fOczte8ztODSe+jX+X5JNZXr5xN3z5Z4bkzsWeklL+r2fy3ubOuZ699V9T37de29IPCvMbVnctzGZHBY17hZ+PxKj8Poq8jd9S9O9cynnJ5HM/3G/9yy2CReQtxP5ba11rq3mWZ2zKvzPfxDAo3fdYyt8vOue+fO7GvtdS9O9dyzVD4nH08THQdLiL3c1en9HUWjbp351pUH/3nnIFstv9Zy7wcPv9xpvDvfqGmd+Xf3BM6rvMJktffoTvPRZpXBNKnxLiWuneflueg/Xy75/lp/H+upe7deaTe8/oxw/GYe1z/xsuZ5GTMa+Qxr9Jfa6l790nYc+gfxzyd55J/2zLz4XE9Z9IVr4pzLXXvzrXMs3GGJ5JxXeffBeAZ4h71iL4HF647dx4c9LnKz6g8BxT6bMrfbZHJ19HPTc/avwe0P55APq+If2Pl/A/neCaN50j8tZa2Z8eTlFnnrdHzrv6zls+GzOvKvOBeX2tpjlue5xDNo3QOJ4fc/7WS5rClOSjQg5R8fo7wFDSj3NMfD96g8nXYNrdncy0zgY5nD8scve1zk2cfeng8czpfO7m5PeO/AYrm3eUcZ58BCm5bjdJa2pvf50ZhPAvq8wXnpyL9HPxzr57H1y5qbs/miUjPF82u8dyJsMS1PJ+Li2tpepc/V6IZVJ4vjt36WcvzyyKe1/l5lfyqqLk9m2u5nt8Rz9vn+3ln8bOWhwGleTv8nAxxJU3nygxM99zXSs/I/RR0zvHpOQifLwDZ19nc3J3NtTwXv/N6Nv/5UtizluPzk6br+QDfd0FN5+q8R2V6gufTt3/p57qeJDY+v1L+WkvTufrveYPmuR2a14C/lcw0JM8N/czgXyd0c3PGM6LPhsccbZ+x/u8u5P6cD/NmbR7vX2tpOnfeos4MOYen2Tn3JynPYW8e/vPujD6zSXEtTefO8emBTeZdtD5d+hc5SK8H3j0eaDiupelcewYkec6yGevOFTk+F+hDnl88xJU0WeF84vU1R9h5z3qa/V5Jc282VzKP/nkvx/OE5nsN2n+JcN65fg+Wzc3ZPJ+HPVTrmCH1mWX93OHNM06fw5/H135ubs5mJpxn4Tz053F3zTr+Bu451MzbCplDxddK2owrz2zA3AIlee4T59Gv81x4Dp/bvndQd3O28rbMwV+fkP6s5foM3PM/H/J1Pnc3Z/PqPMYz2SJj3qf+51qazp3DkVwfgeB8JljnWmZ337NX7/HMFX5dRPrbM3peJLY5RtFMO5+1zFPwup6kIN9Jobs/G8+N+zze5xrmfdDfYEmfmUIhslRR07tj9u5My/Rc0fReA/c8/Z8Zynm/FUeos7s/CzOoankGdXaS/ft8QPT5CtWlsMqmq3E6da4kT6fOVc4oPVc5L23XbBhW2R7Un7nVudrnhQF+51ZFn59M698qHyDqmVGbwzOsspl++M+J1jnKy9PsDP+z6ffJzlxlO0eJs65XnnX9rHLmu+dD/LfgKps7vP+egv2sEtbTTPyE9azbkDAJ+72eZuonTsPmWdjPap4DSZ+z4v0h+nU2t3y/p2R5Ffi5n3siwftwYa6x3g1z4AsLfN243b9W2dwL/vcq57n2drDC4dfcF841qk9dzXH6/F9ZY71r/nuNT2yB/w84+pobxp8T3Z8b6R+rbGeacdab8qz3Z5XX5znKMx8NhTe3kj55Pderc4D5mgEf42+NzzH2tHm8H6y/zua28ms6fOTp8B+rbE6cMDcunOfGnw78d6jO+85ZOsOg2Nxwfk2UW54o/6zSnl/8z4A6ByRY5f+j5wD0XfhnSv/699y30OfnIrDDm3vR/97K5zHFPx2f9/Tm/QKcjc296X8/IbAx7/aeTy7oZ4ITCm9uVOcqZ/K8Zut6Pb86/ZtIIJXnX+YOnm3Mi8I/ec6GzxwxDGzNXetcpc7Nm6PUvL+ST/p5ZryfrDmeb1PHxHE2t63//WRm1fooPJeEa0r3iHFe8g85np0oj4D6N1FBs0tl3l4/OfrQecGewe8SfvIerLF9rIAPWzQ/bJlH4v3PzueBxzObDL3XPXs85lGms5+f7wzL+JurumbKf67Nz7b9rfJ67vPmvTggS9fZPYj8r8cwnzXOnGwzUc3iT1hj+2Dn9zOZzxo/l7eHHruhJ7sHlGGN+zoND2h+rLLdOfi05spPaz6rnMf9/bnNxkO7e3QZH92M/AD0s8rP6fiJ7rjKeufM8xkXGOXVq1tlmwP+Y5XtJba5h55x5PQr4hOj/lfW2MWA/1rjDFfh/wNW2WTl+EiMqot2u8rmhuW/no89CfAzc09/d5mwxp/P7fxhmaWHZXsbn2/dzmHlXWN3Dx6fnNHXk7NP+H7mDfV5HWPgN4Kvs7sh/8/naGuV87ZtXtRxoOxuzv2Z2n08d3r8PlN7+n7eJP/VLfN+/eanbFxls2/CA7Zxxwds198K56kznjnxCy/Y3V17fNY28lOyz95+7uznvwpAH7Ob2/MmLPD1+I6uX6tsT5z/WGV7Kjb39nON/Kn8gyaQ/K+ssRvT/muNs+zw/wGr/D2lsh5han4Q2q5ydDMA8XnmfkL7Ps+cq5TnIHsezM2TlWCV7SPF3w83P2ucZ8I8+elk3Mb2/h8fdP7/OTuXZdtSHT2/TjV2rJjcUdPhcKM6ZYdd7/8sBiZi/ELSWDvTYXtl5pkIJC7jEwjU1EHncv/n1Axzp+OJYe/RP8XFU890n3ruNg4rDEuMGkIGkX917Fj1EehX7flJmoebFfT2Dnh/PQ9d3U2r+6Jglugf996t1J8Hr5XuzBEFzI+YJ9KdOr+I9CZjdHcF5r5UntvN4TNf8f17ie6mwG8SI4lfRBDpnhbjmbP57XZFOnvt4gC69vsAereyrRjFGRwLEt0To18Oo4fEMb2Gqztjd2tEU7pnyngyzV9aOJleIsPcIS0zFxmsQf4BMxxTt66PqZfIlAbPtOF+PXdJenS2BX4/s14iZy6EYYvacAw52wKjI7BAuUS2N4nezPlFojvMnT2BmKdTMtBq4ElgT+yvBDo7Ar8KHE64+AFI/JswgGj1iyvxr0ICkg4JGCLD0Hv8anwfPvgNc/YDZHxACDo+YIkc87DNHfyQYSY6mwNXsEC6gwV2K2kdK9QM74KOuf6vQgeGvPhTl/M5NyLBkM7WwO9REcPJHPNqzOw4/JWQsYlO37w3cTBP/Rl0PlgljEkCHePsC8xQhxyGwDTzXtG3iXF4EnXQf5qRb7hRE529gOkRja9q+6z16VP2XsDc+hkex8z5OVozlrA6n/UY7it4C9HZDJgOTIozj+T45M+b11NkGJg/VubhRMxdqmHaMfSHIUstFcnM2QyQYR1zt/0O61g9PNc3Gg7ApwFQOJsB7zEe8xbJGoRt+qQltQ/2iLsZIArkK+IjlzeR7ir2i0h3GXM3A8a4bWF4xGW+6PePJHo+zW8S52IEvwC1vZN2GToTdezMi0jn8y8DaYoOpBkixwwc42h8uwbMwBBydgOuqJqko2qWyDH0J7Jg5oIene2AK8Sm3yE225YTMeuouzSYjs52wOoeKHCJbPFNpPv5/0WkO4ac7YABznhaW/6JRG/m/CbRPSGO3pG+jFy6Yo7CZ4scjv34tI5RAL6Xvx2Av5cCx2r3ItD1ad4FumZ0NwMGlw0WpmGlMMblP5HoejS/SFzwCL84IpOzF/AeDPbtGFekG+uGkWFZR4atWTN99+GTdNzRTs5uwK9hYkviwJMwWGB4IRUkui7NLzFjS+9cPvM2SA0fFOm6NBhAFu4Aso32sdZ5vtDhTYmenN2AK5qs62iy5cr1+ZT4+LYnbKWzG/BraNmSGOfh3PAm8KAzOZsBHGcW0vT9vieGO86s1xLXQeeY/zTfEZjvi8JBZ3I2A66gs6iDzpbIeVwxMLfCQ61DpNM7MgIt6wi0JbLOM5O5Dfa8KDGWLDfADsPRuookWxLn7YUxCwatwdRxYwRkASmxr6ANV6T7wflFpLcKJWc3YO4bjokxT+Bi+OT+TyS6H5xfJI7FHH8BK4azGXBF+Vl940p0ttFEyF8nHfK3RH7m+XQZQx9cpeTsBfwe/7c+Yi2mscjNR75hTDqbAb8GA65907kXFOY+C2wnJWc34IoMvAMDeadvkMGY/Al2+pKzG3AFCV7Rfd+9w72hPfkygdLObsCz7b4KxEtkCm8ifzsb8ES6g9zZDVgHf591gJrmSzP/RKI7bX6RuI6Cnl9A3zibAVfo5S2y5DeR/zYOc52plZlhrc+nlmBN8+LgZVBm0UGZS2TtY7bGgQS4TDpbAr9HaK6pOPG9ju9cgdCa5OwPXOGaWYdrLpFjNZonO9NvekQ6+wOjxzGMMt2Bln6cZXK2B5bEJ4qyXHGWHLq5fjHExgDQ4mwPrNA5iKK84ixr8uMskx8rgFGU4Y6zjH6cZfJjBcrPFVwZ76DI5O4EfAtjRGUjVdgNBBQBk1dIJTfCCqlMjtO/IgEhgu6KsVv7CE6MXXKc/iUS4t2uILuQISJuyE3I3I7Tb4jEyKYPiryC7JLj9M+vHITQpTvILvhBdsl1+mUI3R1r5sfYJcfnD7HXnzjdlTF/eq633v1Nb7t3wlidh4ixtgxcqlEFxL220u6d4T19fr72G6P5Uz4r3m7bL62U12PFBzmOq19nNEOdth7reftuDs7vRRj/EOoKeJjkPZlmuEO4Q50cV3/wURiNKuOb0/jg/zNDuOYO5Ojsr8QB7nXGTX3gBDw5vn4Pw0OZB/IzYKbsE/Dxz/PC4GhZZJHzozbMF5BqXG9fxrtdEXEh+RFxyXX3RbxbuCLivgvF+C/zqzUoGVL39Oy4+0skBLzdIXF+RFx2vP0l8YlO61dEXEl+/Fp2vH1DJIbExf4m8qV3noC3KEPiCpEfEpcdd3/FozwRUO0KkfokP0YqO+7+iQ37hkDdMVJfF8MOksqOuz9EYghUvYOkoh8klf3DfwyBumKk+gm7UjFS2T/6FxFQd4wUhkgN/6BiE1/IGEKg7jcIoh8kld2zfxkScwXNxOIHzWTX28eYmMx6c9AMx+EYUTPZdfZFUAzf9+aomRz9sJnse/siKOYKm1khr07YTPbd/TvUA8NmWvGjR7Lj7i937QmKuaJmWvOjZrLj7q9YjxMj0eiKovgUN4oiv538PzES5YqiCNWPoshvR/9PjES8oig4MMOKosju4b+IkVBRFMGPosj+8T8enOfraH1daXKO1rPr8cuDc3nIPL49/tF6dj1+cXAer6P1FQUpfwEi3VNNPDsv4tx6/Pfon65nx+cfvxxf18+EtaHXDqUAkS8H9tkPAJg79cMDHGCSyjfULg3qGP7e3J3fB8TzH2edEKqZHZc/jGV7jJCVmWcMxC8SzA/3jOg7aqex9o72RXD4s+PwP2wKgQTp7mMYiY6XPzSYpwRlYPi8B/HdcAszv8oY3vPa8VdkmZNghgBnbJp7zIyn59fx+to3ED94BLo+vjxLvU9bg3/aml0nX5ylhuu0dW3BOKet2XXyxRFOvw55QvcPebLr5IsznHId8qTkn/Jk18kXZzj3KU9N/ilP9oMAxBnOdcqz4NQ55cl+FACe4ZTrlKdn/5QnuxsC4hAnX8c831g4+5gnuxsC8hDnPuaJcMzTx7cCQcDdEBCHOPfbArH5xzzZ3RAQhzjxOuZpyT/mye6GgNjWL9fG/3dr0N74z24UgNjWj9fGfyB/4z/7YQBiX//a+Oe9QWvnP/txALizn6+t/2VLZ+8/+/cCxFbvvRns7wVnPw5A7PRee8ELLsQvQO+3SIBnp7dde8G5+nvB2b8YgDu96doL/m6C23vB2Q8GqD9pvtP2KeGTv4t6mUfXg6wy5fv2ArB+cXcHfvv0vIh0QS3+zDD+OI8M9to2IzfHRCpjDt5BEEKkC2q/UNWLyJfws1f2exH5En72Sqi+SHd7YN3SnHEatXd++2qFvA48/6iDVyHS/fT8QvsvIl/cnFef5EXki5vz6jm9iHy5HPDi3r2J9HcIlA8694MKDVRJ7xLfNgh8R/m+wSBEvu4QzGDAoeq+574+4fPiTH0bQv4GwS97Di8i3z48/sbI2xDyNwh+2b55Eflyk/N1k+lFpNs7e6Mr9ZQi3BZcL3C+dri7RfDLbt2LxLdj57SunH5mTt7vjtD46AwZn/g6htwdgt82Pl9EvlwXXJuv0wEp6WwJrcDv+vp5dHcI5hbxZ0aizezj5/3msbClPgbC27B0dwjet7rfuseNCvhtQ94X6ewQfBUv80WX0nPI+62EMr63fT648Cbx5dQADi700caLyJfeeT2AeRHp9g6eoamXLN4kup3zy3mlL9LdL/jtVPVF5MtTNc/J7n32+woaflBA/ZkDaAZDUKl8AJPmN/0zvplvIl+CAl7P0V9EvgcFXOf6vpxf4gOu4IIXOW+hAmk9qtX6d7R8lsThetb82rJ/G5zxIvIFAL4BIiuAWCZBeFu63W2BGf85lg6K9fuewYw/zxTjdLjaa4e42wK/+V8vIl8C0MEHvL3Et+72twV+8WVfRL58/stQcd4gmh7cFLmCpMp85LK/dc/btsB8meT7COk3NC6PMR7HCOhNXYNBkf62wOvmxduofLsf8LrF8iLS7Z5fNoJeRL5sqr1uV72I/Lebaq7I6u8LPBt7/dNh62++JJpfWlndfYHXDcqX3qnutsBvu6gvIl/8zte93heR/3ZH2hfpbgv8tm/+IvJlW2C+spH6/Dp/l8th2bGCjplaPq8iXwDgFVPgobEZjZBB5L/EM35nLA5zhwo7f9V/SHDM8AEUfa7i3+iYGSY0fNsZHTokjp4aWqQ8rwp3iDSq/juC722Mwxf5CeNf5h4oZA0dEl/i09IQ1ecrfqXBK2ODVuY27Ypden7RQeS/7Zvz5Nj80n1KAJFu3wyI+tDwFuYe3Q40Gv0wZ05b5MtvjrXxiQ8RFf/X4YNxbjaO/i65dnxTprq7ArOVND4KE6l2hFUY38X5MavrQ9TXyF9P30EET3X3BN53/QguP48R2bG/3T2B37Y79/3neY8pRkiiNUS+3bZtOaTJKnwnJI3Pzry5vRb48imTgWudOa0harL6bwbEacmx3ubhfH4V/7TZs22Oy9E5g7bGN36MoDEMKo5KP2wgri2a+RJl+jZyRQjMNSm0P9QGuQ7ncRj283nSKs+3XZY8kbRsJoj68/2b9l8YHtvh10nL1kMxT9Ky8a/1/PI/9g+gC3dC2avmb6o4aAHUvJPMmjV3UfP2zaHm8gE5rzpzC560mqOEr3OROhelcwGdi6nzsXLROldf5yJ1rkrnCjpXW2e2NrHuUMLXuUqdq9IZp2q1+7lIa0NoTG2+zlXq3JTODXRups5lW5tbIGr2dW5S56Z0hmv2tdk6p8va8Gnovs5N6tyVzh107nY/7xpbMGr2de5S5650hqPw2m2dA9Y8nwN9SpCvc5c6k9KZQGey+/nUuFsAqx75OpPUmZTO8AhAJUPn+Tz6H6n7U3P7+DqT0Ll9bp1HWZBj6Dyfd/8jWiBqdnWe8bei5lvnURbkmP3c9tj+JiGdLXlKBFfnGc+PNQelcwCdw4vOUHOAEr7OQeoclM4BdA52PweseaYKe0pEX+cgdY5K5wg6R3Nsc42tGTX7Okepc1Q6A1m2aPYz0VXzM59b8nWOUuekdE6gc7J1Jq6RWwAlfJ2T1DkpncExacnWmWvcLYCI2JZ9nZPUOSudM+hscxjPY26BqNnXWXJYUxzWgMOazWF9zypuAdbsc1iTHNYUhzXgsGZz2KlxtwCi7JvPYU1yWFMc1oDDms1hp8aia/Y5rEkOa4rDGnBYszmsc//yGIe2+hzWJIc1xWHoIjebw+juZ1hJfA5rksOa4rAGHNZsDuPVk1sgavZ1lhzWFIdBUvrxz6/r9nctm8kZnxI+hzXJYU1xWAMOaxaHcc2zxv0XvpI+hzXJYU1xGF4tbhaHzZq+NXbSX0mfw5rksKY4rAGHNYvDZrpJWTPq7HNYkxzWFIc1nCM2h52aG7fglOg+hzXJYV1xWAcO6zaHcY3cAghl7j6HdclhXXFYBw7rFofNvEdSZ6zZ57AuOawrDuvAYd3msH503X/B2j6HdclhXXFYBw7rNoedmvcIC8/Y7j6HdclhXXFYBw7rFoc9NYc9n+EiU/c5rEsO64rDOnBYtzhs1iRrhiuS3eewLjmsKw7rwGHd4rC5O/dHtgBr9nWWHNYVh+EGcbc4bNa0a9z9DEzSfQ7rksO64rAOHNYtDptpXWXNqLPPYV1yWFcc1oHDusVhUCO3AOazz2FdclhXHNaBw7rFYU8/cwvgwbbuc1iXHNYVh3XgsG5x2KxJ1gyRzd3nsC45rCsO68Bh3eKwp+a4dQcfo/sc1iWHdcVhuHXdLQ6DGouu2eewLjmsKw7rwGHd4rCn5pi4BVDC11lyWFcc1oUcu5+LrBlXPZ/DuuSwrjisA4d1m8NaktYWNfs6Sw7risN6Rzl2P++vYzN09jmsSw7risM6cFi3OayFq2YYYT6HdclhXXFYJ9TA1plXkKBqJp/DuuQwUhxGwGFkc9ipcbcA9nrJ5zCSHEaKwwg4jGwOOzU2XbPPYSQ5jBSHEXAY2RzGNXIL4BVC8jmMJIeR4jACDiObw2qROmPNPoeR5DBSHEbAYWRzGNecdn/DLjP5HEaSw0hxGMHsJJvDcpM1w3NZ5HMYSQ4jxWEEHEY2h52a93wGliCfw0hyGCkOo4RyTJ25xlR0zT6HkeQwUhxGwGFkc9ip0dDZ5zCSHEaKw0jIsfs5yJrRSj6HkeQwUhxGwGFkcxjrnHZ/wx1W8jmMJIeR4jAqqIHdz98aYzFq9jmMJIeR4jACDiObw1jXRNwCKOHrLDmMFIcRcBjZHMazqu5+xhI+h5HkMFIcRsBhZHMY13haANb2OYwkh5HiMGqogb1uB1kzXA4nn8NIchgpDiPgMLI5LO9vVCGts89hJDmMFIcRcBjZHHZqDtyCp4TPYSQ5jBSHEXAY2RxWktQZzmLJ5zCSHEaKw3DPmGwOOzW3W+eBUr7OgsPGLy+dZ1mQY+vMNe693me9nWnYnJqnMFlzVTWjHFvnxjXuFkAJl8OmMFHzzWGzLMgx97e5Rt5lFjX7Ogep881hsyzIMff0eR7zWR1a2+WwKUzUfHPYLAtybJ3Z2rzLDCPM5bApTNasdI6ogb2nf+sMNbscNoWJmm8Om2VBjr2nf+sMbXU5bAqTNSudE8p5jTPIKp5kRtb7NUudbw6bZUHOez9/x3jY5xnh2dsfJX3ds9T95jH64Ig1eSx8Lt0f4p9Ps/g1S91vHptlQY7V30/NTevs8tgUJmtWOuP6YJ9PcjzJHmnhAzq7PDaFiZpvHptlQc6LzrNGPbtcHpvCZM1K5wo6O3FiHK0VsAUzyfxT0uWyKVS04OayWRbkmLoHjpniqJ5ktMC3QZM2uPmMYL9t/PNrTGTZvbD3/OFZRPq4nDaFihbcnDbLghzbBlvnwDZQ8YKjpG+DLm1w8xrBkyrjn835Hlj3Ex/6lHB5bQoTNd+8NsuCHFt3jhPkcQD97vLaFCZrVjrjd8LktbB3ZsPeH50Xr8EG4+/TkuDy2xSOLQmK3wLwWzD57dQY2foJSrg2CJLfguK3APwWTH4Lda91HD+4dy/D3vEJT6wsBZ/nguS5oHguAM8Fm+c4NmOfrMI7p6OEbwPJc0HxXAgox7JB3NaP+zwk7nERz765PKmJe7ZGlOxzX5DcFxT3BeC+YHPfiWDmlQl6xee+ILkvKO6Dmw7zRTRzjjQ5J7CEz31Bcl9Q3BeA+4Idj1bTNSewZl9nyX1BcR8kpR3/bMeLlz9C9wjrgM99QXJfUNwXgPuCuf8W9p5ySCo6f5TwdZa8FxTvwXOd8yKIXzNErEMJn/eC5L2geC8A7wXnXoCoeeoOJXydJe8FxXuhoAamzntPOez91rB3wwIzb4V+9/kvSP4Liv8C8F+w+W/vegZmXuwvn/+C5L+g+E+soeZ+XMgc6bptAT5O8LkvSO4LivsCcF+wuY8pm63O9I1W97kvSO4LivsCcF8w9+WCjJ2XNfu8FyTvBcV7AXgv2Lx3+nuvNBms7nNekJwXFOcF4Lxgc14OsmZcDX3OC5LzguK8AJwXbM7jmvd+eyL+d1jjfN4LkveC4r1AqMlLDD3Msoeyos93QfJdVHwXge+izXepyLGesGZX5yj5Liq+i8B30eY79utOzVDC57koeS4qnovAc9E8J33GNkd3Byjh6yx5LiqeQ+qKJs+dmo/uUMLntCg5LSpOi8Bp8Zd7AzzS+O8Z67tl0P8+v0XJb1HxW4yomd3/4iaDrNnntyj5LSp+i8Bv0blPwL3A90calPB1lvwWFb9F7E2b3/gewdEZavb5LUp+i4rfIvBbtPmNdxJOzdBWn9+i5Leo+C1mlGP387k78QdsIHX3OS5KjouK4yJwXLQ57kT3M0nsFsBOQvR5Lkqei4rnItry7X7BrHH/PfcNnpI+x0XJcVFxXASOizbHVeE94w0Hij7HRclxUXFcrKiB7cef2xxaZ5/jouS4qDguAsdFm+PYW+K174kCp+jzW5T8FhW/xYYamDrzCnNaAGubz29R8ltU/BaB36J937PTH9GCc1sLxrrPcVFyXFQcF7H3bI47t7X4fgnv38CI83kuSp6Liuci8Fy0eY5XmnOHao/9Bv3v81yUPBcVz0XguWjv3507VA1bMlt2Siaf66LkuqS4LgHXJYvrntt6+3QsPPHplHyuS5LrkuK6BFyXbK7jtY7vUsFJYPK5LkmuS4rrEnBdsrnu3AYIRs2+zpLrkuK6BFyXbK47dy4C6/6U8LkuSa5LiusScF0y49/Cc7fmakGDkr7ukuOS4rgUURNTd55dPMbPiNsrEaw8yee6JLkuKa5LwHXJPo89d27S1QIYBz7fJcl3SfFdAr5L5rls2Cf+T83QCz7fJcl3SfFdAr5LNt+dG23n/hGU8HWWfJcU36WMcsw96nOjrWlr+1yXJNclxXUJuC6Z57HxjHmpe/zAiPO5LkmuS4rrEnBdsuPk+A7ObgG3CL3f5HNdklyXFNcl4Lpkcl3k/j43ZILRAt8Gku+S4jt4rX78s93/bPX7vgp8cXzOS5LzkuK8BJyX7Pi50ETN3JIYYBz4vJck7yXFewl4L5m8F9nq9z0lOA1JPvclyX1JcV8C7kt2PN11MhTjuWEBJX0bSO5LivsSftFM7uMaI99zsFrgc1+S3JcU9yXgvmTH1101c0sinJIkn/uS5L6kuC8B9yWT++I+JYkcE86R+M+9B8o+9yXJfVlxXwbuy+Z+XjwR2rIFEc4uss9/WfJfVvyXYV3JJv9Fjh3mCN69wxRP/LRsIbcYd0+yz4lZcmJWnJiBE7PJidySyHF6J846QUnfRpIXs+LFHFAT00a75pg5zpptwtHPIMHnxyz5MSt+zMCP2eTHE+F94q0JSvg2kNyYFTdCls3xz6YN9i5MrDw+oGafE7PkxKw4MQMnZpMT2doxnxZACV9nyYdZ8WHGXnPuT5DoZ1Gzz4dZ8mFWfJiBD7N9f4JnYeERB231+TBLPsyKD3NGOXY/l6tm6GefD7Pkw6z4MAMfZpsPeYTtfs6FbQBW9/kwSz7Mig8z2tDkwzPCzoiD74DPhVlyYVZcmIELs82Fx+qkdfZ5MEsezIoHIcvkTK9i1czzmaPcE/S3z4FZcmBWHJiBA7PJgcfKfKsBzu+yz39Z8l9W/JeB/7J9j+LcSmLd2fr73yFqKvscmCUHZsWBGTgwmxwY+T4cf9sy1uzbQPJfVvyXgf+yzX+n5qR19rkvS+7LivsycF+2ue/cXtlWx/7yeS9L3suK9zKhHFvnPbt2jEJsrPtuCUTJFJ/7suS+orivAPcVm/ua7PfTAth5Lj73Fcl9RXFfAe4r9n0LjoJnpmncArCBz3VFcl1RXFeA64p9/5Vv9PCq27glBCV9G0iuK4rrCnBdsbmOX044922CboHPc0XyXFE8V4DninMPo4gWcIti53/fvbJ3LCPvVMGeSfG5r0juK4r7CnBfsblv7xPGvU8Y985V4n2kc2OIf7c1IBjJPh8WyYdF8WEBPiwmHz4t4fs7MIJ9PiySD4viwwJ8WEw+TLyjVY5NnhI+HxbJh0XxYQE+LCYfJt47reFqAVjd58QiObEoTizAicW+Z3vuXYY/2KIEdx2Kz4tF8mJRvFiAF4vJi4l3sM5t9mS0wLeB5MWieLEALxaTF7kFifcVzxsCUNLnxiK5sShuLMCNxb5/W+XrBdySBLt5xefHIvmxKH4sQhPTBrx/yC84QOxb8fmxSH4sih8L8GMx+fHUXEnr7PNjkfxYFD8W4JHivIeShM4J9g2Lz4tF8mJRvFiAF4vJi6xz4j1UiIUqPi8WyYtF8WIBXiwmL6bzuhD3d9K6+9xYJDcWxY0FuLGY3MgtSM+bP9wiKOnbQPJjUfxYCOW8vne0a+aWpL2Lm/ZOZor8v+8Ww25e9bmySK6siisrcGU1uTLxbh2TTbNa4NqoSq6siisrcGU1uZJbkHiXrp8WPSV9rqySK6viygpcWd/ft+uyJQn8y+pzZZVcWRVXVuDK6rxzx+8Ynpr332dtrD5XVsmVVXFlBa6s5j5h4lcw+Ly5Wy3wbSC5sSpurMCN1bnnK1vALUrb30ybfNP2P9L2AhLsfFSfG6vkxqq4sQI3VpsbmfrPW9zBaIFvI8mPVfFjBX6sNj8WvnleREsgfzdVnyOr5MiqOLICR5r5I+A29u6Nwn9hrvgcKfNIkMojQZBHgsw8ErOmXeO5ib7/Qgt8jpT5JEjlkyDIJ0FmPonjsXxOb/BIhLnic6TMK0EqrwRBXgky80qcW9mPdwf97/OjzCtBKq8EQV4JMvNKzJpEzQl2uP28EiTzSpDKK0GQV4LMvBKzpl0j39KFEj43yrwSpPJKEOSVIDOvxKn5uSsN1va5UeaVIJVXgiCvBJl5JeBO9J5laCWfG2VeCVJ5JQjySpCZV+JYOXGEI1rb50aZV4JUXgmCvBJk5pU4OnPNiW9nwa1sP78EyfwSpPJLEOSXIDO/xKkx8Q1VvpUtWuDbQHKjyjNBkGeC7DwTz63sIFqSgN79fBMk802QyjdBkG+C7HwTiT0Vvk9wbmknKOnaQOadIJV3giDvBJl5J6Bm7gW+DwolfS6U+SdI5Z8gyD9Bdv6J5xbmHokccwvxBn4eCpJ5KEjloaAmNLFtwDXrG4p+HgqSeShI5aEgyENBZh6KR1e+qYg6+xwo81CQykNBkIeCzDwUp8bEnkjnlsDI8zlP5qMglY+CIB8FmfkojrW5BcLqPt/JfBSk8lEQ5KMgMx9FT8xzTN+wUvj5KEjmoyCVj4IgHwWZ+ShmTaJmvBvn56MgmY+CVD4KgnwUZOajgNt4fDuv6Bb4PCfzUpDKS0GQl4LMvBRwR46tD2Pd5ziZl4JUXgqCvBRk5qUYNQWukUfcU8LnOJmXglReCoK8FGTmpXhq5BbA7rufl4JkXgpSeSkwdSOZeSlgjH9rrrwXAhHsfn4KkvkpSOWnIMhPQWZ+ClhZ6Op3aLvPdTJPBak8FQR5KsjOU3Gsz7bAee5zncxTQSpPBUGeCrLzVDwri2F1n+tkngpSeSqooe3s/cCjs77/6+epIJmnglSeCoI8FWTnqQj8rg/vqrANeL8HPEc/bwXJvBWk8lZQw140uS5x/Dh7zVCzn7eCZN4KUnkrCPJWkJ23gm2QOHof1iY/bwXJvBWk8lYQ5K0gO2/Fo6u+F+jnrSCZt4JU3gqCvBVk560IvFOwa85w2ubnrSCZt4JU3gqCvBVk563I2z/PfFOhGLr7/CbzV5DKX0GQv4Ls/BXnJmIh0RKM7/TzWJDMY0EqjwVBHguy81hwC/L2XTP7shA34uezIJnPglQ+C4J8FmTns3hq1O/6+PksSOazIJXPAhMek53P4qm5aJ19jpP5LEjlsyDIZ0F2PovnXiD3N98XhJHn85zMa0EqrwVBXguy81pwjZm95ma0wOc5md+CVH4LgvwWZOe34Joze9H9tARK+jaQXKfyXFDHtdPkuszecpctyOA9+/kuSOa7IJXvgiDfBdn5LviuHLcAY5b9fBck812QyndBHeeQyXese2Z/HcjAz3dBMt8FqXwXBPkuyM538dRo1ezrLHlO5bsgyHdBdr6LzHsUu+YMZ5x+vguS+S5I5bsgyHdBdr6LwN5Tv1sAY93nOpn3glTeC+poQ3u/bhNF5hsqfEMR7on5+S9I5r8glf+CIP8F2fkvMt+JObezArcISvo2kFyn8mAQ5MEgOw9G/BTRAm4RRsn7+TBI5sMglQ+DIB8G2fkw8t6jynwn5tzawha4NpB5MUjlxSAScsw5wDdRzl05HhfPXPDzY5DMj0EqPwZBfgyy82NwzdySzDdQ4J6YnyeDZJ4MUnkyCPJkkJ0n46lxj4fzXh+0wOc+mS+DVL4MgnwZZOfLeO6H7TnAt29wJPrcJ/NmkMqbQSTk2DbYYz/dt7SgpM99Mn8GqfwZBPkzyM6fcW5p7Zq5JRl2lPw8GiTzaJDKo0GQR4PsPBqZb9vweDgjElrgc6DMp0EqnwZBPg2y82lEtv65fcXjgaCkbwPJgSqvBuHL43ZeDb4Xls/9ML4T9TCQn1+DZH4NUvk1CPJrkJ1fI58W7BHJEaccwYw6+Dwo822QyrdBkG+D7Hwbzw2VPSLhvN7Pt0Ey3wapfBsE+TbIzrfBunLNeAvLz7dBMt8GqXwbhK802vk22NqP9bkFMAd8HpR5N0jl3SDIu0F23o1T8x55uWDNvu6SB1XeDYK8G2Tn3cinv7kFULPPgzLvBqm8GwR5N8jOuxHvmiE2xc+7QTLvBqm8G4Sv+th5N/K5CxV0zT7/ybwbpPJuEOTdIDvvxmPloq3tc5/Mu0Eq7wZB3g2y8248Vm7cgl2ifPy8GyTybsxfSp1XWZBjj2155+1ZUWYJR+clTNZcVc2ogX0nJsl+5paclYYeCR7vLeGiJUHZIIANTN7L54Yp37aEtnuct4TJmpUNAsqx+51r5ts4YH2P75YwUXNUOkfQ2ea7c+fl3P/5Wv3E4cySvu5R6h6V7hF0t+937BZk3t/j8dCg3z2+W0JFC5KyQQIb2Pt6XOO583LfwpklfRskaYOkbJDABibf8Z2WzDEqH75JAL3g8d0SKlqQlQ0y2MDku8wxKh/ZgoxzwOO7JVS2QNkAVzL73PYjW8AtyhV6weO7JVS0oCgbFLCBzXc7KiZzrArfrjj3OWZJ3wZF2qAoGxSwgb3Pd2LaZQtyg3Hg8d0SKlpQlQ0q2MA+x+W9Tl4HOGIkwIrkcd4SKlugbIDjyea8XWPmqAlcPT2+W8JEzU3p3kB3m++OrobOHt8tYbJmpXNDDey7DU3UnBuMOI/vljBRc1c6d9DZ5Du2cuYz7IA1+zp3qXNXOnfQ2ea7XWPmiIFgtMDjvCVUtICU7gS623F559aEbEHuMNs83ltCZQuUDQhsYJ/fsh9/bgrw36cFbr6OJRRbcOfrWGVBjtn/54ZAES3IPUFJ1wZB8t+dt2OVBTn2fY0mWsAtyv0ZB26+jiVUtEBxXwDuM/N1nBZk3uvmyIJEUNK3geS/O2/HKgtyzLlw7ijw3YSgW+BzYJAceOflWGVBjn1fY4/EcweBbwLASPQ5MEgOvPNzrLIgx7TBuXtQRAsyQQt8DgySA+88HassyLHvYzTRAm5Rhnns5utYQmULlA0SyrFtwDXLOwnPbYhR0ufAIDnwztuxyoIc+y7CZuAzDnhcYAt8G0gOvPN3rLIgx7JBOdlS+C/0v89/QfLfnb9jlQU5lu5PzV/dC5Cnm79jCZM1K52B++z8HVxzOflaYPX1eS9I3rvzdayyIMfWmXbNrDPW7OssOe/O17HKghxb5/YHWyD62ee8IDnvztexyoIcW+cgai4Na/Z1lpx35+lYZUGOrXPgGvdfsLbPeUFy3p2nY5UFOabOm22fFmDNvs6S8+48HassyDF15prLGWlPCZ/vguS7O0/HKgtyTJ25xtMCWMN8rguS6+78HKssyHnVueua3fwcSxjWfOfnWGVBzms/b64v0D9ufo4lTNZ86xw/KMfUud81PyPMzc+xhImaFb9F4Dc7P0fZHkTZFF3Ae3LzcyxhsmalM3CbnZ/j1Mw6w46Rm59jCRM1K16LwGtmfg6oee8cAi27eTiWMFmz0hk4zc7DcV6CIR7jz3x283AsYaJmxWcR+MzMw/G8BHNaADr7XBYll915OFZZkGPvzzVZM84qn8ei5LE7D8cqC3IsnSuf+JNVs6+z5LA7D8cqC3JsFv2OrNMCrNnnsCg57M6/scqCnDeduQUFdkHdvBtLmKxZ6VxQA0vnune/uAWiZp/DouSwO9/GKgtyzPnMN3AbtwBr9nWWHHbn21hlQc6bzqfmD6xhPodFyWF3vo1VFuTYZw9cYzNq9nWWHHbn21hlQc7bm7NccwQCdPNtLGGiZsVhETjMzLfxvHKbrJp9nSWH3Xk2VlmQ8/r2HLcAa/Y5LEoOu/NrrLIgx35jcM9jHmmwq+Hm1VjCZM1KZ+AwO6/GqXmfZhSYVW4+jSUMa77zaayyIMecz1vXUzPwk5tPYwmTNd86JyHHZJJ9flI+pHX2OSxJDrvzaayyIMdew5qsGdvqc1iSHHbn01hlQY65hm2dz3xODxm4+TSWMFGz4rAEHGbn0+CaeT4XODNw82gsYbJmpTNwmJ1Ho+6RxS0QNfscliSH3XkzVlmQY49trpnXb6zZ11ly2J0vY5UFOebY5u9y4P6Gse1zWJIcdufLWGVBjt3PQdRciKCEr7PksDtfxioLcmydG9fILXhK+ByWJIfd+TJWWZBj9zPX3LTOPoclyWF3noxVFuTYOpOsGc6E3PwYS5ioWXFYAg6z82M8NXJOCNDZ57AkOezOi7HKghxTZyb888oYlPA5LEkOu/NhrLIgx/w+nxqbUbOvs+SwOw/GKgty3vKVc83C2j6HJclhd/6LVRbk2DrzmD4vpkEJX2fJYXfei1UW5Nj9zLHcuwVobZ/DkuSwO9/FKgtyzLEd75ph3fY5LEkOu/NcrLIgx9SZo8hPzc+67ea3WMKw5ju/xSoLct50Lvtco0Bb3bwWS5is+dY5f1COrfOuOfJIe6zt5qtYwkTNisMycJidr6Lss5ujM4xtN0/FEiZrVjrDl8fOU3F0jbx+Qz/7HJYlh915KVZZkPOqM9fcCUr4OksOu/NSrLIgx9Z515iCrtnnsCw57M5LscqCHHsPUNaMLOHmpVjCZM1K54RyTJ35FRdePbFmn8Oy5LA7L8UqC3Lsc+oiag44q3wOy5LD7rwUqyzIMeMUzjuBRs0+h2XJYXdeilUW5Jj9zFEhnO1b1OzrLDnszkexyoKcN525BQVHhs9hWXLYnY9ilQU5ts58cnJeaYQSvs6Sw+58FKssyDHH9q7xaQFY2+ewLDnszkexyoIc+7wqyZrBi3XzUSxhsmalM3CYnY/iqXn3N0R9uPknljBRs+KwDByW7XPJHfV9as6wevocliWH3fknVlmQY69hxDVqa/scliWH3fknVlmQY+p8auQWYM2+zpLD7vwTqyzIedM5VF2zm29iCcOa73wTqyzIsecz39rnjNYEJVydi+SwO8/EKgty7PzC4bL2M7bd/BJLmKhZcVgBDrPzS5yaM/9NUMLXWXLYnVdilQU5Zj/zl+L0M5TwOaxIDrvzSayyIMeez+fEe9MQjDCfw4rksDtPxCoLcuyz2Ca+kgW+bm7+hyVM1Kw4rACH2fkfzsl355pBZ5/DiuSwO//DKgty7LPYc/qrzp/d/A9LmKhZcVgBDrPzP3DNfP6cIKrDzfuwhMmalc44Um0Oq/LMPUHEkpvvYQkTNSsOK8Bhdr6Hp8agre1zWJEcdud5WGVBjq0zv12qIxzc/A5LmKhZcVgBDrPzOzyRDfeLsbOEr7PksDuvwyoLct50fiJaoJ99DiuSw+68DqssyLHfaz01bp3B2j6HFclhd16HVRbk2Dqztc87rU8Jn8OK5LA7r8MqC3LsfuYam7a2z2FFctid12GVBTn2m6TyTdoTG4e6+zxWJI/deR1WWZDz9jbtEwvJ73WCDXwuK5LL7rwOqyzIMRllR5zy27T8Vm2BkefmbVhCsQV33oZVFuTYb9OeyNNdc4ESru5V8tmdr2GVBTm27hyZeF7FfUr4fFYln915GlZZkPP2Ji1H3yZYVd38DEuYrFnpHFCDt3jfpwVQwuezKvnszsuwyoKct7doOQ60butXPlHjjCHwbXPzNKxKZIuULSJq9h77HHQv+NxWJbfd+RdWWZBjnunxvtl5ORR09rmtSm678y6ssiDHjrkhQcl174tX2Bd38y4soaIFit8q8Judd6FG+VpqhZMXN9/CEiZrVroDv9n5Fh7djw2eEj6/Vclvd56FVRbk2HFle4wno799fquS3+78CqssyHmN+946V9iRd/MrLGGiZsVvFfjNzq/wvIYbdD/7/FYlv935FVZZkPPWz4+1QWef36rktzu/wioLcmyd27Wmndh3KOnrLjnuzrOwyoIcU3e+UbgjkiuctLl5FpYwUbPiuAocZ+dZOFbnkxh4PcHNs7CEyZqVzsBxdp4FfgX5fEEgLtjNr7CEiZoVv1XgNzu/wtPPjUcclPB1ltx251VYZUGO2c/pzCqls5tPYQnDmu98CqssyHnbZ+H3d5+RFsQXBVdXN7/CqkS26LZFA46z8ys8Oz/3K8ijhM9xTXLcnVdhlQU59lvzJGyBO/ZuPoUlTNasdAaOc/IpcEwO75/DvrmbT2EJEzUrjmvAcU4+hVMzv4qLNfs6S1678ymssiDn7S1i3sXOEP3l5lFYwkTNitca8JqdR+GpMWhr+7zWJK/deRRWWZBj68xvDid5ZgD7524+hSVUtEDxWgNes/MpcAt4Zxf3ydx8CkuYrFnpLuS86V74NSR4DcPNo7CEiZoVrzXgNTuPwvPqMZ9aYM2+zpLX7jwKqyzIsd+a5pFmWNvntSZ57c6jsMqCHPvMIIlzEjwzcPMoLGGyZqVzRQ3scxIe2+el56eEz2tN8tqdP2GVBTl2P5+TmW/NELHs5k1YwmTNSmfgNDtvwqnxtACs7XNak5x2501YZUGOvZbJUymhs89pTXLanTdhlQU59tvC/ILzacFT"} |  |  | - |  | - | -
[14 empty] | {"index":129,"total":402,"filename":"Advanced_Project.ifc","data":"Ay5Z6dH/8aYrkMfs2xen+qAh+SYs8JYiwsB8zBoi0nGP9aT4pivw1pDRrjhyT8AvEgqgH8ObvdfoDxrYuSvgvaqAH2PUY0kjrUpP8I8qD0Afm2/kMCeZpoy3BX8rYicfg2Ti6TzG6JH7Ad5TRDwgdA2hcLPya7wjdwMgwN/3UcA6G/Hu9PqB1oszXNlgm+17ddAsdPV35F4AxLnjAFdJwFdDQqjEzTkQgi7yMU7LiL/auWtyL8AvoyeSj2lY516ABS+z3PDylfnohUQsE6xG2GY7lMFPP2f7/xN6z3nkbgDUG1xsXxZbiri08xy0olcR+AoVBGCTjM5cR+4G+GX8lMoLghnl/4Re7By5F+C9IUFS9r+cEGPY+J3kkTsBEImPAQcnUSPSqLcYWEG+Y/9AZbTeEmH/Zs/UkTsBflnEAFI+KmnUzSg6ghy5F+CXRaz6y+G/3w8Tumg4ci8AwsdhkRxSOt0Q93MCm6JUjDKccYD/LsfGKf5xPassMG/oqn5F4XnHm5pAVY93y72F8a4+R3AFtEDM1zd7hAeVKlS2cYLvqjVQOPWx3KNZd5Ch3ISuEGW8/PY282be+X3/kbsAPEm8AvYd01o00A5e+lEvrvDObUcEvJ9DvBEW8n0cuQvgt50fQ1wBtjjwNoRSfOkZ35RKfTl8dkqvG1EIFz3dWgH414eNn27watm4kG99A4ycNuQZ6o23XfXhLYQ5IPaC9wH7VqOYKMm33nGDCzasNh2Ouq3IdeSC6In/F26Qk88yuSegnvp86uq6HD2m3v8XL1caawzu3mI7QgDZyss9Ab9MQxCzIfVSowl3qnTuCEDXKICikAvoXYOnftDvWsGxhGWJF/D7dtJTryN3BCwfbIXqY/w8O8D+vDZ92zdYZW44LhAaQBwSN+VftQQiD5l8zseftQS+0MS0AP1ZSyCShkMp/6YlUL45wpTiX6UEEkAvfExZir8oCXxRhJ8hdP5ZSeCLU1soyb8qCQTs7LZxKf+qJBCZv7RDnPkjgV+SrFhZ1MKXACv0cvDMHwn80pbxAHLmLwN+U3cAVnbBA3+osdKKe74FDLzWFlhZH9cIP5CdRRrP/GnAL6XEBRre1fqBfgdWmZL8a5/cWFkINJlyxV/65DXJowk2AdB6sJP4fIsYQBSUL9s9wNqnOO5A1JdJ8WMI3BjAOhmCUajeuQcAQZbQdENYTXMpbDsMvKMG7deLm72+oRLaEM/cAfDbCIpMWZovb5ED4uu+b3bwqPdTCOSa7MCNOR6V4Q3chu1roUjj8y1ywA1IKV6Yy4WEY8hu4GHhZg/HEEzBRQqQ8hTEe+YugLfurseQHXrO3tNYg6m33wIHXpvy8JmzrfCQwsNEZt+ZuwOwTbu14+b22hWfFO9ftx1teVFqQby1pUbyUpJ/Xs0AqsWrdOxpQvdTZ+4RqOHyMMD9KNROSyfiW/ycvS/bj5f2A1HspT6T4c3mTUgAQSXQO9paKQ8UaoMibQ30QNDojufCOHNRii+9g7hEvFeRfrbR/ZLhrYdlaEv4UeW8rihpFX8jD0C0F+rcF53GC1mAdoCwC6zVcuLmt8rQ+ACggf5GHnjvHRyY/KgteO61kVV+5k6Bs2oT4B52O5rcwVoXHRCycGSCjNxx3S6S0/DMfQIVJgPz1K4X5Tjf+DHMALe1n+pDVjwnRAAB+XPP3Cfwm21hCKeEgJhBUYNSfOmbE08BIRu4dEPfp0zBszeYFkvBy68FLx4xpynJt3XN1wIriBnsMF23R5elXa3ABAaxD5aF8JKROwWwVJ51AGlbKncxhHRCzRmHBwgi+Fg/ECnC4zz3CiA+AKu1QsDk29KvmNqKlPbuKsqOqjNxC0BkZ9v1hA8TAOefAR74FVRPbZn4BW7tb1h/Ws6vC6D1KwKerpTODEcIsRk8LD0qM+mbcCj2VshEovMCUCq8/ngP+F3I/aWUiWvg4eh5/22HHngIfCkIFNxlgJtE8ZJn5g5o0EncE8Ix8X1/pt8loxQztSfcsPpEgbzM0ZrPVy1bC3wp0mUOEOwKmQq2fhJ3ANrbZ+xWV3C165JP4A6Fr2eprff8wOgF0Zl4A7AIYC65MYJQ7+tGDnJCa4GfV2uSVU78BISBdNPPxB8QybcNrhrIt/moSfwBXrJPffqLh/zLNWh2PJvFYd236FpGuHMVAgWqnOJf46FRSFz67SsGBL1KPzN/wK8s3Zd6Z3JCy4q7xwUXgdLioXWt4DbIUV7DHPzSYj5I+cL0zKADBW4yvML15Uy+F4nF8lGeIQfgBtl8F6n+0HZH7EVZ5cRj/taQEL1ywwK7B6WYzBtwnMo1MdxG05CkyG4hSTxEoiQz5boLkolDgS+429dDg7J9B0NzQ/6f4Du/Ir+fZEriAuhcUV+ycXEysBDygpUMMtCZgYh9PWWkd+L9PSKMfaFAlM1OKWbIe2Jt7vsAqtjeqp3pcDIRtMxW2zzJpEO8Mn4CwlzZ8Grv5wvfWfvYt/sdr9BPOOOfJBNfALzgn6rB4Ia41GHD+M6z6vP4Qik+gU806EFJZig1RM+gg2uo0PXygwCetZR4YYmS4mVGoSST+eLzypdoOPOw/00InpwkTBZKct49qocvuLsfW4qvZTPSXQzfVUrxN2gKsQe/wmupQ5LTf+NCrj5w3d469DvB7SXFDMlRWuwzcCX9beoTlmV5TTPwYAdsntDCn0GLvsrIhUy10i+kH4SYy9lCqB545d5Cn/GGxHDVRXM6O/4v8AP60PUi1EixWG39rvZzviwZd1BPiKH5TnT6uNEeftjZlVJDasRP/jBMDiGqiyeZ2WTX/Npxn3wM7MqrlElTZmABhXNaEVm4IkDwJ7Irj9o7B14UQSTG1ydaeLLjv9ccV3rFf3LeOMyHXVkny6G4VPBJGRTWSnL89wUJ1xs7njmC3PgT4ZV1mANsg4tICFrQqMwgAxts+R2RpDus3O8ZnQ/z5PAPvQKI0ijE2kujXhG58tIu8y13ReySj2BOMtv4G6PVDQ8/Bl+DksiVNc4LIXgHFPYQPUpJZmwuNx2hW4CXfj2g5gFX1okDXYyC1RjSIZRispDtuEnaZDtr5fv75htceSXpRzDEUFkRshxLcvhviFb4k/3IUOR7Vdu/ZQho5iSnfz+1fRCD4i3vBekL+AOulGszhA8bEQwnnRRKcvz3zf9Tr8bwymGVny9u5dU5iC73yQ16Fdc732Ugs4Q4FNEy0I237wgq2riS038zfnqg0LVSBrxbDXfCzQgiMBZy55bk9A+6cUUrCTzC+4B3a0nCP1UdSGThluT0DziEjxE3ZiGAt3QpixvvVivuc3ODHuIGsRBKMps7DSa2+eJ9kYO/YGJfr885yQx3O+Wcfb2153QymN2FYMO7HkRfT84cadHSM/9j4/pc/hkwZ9gvEX/mMxJcdVookuN/ZJJt53e995d6Z+f/SE6TryRh/uRJJl3io/YDpUi4Aa832AFzVseiukGAkeT2Iq25GVoAJi5AiAAiXvtCoJzVEFNfH6FFCDkg2ruS878P4Po6eoVv+lIoZiJZbUgf0gtiQwuE3SjFZLrAwPWy4MzqC97+leLGKaouFGBakuP/FcJkBZGUCDj4co5u6/ezTxpAGVngVjKnG4/962Um7y/Jmb8jZ3CjcXRx3iBD/ZUkrdzJmT9QkI5BSXd/qWx26G8UJEizyTUBv7TR83pnp345QLGpkUw18uhbG/2lkJn70rByY4cReA9+bvXti7Qj9SEupCj2/QSMh5NMZsvig9snKjAOxz6Om5dSSuIA8B6pG/MJm2fZn1JqFYi8HveilDViG9Y6JfnCf9oXKCmd/UVXEKF+KWSy9yu2PATwQRZCG6wJT+RBt8ST9vqm2c/pWEX2jdyEknkAfHn4XIryPmeb4m+DFslyiaF9dpyj8JBNORpSMg8AKFXoFoFmt+2cJNYz4SSh0vssPZK9BmgorQ1vm3SZsLTSgS6JByBSqmxgkh3f3cOlTLyZEPKBypmPeB+c90VcQyuV+ord9xlbK0slVjzzZqrCHX7gkdm+NUBMRytZqRX3aQDbD56QjSueOWg2RbChG4sLLhnbneaFVoIqwjWI0DE4yLKoiiT+gJt8hdF0BY7jSkrBV9ig64kkD5xI3TI7obZDSc67Z8c9W315u9ujt25upQI1cJ5Xkngm7RblsTMpRTKygBU8kMNDVOAkrJUSAnUKx2BtywNP6AQsUeNBlHkE/PTqtgME1qFa0lIUCEbBVXilqIAaQTxqI5kxSRwCvFpu0lLEG6FjwzVzHZU4zXuSCo8zzfCUK1AZYpC0Mihmf8+d8jJ3MtLgLqsbdogZ390q6HfY0AKFOK4d1xDSei0OZionmZoCiyd5AG4H1+DEFIhvsGgdShwC901cWfRYdKj4/vVgikKxJHEINDjFhjF3KfsMVkFMkkqZeAQiMmXYb/eXemcugUZM8VGMVwjD+4/tpd6ZS0CqIO+Bt6PLTTpjqyAvZGoVFLiB8ZTnwVQ9TI7rgVzla0CRgEWkJXMJVOoDCAIGYca2ZOxu1kNpDeF9SBKHPSAxfHGhUmbvARbzlQ1CkedWbIBprfZdcWrKDC2AO2coY+OOqzRKZyeH4HiGJHccvn0n2cD3oSSTfafTZ/CE4LqO/N4d0w5PwYMVRnIAJbH2ByBx0UgHeuITwC02XqLCdSH9wTOExQASMV+lWo/7Tqbgt1N4hGQvAjZffquAs++le+mvSxvfRK6mLMCQAJFz8raTxQksiH6AXIX/fGvhd51vsm+wXY4qmwSdzxOXoZRk5ur0JBRyp1KFjtp+e/FNcJ90PQWFYCYcrQc9U5H0RcAzeXZrLAlZK/zC/9teQvhMwAvYpXBwpGTeAR+SUCRawa1bGge0yhRWmfmrjFvBQ3Dc99FsTHwDoFNA4+PYoRU+rJTHywBKfAOAU3hl/PiEZ2P7NSbxHNv/WSVJXn2De6AqtUdiAZL5BqqJ7scO8WYqMqxrbwtb4hvwoYaWQohE1Qi/UgRoEbKURx1AQGlgM8Z7GkowW9Y2CFgg/Ni359If5xQ8ZjgRYH3NG8Ak8O9XHj+Jb6BNxU1QxQYv+oe7WOIbcPsCDhA3dRFx347LiB+DKN6yXgpmoDoVHPVZWViab+A//+N//n//8z/+4z//5V/+L8hm+MZ3/Xm2P6X9SQ3WXAD/z7/+93/7j//9X//2v/7bf/zvf/+//6Ul+vP5r8/zS71/+S/tB7QW2DItQc/Rrj9XG0tgW1oCW0IJ2gmeSkC3YmLTNrhzbH/urU2k/f1ofy/t735av/7eSr5zSfO2sthWNrQVRQ74NjUr6dFyPFpJ6DbbjxFZzp4Y56zLdxsp0YZ1mbbRXeeWM2kC6pLW2ROLOX/XWckf5hvgLGdZY51p3vlqn+a8xjqvQ51p39N1XufW2qXNDXo7p2te5zXWeR3qTHcFuk3rrGccadzaW17nLdZ5G+pMN4a6Tet8j7Cztzp9kdd5i3XehjrTGVz3+dju/XuOY3vP67zHOu9DnckK031a557jcc97+iKv8x7rvA91prswPxhNR1jLeZ/M5yOv8xHrfAx1pksZPaZ1Ln1WySTnvM5HrPMx1JkukPWcj+09rp7kPNMzr/MZ63wOdaYzgZ7z+dxy7vOa5/OZ1/mMdT6HOpO9q2W+hn3tLPS+QEte5xLrXIY606MeLfOxvcf5TJaVlrzOJda5DHUmHTS3Pd5Wz73PZ+pnyesssc4y1JlkP1Wmde4jTCfrtuR1llhnGepMHjrVaZ37rCp7n9f0RV5njXXWoc70EFzndlzPua8kZPBqbr9ptN90sN+U7Ded22999Twn63Zut2m023Sw25TsNp3bbfeOIX3noC/yOkc7TAc7jGlANrfD+gg7bRjbltthFu0wG+wwIzvM5nbY3vq5l2DnsqZ1tmiH2WCHGdlhlthhvc77MKsst8Ms2mE22GFGdpjN7bC7n7s1xGXN6xztMBvsMCM7zOZ2WF8171WU6pzbYRbtMBvsMH65ZXM77K7rpLVzO8yiHWaDHWZkh9ncDuvzuM9rsoYst8Ms2mE22GEsCGxzO6x8nbe4n3M7zKIdZoMdZjxH5nbYXddu/e70RV7naIf9/5T9zbK0OLM2aJ5ODbY9BvI/GJa19aAm1WXddf7H0iKWXNwe7h5Z356szHw3CBcgbgTBdacchi+U300O+x7DTliirznmsDvlsBty2F3nsL2f75RJ7j6H3TGH3SmH3ZDD7iaHibf4+Xv5+Q1Xy7vPY3fMY3fKY/jpgbvOYzt7+igKtfd57I557E557IY8dtd5bKffTx88v3zJ43ify+6Yy+6Uy9C+vJtc5vtb8hHX57I75rI75bIbctnd5DJPCJ6/seW+5pjL7pTLbhwnylzGa4bneSvi799xib7mmMvulMtuyGV3mct2y+dfzYzX2T6X3TGX3SmX4U8i7zKX8UlfNUNG6XPZHXPZnXIZfgv4LnMZj++W4bzuc9kdc9mdctn95rLno9JlzbJa9JR0wxJdzc/KoOX5r181P8vCen7W7HOJt8ASXc3PymLLV2oZai5zmdc621w14xJ9zWes+TuXDfhs1vzn8ny+79AyH1Bzm8uelcWWU80nVFDmsnkWrV6m3NttLntWFlr+zmXPsrCeumbv7TsfYW0ue1YWW041D6i5zGXPg7vQ269T/8hRbcsUa/7OZc+ysJ56DJN4PuN+bnPZs7LYcqqZoOY6l1331/mMS/Q1c6z5O5c9y8J6ypoPb1nyfm5z2bOy2HKqmaGCMpftcdt7/YCW21z2rCy0/J3LnmVhPfV+Pr9ahv3c5rFnZbHlVLNAzXUeu1cv3+sq+X4X7vmIbduyxpq/8xh+APf56Hs5bnvNPoalhDCX7GvXWPt3HhugNI+jzGM7IewxDXq9zWPPykLL33nsWRbW8/OadezzG5boa7ZY83ceG/AK3/MF4B8tv1cQqLnNY8/KQsvfeexZFtbz85q1twC3ta/5ijV/57Fx4MhUz5NdFsZv35L3mF9/190Rr3tSpvXf10wAs//15aDv2lz3bFSo4DvXDfhe5Pzn8nhZ+Z3X/Rr8pG0u0ffdHfvuO9c9y+71nHWuW7NevJ7EwWfbnmf/XctnzHVnynUn5LqzznVmcW+8d8lzibbmM+a6M+U6MObHWee6NffE636N3+ckj3DYthxz3ZlyHQDGzzftqpa9l73XB7bc1xxz3ZlyHfxG6vk6X9nbq0Xxv7Cf+1x3xlx3plx3Qq47y1y3zypv+Z3pe1627VuONadcd0KuO+tcR76f15FGUHOf686Y686U607IdWed6/zI0jOfVX2uO2OuO1OuOyHXnWWuY6FYM8NZ1ee6M+a6M+W6E3LdWec6H7t89GSouc91Z8x1Z8p1J+S6s851a9aD14wfG9Tc57oz5roz5boTct1Z5zpe+3c9GwpnVZ/rzpjrzpTrTsh1Z5nr9jVrn1XQcp/rzpjrzpTrTsh1Z53rLm/Zsw1ua19zzHNnynPgP42zznPm+9dyb/d57ox57kx57oQ8d9Z5zq9R3jKeh32eO2OeO1Oeg18mPD+2/3WE7TEMrhh9njtjnjtTnjshz531/Jrv58u3AFvua4557kx5DgiJcdbzaz5qUjF69jnsjDnsTDkMvos0//lnDlPK16o+h50xh50ph52Qw0adw/yKMfaVA5Zoax4xh42UwwbksFHnMM8ke9y+YYm25hFz2Eg5DH6P+bzkXLZMMXtiy30OGzGHjZTDBuSwUecwr9Vbhhw2+hw2Yg4bKYcNyGGjzmF+pfBrFlyrRp/DRsxhI+WwATls1DlMv1pmqLnPYSPmsJFy2IDxf9Q5zFv2hCBQc5/DRsxhI+WwATls1DmMdiJIV4zR57ARc9hIOWzA+D+aHHbGluGObvQ5bMQcNlIOA19r/nOdPb3ldXYZttzXHHPYSDlsQA4bdQ7zK4VfLeGKMfocNmIOGymHwY/O5j/X+9ni9Rlr7nPYiDlspBw2IIeNOod53t6ZBJfoa445bKQcNiCHjTqH7Zr9GIdju89hI+awkXLYgBw2fuewfa8B53Ofw0bMYSPlsAE5bNQ57PpKQ4bb2tccc9hIOWzgeuocdn3dV8Fsxehz2Ig5bKQcNiCHjd85jCgfYX0OGzGHjZTDBuSwUecwb9G3AEf6PoeNmMNGymEDctioc5gng2vP1MASfc0xh42Uw0AQeDjSX3NDOwnesERbM8UcRimHEeQwqnPY9ZUAPRH6Fvl1269p+95z/e/vFzVmC20fUcxtlHIbQW6jOrf5k7rb95KfE9BXfX6jmN8o5TeC/EZ1fvMWfQt87hn3b5/jKOY4SjmOIMdRneNWi+JPNW7JW9DnOYp5jlKeI8hzVOe51aJvgaynHAIz/tTnOoq5jlKuIzjbqcx1b4veF5S3oM93FPMdpXxHkO+ozHeynqfJegdE1hMfeeXDQX3Oo5jzKOU8eHdoUJnzdovraZecZ96CPu9RzHuU8h5B3qMy7+0WfQvW0w74OuOgPvdRzH2Uch98uO7Bv6st2C16X1Degj7/Ucx/lPIfQf6jMv+9La4tWGMifDl8UJ8DKeZASjmQ4JpLZQ58W1x9sUZvWVlJ1h2nrHshWTlC1hxH2NI+N1LMjZRyI0FupDI3ykpt/n6cwB0o9bmRYm6klBsJciOVuVHWfYGsq7vAHAf1uZFibqSUGwlyI5W5cbfI3tvYcl9zzI2UciO8RztvEsuaLz8u/DiAlvvcSDE3UsqNBLmRyty4jzw/EhXOxj43UsyNlHIjvilCZW6UdQcq7FsAx3afGynmRkq5kSA3UpkbZc3n7C0ILfc1x9xIKTfis2wuc6OwH2GSepv73MgxN3LKjQy5kcvcuFv2/Uy4rW3NHHMgpxwI71MOLnOgrLkNUf97wxJ9zTH/ccp/DPmPy/y3R5I9hhEs0dcccx+n3IfvpnCZ+3bNVz7CuM97HPMep7wHPsHgMu/t89mPcbgD5T7nccx5nHIe3tVxnfN89PRrFozb3Oc7jvmOU75jyHdc57vdIqVxm/tcxzHXccp1+PyG61wnX9drrLnPcxzzHKc8x5DnuM5zPnb5foZ5Wu5zHMccxynHMeQ4rnPcHj39WgXHdp/fOOY3TvkNvikzuM5vavEq6VdN8WMdt6Tvg5jjOOU4nDvhOsfZd8vQ+30u45jLOOUyhlzGdS7bo+lOjLBEX3PMZZxyGUMu4zqX+fjtW2C4RF9zzGWcchlDLuM6l3kv7/Ec9nOfyzjmMk65DOcFuc5lfuXwjIIt97mMYy7jlMsYchnXuWy3aPkK0ucyjrmMUy5jyGVc57K9n/2qCcd2n8s45jJOuYwhl3Gdy/zux69heO3qcxnHXMYpl+FsizS5zOL1Gu52pM9lEnOZpFwmkMukzmV+n3Xt8RyWaGuWmMsk5TKQdIfUuez6us+C/Sx9LpOYyyTlMoFcJnUu8xZ9C+BuR/pcJjGXScplYAYOqXPZvnL8/dU1N6VrZkjXLJmut5HV56wuXHPfNzG/ScpvAvlN6vx2eT73ROFHpqerPQZ+3T353RTsxT7vScx7kvKeQN6TMu/pmtPS4X2GS/R9FPOepLwnkPekzHu75b3XsOW+5pj3JOU9vCeSOu/dftz48QG93ec9iXlPUt4TyHtS5j1dc1dvb9+wRF9zzHuS8h7mBynznq7ZU/UZxJdVnEv0Nce8JynvCeQ9KfPertlnT+HNfOnzncR8JynfwffxhpT5zseFfTZiy32+k5jvJOU7gXwndb67LI482Nt9vpOY7yTlO4F8J2W+0/UrhH1sw++bpM93EvOdpHwnkO+kzHd7tN3HNvR2n+8k5jtJ+Q4TqpT5zo9prxkc9rlEX3PMd5LynUC+kzLf7bPKa8aRpM93EvOdpHwXrlR1vrvp63yGmvt8JzHfScp3AvlOynznx7TXHo7tPt9JzHeS8p1AvtMy3+0jzHsdftOlfb7TmO805TuFfKdlvttH2G5ZYIm2Zo35TlO+w2ue1vnOn/yt37co/KZL+3ynMd9pyncK+U7LfPeex36VzAlB+5ynMedpynlhPWXO2wnBx3EYv7XPbxrzm6b8ppDftMxv+5p17PMbluhrjnlMUx5TyGNa5zF/urUzCtTc5zGNeUxTHoOv6A6t59+8xb0FuK19zTGPacpjCnlMyzym60merudjSn4lwSX72mMu05TLFHKZ1rnMWyTf31JsQd8HMZ9pymcK+UzrfEYWW/YtIRjj+pymMadpymkKOU3rnMbe++Yt//2FmUHt85rGvKYpr8Fn9J8P8/7agvWUQ9m3AJfs+yDmNk25TSG3aZnbdoviWyLFFvR9EPObpvymkN+0zm9CsWXfEni/UvscpzHHacpxCjlO6xwn3rL3Bez/PsdpzHGacpxCjtM6x+n51TLU3Oc4jTlOU45TyHFa57g1l6HrSYDCEwDtc5zGHKcpx4G8OrTMcbvWXTsu0dccc5ymHAeK5dAyx5mPtitJ2gH7uc9xGnOcphyncN2wMsfZShLm4/6aQbKBS7a1W8xzlvKcQZ6zOs+p72ffghuWaGu3mOcs5TmDPGdlnnt729ZfaLnPcxbznKU8B9+fH1bnuWvv57XfT1iirznmOEs5ziDHWZnjbPj+9pah5j7HWcxxlnKcQY6zOsf5fbhnG8Nt7WuOOc5SjgtHap3jVm43T88XLtHXHHOcpRxnkOOsnlfzWdH15iZec6zPcRZznKUcByblsDrHrdlMXU94wkjQ5zeL+c1SfjPIb1bmN+9l8zsGPML63GYxt1nKbQbXfatzm/ey9zo8vbQ+r1nMa5bymkFeszKv7RHEEyP8DsL6nGYxp1nKaQZXIKtz2h7D7nTlsD6fWcxnlvIZ4NrD6nxm8Xw2mGOyPpdZzGWWcpnhOVLmsn0e7/MaRs8+j1nMY5bymEEeszqPXX6dNj+7YIm+5pjHLOUxw7GwzmPrGbH57Afcf1ufxyzmMUt5zCCP1Z6C72db8y12YMt9zTGPJUdhGI7CZR57R5DV2/D0svcTRvQTRvITBvgJo/YTzO9B1c9rOJ/7PBY9hJE8hAEewqg9BD+P3xx2wxJtzdFDGMlDGOAhjNpD2Pt3ZVHcz72HMKKHMJKHMMBDGLWHsNPQbplgib7mmMOShzDAQxi1h+D5a/c65LDeQxjRQxjJQxjgIYzaQ9j7d4/buERfc8xhyUMY4CGM2kPwHPaOonCE9TkseggjeQgDPIRRewh+Hu8xDN796D2EET2EkTyEAR7CqD2Et2VKV4zeQxjRQxjJQxjgIYzaQ/BEsPM2JIPeQxjRQxjJQxjgIYzaQ3hr9usz9Hafw6KHMJKHMMBDGLWHYKeFmoG6Gr2HMKKHMJKHMMBDGLWH4NfnfZcDz3R7D2FED2EkD2GAhzBqD+FNQXeuuc9h0UMYyUMY4CGM2kPwcXtvATyV6D2EET2EkTyEAR7CqD2Edz+f6frcewgjeggjeQgDPIRRewj7WrWPMLhW9TkseggjeQgDPIRRewi7RX9TAs/nPodFD2EkD2GAhzBqD2HfW3jih7zdewgjeggjeQgDPIRRewi7RR/L8FrV57DoIYzkIQzwEEbtIfgd3b5KYhrqc1j0EEbyEAZ4CKP2EHbLPi+muERbc/QQRvIQBngIo/YQfEZO1fMYwRJtzdFDGMlDGOAhjNpD2PvZcxgcYb2HMKKHMJKHMMBDGLWHYEfMnnjn3nsII3oII3kIAzyEUXsIvn/3PCj2dp/DoocwkocwwEMYtYdg/lTJ9/OeifW7nX22+UgTRx6/FzXvO6y177OY45KnMMBTGLWn4Ftu6+mUrWdEBm8d9q7CiK7CSK7CAFdh1K7C26JvyV1sQd8HMdclX2Hc2Jd1rlvvt74try2Bb+n0zsKIzsJIzsIAZ2HUzoKt52O2nhGZeJ/gtvd9EHNe8hbGjeupc956QmPrudjeAnhW1LsLI7oLI7kLA9yFUbsL17p/uzzvwb1M7y2M6C2M5C0M8BZG7S3Ymnu6PO+tsxPv/Hp3YUR3YSR3YYC7MGp3wdZTKlvPywzHzD73RW9hJG9h3Hilq3Of31n4nSRkoN5bGNFbGMlbGOAtjNpbsDWrfR3e+3Ck9bkvegsjeQsDvIVRewvmdxZ+jYT32XtvYURvYSRvYYC3MGpvwS4/stYWXNhyX3PMfclbGOAtjNpbMJ+X8SsRPIntvYURvYWRvIUB3sKovQXzebf1TNBubLmvOea+5C0M8Bao9ha8ly+fKXjfqKPeW6DoLVDyFgi8Baq9hd3L3uuG29rVTNFboOQtEHgLVHsLflb5GAYzs9R7CxS9BUreAoG3QLW34GfTPp8P6O0291H0Fih5CwTeAtXewjuGecsnLNHXPGLN37mPwFug2lt4z+N1Xr9Pnan3Fih6C5S8BQJvgWpvwTwp+r2NQsttXqPoLVDyFgi8Baq9BVPvZT/CsOW+Zoo1f+c0Am+Bam/BE4L57IjBfm7zGUVvgZK3QOAtUO0tvCPI6u33WRH13gJFb4GSt0DgLVDtLVw+R6E+lkFvt3mMordAyVsg8Bao9hb2WbXTELbc1yyx5u88RuAtUO0tXH735JkER/o2h1H0Fih5CwTeAtXewm55PSe7BhxhbQ6j6CxQchYInAWqnQWv1bcgtNzmMIrOAiVngcBZoNpZ2LXuXodju81hFJ0FSs4CHXjNa3KYt7yvHLBEX/MVa/7OYQTOAtXOwh5JbCdBWKKv+Yo1f+cwOvBqW+Ywvzru63RYoq/5jjV/5zACH4FqH2HnbZ9vNR/HcQv62u9Y+3ceI3ASqHYSvOU9msIo2jsJFJ0ESk4CgZNAtZPgiX9fr2F/904CRSeBkpNA4CRQ7ST4FWNfLRWX6GuOeSw5CQROAtVOwm753FsAS/Q1xzyWnAQCJ4FqJ+Ft2Y+4E5boa455LDkJBE4C1U7CzqC7ZTjC+jwWnQRKTgKBk0C1k/C2LGks650Eik4CJSeBwEmg2knYsxZ+z4HnYZ/HopNAyUkgcBKodhJ23vYtUNjPfR6LTgIlJ4HASaDaSfAZG1tv+V4Dzuc+j0UngZKTQOAkUO0k7GvW8LMKWu7zWHQSKDkJBE4C1U6Cp949P2a4rX3NMY8lJ4HASaDaSdj71+fJsLf7PBadBEpOAoGTQLWTQJ5+5WsLzphN37kk/+8+y7EUowFnY5/joq9AyVegE0fv2i8d3kf+d7lZOIL0eS46C5ScBQJngWpnwVu8htd+F1vQ90HMdclboBOPu9qZX29cecu+JRe5qLv6Zs23X35HyTB+9PkvugyUXAYCl4Fql2G37FuiviXmWwRr6Psq5sHkNBA4DVQ7DW9ffPrmHD57InCO9bkweg2UvAYCr4Fqr+HiL+d4ZSUi3IK+D2IuTG4DgdtAtdvgLV/iLd+wRFt7dBsouQ0EbgPVbsMlu7fXXiBYoq05ug2U3AYCt4Fqt+Hy+3nyIw5a7nNhdBsouQ0EbgPVbsO1zs5rPWu43ic81LsNFN0GSm4DgdtAtduwa11P/ODtI+rdBopuAyW3gcBtoNptID/fPS8IttzXHHNhchsI3Aaq3YZL3Gwvju0+F0a3gZLbQOA2UO02vEeYH9uwn/tcGN0GSm4DgdtAtduwR1P2YxuX6GuOuTC5DQRuA9Vuw7t/z3yE9bkwug2U3AYauJ56nk7iKIrXst5toOg2UHIbCNwGqt2GfQWR4nzuc2F0Gyi5DTTwHKlz4T6fizGsz4XRbaDkNhC4DVS7DXsEkTvv5z7fRbeBkttAA4/UMt/5+fy2DDX3uS66DZTcBgK3gWq3YR9hq+UwkvR5LroNlNwGAreBardhjyRaXCX7nBbdBkpuA4HbQLXbsK/PWlwx+lwW3QZKbgOB20C127BTkWdTgfO5z2PRbaDkNhC4DVS7DTuDyt4CWKKvOeaw5DYQuA1Uuw27ZbZUc+82UHQbKLkNBG4D1W7DvmL4/mbc1rbm6DBQchgIHAaqHYb3CNt3BLBEX3PMYclfIPAXqPYXLp898Zmj980L6t0Fiu4CJXeBwF2g2l24fMb/8pYJluhrjjkseQsE3gLV3sLlz5J8hvDCbe1rjjksOQuE97a1s3D5DIH3Njzl6H0Fir4CJV+BwFeg2ld4a3VRGVvua445LLkKBK4C1a7Crtln+g2X6GuOOSx5CgSeAtWewj621/OVcIT1OSw6CpQcBSIcF8ocRnv/Jq+cej+Bop9AyU8g8BOo9hPes8r3N9Tc57DoJlByEwjcBKrdhLfFO7fc57DoIFByEAgcBKodhLfFdXeD15g+h0UHgZKDQOAgUO0g7LHr2iMKLNHXHHNYchAIHASqHQTyOch9PuO29jXHHJYcBCI8O+sc5jX7iILHdp/DooNAyUEgcBCodhD8bPKWw1nV57DoIFByEIhw/K9z2L5iUK65z2HRQaDkIBA4CFQ7CG9vF1fJPodFB4GSg0B4vNQOwtvyTgiwRFtzdBAoOQgEDgLVDsLboo/bNyzR1hwdhPmv3zUz5LDaQWCfJ7+/RlEfVf0atv73ez3Bv4f/+99xcsMTv95PoOgnUPITCPwEqv2Eez1XvdezxvvAlvu+ivkt+QkEfgLVfsK95tHvw3LLfX6LfgIlP4HAT6DaT9i9v55u3PD0q/cTKPoJlPwEAj+Baj9h9/J68nPDPWjvJ1D0Eyj5CQR+AtV+wj285eWjwTxa7ydQ9BMo+QkEfgJxmd/u9dzkJv97whJ9zTG/ccpvDPmt9hP2WUW+n2Ec6PNb9BMo+QkEfgLVfsKu1Y8wmEfr/QSKfgIlP4HAT6DaT/Ajy8XGMJL0+S16CZS8BAIvgWov4fa5hr8nvOcw73Wovc9x0U2g5CYQuAlUuwlbqfT9jrX3OS66CZTcBAI3gWo3YZ/Pfn7De2+9m0DRTaDkJhC4CVS7Ce8Vo6i5z3HRTaDkJhC4CVS7CXtEGX4FgbOrz3HRTaDkJhC4CVS7CfuatVuGUbTPcdFNoOQmELgJVLsJPnq+LcN+7nNcdBMouQkEbgLVbsJ7Pvu1C2ruc1x0Eyi5CQRuAtVuwq51X0Fwibbm6CZQchMI3ASq3YRd86B0zerdBIpuAiU3gcBNoNpNWGPYHr8v7KU+j0U3gZKbQOAmUO0mvKlI0rHduwkU3QRKbgIJ7rU6j+0s6rXjEn3NMY8lD4HAQ6DaQ9hjmF+nIRX1vgFF34CSb0CCFdR5zGvdtcMR1uex6BtQ8g0IfAOqfYOden1/w3OQ3jeg6BtQ8g0IfAOqfYM3j+XRs/cNKPoGlHwDAt+Aat9g71+/SuJ+7vNY9A0o+QYEvgHVvsH9PXpCEux9A4q+ASXfgMA3oNo32DV7r2Nv93ks+gaUfAMC34Bq3+Bt2a8YUHOfw6JvQMk3IPANqPYNdvplP7ZxW/uaYw5LvgGBb0C1b/CeVXduuc9h0Teg5BsQ+AZU+wY76e/kD73d57DoG1DyDQh8A6p9g3s9v969DXm79w0o+gaUfAMC34Bq32C3uK+SUHOfw6JvQMk3IPANqPYNtju+RxQ/u76unvt48PN+/e/wvLv3ECh6CJQ8BAIPgWoP4V7P+G+327dTDnupz2/RRaDkIhB8h51qF8Fb9C242cX0G5Zs+yD6CJR8BAIfgWofwVu83THaUjpuQdsH0Umg5CQQOAnUOAl7v6/jxCWlsGTfBzHXJS+BwEug2kvwFm+3wLaUjlvQ90HMd8lLIPASqPYSXEa/17Pi211LuG/r3QSKbgIlN4HATaDaTfAWb1clt5SOW9D3Qcx7yU8g+B4/1X6Ct+hbcLuDF5bs+yDmvuQoEDgKVDsK3uLtPtqW0nEL+j6I+S95CgSeAtWegrfoW3C79Ql3V72nQNFToOQpEHgKVHsK3uK93tS43TlzMT1sSd8XMRcmV4Hgu/xUuwouJt+uTsJ7E72nQNFToOQpEHgKVHsKXqvXfsMzit5RoOgoUHIUCL4QT7WjcG+Hfvc6LNHXHHNh8hMI/ASq/YS9v9dbKjc8i+rdBIpuAiU3geBLWFS7CbdZ2M+ht/tcGL0ESl4CgZdAtZew9++uGVvua465MHkJBN8qp9pLuNdbC7t2+G197yVQ9BIoeQkEXgLVXsLb23fRcl9zzIXJSyD4SjrVXsJ7Pntvw/nc57zoJVDyEgi8BKq9BNfe7/XE777939eW3FubgzX1fRFzX3IUCL6eTrWj4Fuytwz6ovcTKPoJlPwEAj+Baj9h1X4ePqsCNfd+AkU/gZKfQPCVP6r9hHs94b8988I7JL2fQNFPoOQnEPgJVPsJb8u+/7HlvuaY65KfQOAnUO0n3H/P2d/ehncLej+Bop9AyU8g8BOo9BNmi15rEhSp9xMo+gmU/AQCP4FqP2HVfNyXn2W4RF9zzG/JTyDwE6j2E979e+f93Oe26CdQ8hMIvpVHtZ/wtuimHy7R1xzzWvITCPwEqv2ENYbB/saW+5pjPkt+AsF34aj2E95R9Mznc5/Pop9AyU8g8BOo9hPke9zGY7vPZ9FPoOQnEPgJVPsJe+y6d6/DEn3NMZ8lP4HAT6DaT3BN8D2fcVv7mmM+S34C4dcCaj9h1exH2PwLvd3ns+gnUPITCPwEqv2EtX/3sR32c5/Pop9AyU8g/F1z7Se8ZxXlmvt8Fv0ESn4CgZ9AtZ/w9nZxlezzWfQTKPkJhF8Bqf2Et+WdEGCJvuaYz5KfQOAnUOknQIs+kkAm6XNY9BMo+QmE3ymo/YTlFs6W/Uhzz5Bgybb26ChQchQIHAUqHQVv8Tz8K/dbD8QtaPsgegqUPAXCb680noJrgSS4JfMvbEGfz6KrQMlVIHAVqHYVthpI3hfrSIT3JXpfgaKvQMlXIPjKJjW+Au8W19/11dz3+6zUOwsUnQVKzgKBs0Cls+Atzr/fjiFuQd8HMbclb4HAW6DGW9h64Ilbch7wvkzvLlB0Fyi5CwTuApXuwtPSatE9lSQoUu8vUPQXKPkLBP4Clf7CefhX0zVswbNFsGTfBzHPJYeBwGGg0mE4j2sdB7yORLgz7B0Gig4DJYeB8PdOpcNwHrr2t52+BbBEX3PMc8lhIHAYqHQY3hbH2gJ4C7F3GCg6DJQcBsLfYJcOw2x5tXit3oarbe8wUHQYKDkMBA4DlQ7DrHG1zJZ7u89z0WGg5DAQ/hK6dBhmS6u31WvGJfqaY55LDgOBw0Cdw+DfIF9b4IImzDX2HgNFj4GSx0D466PSY5i9vsZ5H+PgGxi9x0DRY6DkMRB4DFR6DPPYXvtZ/S/s7z7XRY+BksdA+Pu20mOYLXmtSSGj3mOg6DFQ8hgIPAYqPYZ3DPOrK7xH03sMFD0GSh4D4Rtfpccwz2vy0XP9xSXamqPHQMljIPAYqPQY3vPZR5bQcltz9BgoeQwEHgOVHsPbso8skCB7j4Gix0DJYyDwGKj0GJ6zKNb8fnOaeo+BosdAyWMgfJux9Bjmsb1a3se4wBJ9zTGvJY+BwGOg0mN4WopXDhhJek+BoqdAyVMgfLOv9BTmfvb9a7nmPp9FR4GSo0DgKFDpKLw1i1+7bliirznmsuQnEL4JVPoJb4u+BfAduN5NoOgmUHITCNwEKt2Et7f3tQpb7muOeSx5CQReApVewntM+zEuuERfc8xjyUkgcBKodBK85VeDhetz7yRQdBIoOQl0YwV1HvP9vLcAWu7zWPQRKPkIBD4ClT4CJAK/PmPLfc0xjyUfgcBHoNJHgP27swks0dcc81jyEQh8BCp9BGi5GMP6HBZ9BEo+At14zatzmGfPnYZgJOlzWPQRKPkIBD4ClT7Ce5fDOf32PgJFH4GSj0D4lKP0Ed67G98CPDL6HBZ9BEo+AoGPQKWPAHd0lO41eh+Boo9AyUcgeNbApY/wtuhb8N7Zce8jcPQROPkIDD4Clz7C26L39vvOJ/c+AkcfgZOPwOAjcOkjnIfPo+0Mikv0NZ+x5u8cxuAjcOkjQNr1/Qy93eYwjj4CJx+BwUfg0kd4W96JH5foax6x5u8cxuAjcOkjQG/v3A1L9DWPWPN3DmPwEbj0ESDp+1+BJfqaKdb8ncMYfAQufYRnluJ/Yu1Qc5vDOPoInHwEBh+BSx/hSfZ+b/F9xeDeR+DoI3DyERh8BC59hLflfZeDLfc1c6z5O4dxOFLrHOYt252P7TaHcfQROPkIDD4Clz7Cm/B9f19whLU5jKOPwMlHYEiSXPoI0LInA2i5zWEcfQROPgKDj8Clj/CmoKs4ttscxtFH4OQjMFxtufQR3ivFlWZouPcROPoInHwEBh+BSx/hnZG7ipGkzWEcfQROPgKHK0/tI9CeE4rpV77O8z1b6f/uWwx7p81tHD0FTp4Cg6fAtadg+4hcW+JOCsM40OY3jq4CJ1eBIQdy6Sp4i/PvlyaIW9DmOI6+AidfgcFX4MZXcMPPr7L+xPaG46XNcxx9BU6+AoOvwKWv8LS0WnTLLzmG3DsLHJ0FTs4Cg7PApbMwW3bHMGzBGbe97YPoLXDyFhi8BS69hfNc9+Xnej52Yu19voveAidvgcFb4NJbmC3RalF8C2CJvuaY75K3wOAtcOktvC2u9yHO930I7r0Fjt4CJ2+BwVvg0luY275aXDMD8C157r0Fjt4CJ2+BwVvg0luYvbtaHmfu7T7fRW+Bk7fA4C1w6S2c53oKfa5R93xnu7j3Fjh6C5y8BQZvgWtv4TVEfAvchsIl+9pjzkvuAoO7wKW7MI8sW72+tgD3U5/zorvAyV1gcBe4dBdmy2s/r6vxSbC/+5wX3QVO7gKDu8Clu3Ce5L2dpDXu3QWO7gInd4HDuVLmvD2GrbcPzvedD+7dBY7uAid3gcFd4NJdmL1sPnqu8xqO8T7nRT+Bk5/AJx6pZc7b5/MeWaDlPudFN4GTm8DgJnDpJsBI4qMobmtfc8x5yUtg8BK49BKes+irZhi/+9wWHQRODgKDg8ClgzBLXS37MQ7zML17wNE94OQeMLgHXLoHT0vxyoEjSZ/TonfAyTtg8A649A5mS6uX15tUoeY+n0XngJNzwOAccOkcvDWTX7sIlmhrjs4BJ+eAwTng0jmAFn0LBJZoa47OASfngME54NI5eHt7X6ug5T6PReeAk3PA4Bxw6RzAuO3H+AlL9DXHPJacAwbngEvnwFt+xVvFJfqaYx5LzgGDc8Clc/Du570F2HJfc8xjyTlgcA64dA7eREB+fcYl+ppjHkvOAYNzwKVz8O7fsbMJLNHXHPNYcg54YAXlfNvbch7DeueAo3PAyTlgcA64dA7e7OlpCO5ye+eAo3PAyTlgcA64dA7eu5wzp9/eOeDoHHByDhicAy6dg/fuZt9nYct9zTGHJeeAwTng0jmAOzrPYTcs0dccc1hyDhicAy6dg7fFfYcHx3afw6JzwMk54IHjQp3DvEXv7QOOsD6HReeAk3PA4Bxw6RzMlvzY9lQE+7nPYdE54OQcMDgHXDoHb9r1lk/o7T6HReeAk3PA4Bxw6Ry8LftZNaDmPodF54CTc8DgHHDpHLy9LTt3wxJ9zTGHJeeAwTng0jmApO9jGJxVfQ6LzgEn54DBOeDSOXhmKf4n1k6wRFtzdA44OQcMzgGXzsGT7P3eIl0xeueAo3PAyTlgcA64dA7elr3XwxJ9zTGHJeeAwTng0jl4WxZKx3bvHHB0Djg5BwzOAZfOwZvwfX/LDUv0NccclpwDBueAS+cAWvbzGVvua445LDkHTHi8NDnMYst4bPc5LDoHnJwDBueAS+fgvVJonqHpnQOOzgEn54DBOeDSOXhn5DSPJL1zwNE54OQcMDgHXDsHrj2upP+m3/F1nvucgl/PXfmDrNq7CBxdBE4uAoOLwLWLcPkWqe+l7VPCkn1fxfyWfAQGH4FLH8FbnH+jTxm3oO+DmOOSk8DgJHDjJLg/6Xl9vd90+t67/O/a0vXuwLmeLePdbu8qcHQVOLkKDK4Cl67Ced6+BX9/xwljZp/7oqvAyVVgcBW4dBVmy+sIXr/uPG8YP/rcF10FTq4Cg6vApasALdPqbTiL+9wXXQVOrgKDq8Clq7D3797fF/R2n/uiq8DJVWBwFbh0FZ4jKhxhOG/WuwocXQVOrgITrqfMfeP4OuZv6O0+90VXgZOrwOAqcOkqPDV6L6/9DEdYn/uiq8DJVWBwFbhxFciPLJcRBZZoa46uAidXgcFV4NJVgP17pv3cuwocXQVOrgKDqzDXWh7bq7eXKxvGsN5HeFYWWk65D3wELn2EWfO60vh5/b6bzb2PwNFH4OQjMPgIXPoIcB5LGsN6H4Gjj8DJR2DwEbjxEfYRto80WKKvOea+5CMw+Ahc+giz1u/ehpr73Bd9BE4+AoOPwKWPACOJ+IgCS/Q1x9yXfAQGH+E50MtEsceu3HKf+zjmPk65D3wErn2EV2veZxcs0dccc1zyERh8BC59hH113COJ4RJ9zTG/JR+BwUfg0kd4MkhsGcfbPrdFH4GTj8DgI3DpI8CxLbnlPodFF4GTi8DgInDpIkDLnobgfO5zWHQROLkIDC4Cly7Cu5/vnEl6F4Gji8DJRWBwEbh0Ed797NkTrs+9i8DRReDkIjDjkVrnsJ0A/85n2Tkcau/zWPQROPkIDD4Clz6CJ4M9fp/wrl/vI3D0ETj5CMx4va/n4fZ1Ohmr3PsIHH0ETj4Cg4/ApY/gLb9OtFAe0/pcFp0ETk4Cg5PApZOwrxz7SgLX695J4OgkcHISGJwELp2EfcS9Ld+wRFtzdBI4OQkM36bl0knYY9k+27CX+lwWnQROTgKDk8Clk/Dm7jPn795J4OgkcHISGJwELp2Ec6ynVmM9tcInbL2TwNFJ4OQkMDgJXDoJb8vriR0+z+ydBI5OAicngQXXU+ay4Ylw1yywRF9zzGXJSWBwErh0EmaL3y3Dsd3nsugkcHISWHCvlblsrCfvw+dbIIv2TgJHJ4GTk8DgJHDpJLw1+/6GJzi9k8DRSeDkJDA4CVw6CV7rPLK2uQpL9DXHXJacBAYngUsnYdZ4Y8vzL7bc1xxzWXISGJwELp2E5yxavUy5t/tcFp0ETk4Cg5PAtZOwXNm5BXc+wvpcFp0ETk4Cg5PApZPw9G7sbXirpHcSODoJnJwEBieBSyfhPav8fMb93Oey6CRwchIYnASunYTlCMP5DC33eSw6CZycBAYngUsnwfev1x73c5/HopPAyUlgcBK4dBLecdt7HZ7g9O4BR/eAk3vA4B5w6R68I8luGXq7z2HRO+DkHTB8k5BL7+A5f9d5vM5reKukdw44OgecnAMG54BL5wCuUT6G5YTQOwccnQNOzgGDc8Clc/BeMfaYJrBEX3vMY8k3YPANuPQN3mvW2Oc3LNHXHPNYcg0YXAMuXYO35X0FgZr7PBY9A06eAYNnwKVn8La4twC3ta855rHkGDA4Blw7Bi6YXvY1jvsW7WN//e9rjmmsefKx3lYYfr+2ni0PeA+qdxA4OgicHAQGB4FLB+EcrkSuJ3njgrO0z3XRP+DkH7DiuVb//mD7lP4Xl+hrjrkuuQcM7gGX7sGs+Yx7AX5T1TsHHJ0DTs4Bg3PApXMw96/Xunob7hB754Cjc8DJOWBwDrh0DryXt6h34fjd57roHHByDhicAy6dg3P4/bj6X1yirznmuuQcMDgHXDoHcDZ5y3Bs97kuOgecnANWrKDOdez7eR1peGT0uS46B5ycAwbngEvn4D2yfETCs6rPddE54OQcsOJ6yvm2sZ5/75rhdwe9c8DROeDkHDA4B1w6B+/Ypd4ybmtfc8x1yTlgcA64dA7mse0jiY+eUHOf66JzwMk5YHAOuHQOnt5dtVI+q/pcFz0DTp4Bg2fApWfwXqv8rBJcoq05egacPAMGz4BLz2COlt6yX+8Flmhrjp4BJ8+AwTPg0jOYLft4fabe7j0Djp4BJ8+AwTPg0jOAa5Qf2ycs0dcc81zyDBg8Ay49g/cI22PYDUv0Ncc8lzwDBs+Aa89g7+d7pyZYoq855rnkGTB4Blx6BtvKfrMJLtHXHHNY8gwYPAMuPYM3h5mla1XvGXD0DDh5BgyeAZeegV8x3OR7+gCW6GuOOSx5BgyeAZeewZv8fNzGmvscFj0DTp4Bg2fApWfw9vLeAmi5z2HRM+DkGTB4Blx6Bm+tlnNY7xlw9Aw4eQZsOArXOcyvFPuaBfu5z2HRM+DkGTB4Blx6BnB19DEMzuc+h0XPgJNnwPh7pNIzeFveCQFq7nNY9Aw4eQYMngGXngH0dk69vWfA0TPg5Bmw4YjU5DCJLcMdXe8ZcPQMOHkGDJ4Bl54BtOzjN7bc1xxzWPIMGDwDLj2D90rhV0u8YvQ5LHoGnDwDBs+Aa89g38H79Rlr7nNY9Aw4eQYMngGXnsGbt71leK7dOwYcHQNOjgGDY8C1Y/DW7Mc4bmtbc/QLOPkFDH4Bl37B26JaOp97t4CjW8DJLWBwC7h0C94jzPb+hiX6mmMOS14Bg1fApVfwpqHdMtTc57DoFHByChicAq6dgt0yWz7C+hwWfQJOPgHjO9qlT/C2uLcAau5zWHQJOLkEDC4B1y7BTgY7jxEs0dccc1jyCBg8Aq49gj035C3DuN07BBwdAk4OAYNDwKVD8NrIOwHS/4Qt2tdt/+8+t/z3vxO8l9i7BRzdAk5uAYNbwLVbQGsLycWcbSlDX/X5LfoFnPwCBr+AS7/AW/QtOMmF67DtfR/EHJccAwbHgGvHYLU4/0bNOWxBn+eiZ8DJM2DwDLj0DLxF34L5d2vOsGTfBzHXJdeAwTXg2jVYLZ7kzvjSnMMW9Pku+gacfAMG34Br32DpzXML1nFwbs0Zluz7IOa85Bsw+AZc+warxfk3as5hC/q8F50DTs4Bg3PApXPgLfoWzL9bc4Yl+z6IuS95B3xhrihz32rxJPekt6UMW9Dnv+gecHIPGNwDLt0Db9G3YP7dmjMs2fdBzIHJP2C8P6z9g9XiuX49dtJ6Cka+ZesJMK3Rm9j7ytKW9l4CRy+Bk5fA4CVw7SXQel+K1LcIW277KHoJnLwEBi+Bay+B/EhduYIgT/ReAkcvgZOXwOAlcO0lrBZfd1hxW/uaY25MXgKDl8C1l0BbOvb9fcMSfc0xNyYvgcFL4NpL2EeeH4mMLfc1x9yYvAQGL4FrL4HWWw5EfuzjEn3NMTcmL4HBS+DaSyC/Ju4twJb7mmNuTF4C37ieMjfSeseAxp17u8+N0Uvg5CUweAlcewm7Zd4jECzR1xxzYPISGJNM7SWQX309jcHvknsvgaOXwMlLYPASuPYS9kiyxzDc1r7mmPuSl8B41a69hF2zFkdYn/eil8DJS2DwErj2Et7z2WuH/dznvOglcPISOIyFdc7b4/WZx+0+30UvgZOXwOAlcO0lvC1aHrf7XBe9BE5eAoOXwLWXsFve12uouc9z0Uvg5CUweAlcewl77PL9DG+p9V4CRy+Bk5fA4CVw7SXsFvdIgkv0Ncf8lrwEBi+Bay+Blr24rpLPVROW6GuOuS15CQxegtRewh5J6P5uWXovQaKXIMlLEPASpPYS9kgiOyHCEl3NEr0ESV6CgJcgtZfwjtc+lkHLbQ6T6CVI8hIEvASpvYTdy97rgtva13zGmr9zmICXILWXsK8Unkmw5TaHSfQSJHkJAl6C1F4CrVnSdYx7Inz6Apbsax+x9u88JuAmSO0m7Jp3H+ASfe0Ua//OYwJugtRuwj7S9nUaam7zmEQ3QZKbIAdWUOcxv9/yq+Z7tZTeTZDoJkhyEwTcBKndhLflfZbBEn3NHGv+zmMCCoLUbsJ7Z7evILBEX7PEmr/zmICbILWbsI9pTwq4n9s8JtFNkOQmyIFnaZ3HvMV9Zwctt3lMopsgyU0QcBOkdBPea5X/XU/6aD2joPVUm27/31eGuWC0bXObRF9Bkq8g4CtI7SuQfV1VBVpuc5tEX0GSryDgK0jtK9B6YkC39wGcA21uk+grSPIVBHwFKX0FaFl8r8ASfc1XrPk7twl4CVJ6CbO3V8uX72+CJfqar1jzd24TcBKkdhLY5+N3b+MSfc13rPk7twn4CFL6CLOlNbpe6+zDmtvcJtFFkOQiCNgCUrsIb82r198nRNJ7CBI9BEkegoCHILWHsM/zff5jy23N0UGQ5CAIfL1NSgfhGTm+RhJouc9t0UGQ5CAIOAhSOwh00dexfcMSfc0xtyUHQcBBkNpB2KPnPrah5j63RQdBkoMg4CBI7SCsY9prnr0tsERfc8xryUEQ+D6g1A7CPqu8ZtzPfV6LDoIkB0HAQZDSQXiOqK/zGWru81p0ECQ5CAJfDpbSQfBj2muPx3af16J/IMk/EPAPpPYP3iPMa8dt7WuOeS35BwL+gdT+wT7CdstQc5/Xon8gyT8Q8A+k9g9oPVum9X46v8+OpfcPJPoHkvwDAf9Aav/gPY999MwJoXcQJDoIkhwEAQdBagdhXzH2OA693uex6CBIchAEHASpHYR9zbr2+Q1L9DXHPJYcBAEHQWoHYbe8MwrU3Oex6CBIchAEvlQjtYPgLb5bAPu5z2PRQZDkIAg4CFI7CMfhLdP6u9yiA3q9z2XRQ5DkIciJ40STy/zsWpLW+jpD2II+n0UXQZKLIOAiSO0iHOu5uLfMu09wC/o+iDkt+QgCX7iQ2kc41vNx3xJe7wzw+/VD6Z0EiU6CJCdBwEmQ2knwLWDvg90nuO1tH0QvQZKXIPD1Nam9BG+Rd1/ceQv6/BbdBElugoCbILWbcKzn4t4y7z7BLej7IOa45CfIwPWUOY7X2wnsta/n5ceA46DPc9FRkOQoCDgKUjsK7H2wntD7FvD75XfpPQWJnoIkT0Hg+yNSewq8ZvZ5/SKO3/elpPcUJHoKkjwFAU9Bak+B10wv+/V+zRSx4Rb0tcd8l1wFgd90S+0q8Op1Hl477Pc+30VXQZKrIOAqSO0quALN7lwSttzXHPNdchUEfk0otavAa8aX13MVJujtPt9FV0GSqyDgKkjtKrBfdXkfcbBEX3PMd8lVkIHrKfPdbnHN+LJCzX2ui66CJFdBwFWQ2lXYsvk+wnBb+5pjrkuugsBvBqR2FfbZ5SPKhUv0Ncdcl1wFAVdBaleB2Y+w1fL77F96V0GiqyDJVRD4xZXUrgL7WaU+ssAo2ue66CpIchUEXAWpXYXdIvkW4Lb2Ncc8l1wFGbjX6jznvey9TtDbfY6LroIkV0HAVZDaVdhn0+UtwxjW57foKkhyFQRcBaldhfd8pjSS9K6CRFdBkqsg4CpI7Srw5ft51w5LtDVHV0GSqyDgKkjtKvh47VcOnGnvXQWJroIkV0HAVZDaVdhXivVUA68Yvasg0VWQ5CoIuApSuwqsngj2eQ1L9DXHXJZcBQFXQWpXgdezo90yPKXoXQWJroIkV0Hg7QWpXYV9hK37cTyreldBoqsgyVUQcBWkdhV4zXbtVAR3xb2rINFVkOQqCD7ZrV0FT0FsPpLcsERfc8xhyVUQcBWkdBXeEWRnT6i5z2HRSZDkJAg4CVI6CXCErZbh6WTvI0j0EST5CAI+gtQ+wk78u2Xc1r7mmMOSiyD49kLpIrz3GN7rcK/ROwcSnQNJzoGAcyC1c7D3r7cMb5f0zoFE50CScyCEo3Cdw/yY9qQ/YD/3OSw6B5KcAwHnQGrnYF8xNGfP3jmQ6BxIcg4EnAOpnYM9bnMxevY5LDoHkpwDAedAaudgt7ivHNhyX3PMYck5EJx/r52DN3ve+Xzuc1h0DiQ5BwLOgdTOwZuG7pxJ+hwWnQNJzoHgE9vSOXjTrh/jiku0NUfnQJJzIOAcSO0c7P1sZzqreudAonMgyTkQcA6kdg523vaRBK4Y3Oew6BzMf001Qw6rnYPdss+XDGy5rznmsOQcCM631c7BPsL8igHvs/TOgUTnQJJzIOAcSOkcPGdRbBnubnrnQKJzIMk5EHAOpHYO9vm8syfU3Oew6BxIcg4EnAOpnYM9Q2P5XrJ3DiQ6B5KcAwHnQGrnYO9nv6ODq2TvHEh0DiQ5BwLOwfznn3nba4dnvL1z8Kwstpxqhmte7Rww+fwIpWtV7xxIdA4kOQcCzoHUzsE7Xksat3vnQKJzIMk5EMxztXOwa/WWseY+h0XnQJJzIOAcSO0c7LHLZ6cu3Na+5pjDknMg4Rwpc9ixnmsfFPPYO2Pjo+q+fvuIE+dXfCYP3jbpnQSJToIkJ0HASZDaSfAtZ/+7nlIfN+y1Ps9FL0GSlyDgJUjtJXiLvN4JOPZf2II+10UvQZKXIOAlSO0lHOvNOW+Z918YJ/p8F90ESW6ChOOwzndrC3g9qT/2X9iCPudFP0GSnyDgJ0jtJ/B6S+HYf823CJbs+yDmveQnCK6n9hNknTOyxkxZZ7G837CV3lGQ6ChIchQEHAWpHQVZz83l8JZvWKKtPToKkhwFAUdBGkfBW3Z58YCa+9wXHQVJjoKAoyC1oyBrxJH1rFgg6/aOgkRHQZKjIOAoSO0oyBrzZN23wxf5pXcUJDoKkhwFAUdBakdB1qgr6+lFOML63BcdBUmOgoCjILWjsKXzw3sbWu5zX3QUJDkKAo6C1I7CPqu8ZUhfvaMg0VGQ5ChI2Gtl7pP1/FvW02h5pQ7pHQWJjoIkR0HAUZDaUZD1BF5W7hP4dUDvKEh0FCQ5CgKOgtSOgqysK3Lns6rPfdFRkOQoCDgKUjsKu5e910/o7T73RUdBkqMg4ChI7SjI4S3uswuW6GuOuS85CgKOgpSOwtO7a/+uY5zhrOpzX3QUJDkKAo6C1I7CO5KsXoe55d5RkOgoSHIUBBwFqR0FH7f9ynHC2wW9oyDRUZDkKAg4ClI6Cu8VY/hVElruc1p0FCQ5CgKOgtSOgqx5mX1W4XnY57PoKEhyFAQcBakdBVkzvLLeJhPs7T6XRUdBkqMg4ChI7SjsY9uvz/AeW+8oSHQUJDkKAo6C1I6C6B6vPY/BEm3N0VGQ5CgIOApSOwqegva4feK2tjVHP0GSnyDgJ0jtJ+zz2ccwrLnPYdFPkOQnCPgJUvsJQn6l8CSILfc1xxyW/ARR7Ls6h9G+UngegyX6mmMOS36CgJ8gtZ/w1noXLfc1xxyW/AQBP0FKP+Gtdff6CUv0NcccltwDAfdAavdg1+zpF55S9e6BRPdAknsg4B5I6R68Le4xDI6wPodF90CSeyDgHkjtHuzr8rGPcViirznmsOQeCLgHUrsHu0XfAshhvXsg0T2Q5B4IuAdSuwfv/pW8n/scFt0DSe6BKJ4jdQ7jfXXMo2efw6J7IMk9EHAPpHYPdss7IUBv9zksugeS3AMB90Bq92Af0zsZwLHd57DoHkhyDwTcA6ndg13rziYwkvQ5LLoHktwDAfdAavdgXx33nAEcYX0Oi+6BJPdAwD2Q2j3Y2ZPzXWzvHkh0DyS5BwLugdTuwe5tKWruc1h0DyS5BwLugdTuwZ6N2kkfau5zWHQPJLkHAu6B1O7BbtG3AGru3QOJ7oEk90DAPZDaPdjXKsmpt3cPJLoHktwDAfdAavdg521vGe5ie/dAonsgyT0QcA+kdg923t4jyQ1L9DXHHJbcAwH3QGr3YI/X3jL2Up/DonsgyT0QcA+kdg/2keVzRDA31LsHEt0DSe6BgHsgpXtwXOse8vQZV9qJP17Djj1HGLOqz3Ks5U9497p3EyS6CZLcBAE3QWo34VxffPTvLvp3GE94i7D3EyT6CZL8BAE/QUo/wVs8/FuU53orJWxBn+uioyDJURBwFKR2FLZcv77o6N/h9O+ByOVzjX5crb13YW19H8X8l7wFAW9Bam9B1lMtWc+YxFzEhuOkz4HRXZDkLgi4C1K7C7Kes4v6lsDe6XNgdBckuQsC7oLU7sLqfd8bB74p2bsLEt0FSe6CgLsgtbsg6zmsy+dhf/c5MLoLktwFAXdBandB7IxHGo4HfQ6M7oIkd0HAXZDaXdhHmtd+Y8t9zTEHJndBwF2Q2l3YR5ats/DvWfPc33Ck9Xkw+guS/AUBf0Fqf2Ed44d/jUfCNve1xzyY/AUxPG6qPPi2uN45EHjLofcXJPoLkvwFAX9Ban9hH2F+xMGbWr2/INFfkOQvCPgLUvsLclk8xqHl3l+Q6C9I8hcE/AWp/YXzrXX19g1LtDVHf0GSvyDgL0jtL+xR1LcAfs3d+wsS/QVJ/oKAvyC1v/C27L0ONfd5MPoLkvwFAX9Ban9B1lsIu2a4cvT+gkR/QZK/IOAvSO0v7Ov1tbcAluhrjnkw+QsC/oLU/sJODN4yjN+9vyDRX5DkLwj4C1L7C3s/X5Sulr2/INFfkOQvyIXrqefl/HxeV8vz9lQFR1qf46LDIMlhEHAYpHQY9vm8z294P653FSS6CpJcBQFXQWpX4W3xTrms9xQkegqSPAUBT0FKT+FNhH6WrTdwBNJz7ylI9BQkeQoCnoLUnsKbTX0L4Czr81l0FCQ5CgKOgpSOAowolK8gfT6LfoIkP0HAT5DaTxCVr96GY7zPZ9FNkOQmCLgJUroJb4v7GoYt9zXHfJa8BAEvQWov4XTV5HQhG5foa465LDkJAk6ClE7C27Jr4DgW9bks+giSfAQBH0FqH2G3vPLZgOcrvYsg0UWQ5CIIuAhSughQ87bYYYm+5pjLkocg4CFI7SG8NfsW3LBEW3P0DST5BgK+gdS+wVvzsv3get37BhJ9A0m+gYBvILVv4C3r4d48wRJ9zTGXJd9AwDeQ2jfwlmVdLTVsa19zzGXJNxDwDaT2Dd6afSyD/dznsugbSPINBHwDqX2D1fLhX5JSeEuw9w0k+gaSfAMB30BK32C3uHsdrtO9byDRN5DkGwj4BlL6Bs+x/NfylWduet9Aom8gyTcQ8A2k9A12zWL5+tz7BhJ9A0m+gYBvIKVv8LbsfyGT9L6BRN9Akm8g4BtI6Ru8LWu+Pve+gUTfQJJvIOAbSOkbQMs+lwA19zks+gaSfAMB30BK3+BYX58/1neani2BJfqaYw5LvoGAbyClb/C2/JcMDvxGVe8bSPQNJPkGAmaAlL4B1Hz6FsASfc0xhyXfQMA3kNI3gJrNtwCW6GuOOSz5BgK+gZS+AdRsvgWwRF9zzGHJNxDwDaT0DXbL/qVH/B1g7xtI9A0k+QYCvoGUvsFucW8Bng19Dou+gSTfQMA3kNI3eFuWNSspcIT1OSz6BpJ8AwHfQEvfAFpef993AbT3DTT6Bpp8AwXfQEvf4G156YDwO33tfQONvoEm30DBN9DSN4CWfQ74hCX6ms9Y83cOU/ANtPQN3pZ1PWVgbLmv+Yw1f+cwhS/FaekbQM1/LcMdt/a+gUbfQJNvoOAbaOkb7JavdWxf77s92rsGGl0DTa6BgmugpWvwtrzkTJhd0t410OgaaHINFFwDLV2Dt2VaNeMR1uYwja6BJtdAD6ygyWHkLa4tgPO5zWEaXQNNroGCa6Cla/C05PdTf38vbLmvmWPN3zlMDxwXyhy2W1zvo44DervNYRpdA02ugYJroKVr8NZ8ee03LNHXLLHm7xymB56dZQ57e3vdxV64RF+zxpq/c5iCa6C1a/DWbH6dhiX6mjXW/J3DFL6ipKVXsO9uxuH3V3CEtTlMo1egyStQ8Aq09Are+yqf+72x5b5mizV/5zAFr0BLr+Btec3InRf0dpvDNHoFmrwCBa9Aa6/gx0yc9l6BRq9Ak1egBx6pv+fD8kyc9l6BRq9Ak1eg4BVo7RX8mInT3ivQ6BVo8goUvAKtvYIfM3HaewUavQJNXoGCV6C1V/BjJk57r0CjV6DJK1DwCrT0Cn7NxGnvFWj0CjR5BQpegdZewY+ZOO29Ao1egSavQMEr0Nor+DETp71XoNEr0OQVKHgFWnsFP2bitPcKNHoFmrwCBa9Aa6/gx0yc9l6BRq9Ak1eg4BVo7RX8mInT3ivQ6BVo8goUvAItvYJfM3HaewUavQJNXoGCV6ClV/BrJk57r0CjV6DJK1DwCrT0Cn7NxGnvFWj0CjR5BQpegZZewa+ZOO29Ao1egSavQMEr0NIr+DUTp71ToNEp0OQUKDgFWjoFv2bitHcKNDoFmpwCBadAS6fg10yc9k6BRqdAk1Og4BRo6RT8monT3inQ6BRocgoUnAItnYJfM3HaOwUanQJNToGCU6ClU/BrJk57n0CjT6DJJ1DwCbT0CX7NxGnv"} |  |  | - |  | - | -
[14 empty] | {"index":128,"total":402,"filename":"Advanced_Project.ifc","data":"KMjAURDiKMico3CvJHd/U1lzOyxyFGTgKAhxFGTOUbhz3nWoc85RkMhRkIGjIMRRkDlH4d6ren9TP+ccBYkcBRk4CkIcBZlzFO4c792SvsjtsMhRkIGjIMRRkDlHoRNRu01y26J9hbmt4W5B9JJSr+T2WuQtyMBbEOItSMJb6L6Gdm8mnaPCX+Z2W+QuyMBdEOIuyJy78OTYmY1lUoK8DaL9NvAXhPgLkvAXrpy3ptKzdf0gabcdIr1trpJp97+1NwSinW707I05r0Eir0EGXoMQr0HmvAZptyHaPERK/tec0yCR0yADp0GMZ8bU7tPus2g3fkJvv3I+g0Q+gwx8BiE+gyR8hpvcNcs5r3O0+wYugxCXQaZchq3rB+nSW5v6Obf7Io9BBh6DEI9B5jyGm8zWPUS0p+VcBYlcBRm4CkJcBZlyFbYWhbB1DSWhlzk5V0EiV0EGroIQV0HmXAVt/ay9zhSbm3MVJHIVZOAqCHEVZM5VEO3zuudMq3Bu90WuggxcBSGugsy5CtrvUZovSulWI+cqSOQqyMBVEOIqyJyroEuvq/Y17/kit/siV0EGroIQV0HmXIW2ut6rbZhVud0XuQoycBXEeI7M7b67n/vYppxzuy/yFGTgKQjxFGTOU5B2Wy39dppHWG73RZ6CDDwFIZ6CzHkKfe+6c37eS2jOU5DIU9CBp6DEU9A5T0Hsaz6HnLM6a+Qp6MBTUOIp6Jyn0PeoYxt2DM15Chp5CjrwFJR4CjrnKdwWQ59VRmVN7TmNPAUdeApKPAWd8xS6TaJL+d4xNOcpaOQp6MBTUOIp6Jyn0PfnbpsQZVJznoJGnoIOPAUlnoLOeQq9n/sqqivlnNphGnkKOvAUlHgKOucpdPvrbvXnBl5znoJGnoIOPAUlnoLOeQrPCtLXbco5tcM08hR04Cko8RR0zlPoVlBfRWnd1pynoJGnoANPQYmnoHOewm0ZtJOCLtTPqR2mkaegA09Biaegc55CX8Oe1ZPqnNphGnkKOvAUlHgKOucpdFvksYZo9UztMI08BR14Cko8BZ3zFJ41rJ9JqaypHaaRp6ADT0GXkM7r/mw6jrDUDtPIU9CBp6DEU9A5T+GeTb3uSiMstcM08hR04Cko8RR0zlO4Z5VM5nNqh2nkKejAU1DiKeiUp0Cnm6XbY/RFXmeNdf62w3ThnWdqh7U697MGnzE05ylo5CnowFNQ4inolKdw53iXoFCdUztMI09BB56CLrzPT+0w7a9KymiH5TwFjTwFHXgKSjwFnfMUbu9FL8ETzaM5T0EjT0EHnoIST0HnPIXuH+k2CTG3NecpaOQp6MBTUOIp6Jyn8FhBOsk5r3O0wwaeghJPQec8hcci6D4D+iK3wyJPQQeeghJPQec8hb5LSuk+IqUv8jpHO2zgKSjxFHTOU+itfVtFZG/nPAWNPAUdeApKPAWd8xRuj9x9yqGxndthkaegA09Biaegc57CXdd+cl+ozrkdFnkKOvAUlHgKOucpPL6CbhVRnXM7LPIUdOApKPEUdM5TeHIuY51zOyzyFHTgKSjxFHTOU+jex9tfIjSfczss8hR04Cko8RR0zlPQ9fuMQXXO7bDIU9CBp6DEU9A5T+HJWfu8pi/yOkc7bOApKKnh65yn0HeKO2eeVbkdFjkKOnAUlDgKOuco3HuUdt8B7ZK5HRb5CTrwE5T4CTrnJ0i3DLbbF/h8kdthkZugAzdBiZugc27CvV739dtobOd2WOQl6MBLUOIl6JyX0Ot658w2SW6HRU6CDpwEJU6CzjkJ3TPTCdhEvNacj6CRj6ADH0GJj6BzPsIRfUMb6W1qzkXQyEXQgYugxEXQKRdh68pSt1dKOOe0zpGHoAMPQYmHoHMewtIJ13u/r6KcczsschB04CAocRB0ykG46/x4ajjnvM7RDhs4CEocBJ1yEO6c9b7nfFbPnIOgkYOgAwdBiYOgUw7CU+f+Io7mc85B0MhB0IGDoMRB0CkH4cn5Plc9syrnIGjkIOjAQVDiIOiUg0D9fHvY6Yu8ztEOGzgIShwEnXIQKOd+l0s553ZY5CDowEFQ4iDolIPQc+43ZVvh/sntsMhB0IGDoMRB0CkHYWt6bXfOpJqmOf9AI/9AB/6BEv9Ap/yDJ2dr52dew3I7LPIPdOAfKPEPdMo/eHKWtm7zqpfbYZF/oAP/QIl/oFP+wZ1z02nzotIIy+2wyD/QgX+gxD/QKf/gqXNpI4z8YTn/QCP/QAf+gRL/QKf8A6pz8w3xSpLbYZF/oAP/QIl/oFP+AfVzy5nOkjn/QCP/QAf+gRL/QKf8gydnbbOq0NjO7bDIP9CBf6Ck56FT/gH1c7OGDqpzbodF/oEO/AMl/oFO+Qc9Z+R4/blTnXM7LPIPdOAfKPEPdMo/eHJuL6IWau2cf6CRf6AD/0CJf6BT/sGTc2/tjXNO6xw5BjpwDJQ4BjrlGDw5tz1rIa9UzjHQyDHQgWOgxDHQKcfgybm9K1meF8yacww0cgx04BgocQx0yjGgfm5kU9rRc46BRo6BDhwDJY6BTjkGlHNv9Y2+yOsc7bCBY6DEMdA5x2Bp56lmdwfLIOcYaOQY6MAxUOIY6Jxj0C39XoKDVpI9t8Mix8D/OtSZe23qD7vPGG0lOQ4a27kdFjkGOnAMlDgGOucYPDn38xWVNbfDIsdAB46BEsdA5xyDO+c20o6dRlhuh0WOgQ4cAyWOgc45Bs+JbusnO/oir3O0wwaOgRLHQOccg7eTe84x0Mgx0IFjoMQx0DnH4O3knnMMNHIMdOAYKMX/6ZRj8HpyzzkGGjkGOnAMlDgGOucYvJ3cc46BRo6BDhwDJY6B///3c9V4ct9zO2yPdtjAMcC3lM7bWXJ2cs85Bho5BjpwDJQ4BjrlGLye3HOOgUaOgQ4cAyWOgU45Bq8n95xjoJFjoAPHQIljoFOOwevJPecYaOQY6MAxUOIY6JRj8Hpyz/kFGvkFOvALlPgFOuUXvJ7cc36BRn6BDvwCJX6BTvkFryf3nF+gkV+gA79A6c28TvkFryf3nF+gkV+gA79AiV+gU37B68k95xdo5BfowC9Q3uen/ILXk3vOL9DIL9CBX6DEL9Apv+D15J7zCzTyC/yvQ51pn5/yC15P7jm/QCO/QAd+gRK/QKf8gteTe84v0Mgv0IFfoMQv0Cm/4PXknvMLNPILdOAXKPELdMoveD255/wCjfwCHfgFSvwCnfILXk/uOb9AI79AB36BEr9Ap/yC15N7ziXQyCXQgUugxCXQKZfg9eSe8wg08gh04BEo8Qh0yiN4PbnnHAKNHAIdOARKHAKdcgheT+45f0Ajf0AH/oASf0Cn/IHXk3vOHdDIHdCBO6DEHdApd+D15J7zBjTyBnTgDSjxBnTOG3g7ueecAY2cAR04A0qcAZ1zBt5O7jlfQCNfQAe+gBJfQOd8gbeTe84V0MgV0IEroMQV0DlX4O3knvMENPIEdOAJKPEEdM4TeDu55xwBjRwBHTgCShwBnXME3k7uOR9AIx9ABz6AEh9A53yAo73eOVvs8Ur2ds4H0MgH0IEPoCf32pwj1XJsJdhIu01zPoBGPoAOfAAlPoBO+QBb13jqdVfu59wOi3wAHfgAenKvTf1ha4ufO5e77s8XuR0W+QA68AGU+AA65QPcddY2wkj3QHM+gEY+gA58ACU+gE75AE/O/cUpj4zcDot8AB34AEp8AJ3yAZ6c23z2sUNf5HWOdtjAB1DiA+iUD/DkfPYXSzS2czss8gF04AMo8QF0ygegOvf+prLmdljkA+jAB9CTx8vUDntGWDtr8F6V22GRD6ADH0CJD6BTPkDPeWtEmo00NzXnA2jkA+jAB1DiA+iUD7A1rbY7Z9Id1pwPoJEPoAMfQIkPoFM+wJPz9SZuK2Rv53wAjXwAHfgASnwAnfIBnpwve3sjJVvN+QAa+QA68AGU+AA65QPcOTctxq3wXpXbYZEPoAMfQIkPoFM+wFPn7huiL3I+gEY+gA58ACU+gE75AE/O1mYVxSbkfACNfAAd+ADK/pYpH4D6uf1JPsCcD6CRD6ADH0CJD6BTPsCTc/MBkl685nwAjXwAHfgASnwAnfIBqJ8v23OlM0bOBdDIBdCBC6DEBdApF6DnjByvP+kVdc4F0MgF0IELoHxWmXIBnpzba+qVfAY5F0AjF0AHLoASF0CnXIAn5+4zMKpzbodFLoAOXAAlLoBOuQB3zkuL8Fppf865ABq5ADpwAZS4ADrlAlA/t5xp9cy5ABq5ADpwAZS4ADrlAlA/t7FNEQI5F0AjF0AHLoASF0CnXIAn57W3OpU1t8MiF0AHLoASF0DnXIClRSs2uztYBjkXQCMXQAcugBIXQOdcgG7p9xKcdFOWcwE0cgF04AIocQF0zgW4zxjtpuzkfs7tsMgF0IELoMQF0DkX4Mm5nWbpHiPnAmjkAujABVDiAuicC9BzPqyfq2g+53ZY1PXXQddfSddf57r+T873yY6+yOsc7bBB119J11+nuv73fVXnMB8txuygO5xc31+jvr8O+v5K+v461fffOvX6aFGqrQRb4V0zt8uizr8OOv8arKz5u30NJegl2gqd6HO9f416/zro/Svp/etc7//QO8f2Z2sL5RKkbRB1/3XQ/VfS/dep7n/PcetE2KPpVIUS5PZa1P/XQf9fSf9f5/r/Lcdegq3TUbV5eLT5ilX6abj9+73/rpeY6prbeZEboAM3QEktXOfcgCfn7pugtsrtvMgN0IEboMQN0Dk3QEuve2sL2rdzboBGboAO3AAllVmdcwOOFvV69vgezjm38yIvQAdegBIvQKe8gK1zWrXHltO5LecFaOQF6MALUFLu0zkvoNf16DHH5MXOeQEaeQE68AKUeAE65QVspc+JY/TD5LwAjbwAHXgBKtxrc12MHmvcI8jID5PzAjTyAnTgBSjxAnTOC9D9y/dE2gE5L0AjL0AHXoCSHqbOeQF3XWVS59zOi7wAHXgBSrwAnfMC9Ox17SOMVpLczou8AB14Acr6GnNeQFtdn9WWZ1Vu50VegA68ACVegM55AXc/792jyznndY523sALUOIF6JwXoEdfQY5xhOV2XuQE6MAJUOIE6JwTcOfcFVjIysr5ABr5ADrwAZQVmeZ8AO2rZ1fYOajOuX0X+QA68AGU+AA65wP0Peq+J+G1J7frIh9ABz6Asv7VnA9wWwx9VpEHKOcDaOQD6MAHUOID6JwPcFsGZRt2jJwPoJEPoAMfQFnxYc4H6PuzNn1avhvK+QAa+QA68AGU+AA65wPctkhfPWntyfkAGvkAOvABlPgAOucD3JbgvUtSa+d2WOQD6MAHUOID6JwP8KwgbYQ9+sOa8wE08gF04AMo327N+QC3FdRXUVq3cz6ARj6ADnwAJT6AzvkA99rVVxK6D8v5ABr5ADrwAZRtmzkf4F7Deqtza+d2WOQD6MAHUOID6JwPcNsid51pVuV2WOQD6MAHUF4L53yA+7Rzr2U0tnM7LPIBdOADKPEBdM4HeEZWGUdYbodFPoAOfAAlPoDO+QDPbOo7Bo2w3A6LfAAd+ABKfACd8wGeWTWZz7kdFvkAOvABNKyF8/dn99jut5DUz7kdFvkAOvABlPgAOucDaL+Z0T6rqKy5HRb5ADrwAZT4ADrlAzw59hLwrMrtsMgH0IEPoMQH0DkfoPsK+v58bpxzXudohw18ACU+gM75AI9FUMacczss8gF04AMo8QF0zge4fQZHP9nRrMrtsMgH0IEPoMQH0Dkf4N6Xb8vgGds5H0AjH0AHPoASH0DnfIDHM3MMdc75ABr5ADrwAZT4ADrnAzxnya6DQl/kdljkA+jAB1DiA+icD3C/Uyn3CZ6+yOsc7bBB919J91/nuv/a43nu0w19kdthUe9fB71/Jb1/nev933WW0SbJdf416vzroPOvxr02t8PuE12vO+Wc22FRr18HvX4lvX6d6/XflkG3huhEl+v1a9Tr10GvX0mvXxO9/l7XbVLn3A6Lev066PUr6fXrXK//9krdOdNKktthUa9fB71+Jb1+ner1PyPrntf0RW6HRb1+HfT6lfT6da7Xf9e5r2X0Mj3X69eo16+DXr+SXr9O9fqfVbOv23Qfkuv1a9Tr10GvX0mvXxO9/r523TsGrWG5HRb1+nXQ61fS69e5Xv89n/X21Dxf5HZY1OvXQa9fSa9fE73+/sqv50z+sFyvX6Nevw56/Wo8Uufvz9rLt05ePsnezvX6Ner166DXr6TXr3O9/rPZYe0V78Z3Lrlev0a9fh30+pX0+nWq1791Hu7Z7TCyt3O9fo16/Tro9Svp9etUr7+3MpWAc87rHO2wQa9fSa9f53r9Z1tBWp17CTa69bFct1+jbr8Nuv1Guv021e3fGoto65Sszmk4H0+75fr9FvX7bdDvN9Lvt6l+f8956wy6xufZSaHYch1/izr+Nuj4G+n421zH/2z7dScDtZJsxK6yXM/fop6/DXr+Rnr+NtfzP9v5upVka9yujbhdluv6W9T1t0HX30jX3+a6/q0Em/R530fmSW2Q2m0W9f1t0Pe3hUf0/L1af+Xb539ZxhKk9ptFnX8bdP6NdP5trvO/tr1tlbsE9EVe9z3W/dt+M4qlsrnOf8+xlWCTk/o9td8s6vzboPNvpPNvU53/rTPJet23592a5Tr/FnX+bdD5N9L5t7nO/92/zeewCvVzar9Z1Pm3QeffSOffpjr/d523/mLOqLVT+82izr8NOv9GOv821fl/Wru9Z1qVWju13yzq/Nug82+k829Tnf8n597aRq2d2m8Wdf5t0Pk30vm3qc4/1bmNbZ5Vqf1mUeffBp1/I51/m+r895y3RgTchMdkar9Z1Pm3QeffSOffpjr/fQ17chbq59R+s6jzb4POv5HOv811/u+cW/y9cP+k9ptFnX8bdP6NdP5tqvNPdW5/Ks2q1H6zqPNvg86/kc6/zXX+75xbzITwjpHabxZ1/m3Q+Td6z2pTnf8n5/ZawJ5Xgpbr/FvU+bdB599I59+mOv/3LmmdVvfcKlqu829R598GnX8jnX+b6vzfOWu/PaZ+znX+Ler826Dzb6Tzb1Od/yfnrhdN/ZPr/FvU+bdB599I59+mOv9U524ZUJ1zuyzq/Nug82+k829znf+z+8Mna1iu829R598GnX8jnX+b6/zf+3MvAa16uc6/RZ1/G3T+jXT+ba7zf+d822FKX+R1jnbYoPNvpPNvc53/p87abZPni9wOizr/Nuj8G+n821zn/832zHX+Ler826DzbyuPl6kd9mZ75jr/FnX+bdD5N9L5t6nO/6vtmev8W9T5t0Hn30jn3+Y6/2+2Z67zb1Hn3wadfyOdf5vq/L/anrnOv0Wdfxt0/o10/m2q8/9qe+Y6/xZ1/m3Q+TfS+bepzv+r7Znr/FvU+bdB599WXpHmdtiL7Znr/FvU+bdB599I59+mOv+vtmeu829R598GnX8jnX+b6vy/2p65zr9FnX8bdP6NdP5tqvP/anvmOv8Wdf5t0Pm3lff5dztsYnvmOv8Wdf5t0Pk30vm3uc7/m+2Z6/xb1Pm3QeffSOffpjr/r7ZnrvNvUeffBp1/I51/m+v8v9meuc6/RZ1/G3T+jXT+ba7z/2Z75jr/FnX+bdD5N9L5t7nO/5vtmev8W9T5t0Hn30jn3+Y6/2+2Z67zb1Hn3wadfyOdf5vq/L/anrnOv0Wdfxt0/o10/m2q8/9qe+Y6/xZ1/m3Q+TfS+bepzv+r7Znr/FvU+bdB5982brt3f9jE9sx1/i3q/Nug82+k829Tnf99b3d7e7tpE157cjss6vzboPNvpPNvU53/O2fpBDeyAHOdf4s6/zbo/Bvp/NtU559ybrqUC61huR0Wdf5t0Pk30vm3qc4/tfbRW/35IrfDos6/DTr/Rjr/NtX5p5zvEtAXeZ2jHTbo/NvGs3P6vr/lvFkbYTvPhtwOizr/Nuj8G+n821zn/86x110557zO0Q4bdP5tC+lMGVOdud5u1nYeGbkdFnX+bdD5N9L5t7nO/11n7XWmHSO3w6LOvw06/7bxnje1w56cW53J9sx1/i3q/Nug82+k829znf875/YShjSPLdf5t6jzb4POv5HOv811/p+c2/t+/iK3w6LOvw06/0Y6/zbX+e85H03x1GivynX+Ler826Dzb6Tzb3Odf2tKp3atYSjJ80Vuh0Wdfxt0/o10/m2u8//k3FcUGmG5HRZ1/m3Q+TfS+bepzv+T897rTF/kdljU+bdB599I59+mOv9Pjs0yWGiXzHX+Ler826Dzb6Tzb1Od/54zcrxKQH6SXOffos6/DTr/Rjr/NtX5f+rcvFLGK0luh0Wdfxt0/o13nqnOP+Xc/iQPTa7zb1Hn3wadfyOdf5vq/D85N9Vmehtluc6/RZ1/G3T+jXT+barzTyOszqqDlG0t1/m3qPNvg86/kc6/TXX+e85HU7Y9lo1zzusc7bBB5994t53r/N85by1nemuR6/xb1Pm3QeffSOffpjr/VOetlYBzzusc7bBB59/Cnjf1hz11bjnzCpDbYVHn3wadfyOdf///r3VucRzCdc7tsD3aYYPOv7E9N9X5R07dwr9KQH6SXOffos6/DTr/Rjr/NtX5fyzAXgJu7dwOizr/Nuj8G+n821Tnv+eIurY/n/051/m3qPNvg86/kc6/TXX+Keel75b0RVrnqPNvg86/sVU11fkne7uNsJ3qnNthUeffBp1/I51/m+r8U87tT1pvc51/izr/Nuj8G+n821Tn/8n57HV+xnau829R598GnX8jnX+b6vwjzqn5w3ocHvVzbodFnX8bdP6NVIFtqvOPF39fnjjq59wOizr//suhzmSHTXX+n5yt15laO7fDos6/DTr/RqrA/v+nb6Dt2/v47JK5zj8SCzkPdhjp/NtU5//JuesgFern3A6LOv826Pwb6fzbVOcfERl9ZPWR9nyR22FR598GnX8jnX+b6vz3nDfpbyKbFpCcVPfcHot6/zbo/dvB68PUL/aMtKV52inn3B6Lev826P0b6f3bVO9/72yDZ4xTq+f2WNT7t0Hv30jv36Z6/8+KYpP+zu2xqPdvg96/kd6/TfX+nxF29zu1dm6PRb1/G/T+jfT+bar3T/27jf2c22NR798GvX8jvX+b6v0//dzXb+Oc8zpHe2zQ+zfSerKp3v/dz2cpY865PRb1/m3Q+zfS+7e53v9zg3IMNym53r9FvX8b9P6N9P5trvff+rff1W1sIeR6/xb1/m3Q+zfS+7e53v/Tv/2WcKEv0jpHvX8b9P6N9P5trvf/rGHbMJ9zvX+Lev826P0b6f3bXO/fljCfY51zeyzq/dug92+k929zvf+Wc985UILni9wei3r/Nuj9G+n921zvv9f5GWlU1twei3r/Nuj9G+n9W6L33+fxbRH2Nmh/tn/efUm29r/3ta+NzLW/yaFxkttzkRdgAy/AiBdgU17Ak3MvycY5520W7bmBF2DEC7A5L8CaxqO0HUd7vBfZsjk3wCI3wAZugBE3wKbcgN3uO/z2J/lRc26ARW6ADdwAI26ATbkBT84t2srI75JzAyxyA2zgBhhxA2zKDcCd+DXCbDLScnsucgNs4AbYyXNtbs+1OyBrZ1PbqLVzey5yA2zgBhhxA2zKDdibhx77Z/uTyprbc5EbYAM3wIgbYFNuwD2fn/lNdc7tucgNsIEbYMQNsCk34O7nuwQh57zO0Z4buAHGrxCm3ICnlddWAophy7kBFrkBNnADjLgBNuUG4F1PX8PaSKNZldtzkRtgAzfAiBtgU27Ak2OfzwvNqtyei9wAG7gBRtwAm3IDsHK0Md1HGpU1t+ciN8AGboARN8Cm3IC+fuPVXGv1p59zboBFboAN3AAjboBNuQHPmO5rGa1hOTfAIjfABm6AETfAptyA/ezW1NbX72eE5dwAi9wAG7gBRtwAm3IDqJWPYZfMuQEWuQE2cAOMuAE25QZ0m4VsGGrt3J6L3AAbuAFG3ACbcgOesd1n1cY553WO9tzADTDiBtiUG3Dvjnb2kUZf5PZY5AbYwA0w4gbYlBvw7JL3Gkb9nNtjkRtgAzfAiBtgU24A2aTbmHNuh0VugA3cACNugE25AVTnY1xJcjsscgNs4AYYcQNsyg3AWI42CXnqc26ARW6ADdwAI26ATbkBT133yazK7bDIDbCBG2DEDbA5N+DJsc8u+iK3wyI3wAZugBE3wObcgDvnddLauR0WuQE2cAOMuAE25wZYjyW/12/KObfDIjfABm6AETfAptyAJ8deArIlcm6ARW6ADdwAI26AzbkB947RLQOeVbkdFrkBNnADjLgBNucG3Ot2t8cOzjmvc7TDBm6AFW67xA7rOW7jjpHbYZEXYAMvwIgXYFNeAJ0tulVElkFuh0VOgA2cACNOgM05Ac/ptf/55JzzASzyAWzgAxjxAWzOB3hOr/1ExzmndY5cABu4AMZvb6dcgKe1+ymHVvqcB2CRB2ADD8CIB2BzHsBjEfSclb7I6xztsEHX30hjxua6/neOXZ2ELMBc19+irr8Nuv5Guv421/W/67ze1i99kdc52mGDrr9JSGdW59L1UPoq2kvQZ9k99nsJbx/S5VMiqyfnAFjkANjAATDiANicA9DJgF1juTEzUAP6Mm+raL8NPACTUJN5W21cgq2rSRbaZXMugEUugA1cACMugM25AC3HrbMxOrUjliBvg2jPDXwA49iLOR+gUzq6fnxXrypkXeWcAIucABs4AUacAJtyAnqOW1cFLm1kxhLkbRDtu4EXYOzTnvMCtqbAt8ldgueL3L6LvAAbeAFGvACb8wJ6jq0Em3JZc/su8gJs4AUYx9DNeQF3Kx+97rQT5fZd5AXYwAsw4gXYlBewNTW6rasDx5zzOkf7buAFGPECbMoL6DlSCaifc/su8gJs4AUY8QJsygvYmlpsH+MbKadazguwyAuwgRdgbBtPeQGU49b7+/kit+8iL8AGXoARL8DmvIA+stpIi62d23eRF2ADL8CIF2BzXkDpa1lv9dLH+tPqOTfAIjfABm6AETfAptyAnuPWeSCl2XuxBGkbRH6ADfwAI36AzfkBnTTTcu4l2Ujj03KOgEWOgA0cASOOgE05Apv2Na2vqvf6rvRl3gbR/ht4AkY8AZvzBEof+9L+1F4SaoPcDoxcARu4AkZcAZtyBXqOW9e/tFYCa7PRWvSHNS05a2tiJ47GkuZtFe3GgUNgpFpscw6BlSWWhF7O5xwCixwCGzgERhwCm3MI7O6d9ma/qRmSBrflPAKLPAIbeATGFu2cR9Bb/a47xfvnPAKLPAIbeARGPAKb8wisW+m99ckvn/MILPIIbOARGPEIbM4j6FEh5Rlxzxe5vRd5BDbwCIx4BDbnEdg9F/ocoNbO7bzII7CBR2BsO815BL3Od39zP+d2XuQR2MAjMOIR2JxHYNbndysB7WE5j8Aij8AGHoERj8CmPIJnhDW73ugMnPMILPIIbOARGPEIbM4jsH4j0OtOr1pyHoFFHoENPAIjxWab8gj2Fo+yt1icneOPch6BRR6BDTwCIx6BzXkEz+pZxlU0t/Mij8AGHoGFtXDux9M+q/paRq2d23mRR2ADj8CIR2BzHkFbv+Hjb39SWXM7L/IIbOARGGslzHkEzzzWYQ3LeQQWeQQ28AiMeAQ25xGUPo+lzy6lL9I6Rx6BDTwC47voOY/gbuV716Qvcnsu8ghs4BEY8QhsziOwwZah1s7tuMgjsIFHYHybMucR3GO775I0q3IegUUegQ08AiMegc15BH13NOvzeaMv8jpHe2zgERj7A+c8gnuXvNcw+iK3xyKPwAYegRGPwOY8gsc21UnOeZ2jHTbwCIx4BDbnETw5LsNKkvMILPIIbOARGPEIbM4jsPaW+7ZJdKEv8jpHO2zgERh72ec8gruud840tnM7LPIIbOARGPEIbM4jeOyvPrtobOd2WOQR2MAjMOIR2JxHcOdcJq2d22GRR2ADj8CIR2BzHkHr537WCLZnziOwyCOwgUdgYaRO40bvHHsJyCbJeQQWeQQ28AiMeAQ25xHcO0a3DLisuR0WeQQ28AgsrAtzO+xet0svwfNFbodFHoENPAIjHoHNeQRPjjruGLkdFnkENvAILNZgbm93a7efp6mfczss8ghs4BEY8QhsyiMgC7/PKs45r3O0wwYegfFZZc4juPfl+zTbc0ZAZ15ntsPwy1jn+i2l83qu6ie7+4yBL5I618RizjLkXCideT+Xr5yP54vMDquJhZzXoc4r1Xluh9059pM7lTWzw2piMeehziun81rnx/p9vsjssJpYyHkb6rxRned22F1XjSW4Z9n2tcbdPqTLp7S3KO61Re33W1Brf1+5JnkbbrENt6ENN2rDmV1HsdUtsv2OMvH/m9l1NbGQ8z604U5tOLPrvI5fdeYxntl1NbGY81DnndOZ+mHvVu51prmS2XU1sZDzMdT5oDrP7Dr061c/c855nY9Y52Oo80F1ntl1PedeZ7TB80Vm19XEQs7nUOeT6jyz6/wf9/5dxtbO7LqaWMx5qDOvMzO77hnb6yTnzK6riYWcy1DnQnWe2XV9bN+tbdzamV1XE4s5D3UuVOeZXddbe2sv9bbmkyAFA/9JZt/VREMJZKi7UN1n9t1T96X9udGKktl3NbGY81B3obrP7DsaYTrWObPvamIhZx3qrFTnmX331LWv51znzL6ricWchzor1Xlq391rWV+/V8o5s+9qYiFnG+psVOeZfddn16NIEnLO62yxzjbU2ajOM/vuXkVb3fdCX6S8gpoY5/zNK6jfUjrzsd1HVtcF4ZzTOq/RvvvmFdRvKZ352D7inkXWUcorqImFnAf7biX7bsoroPmswyqa8gpqYjHnoc6hBtM6b0vMmb/I7bs12nffvIL6LaUzrfO28CqKEtAXeZ2jPfbNK6jfUjqvdb5HGn2R22NrtMe+eQX1W0pnWuej5VzanzvVObfH1miPffMK6reUzrTOZ1eSuhWlni9ye2yN9tg3r6B+S+lM61y2WOeTc87rHO2xb15B/ZbSmfdzV5JqOfPIyO2xNdpj37yC+i2lM+/n3sqTfs7tsTXaY9+8gvotpTPXHuwKj7da2vNFbo+t0R775hXUbymd+XwusbXJMkh5BTWxmPNQZ7LHpryCJ8dzknNuh63RDvvmFdRvKZ15P98aZS1nKmtuh63RDvvmFdRvKZ15nVv/nq3VT+rn3A5box32zSuo31I6r/O5nb+FZ1Vuh63RDvvmFdRvKZ35GtYtvzL2c26HrdEO++YV1G8pnbmW6BFHGM+q3A5box32zSuo31I6837W1spNffpeWZ4vU25BTZRL8M0tqN9SOtP+3rWP7db6G32R1n2L9tg3t6B+S+lM695Xz3sdp5xze2yL9tg3t6B+S+m87tP3znHQF3mdoz32zS2o31I6r/t0z/mgnHN7bIv22De3oH5L6czX761bBpOc8zpHe+ybW1C/pXTm+/Sd47BbptyCmljIebDHNrLHptyCp5/vnBf6Iq9ztMe+uQX1W0pnXmeNK8pJrZ3bY1u0x765BfVbSud1Ph9l2LNSbkFNLOY81JlXpLk9dnzVeaN+zu2xLdpj39yC+i2lM69zWL+xntMXeZ2jPfbNLajfUjrv/Tza3Sm3oCYWch7ssY3ssSm3AKsl79Owv+mLvM7RHvvmFtRvKZ3XNey2xyjn3B7boj32zS2o31I6832617m3OpU1t8e2aI99cwvqt5TOiz3WLYWt3ULGEuR22Rbtsm9+Qf2W0nm1y/r85v7O7bIt2mXf/IL6LaUzrXs/2d27Jo3x3C7bol32zS+o31I6L3Xu1lHcOXK7bIt22Te/oH5L6cx1c1uOZbSCU35BTYxz/uYX1G8pnamG7JNjnN99vveS3f++eTnad+xnSXkHNfNY0u822heu8bSNnhyvP5tPUWj1TbkHNdFQgsGO28mOm3IPeo5bJ8UfLdo7liBvg2jPffMP6reUztUG//1f/9d//dv/+z/+9d//8z/+x7//17/8y3l+tqIn2K1l9R1w3bePLrLuevg/L/oTfnCSzdL5CJMU/Rhgm6gsCDisSYr6/66nVEW5+Au6IN+3PUtSl+NUbLYHLijWff/49ldWb/YTjrLwi5VTPP9JijKmCCLDZ4UCmcnJg6mZkO/V3vW72ueVonf2Im7027JTkv+kb2TSOTVJ8YGwKPKkUu5J52yfVXbs2Kj4uXuS5bMuWFhVzXT/Cb84ydO770nn/Jqkl1I+6huo7BLbck96Z/vsd5K7rDVJvM5AdGeBHk74xbFRW+5J92wfNyWP9fR2PL2XapKnD0/x8XSW4/yJv6ANbd+T7sEHepx4iYRurkmWHdG7ungf6VVx82lT3xioPEkeaff8UvGaZLnbkpP8a/f4AF8/imlw+n+Ek/xr96znsnwonbRPfkvHVD5SijezT0syTjvyYtonsqzrovuirUuWOok8Gd9rVjn2j+ruxzOKw/EEz79OmNWX8Q+Gsi8ntoQk0x75rdpIctt3HzkqPsAoybRH3HRfDt92gQ45apKH+BbjewtOBj9+KLSPL/AAtj5630jxr31z+mK0Y8kWmNL7SUm+9E1BE22AepbWOT5RpKyL9/GPyIYVDzVZlD0wnd3xh/lyFJ8vkFrxQ8tBl/B7SXtnwTt4Eehq7VaT1NMt3MW8sn5g2rz4WHRP9aXCs6Uk097ZDoXmJGRzzqviergNsx6nJ1vXnucXdI7oPJA/LOPeO+tS4z5P4QdZHSLyf5qkj6nDVl/NfHHzDW3npUfS3lm8hdZFAB/YtmtUesMZNixv3R+f1J4kwoj8r75RUpIvvbPrWRRRm2XrTXluPrbFU0OSXu61iPf4wfc/u+RzxxdULyg27qI1SV8OfAXx7l8wd5bFN24Ez20YvNSWkm823krFB7ZVJASS9G0B6jc+rmAcFF9zF4DVEZG5cVv+tXs2Xyg+6O7VR35YKzVf2rx63iGLjxS9tsS9eF+cvqt5UdvG7fur/w3xMJRk3j3nWaAI6NW2az76j4tbQOvpI/vH5/bHd1vvOp+idCvgfZo35eFGj+/Z55XeJr7erGg6Kz9uc30MS73AqqLkUivNh8lWztULcc1u/azqFSy751LOn/gLpbVXX6y07dhQ422tSfqm71YF5Dh87f2JP6BTY6e2DCkevuAUt/M2Pwwg7nlce8MveIOwpGNikvvUsDh9g6iMQG8NakpLTej3ejfjVNykOCENSin+o845x865jPJNxP/uGy4Zp5Z2DicpY5Kr//uPLxQ+StdjoyQ7X+aXpiy/WT9euL8WzWv6wS6znYiJ2CnJvEt8NfDFcV/qM5vaJTXu6NxwyEHBFvzHC656UoJJj8S6HrP9dbEPIutVfdCQa6XDbf4wuG35+L+WdcVRmGZgp99Mqu2Gkds9G45Kp1zV1q0y4sXr7oZFHTab7xRu/Sh18vqP5ovMbLQD2fow9Q4LbbmmnePnZ7xVOrwgVmopfefal9WXSz8p/uiqHxjdvp8qogIpyX/UPbOh6DaFr7eQefDWIH/A8eIP8FSwnPruVeegGzt6HMWTWBDWv60KM8DPygoI97MpHLlDwDfnAxuDD2/Zr4r7oXvbvOhYi3x3+PgBSmED8SXUkfsDDmgJ+47txdjrzPE92jdDNy7c+vdqr/JZd2xcOAxQ5+T+AIhPuqkES2CDEeDDGpFmvsWeIFnFX1Df5P4ATlG+U2yLmVvLvoa6uXPS9M79Ab4swDb2nlS56i11a0XrXoV8fmF0LD4yf8D5KVh8YHn6aXKtpTwXH5SnJ7t524ZfrCHJtHMoySJjkrXifl713cPHBHVO5g4I9S421rumCHShm5Y43FGS/6R39nXsHZ8By8fH4+Frpp+KKcV/1DnbWMivbSFzAfyazrb4odhnj58OYTnTdMlcAL9W1tb946camIFurisn+U+6ZFZKP0B9/BBy4izn9iSt4pk3IJZynIG+hnzckADc1jcG3g4zZ4CPRIHB7gdz31SvJE8/xhRseBCxLqYfN8JPHzTA1VGSmTvAk/S9VL3aG7SBryS305cet+Zx57tu6nb14SfIglRodGfuAE8S7xEKjut6XqU83CxAA5cDdoAfGT44jXjPyEIOmiNzB7w3pS89XrAP9ugC0DdP6swd4IX0sSBQMfXd4BpCB+SgfBH3csPBsO/e3AXaX+IrPCX519XsWAuOXeI7mw95OhYfmTvAd+QNxo3vegvEclBKN3S8Ga7D9k/8BUWFHZk74PRR7Av0hiOF6NXhiPbR0+0Tb92f3fv7wLLjtgT7S4/MG+B2317xLzhEb20I+dnS/4FCFGnffZzDVHHTxTdemjmZN+D3paf+E+9pjLSNXBZH5g3w4SE4xfmK7XZDq7abx3qefnw4jh9vAgxzQHIxsmicZ94AT9ITWOC2PBCzW0clzBcYP/6P/R+shtPiCvHHnRzkR+YN+H0V34/VbSQ3O9zs8gM4JfmPps4kyc2PCR+QwU5fVPip+pF5A7zDiy8X/qFvyXpV3C1BnxiekcJ+sbO4yeut4E1eeAxl3gBP8oAqBC4SQF24kvQ9AZdHJxyfbvT50uan9t2P+HSpdmTeABxH3PCDy9CtqLawqVuqsOx9rdx8dfMex9Lhx2+2gDJnAAqpxTfPDQEUWy9k8c6QFTqN1zIEbIyvwd4ilGTaO4c3UAFRZCtnG0I+Yvx86VNl/ylXqQ8s+7bwQM8cAj7XvN194uy6tqUSJwUBQ6Js60/8AV0LHJk/AAa3t7kvB9Ay1Ws2LgJlqqWKBoVfbDwoc4cAJyljkvX0vuOk6APKRyUlmR5w3utdUzxWdL+PCt5tX/wBML5gwVcGFZI0N/Fg6nh/bz/xF/RQ48gcAn6+sRXnOlndLiltBPlR1nv4RMhN/MXJ9c6Pn5TkOSZ5OUJ8J/aTBL8uODN/QKz3Odb7coRgcV7cbFlOSjJf13Y/NMBy2uvMOZbPdvRz3eVTol+UnZJMe8f3GFwG+Ca2tiR9kfBDve86vjD9xF+EJNN1jT5YdEyyVtyXI1/GZFvJA3RmzoFQLXT4d8WvQ1Pxo8QJruxj6Z+ZcwBXj547fPe+Hq5f3aM/4Qcb2YBn5htwwxbWnNdoLUBkfNX7+Im/EEox6Rw/rPoWDQ8xrNNJtfkXuJ6mJJPOiUlOhpC35PZRX9y9jIvSI7Uzcw3Eep/f9W5JYm/32QQN4yfJzDUQO2fom5og3AM45wgta2fmGVCYzpcpJN1uedY1P86GH/AozzwDbuZ4hRbfq/Uo/Th7LxjeDOEXwn2TuQZikseYpNfbzRZva0PTndyQSd/Een+v5/uV4tlPyBu1ZOYZgAutbxBaXe/BqCw/4Re20FTMPANeSLe9F3hpANz43sZ+wg+E7KAz8wzEFNchxavaEC1xy/gIKabzhqotQ7X3a0wu98bI1U7nDcwf4E3x7ukcTcr4C6ENInMSyAcUUBHfsPbS7b/gtuFfCJlWZ+YkiEmW7ySPq+IFl4obpJOoLTMngVdLcG2P2zjVy6m2e+IYIbBmriTho3UzcV+5ezInQegePb+7p/pt1g9GhM+bjeOCzsxLgFL6+MAKhnuKq3t8jviE1BVvsprb3E8vi1eEAgzOzEuAJH37MPOD8Lpce44f9sxPUDuMV/hwygdnZ2/Pw61VSjLvnuJ955aY21atLc8VF3U4lu/eX756fFDtapGfXMqX7tECeIMc3T7HgyPsg37ArV4hNyePDY/dZOUU/9o7vhnBkVBK8ULzG6gz8xLEJAcvgTfl7oenUtA6YM9TKTMvAbzP5ket3WfGKs2VsZWi0IGCP9qPOt7fp/oi5CdBmo6Zk8A7x5cYX4TgYLY+HbEOYQHf5afo4gs0jlOCJ0OcZNo5vnOvbjnhqnvr0xFHAP+fgltpP+bAuPJxJYSwQJJp73iJIFpV07F2ejrWAwde3ED5scvn564nbgDZM3tmboLfp+OOGe6HUquGJJnTmZvArQzDvofniHvbbzfMHFz8H7g3OWHcYDYanG2cZNo93kaK//oyo1dbuk2xe3fgyRecdosfwM2XJRyYDrLYMjeBl8CnzuKrhNiyNNfiDgeHp2twZiw4GJy1ecMh78zcBJ6kwEIF5wtK/leSvvSK29jXinx46x6+Np4hHvnMvAS/9o6nu38gJ4vljkMZz8xLIHixgzeM6jZkK6S3Ir5wox7eLFy9+IBaYSMUcpyfmZugDssdHk8Q59r2WNaqhQY37U8xOETxpM5HwMpNmbkJvCnR6Hh9se9Ha0pvyAOukLo9woXuk1Pw5G2jx0tn5idA7+yCi07fEuvtXbitlZ/wCw7/PTNHwS9JdhN98+O495kPoyfJzFGABKBG5h172DG5r42/MKp45ijA9R98z276X1b/9/OG8ANeNDJHwW8p1mrjCFqg7cfHiMxPEKs9uVO+DOp1QWSn7XzYyfwEMcnZBbDK8jFfJU8faW7m3EmWzFEQBkh1kHxf+IcbopJ5B2LRzknR3Jb8LN5ybkwWjg4pmXfAz2GwZnwbPDY5rht0LJYF9smOHY2fDuwbJ/kPJsy0tr6AY5PzYermB7+jK5l34NckvSt8fcKjRz9q0wpZXpwDlRByYL3YrqtpX123ulCAWOQGwAf4BjxC2ngsltw78FsvL0dxaxBhO5vvL5xk2jsHZMy9M1TXw/p9916FK3E28/PXB6dmN37LohR4UF7cA7+U0nfDD+YkHnhutCWW3D3gluSywrmz7/V059Pa964d/wyNu61uBZ24ufc9cyejt+TuAS8MonN9rQYStFd8Kf6JwlEiG97/QZfcN1p6k1gyB4H3uO+yOBSjqa4e94OCHL47XL7V+nbALWtv1J393CXxEJTzs4JwsCLgsbTVB53hhUKURPkJv+AyzjunHD6dd+wbO17Nr+0JKlpg9f+6ARN+IQe35Lxz/AOfqPAUynacOi4Z4QeFwjxK4h+IKcpkFXKjzeeOYSsvCICgJOd981Xvsdo1RShUwRm8Cs2cxD/we9fgvbSvfSue5Litz0kmnQM/uy+ROLdtC0Y57m9XP5htuB47fuIPhFsy6ZvwQT2QfCVZC+mL0OmFPOnRZEncA0Xg6nM71nxg+373U6NbBI891U/FuxeSf6H06q0k7oGvJI8xSdjoH4R3uLUqSnfKJXEPFDe53ZRU8OxwQflTI2b8oAm3l0EbIP6CXoKVxD2AUvqZCWa0gdd+pegjcIMjzIdU+AEr4pTEO/Brile11Re4RVketCS+gd9r7Sl602JBQ6wn1zrxDfi8WXw59GPBCU+u1gEEnuKBW/MdFjT/wriQSdfEFI8xxToVwZk6Nzxa3yjJpGtQp3UDRK3gWcg1yu/1wk+44Rc7OYNK4hvwD3CxAP8zXqNdpfQC+wEJ7/JNfsIvhMz8kvgG/IMTF2K24fKnvnPwUuKB5rFjK4PLCo/Y4fhbZGO90ZI4B74qfowVr0n6UioF96/0KKFkzgG4ftw68VUNuNQrSZyocWICCP4n/oKe/5fMOYATcbGK0dB6LeaF3ACvAfC6mlb0A9ZJK5lvwD64IIcXzE2CbVLv+At611Iy30BMctaSx4JYHLcH0BCUYGINwBFbIEhRL6muFL0dITkEI3K/UvSOAd7tWOmRXsk8A7FvtrFvapJ4ECkgAdKlRsk8A7Ha+1hvt2dWuJTdkrMjrEKZayCWch9L6SlZ3c/9LIvH9k+SmWvg1yRxBfjBouJr+c5CLSVzDfxacUU4AYQO4BML4zxzDfw6dXyt921M4AKF1cJJ/qPumQ3LrXgxd19tEQ9DDsWSuQZ+nTsHrvP0cIPANyIO6CqZawC+Pj/NqE9pkW5k4Dnd6TsrXk74oPQDjk/ylbgySDCfO4eb324Q+CZg11J5Wn2+vJ/1esfHkB90VtjaGozzzDPw6/z2w/bHt0rBe6FtpdmYeQZQSN+h1hXVatU+fY/EC67L2eDb7Af/FoG/RWnxzTwDWAgRzWILJNHaFlHPczVIzI1MH1gfwxNFP0sJ1Vsyz8CvU+fwA54PIN+KD7gTV0oy7R24WE6vF2JjLpsA3bAVwVlWf9SwyftGtuLBt3Ap/1HvTLpn3RavuBtCcN1tdLkqmZPg19m4wnWnbgX5VosnfZRk3j1VYFP2GjFQk/TUTzy0dztg+8H5zs9+PhfWhVZfyXwE3vIIE17rhUDbI9wYR7yDW43VJPDJuPtyAYQQh5xJ5iNAta1UeSK16pA+fVivbkH65gtnIo1KvAraKMm0c+BM8OOTn+gvz1+d33jQa8eOoMPzOo4hYtl/c1KS/6hzZnuE1vt6X9j2ZWf7XDIfgZcSAW8+fxBieY1KvBFD2AZ80L5HnCvuCBVX6SdJ2EvmI6gVh7brjqtva6YqpjJUGguCAeoRf3MbTIqR708yHwH8z0t9cVSjjq8kFeRPHDtx3eoz8eMTBzcVblxSxbNXBLWUK/zbxdrKBm83aMfebXg7o6g3fBD7auQ9luwRwT+wAX3kAoTtqxRGASWZ9w5e9HhXbLjNunoH70XNd47Nzyrn4kkW5AFvCU/w7BVBfSXsC7D5Wqnb1eGCZ84+QxHA8YP418+CMHw3jzkSUrJXBHh/6+Y4BMG1bNeSviM4wY+iuOn4ib+gZ0eSuQkW78xDMYBkucIMWQ1i8QMU/0LprYNkboKY5D4miWb94GWFj9SN3+RK5idYcGmFnvQjSg11DXIQcvyEX/ADWskcBW7bnt5wKvCgVVf8l1ZH/AXdEEnmKIhJ7mOSteJwbPiMDNqwkjkKYsX3seI1SYEhongcrpRk6v/EM5EFXMrjXK5BBMu0+GpWH+nGX5yc5Jv/805SxySvew0ETS1YjGkFzt4RlI8hUG/1RRv+yMkRin/BL2jl5R2BzywEGSkugK4k8WqoeMsWvAPkX4RC5jfVlOIxpng9HNn8NOvrSOjw7B1BqHc3Vp961yui/QNpTLzROVdOMn33ebo1hGWtwLKfLJf8i8JNmb0jOHybQOyfwfe8le8zc33oS7/ghSh7SHB83FDxf7uUTY9ldmYOv6DLA8l8BfzBbmV6aPamOA7cl+JBBCWZPsvdcJZYEbCyFp2emn2ZF7e28Hact57MWfBr91zvkXGfi+MinaEkcxaElpqdmUXx5B1ytoQUQoL5k+n3Msb7O8k8BL/X1Q2rj68QvrbBL0ydnHkI4riZHZRXn1MI74YcAD+Ek8xD8GspEeEFlzSu7n19pyQzD0Ecijo9KK/+G2zrbk/S2VsyD8GvE+aAnxKxjYg3XemaVjIPwYFzLcIUCiKubkvaT8a7H54RZLDh7Zb/Bu9BwxKZBxlA/sdNO/OtQPuEqZFNfhpHBAhutnCecEvOz3hc8bR7fmvLE17cgpiT6EaWPMpgwwO1Goxa373VszKOnT7dEU7upxKsuvWW8eTH15JHGeCMhAsdhLm3ttxwUvKcvFDXWfmAbeitafR6QDIfwa/j0lPDHZ9bSPBVGlf8pXuWE6pNUHzZ2859+FnBbXE3+X/cxvhUf7ji6SOtkHmUwfva46X9eKvIUoPwHuNCc9GB3ZfS80RcofY7IvWl1e3y0+37H9sOXODqiQgfpYOTZh6C4wOVcbhCsAj2EeTmqUDo5Hr6qojH8jGLS9eNksynDoILcHhqD63QkBuCnDcBRc+XnuUD59BSL3EKJZnH51B3Tw+hx/qpHqbdV3N6cKS5AgEmtiIs3u20sx/oxXMpeBHSoml841prgP+TYuYi8EL66d2HTMFj5LOf5zcc3U9EgNwTp0atUxlz/YE63vx86HPxPii7gekLDyDnOCjveLYIyrgZOaY18xBgXfNmPnzNwhvPdgaF60fxKBAH5WP5AMy74gxSOMl/1Dkzo8qKd3fBWwVf2wtXPO0cuOtwjSXrJfVXz6BoW9zRulG1FB9lW0EQmrcnjcrMQ3Dg9Zjbk3gYv5S9nUHdXq6vZaWGR9alEgo/eAZMSabd48Mbz/X8yLq065J4Bg2/oJ1MEw+B15r0Bs9B4zAVJNTEQVATJLnBr4PYobkgoSYOgprkIzd4fh3ESq5HqIl/AO8lWRrwJ8oaSdcgmogHauIfqEmS6N7PlyxfrsqniXugpli+Cvk8dVhKrsqniXvAu8DnTvFlckO4y/eLteoeSJOcdw5Gyeer/fSl+RKXwKGIoDj9IOsGkiznd4rbW5LzHvGt+OOLM65lT18RB5W29aWyiUtg88X0g3PlgrDazb7HjbyVMukStN/1ws03h1ZxBNManvJvi/SBg8dMiCihLfZFjdCnJ3xRfjRob2SOE86zBfJ+LcW17pCFNGQ0cwjY+amxr75F44h9vWfZql6Xfy93GbdtX9w65b0rcQhc06UVQbbCZawvAGIhhTx0mngE3GY6cKD0hcG31V1jKQFb+yolrTyJRwCjEpHOvquUGpvwNYT2lyGUeAR8L0Vo2epbsixX8Fn5aIH7BrpEZ587Bm1fCE6SlZZ4BOqoxEnBIDxyfA/0RV9KmXgE8BQBMXJu2a2+ix2hlD7y5auUvMUmHgH/+rPXp0S4DTi37xm+vsydxCOwLrglEbfw3RzpFfc54+vbgUcPfaTjwQRifWjqJA6Bte5evhdD+XbVPaSIgOWY4JNe4g3wYR7kzaZrOP+CxmTiD2i74a1v9hPfMR898HeigKaJa+AyAh59s5/4LPOUXAFNE9cA3o27dbrhsZ4bPIPM2FuKv200NAFfmi/xBqwLbpwVATbwkQ9PULeXkiXeAFrCfZhsTQgM1yn7aXY0G6pqlenJcpOa+AKgK1CVV7BH7zKMGn2rdmYzb5/1ilbCA9Dhrfr2lmT2uNM+Bw4CPgZgZ/9cz2RxdbXUSJqr3ideUuEyiKdf4guQqrVTcJ1v8PHUlvQE7DCpEqY1RbzicFv9YBsq8QSsfjLyrvCTxAHL/pKmc7Nx2dYL43wleOJBNK6CVkox6RtPyjdD8T73dqq3VXeKcEWvX0nyMpY4Aur0I0WunxipqZJrdmniCahJ3lpXx3ekZpcFn6hhWeIKqCk+WlffEaq9kDM1LEtcAasbw3gL4GbP7vvNIBiUV9sSTwCOvtfrId/jz1GSZn0rZLKQlYKTIKbFLstZvuttb0nOO0f3JiRn2P2GwNztpd6JJ0D3Om9g+WzW1m+q9vZSxsQTgDcLUEGC0t1Z7/GvAYRXFmddN/sAwiPUhXWxLPEEYCuElixGz4G1+6ve+1u9syfry6dqxxwYQ32Y+xrmR+JTdm39DXvP7cjzpAASSzwBx7XA+JyAc64MkZ/7S1smngCow+DWYjd1y6GVckcJVghwnS3JE8+xfQ0pxOuwxBPgLegpnNhaa6TXlWRVM0DImrXZCMcAPDN0aLDEEeBVUbyaghW6a1coWddzh5L3vralEgdaHDwO5XpnR5vtrCF1BwLhl+O7w9eXDk9cASuEfFc8rII4TFsqT1ylbrjW66vQtiKIWiDb9ySZ+ALctMMVqu+5ECXQK/JzR5ilr/BV3edqStx7wblHb28t8QX4bvSBCiQMCmBsflpM5YlB4LO0Wz/V5w3/kFCS2baDNw1woKD2XQ+iejdh/HYxwur3Ey1MAbTEGYAJgYBFryKe1n+vGqovIz1zBvicc+NqP6ogWFdKMgi1wD239rbE221EZtLmaIljYFsWhGEKAhlgpLUkV6izITSgpwjFKQQEUIKp/cyaRd9CSUfJVY0scwscUbToJ8pgdJnjmayRJW6B6+DQ5YDusNxLrONoLpapYJAlXoHr3PDIAf1E1ZMuczwTDLLEL1CTJKGdL2kWPXMpHsv9AkFo50tAZu220ESKxxK/gCfJijPTFOeSNJa4BWqKJDjzXW/JJWkscQvUJB/JGf3qHdlzURrL3AJHUHPZwxCCTECu92KJW6AmSXIuXwN923LBF0vcAleSt1TK/j0de5ITMRVL3AK1LR+plMFULbmYiiV+gZrkI0KyT+3puUyJ5a4BFiHZf6JMyX7cMiW+QYEcQqVMXAPVoPZ1d4PKxTZoW162alLxxDXQzra3CMnPl0zJXUq8yaiDlZJMLWrcz0J7Ek+B2oa7IIQLS9l667PAkvFTIN1bWeYbOI7i43DZtorF6dbq4jax11XafITe9Qltbh7piZvgWjSeGPipS4R+QWVMvAQ1RQovn/pt5gHolvgJrhn+hJdPvUvzAHRL/AReVwhsLvt+LWfTG4IsyXfHTXCzrLnKgCXOAZ8jaw3MLJ6rjdGk60vRMvcAeW6OGti71wtyaBQuUE1pfQJdHyDQ6drPMv+AQU0OCjy4rz6/5RVOe6t45rvxDW8Bu2KFsTYoNuxvSWbBn4svsla81oI4icvRghfSeGe7l66BBnQjsBvPJQFaN/XdbBvuRm3HetHcQTuUfvAwrZXSjc3dlw+QDSnJ1Hvj6wAeVQsY7ufPHYGOB9XQS69JntCzPBDDa5Tki/sG77xx2XyFJIckY4rrE/LgKWa7TYg3/ha/WEoakYw4gDzJJ+D48kI/IcmiaUgyZFeyJDng+EryCUmuLsV5SLInmS1oITz4J8YP10V3Gj/sCWbLWQjl3X5isO8VsjgN9vUk086hMNl64RkCadcskNZTTPsmhMn+fAXSrmkgrf817RsOal1/vsJetzTs1ZNM+4bDRb8DShHxkASUAmWRJ/mEi36/jq2yifOAUrRDtn9x3OQsxWlgpSeYmmkcNvkdWHmcaWAlNpc8ySdsUr8em1w21TSw0pPMfGtQm6q244a3P9/vV463JF/MtO8HX1vefolLwM0jkLIOW9TwMu47xf0lxcwjcBgMTrzGWbf2Novqur3UNfEIQH3OkyxY8CGo/V3IvIyZR8DPzB/ctuO6Zx2eE61vRcyMgM0NEUUMCp76thBxNSzVbiZp62Gp4MOT4SN4zpW5qfZPFZYq56rtrS2+PqCmpSJ9aCOC9mBhTIRyzV2dC9pNBYvKeozhnkfekolDwJdmaH9V9TC88PpuyvOlKROHAC71N7wQOEAruN/FboiA2ioG/ao3dOMLHn3SEp6GDigeA0Jvz22qs61kxQAuBl2m1btcHnUvNpcyeSjgTQmtEECVEILyXfHyVvFkLbMd4uwHJCSxQLe3l8CaAeS5t7Ys0EDeIWVOa1niETjWFc8ZvL8hkNMeDB6KcyzQQD2mUECkO4H2pCU8kxkAUE7gO4Ubuo10vMJcV9D3ljuUHe/HBNEklGSy0UDp/tzg0gMb5jvgc7V8WOYOgeWzIwIQu3IL1iv1GFKqLM+VIv2Ckkx6ZxVo0nkPn9DOb4X0AroNAZZSH0MHXl1Ao5WaMnMI1HovEAU6ffK198AQ2oQaC21eR3WErFzxzCFwHlBPhn4hAtmHiJY1b8rMH+AbFgBsXkagslqCu3esnxE2a919KlZTvLighS1zB3jel/gVXMxlbe8k/QTlM9R2aUmC+rH7zF02TjLZdGCTQedT8Ayg9LiE1bc28VRLqzZACH7gOReqdvZqADHlp8Chh5uKq7uhnYP1Y7kUfWrf4C3nvgUTLXs14PZoDSqvL+/XoW9e9trEHeCGl89F+HV89V/Way7i9SkYlSpLX4S80usKRUOhJJPOMWDqtv00yG9svW/wsBpM0b6eG55eI1aMTg2JNwBxoxR/uH09OK0vTucRiuuSOAZqkhTZ9/3ktAU9TmL/AFfNk3wi++T7yWkLJ5zE/iGw9MX/84Th/cRAve6kmgTqeZIvjs4nwq1ZQncMXI/9m8TAQTAgS5Ij3OY2+TQGzhf7lzdQT6DXt1G5tquMSSgY9o88ySfQ6zsU7Foqp6FgnuTbHc4d6PVtlGt7nj8JBfMk356nnW6uAeu7D0EEx1uS77600c5PGjBxBwhe2smJd+lVhHW6+GRJZk8Gzw1ocz9QLnLpjY+WflLbxCGAh6A1hN7/T+kKU1+WflbI7M7TrMIOa6TINthpb2VMegTPjLEESOVFd6kPL57vP8sdQujbDBwQcLg9SSb+gHoj7TuO4uVrb8kTC9qKB7hyBzpCdmcDxoCSnHeOTwyEOyGoo8rWT039pCkTfwCGELA8uGowvOuf2fpJWyb+AG8xvPbCXUJZa5R+t/XRmsfe2/IEK/hEeDklmYVHV4jN4cbVCrJ5s/Uh7wg9R20vCBHkgQefJGnj4zyxoqE2ApHSHbomOhxyykvFs+ABdevCLdGCW69SSrf13dJH1Ju0cVn2DSqlCJ6hJJPXNkuBzxEvV92u7JE8uEws3l/94SluezcsTnTGWTNtgYJQL99aoNa3tZBevImo5ijWtzYs8aZM3C6g3km8A94rlVCNkJqlN+W3qZ8My+y9QL3e34EUgJRzOy96eU6ETu57G5bPL6h3Mv/ACrYe9pVt2y9kXLX18aZQm3+g0ifB9IP2AqWYHnHKxw9IiDbfravFuKmPdyz+h/amBPVqRQNRklloB1S6C/acbb9CE0ZTP2vKZGkDpxB8IzU/1/QUIdy0+v/2evuA9xyg9/EkmLgHoOHzweOi3ZdgbaHr9RW8D+oibRFC0CwCLMrz9BbPkDJLf//sGLK64pV/t/TXyuXVvo+VpWrS2MrDPAsj8Bb2eeG72IqgyR6Wue7LWtnZfeZAxRZyvFztZFkD7nEXXPPCNTMoGL1ttolzwEchWLY1sG6zFgIHU19OvFtZ+mYLFPxRTKjaiW8A4iofORB9CiXD+xhWVZIP6UYGngBCylXI1F/z1wLvsWVn3Tl9YwRcfqWVN38r8EtsmaeIOmyC4AoxTvLl7e1bbFnljWOWQ7TqpCuHNX8qwFEM35FM4kniHcfu6W2INFjIgs6fCrzHliHiB4AHXH77GKCuyYMIfokt8yT3u5AHG9B5EMEvSdbDpI+o6uLw0lKSaef80pRB+sDT+WuXIGYbMmNuKax4V/Ikmb8PwAdAAB5bj9pa8DgWsSC4NxeQEPFuw/+9D3BK8a9d4gcsPx9C5BouAS7jS4+8VxspLp4i4s3ozSDOdi/VhpoflkK7rhEPrZeGeK3lW48feWCl7AH8DRndv84Wn5B4VqPwtpWDqp26A66uwa2zXPLd6Jtdtd772I9gGMJTgwBfEzLIU29ArTWmGwy+Fqzm80+gt3vg4L2dBXcSbsYU+KUoyT/PFl/GELKhJ8LFD1rKcm9AfVBS35Av/dYYAHbBYeKopdygTO1HCIOzlJJ86x3fuQSQz+16DbJhq8bNxen2GRKEvQHpDBaEhJ/ljxX37cU+3tsHXvKsT7A+As1eSmmwGHwML124/CyI4dlWbIa+QXw8OWBLYTJQkm9Tx0ByV1O7SrmXgoOH22lyR+n1Xwgl+dfFbPND5AcwLLeTYApQki/dY0DlygJWwNU90IrDGRyHm2eo4xE/bQxb+k4ApTzNT2DLet1Neve48bThZqRGkggmpM/3fYcGCyf54qx5jYEDHRNE3hWX63rSIEpfCvwWA1e3bRjsEIhajUv5Ygi8xsBVVC0UAHDJQy/LPcmXF7evSeLwBWd5gSgfuaG39KXAb00ZN8QtfR7wa8kUjl8fNm7tn0T9wZv+ly6Bx24Ft7d1CVhkvnAW6HHd0r5eV+O9YcufB/w2cAwudFxE7D6pQpJpl/wWj3kseOBYo/V8xXvsni1/IHDBxfB6Ua1F//nRY1/r604FwrgOHVlx60h27pZrCfzWzVbhvLvni32WRk4uJuCTDAS068lqLaXvXIj4wDOVislY4dcAL8wLulKSf+0e3I9/qpYJzmY8YzJ/wPVG3Te9Dc9qrzeSAAW4ZYZAFghKafXfQcjRFyladnN/AFYXxMAc+yVhAxAbZJkW3N94sTcf6r6kr1BmlZDky+ypb6dOnIluPsiCg/pZoEW36AaQjcBRQqrGnuRL97yGAEZCOBktWx5B8EsI4FmdFr6KHpAQWTnJl+55jQEMTHijer9FELzWG1P5U8+kQPbw3vAWQfBayK81Mg8b+CUd33k/O+S53ObYN5qDedjAb3Ge4DMKjGk/7JE0CiRf/1jIDVRBeKfFarzEk2QeNvBbKSs/HVJKwBduNG7eHAE7KPE7Xgo18iwAwUuVTlx/QOv5INzKx83Ca8+bJwBRfT5sVVpo2QnHhwLPt3lDyApDBhF0vlYaF/JtvhhwfNivrvBE4OEwoEG7vHB99Xn2WiPtKMmX3nltyqMGPOPFrCAYjCqeuwK8lGeNsUbXXqU0eKLxTyq9BIoFfnLfcffFG9iboMD7GDp1R4icGzp+cKCz7PYmKFAEO/2CUO5aSmhf+RjwdXNvoWX0C0rypXtAoPSP8HqzJrnjKAqLHpxYt3vx1gE+WKg0UYpv5hlUonAytB5LCNPYN/+qn1Vjf7Ft+7AiTqH/+78GSa9agEzwvq66zjQsc7cAgg/3+mJHSov0xF22p+enbCwaePXuY3Txrl94Hcr9Ap6kIDAYDqhrVML+3nwTrOJX4IbibUyBi5PnTu4W+G0ZL2f1JYuPTAgvUJJ/nTsKhOMJQueOUUn1zh0DCLqEnBluj1qUyO7WhJ/l3AqvjLTdjT+QCdyIoUdaW+4Z8CQhrIxlyDpTW7DWYc2o3uPygcDegpfQbF3kngHY5uC2+BwpDbkLhqtpvcv2Q93ygd6JQvdk5xTfjjbnCpe4WJuN514ZfYIrxWsZKvX+C95T6vA3fQGvHp76H5evAWNI4Q+DJB74uGWpcwdN8UzG/e2RwGtUZjV4T/Cb8TifXgHtb48EXqMyISR3k0qF/CH72yOB16hMHGVtPfBiDzcnJyX55oB+C8vEURarCZ6J2lm44i+d8xqW6UlCcX1boPBDOPp1z90Cv4Rlwj7dD9kqcdWbhpJ8iYd6C8usl+ArnNzmM2zlFF9e2LyGZeLdtW83+4aWLfTofc+9Ar+EZUKpZQMUZAO/mpw2e+4V+CUsEyulVwJ3L/VS+kkydwv8EpYJYn23y/mcvOcOgl+iMpFi1Szz3vCNjGZ47iD4JSozgIONXjXsuYPgl6jMLx79QUm+BHo+MZeNoc5RmRdeHsrDBVdGNMNzB8FrxesZR3FrWYeAcilzBwHHXP58BWV2V0slcyDQhRJ86RzDC+Yr0OwnouOPRmXHSwGtTBMaQrl7wDtnh6sMc7ALSnR0PJ4kwCuLSrsFvBZuyNe+gbSlbwDnNzkePozKt/ctF08piOrgnfXXvvEksTF57++4yKHJmHsHfkmyuJGxX+pOp27kQd1z78DmsxGyCwVKzj+BHb/ChIMqNi6XK9yFHNx77h1AQCweqPiyIc1wedjxvn+v1Ujw5aLSeijFtxBpaFptS5Wh/0LH/3gDYNcB8dYzJo/5njsH0N8LXCuQZPv5IsfjIOpGAaifqPNBtc59A79NxYL5ve24rz6IeORJvm06eF9wVLXpnwiOh2Zg3egwF3E1yFbGm7yAt9KK/15ROAEcj8OtuZ0KEUPcH59c8ZfOUVgMeBu6/nxx46HBe+Dm/AQTXHj3zr0EiDiFvq0Xae82ZcfGw2z1ozN6C88xjQ54e+4k+KVvEF6GRxh436pU59xHsFUiC/pxl75Kdmj82tx00CQ8cIbgvftNWcBHZIG0S+mKNg80vjoylg+e+xf4MZSTfOuZHWyGZen6Jg80/qyoMC/luhiMMMK4eZ3+GrseOczkb9lzH8EvwesZjx1PUl7soLfg9S9oPC29uY/glyRvRLkbv9iWKMm37nlry+hN3HPPwG9Fa2D3HWZ04QnzJiiAiYvD7HXUDPT0Nd648O3fnnsGfhs5jDpf2bLIXQO/CSkEIDtP7Nw1gJtxPIWBhtClEvjg0/Hs3TdBtz1OxPasctKSm7sGfuvmCCan7sldAwjnAY0J0VAUaV7x6QeDyTdEjFDF30II3ksZIe/UPW8hBJtVhpzP50sB4cGnr+cDed+g4cLHsNw3sAE0h/dX+7p849PxjHuTHV4TbKq+jD7dc+TeAdw5Lz265ifi03HErTcubg5DGEofrRS82UuS/C1s/4tNzkmmEdK/hO1/AdQpxTR8/Zeo/Tnj3RNMo2/eY/YjFbxQpXNhgV+C9iP0m5xqRy4s8EvQ/hdPm1JMe+aXoP0v5je1ZK4s8EvQfqRfL9TbubTAa9D+8RM50bQjHrm0wC9B+xF/TQmmq9p7yP4XXZlTTBe1X2L2"} |  |  | - |  | - | -
[14 empty] | {"index":127,"total":402,"filename":"Advanced_Project.ifc","data":"CWfunRfRHWpTvJCnsQS2ARedvb8TnUFZvOK3+SMDjcbR2VJd+Db2pHf4No12YBpwwdn5+sgnfBvkoFf4Nrc7wttQdDZyWFP8NpL37q/4bfLWksA0wAHadvBUH8KNG9MrhJuLDEaHA7RtM/Qh3DjFfAg3NzwwDfgI7WvlUAx3qe8Ybv7KYHg4RFvkFcRdbDt/BXHT0gmMAy5EW66I6yeI20T4K4ibXlQlMA64EO3+7uDxJK8gbtorIwIBh2iX9M7ebUX6IG56DpOIQOBCtN98EltFcRC3RAQCF6O9vXEi6XxFcZNtViLjAEi/YGBIaZEZ73z3+tHwwDjQLg/Nh2hHwOz7K6+AT/5KmkSBccD6S1vmZZM+stc3NWd/N5y8eiWwDuxIRgrrXgLT6bj8WArY6Rv8O+yWjOExtdWisvB4T0VGcvrcf+DMZ5duRLG8sQZfXfn5SqCmBGyCCJ6S2jtqywFe7PJRsy3Cx14jgUUAnow/8JyvcJkvejmvILTcttgdyXeAd0Ics93AYVsiKfCVUABnHSBdDUOs3YyMLGT1CmzBeYnU9Mg6wkUGQ2K99IO4CRwmTQK5/js/+i+CEZi4g8MU/Jf13Jtrkf26eS9B07Z5YxLNRg47eWEJFJkEXPzzPgENyytCmiVQZBPg+Gcp8gIavuKj6RMDg4ALfs5JZsCfD48+uMhoteyKTJDIPwp30DdjPL2K5An0zR50vZfevccyN+IPMO/+YrQz1i/FJWqEH7hZ5SB97ZdzPi7UZ93h0NEGRBEhhqNbK5cY2J5P255M4wB4mcu790599R5dFzSwBhQ4F+Ij7LSHZHjDIKdAff7I4A16w1MiIshxSJU3zXDP7zHmIiPT8wnLf6kZWSx7HCG8OOHKh0zBbZPYTFGYOjGBQQG4GrkIbHhkQTY9O971fBP4juOj4ZE5wNRNs4gDvZRG5DFsQciujYw9OF1sx5VmfNnIs1q/0gnYbERUBK5CLTxagIREz4L5gtMFcafQ/3aKUYnRcjlMxgLSaDfIHeeVn0PvwaECg7HBaQXPe0nt7tWmeYGdLsNJ5bziCGGKV2QU4dGOuIN48GxuukfbSS53coGZbof9+koyg0hXm7mIyhUqMtrKkPIdQXk22PXsdEQkOdiRSvvabQFsOJtXUKKEexoYAxBt8rNDzdvVHJqpBeDajaiJ6PbCYnMyVwQ8wPxD/ngakgdxPYT90O7nejm923V6g3aAx18rsOUYzG3eU4GBkfMoP+2xVHDepQ7DhPuvzWcr8Tpck7bAYbtFkq1PI+4gR9fKdSg8YX9Njrr4W7oeamAN8OG1m7xiE8/jFYBb+Cv/Dnevrwhcyg6jEXmQ42t7TO8rytNF4CqVGEqAX0Dy/i/oUVYjc8CvuPtXCC4tncAe8DtR/RWCy0WGQNVP7Ht5x+BykTEXkuD0r/joHtxBf8EbW2AQ+KaV51cMLpkPNTAH+BDbY0FUd39Box0YAzwLvLmOOxb4/grBpcRmGvkJOGK51plY7kNwqRtjGCFhtvMxqVIXgEuulxqxCL9R4DWOv9XAEADz2I817oS9COfLS/vlryI/yWpeMJd359FGFrkGODT0RIZOXyVGTmgdwYt7mp7pBcSWa0BayvIDoVq0fwd3f+u3H5hDrWv2hXTW9NF9wd3fgcDP6Z6g+0e7o2ABW2YQz4h7wWGyEHzxVwaDc33mgQQbzafCE7HbWoHjM+I1GwiGSgy1s7UL3i22L277e7yvj4zaHWln3X6wKSAV2rm/gdh7Gx07DGC9rVtysiKOG3C46xcQe78i6R5kNt1dNSQRHjbtABhFlMn5nkPyMTiRFQDMXDwAIC+knm8gdrlIW4g2MYEExUs7T+QYAOsRiCTbBt7iG4id29aD4nc441vncldG6rnj6eExDLa0Q2LvfXROmz6mjJA7guZQYAZowtRKRAjq3hL6OyS27FecYzMCIJaEwlA1cg2AMBU87mAubuWNxG7DA7M70i4dgGtSkQGU0MY7wWm44pVZ9IXEvmQFqIx1B2CWPbM0sAT48M3zDantRd5/wS5pGhgFXrjpfWF8DSI8c2AUeCGx35lDYSH2EZ6ViowcNxzcWN9w4/Ju90FF/pfo0B+fFr1vms7eWo6iemVz86a4/V1kpiIjO81m0u5AXs4EwM+LDt0G5EBQ+XVqPjMxR44BHq59vuHax7v7Tiryv8CGbnNFWnT4YbvkRskec3D932FKgTfbhsx0+5sNfe0Ou5rEVbzXMOMuf0UIPOjn07Oh8Qri6NF559YGI9LixW0IEKwi+9tOv39Mv8gCkFsmDKRcrGct+4sNLdcFoTTy2ZldhECOLACeupwW6y4KksxRhIALgTzPV5AkMEY+SDJRkSEbmgjWerwJ1vkVJHlwX65HB+7Je0umD7/N43wVqeWjyChYINgdwg6M8gZ49On7tewo7yJpew0u/o27XBKS3OHNtsxg2o/WBjECxRF5J8L99JXc8Og9JlWksKzIWdPc0G3mCBwXkEsA+S2umWPTvzRfVprfceaAm+h67kx8xdtlKxCBiTjv60Zv1zm49sPh7KeZ/TdkpGwdidcM2SuwlUfrSDjkCO6X8IqhIsP10j8hw01YPJY2af7j/4KCinN07a8K/26RK77XfSXeY3b3lSffgHMYInCxrE0v5DovwfN8zyAa7ihEANmHYHVBWksRvQLcoHuQcwVyGfGMUOetK3m0g5t/Z4G3QPlU83ual+PrIyNKtLbkbSDFlRaH/nzkAd6K+0r7cC7ygxIN8zdMrFXfe27aP9Z3cPlvlGg7PgHfgR/N5QawI8qg+bxc0xK5E1oQAidez9HtH3cuxAruDTGTuUhBggQuUpD6kYoMbWZMS84zLfkV2UeLJ3IDcGjjdLzRxhJH9uXIDcCH4b39VZHxqLkO2u/h7kaPCzmwBPwWMyev6PkcXP9/LwdzHOHWuAjbIqFPi+ICfmtshOTNUViA/8a3pyb85C4kL1zPTyVLa46iAn4Ji/xjUwmWVgQT4aLMJf5T4/EOykI/AiKLtLV2HTxYkQZX/yviCgZLTNuL54I7xoGJjdCVhpBFdFsxVZrJCycHN/+rRJtSppSbtLtKhE8mkpTtDSFrR1FLHmWfxcdrcPV/deQ7UFBqzM7N0dX/t+kDIIQdMrnWDUgXGpvIAQBhgHZYV+RJkh4MCvLnsbeMjHiiwEtd2iBP8QTwFBk5ALTAI93hK3F25kwCq6sgL9oBCqbNxh+4aQPYyg6qOfIBSLYB2G6YrM6tnD1SxRR03eERhcz9VhcgQc3xx84OKvLvAmsbWHNHqp+WVzjTM2mObv6IEkKuToWD7xWLBsMC0pYhIzMQUAimt65snBJa3dHFv4VUFgTH5caib36VFc+qyF+LLIU2OREAZxMVT4pPu0t88z9weWnpqvZrCuFajGdvU2E2J8/dTsuCSM6D35tLcO/H2MBPCVGFCTC75tndkoHAjcEWJ84rG27rhxM17VRkODbIoHjg5rW3Z5SL59wslphZfzATfnbrztIS/RxUZDw2MFhCeBSEdHXpUnELs8vgM80bZ5VshSWwAKDddjPFdgGil3QgmwmXhIZj40zIkwA3Iq2FwkJLYAL4ZcOwk9DUKDIIVJulAL5QifGuhteMCsvtJleUoEkKUFfwwgvzMyZtuva1SpajEhgD/ol1s8MBoSVyE1jNqch4VxP4L8EFfdBj7coN44T9HkkPbVjgSwXzMfYQKjIcnHRF18JDaOsRKzYOgOE1tu9u//WnmURtLj37ZPlIFgDcTTLlt7f7ayOIHXbLqWAxIdP1YbcpvFbAv5p8P0qcLQDmkgNoNduzam/2Di8cm9W2uE2mYJbawYTstmQhLZEt4DtmTJBhZEfM9Y5lBR9lKjIMQ+MQr4XA8GKqBAaA38tphFK7ICGNZOLEQSVyAvilteUNPaWpGDkB+K9850bApn5BT+ELKnsmE3OJnAB+HZMMPK9NK7v6t4hQKvJvx8TEke0UuXHfkG+ZioxjA8GDBpjoaBftoagKMmQCMwRUJ3LpIAPHQZKqRF4AV9TRAXEBC8IjqfAs0SAkxYq8EhGZ5qBYiBJ5Afw+4p5RelKRfzs8qQHyKg5L2JBpFYbmgHbW2OWw5HymrqmQ7Q+pSnJLDl9/GqkcGxyTc0vkBdCiRuC2t9kueF7hcri45KOBxCGpkD2xMd9ghnhKjNwArOcFRlukzR7RoHCl736fcM39gbcOXlfoGlciL4Df9wmQBjUJMhvlRKqvRF4ACBEqmLK2gLdtCCpYZG2HxCO+CSpQwjfkj8jsJ10iNwDEodjRamc0Yo96XDbyDyC2CbY+xPn/gCp5wNhNwIISOQJgaOwK2Bh+tQekFyQyMrEC53ebk4f+IHTc/j9Gh5TAFIChaWH6dpQA8NQVlckcm5OQFqaoUuuKHUEG9eQiw9FB+DrEM0JVrhAvScgOgpwBjS7QpyQyGwg9v5bIFAC8MGJabKoXuYps9l/bdHe4lvwBmB54rg22OOGFE5kCfp9D9nFINS0wzAqr08gWUJsbGAhisBdfRVpX2F574E3PdMBpG4bd121TypzLvURWgdrcZW1hI1bmWopIEW3Xa/gbmrKAH4eU5gYKggGV+He7WkXicNQKG9HOCycyCmBKwtkPJv98XWZb2GVBNm3r/T9Io4e/QecCn0ZFxgtnb9lN8JLQrw1w5gEpzZZiQkdmLC4FrcPdRCKzQEXSG3SioISeHKLCrKbwgMmQfchmh+RYuIWTIojsAu2Egu3Jul+utAu2D+NNCY+5R1Np8oOo/0YzIl/xEhkGfCzNOwyipUZlsh3fRSLDgIvu2N8hJcg09iSulcLPkSUyDPgi34+vLRD/wMXeROzFB6IiQ7/ADPMOPGBxYntKYMJER8D1Xht6GH5aT5GRZcD35Tskoh4vyCL5opc4OsDOErE5nLd8sSUfSqCNMzSG3Vjg2A5UA+9rkWEA7q2gDyNOUfPhKYGypT/uL/imGNkFfmn27mF5Qs8DJTIM5B+bXVBjLWnw6SGBzY7TYXmg1Emi1+IaGQaQlHbHa09CCMzxggSafrOpCXdG2CXzdtLmWyPTwK8N93REsiXWMG8AImBwwTJd0iJNmRK4Awww6IjwA2V2U41MAy7AJL8DTGwG7DZ1fgD7KTAwUoRXjWwDzmn/eGOwJvZnjSwCv5bjmHE8c2pkEnCtLentWrn/SXiLP+F3aeNOof01sgi0xy7EjQJEe3EvHlae/U/EJbNb5047ZI0sAr+220MCeeJEFgHXbn2Pci9xQ4iF7RtkOa2RRQBxTAUYbkE+idOT8tpZA8BABkTDpj8lEq5heAD4FEgp2l5XigflnQguRQwsKsR1hoPQamQQwEdiy0ZMQk2nR+WdyLRqOsY6G7Lfdgq6MNXIIIAHORsWRF0DRvFi5ZUL53v/hZuTkW3AhANSRSH9uJVSPSyvHi3dcYaD2olrSaJQixrZBvwMWizAm9+IOAuKLa2RaQBH7IGXMjzApTcrz9q9W1Xt0aHmZhqjIsPR+fpIXONteSdg0OFO7j4y1gFI0wrXM7AvPCzPNDQS4SK7w6bNXYqC3GscH9BylZT2RlhHEEOn5WHiH3gHrmAagwhCxNMaxwfwjru/1yL0aUNU2G5hd57MszKyDMCbGBPIJjlodp6Wh1weyAkPBbQBh5bJobhGlgH/lW8ndFxwMHErUm1kXBVpokeWAaTnRRlpx5CfL1xebZrqgD+orR/EMnLDw+ER2NY3eE8DoeV4eQl8RG2ZdGyjPCv29KfIyDSQET8GtygIh/P0vLyEEwKxVggOAi+4colx9MaHszy0BY5Yk+i2G+Evuch/JkRgOrVRpD9i48AALuft413yC7FEqcLr34UGWJHpCqlCCt9i9xqai5FJAJEBp20J1lKRi8X2sKX0YIgPdjQ6tWPngF/a/UJq8UeGQ/LZ7oIiTe7t2eYp40lrZA8Q2IsUZzKKTR4sZVvDdcS2QCS74p9kzq6RPUAQsoms99jEr93sAUvZhdDOWMx222dsTSknUK6RQaCFjiBrIxxBc/FkKbwt2UlbGpInNZYNKYHIIiBgHYHDaROuXD35kKXy5blBf0E+fTWyCYgdBPB8hC9pPl5kqfuMRfgT8niIcpH/1NJZLcEbeNbiLrkvw+EBPA37jOIO4MlSgBACEG5bPVIL4YJMh2xkE/j1K5GZBpQugdHpJDtVjWwCgqT6YrPjwCvK/kJLwf8Ap6xdcJC6BLZJKjIeHog6WDYBNn6hpdpVqSKCAg+KCBem1RPGCfy2HGH+/UFgms1Ku9tyw8PhASEtw0kJQSIvtlSFs07D3GpLUJPIClQjm8Cvm2VB/HrCDRTkLTJ21sgmAEdfBGXCXrMPpTbYUifYyzhlbXSO0qIyuMhweOwz7PC07Wg7ypstZSc5Tlk5N8wwGy7hIuM4gbPlhGqPC+eLLWVTIMGkX/b2eLJz8qAaxwlw6MHbCmTz0pGBnpSRyC0VvVFynMDb6xQWG1ObzYnUutQWZaYiw2fPX4oUm+iYUhBEiIajIsPRObCJVbhe1HS8GEto95bg6iYt1d8jWKzEfyqI452ipSSPqzoKd2UcxAEZVmFCbS9szFgC884Kt93SuiAjPKg8JUbWAflp9hppponLFvIgllK+/PLvv6jck5F14Jd2Hx41RDsbwu6jIpFfCQ/OMNPkF2KpZWa4UEP7sduh/NiVrMhwdJCbboeLO3xZPGMJpDekpwC5FnkPbGVyw/+ppbMYcMeWIqlhEjgcHrto4PEHV60XYqlRLwZaqiIbqnKJfxs9AD6XHXcmzcXES6aJHkcPkKu/vF14a35s0eXENZBK/GeCByQvSrRljY/c4Bx97jTekX3At3uRIuuFMaLxjuwDcMhGJtANScquoAmYqZDiFG4dwBjBJXG3UwgO9FRgODbcbFk0e1CMbCOuRHfB82X8jQlElKYDWmCCwGMFefcFqckbcggPUcfZUpNTkeHg/BZ/4pFDVGI4NnhPAEjAjsEefrI1QF6BN1P+Yzr6p0lVPPLng3aMMJvgzwZXbxtHu3jX/aLawA0ex7rAqH9ANsANc8P7HRf51ysH6rci/EjaYwEVGY9ORsyTFdesnnDtaz4HBeGrpq4OBXsiQSshoJBKDAdncJR2eOQzaQlG7/OP+4vjpJUTWQd+bXfEyYFFOWw3Qlvs1lT1ivHYpUKywPcJplmT2T/tQby9TdO2FlkHft0xOmoJj5pI6UNdGVkHjhY9Bo8J233byoHPvl1s4B6Btyv7NCTe2fZKNEO4/8WNtmO1wJZ0XBAsxTUFdm74AV0IowqXRLgR8GhHVoJfW92GpsXAwZq30WYeWQnQSwnARiQAu3Y1ZFZDohWk2il/2uVJYFxqvnFCRYZjgxQ9SZHVWS61Bt4U/FmRuAYJqqstV3xxa45SkdfY/Ps//u3//ds//vHv//Iv/w0RyrL9uf49+r+p/6vXv6X/m/u/Ov57//uyUQ3XaP3v//4///Uf//kf//p//8c//vP//K9/6ZX/+fmPn+cv8/2X/9L/gL+0rr70rrF/IYu8vMc1V1dzv+JTzTzf8rKPcmk1wnZw/UuLKMdtzr7NeWpzpjbnZZtr6b0+Rol6u8Rtzr7NZWpzoTaXdZt7L9fe5p2WUInbXHyby9TmQm0uqzYjkvz6d8w06u0at7n4NtepzSw766rN9/juY5ypt2vc5urbXKc2V2pzXc/t8lpdzy9Mp8Q1uzbv27vN+/PeijQqyxnWZ9aY4zvXHLbZCvM1v9tsv6Vylm2W3uZ6z7TnF3vYZivM1bxPbSa5ue/Lcd793qZPskf7Rdzm3bd5n9rMfbcv21xGm3uvK7X5iNu8+zYfU5sPavPxtYeNmnXnmuM2H77Nx9Tmg9p8rPew3ttjL6N9264bcc2+zefU5pPafC7bXO4zapxZ9Iu4zadv8zm1+aQ2n+s9bOwk23Ri2M07rtm3OU1tpmvKnpZtvneQsqg5bnPybU5TmxO1Oa3ndvLKgE70XeI2J99mmdpMdpJd1nN786uKbl67xG0W32aZ2izcgmWbdWiRMq9njdssvs06tVmpzYFuu/eusZfRL+I2ex22Tzps51Fb67B711ycVbEO270O2ycdtpMO29c6rGuR58TgmuM2ex22Tzpsdy343MPKrIb2WIftXoftkw7bSYftax02lN+9i9J6jnXY7nXYPumwnefLUoc9+/U279uxDtu9DtsnHbaTDtuXOuyucXwBqd491mG712H7pMN2ni9rHTZqHL2tT81HrMN2r8OOSYcdpMOOtQ7T9x2Daw7bfHgddkw67CAddix12FC7Yxd1Ncc67PA67Jh02EE67FjrsC25U5Ky1Nsv4jZ7HXZMOozy+8Ab+qPm+8yiXe+Iddjhddgx6bCDdNix1GG2c/idZCv0i7jNXocdkw47Dm7Bus06ahy9/vwi1mGH12HHpMMO0mHHUoc9KmgoA2pzrMMOr8OOSYcdpMOOQIf53nYzLNZhh9dhx6TDDtJhx1qHFT+33TjHOuzwOuyYdNhBOuxY6rB7Nd07Cv0i1mGH12HHpMMO0mHHpw67d5RKMyzWYYfXYcekww7hFnzdn5+b+3NWHbEOO7wOOyYdRnF19p/XbX6rIRrnWIcdXocdkw47eEda6zA9XM18iz1iHXZ4HXZMOoztr8dah+k9vpPN4Ih12OF12DHpsCNzOV867N5FyWZwxDrs8DrsmHTYQTrs+LSHjZrdeo512OF12DHpMApps/+8XM9Hb/PRaz76uB803rEeO7weOyY9dpAeO9Z2sbOP87G9voD6INZlh9dlx6TLDtJlx1KX6Xn4Lxhf9MAMQDeLv8D1wTnps5P02bnUZ8iJ2/5No+Y+Go/nKiz90RecXqedk047aZc+1zpt1Jx6X5w6vuT5ZazXTq/XzkmvnaTXzrVeS8nXPL4k9f8+9sJug9BxRx07Vd6ohrivvL47J33HrxrnWt/dNfYvJsvPGeu70+u7c9J3J+m7c63vxqnbbxKZ1PQZ67vT67tz0ncn6btzre+6DUJlzBNaG7G+O72+Oyd9d5K+O9f6rltBtKusTMryjPXd6fXdOem7k/TdudR3uWvaPG4S9Lx5xvru9PrunPQdJR2z/9+yzff49plGe9gZ67vT67tz0ndn4nLWc7u8Vhf9ItZ3p9d356Tv2LPrXOo77ffyZ47TOMf67vT67pz03SncgvXe12ss90x7fhHru9Pru3PSd+S3af95Pc6H39t4fGJ9d3p9d0767uRRW+o7lTGzeptJ65yxvju9vjsnfXeSvjuX+u4e3z7eeeOa4zZ7fXdO+u4kfXcu9Z0O2+LYy3jfjvXd6fXdOem7k/TdudR3mu8zapxZ9Iu4zV7fnZO+O0nfnWt9d+8kixMj1nWn13XnpOtO0nXnWtfdO8iq5rjNXs+dk547eS9c67lxLo9zmnaAFOu40+u4NOm4RDourXVct6feexnd11Ks35LXb2nSb2njFnyuZxnr+TmrUqzbktdtadJtiXRbWuu2sYeN+xqtwxTrsOR1WJp0WNq5nPU4q6+Zdr0U67DkdViadBjl5bf/vD6rjteJwTXHbfY6LE06LB1czucelmc1lGIdlrwOS5MOS6TD0lqHDeV376I0w2IdlrwOS5MOS6TD0trOdu/X27Rvp1iHJa/D0qTD2C0zrXXYqHF8AaneFOuw5HVYmnQYZV+1//zZ5tHb9EqRYh2WvA5Lkw5LpMPSWofpe1XRHhbrsOR1WJp0WOJdeK3Dxq45NAnvnrEOS16HpUmHJdJhKdBho+axrqm3Yx2WvA5Lkw5LvCMtdVgeNsVbj9233ueXsR5LXo+lSY8l0mNprcfqSwly22M9lrweS5MeS3wOrPXYsKuOmoVWV6zHktdjadJjifRYWusx8fdovl+lWI8lr8fSpMcSnwNLPXbf6IZS4JpjPZa8HkuTHkukx9JSj5n+ckqQkpnYL+I2ez2WJj2WXAvWbR779hjn5xcS67Hk9ZhMeozyfdh/XrZ53/xpuXHNYZvF6zGZ9Ji4ctb36Pt2M60qifWYeD0mkx4T0mOy1mP6th0U+kXcZq/HZNJjhBdEDqflOKfRy2OmPb+I9Zh4PSaTHhPSY7LUY/ecHutZuOa4zV6PyaTHhPSYLPXYaOtzw3tWlcR6TLwek0mPUU5R+89rbZLcenZzO9Zj4vWYTHqMgi7tP6/bfPfysI89v4j1mHg9JpMeE9JjstZjXQ3d65osNRLrMfF6TCY9JnTaSmAXS65m19uxHhOvx2TSY0J6TJZ6LPdXibyPttPcjvWYeD0mkx4T3oWXeiwfh6/5oD0s1mPi9ZhMekxIj8lSjyHF3FVz//egcY71mHg9JpMeY08MCfTYaOtoO83tWIeJ12Ey6TAhHSZLHZYPfbV5/EvjHesx8XpMJj3GnnSy1GO5vwHm/hqV+7tY5l0w1mXidZlMukxIl8lSlz01977oL3GUwcV+GfeB12cy6TP2Y5S1PjvLq+b+JYnmfqzTxOs0mXSakE6TtU7r7173l/SXuUx3T4n1mni9JpNeY79GWeu18QX9RS7L+IJnJmqs28TrNp10m5Ju07VuGzXK+BJdfEHYB+r1m076jb1WdKnfcr/556Ec6RassX5Tr9900m8crqpL/Za7VSv321Ema4fG+k29ftNJv7Efha71W7fY5nGu0+mqsX5Tr9900m9K+k3X+m1omaGalWuO2+z1m076TWnn0rV+G23uljzX27F+U6/fdNJvSvpNl/otj/dMvb+AfhG32es3nfQbZbiw/7ye2+prJs2qsX5Tr9900m9K+k2X+u2e05dl/tzr+BL+grjtXsfppOPYaqJLHfe0edHrsY5Tr+N00nFKOk7XOm7sKGWbZ1qs49TrOJ10HN+mda3jtPi9jOxqGus49TpOJx2npON0rePuvSzN6zrWcep1nE46ji39utZxd5vLPMNiHadex+mk45R0nK513L1v69zmWL+p12866Td+V9G1fht72RhnsjlorNvU6zaddJuSbtO1bhtzu78++ZrjNnu9ppNe43cVXeu1sYuO/ZtXQ6zT1Os0nXQapxHRtU7Lr5p5fGJ9pl6f6aTP2CKoa302enn0ut5zvH/R9d/LNv7d+r/XF5dxw6DezbGeU6/n8qTnKO15yks9d39Jv+MQ8CPlWMdlr+PypOP4Fp6XOu6ucVhJKHorxzouex2XJx2XScflpY4rx+j9q7fLudEv4jZ7HZcnHUdMd/vP6zb38e532MK9FOu47HVcnnRcJh2XlzpuzKxnpnHNcZu9jsuTjuMbaF7quKetaZ5hsY7LXsflScdl0nF5reO6zbH0l5xC9/Uc67jsdVyedFwmHZeXOu7u5Xt9U5tjHZe9jsuTjsuk4/Jax9V7fEfb6Rdxm71+y5N+o1yWyK23nGGb620itqYc67fs9Vue9Fsm/ZbX+q2OdTzGmb411m/Z67c86Tc+sfJSv90zq3uHZ/LVyrF+y16/5Um/ESox5aV+u9fzsIq5muM2e/2WJ/2WSb/ltX6rm2tzIT+HHOu37PVbnvQb4S9SXuq3Z1WleQ+L9Vv2+i1P+o31QV7qt/tcrsd8Psf6LXv9lif9lkm/5aV+e2aYzjtJrN+y12950m++Bd/rucw7SazfstdvedJvmfRbXuu3sW+Pc5rP51i/Za/f8qTfKIssoBarNg+76rWjnMewetIvS6zHstdjZdJjhfRY+UWPjfN6o1+EbS9ej5VJj7HSKGs9Ns6qu+ZnppVYjxWvx8qkxwrpsRLoscPXTPt3ifVY8XqsTHqM94cS6LHDnxzcS7EeK16PlUmPFdJjZW1Xq3dbJ/VbYj1WvB4rkx5zfRfosW2cz9PqKrEeK16PlUmPFdJjZanH7vW8H/MMi/VY8XqsTHqskB4raz12vnQ3vZeVWI8Vr8fKpMcK6bGy1GN3zbf6PegXcZu9HiuTHiukx8paj/X372dPo1/Eeqx4PVYmPVZIj5WlHnt02KzHSqzHitdjZdJjRbic9TgPNTTOrtdcH/ev4QdRRx/R6ot1W/G6rUy6rZBuK2vd1t+OSn87KufQrtS2WL8Vr9/KpN8I32j/ed1HyX9Bf8Ep9IpVYh1XvI4rk44rpOPKWsfdNY6+OBZfEPeB13Nl0nOF9FxZ67m7xv4F3W5js/35Zazritd1ZdJ1hXRdWeu6u8beF/1dzX9B3Ade35VJ3xXSd2Wt77oPfum2qdLt74VyX5RY5xWv88qk8wrpvLLUeU+NYxTK4gviPvB6r0x6r/COt9Z7d439324NL/QCUGO9V7zeq5PeI8p2qmu9d9fY+6JbDv0XhH1Qve6rk+6rpGjqWveNmru9tpTxBc8o1Fj/Va//6qT/iGad6lr/3TVffVHHWTl2575713Ej6Xb8UvgL4z7yOrFOOrGSTqxLnTi+qPbzo9IpXmOdWL1OrJNOrKQT61In3jWOPqFXsRrrxOp1Yp10YqUzua514jgz+yhUuonUWCdWrxPrpBMr6cS61Im133Vrv3lWikOrsU6sXifWSScSoRUQnmXN22vGUc2xTqxeJ9ZJJ1bSiXWpE5+2LmZYrBOr14l10omVdGJd68Ryt7V/waOFaqwTq9eJddKJnOe+LnVi3cbMGjON5nasE6vXiXXSiYR9sP+8HOcjvXqbfhHrv+r1X530XyX9V9f6rybX5krW8Brrvup1X510X1VuwXo9j7aOmmk9x3qver1XJ71XSe/Vpd672zpslnTXrbHOq17n1UnnVdJ5danzxnoec9vVHOu76vVdnfRdJX1X1/quqGuzO4djXVe9rquTrquFy/nat++5zXtYrOeq13N10nOV9Fxd6rl79xyvnOTNUGMdV72Oq5OOI/ql/ef1+fzew+65LVus36rTb7K99Rt+S+V87mH3OBf6RdRmFOZrzlPNSuWsx3lokvTew2QL9RoKczW/9Rp+S+WsNcnYr9t4g7rd//tBv4zbvvu2v/UYfkvlfOuxY2iU5xehHkNhrua3HsNvqZzPc/qYtIlsoR5DYb7mqc08eoEeG/v3WGXp+UWox1CYq/mtx/BbKmd9Zqnrbbe6Qj2GwnzNU5tPanOgx4qv+aCaQz2GwlzNbz2G31I5Xxr0WWX0raEeQ2G+5qnNicv51iZl7u1Qj6EwV/Nbj+G3VM56Xb90N6/DUI+hMF/z1GbhctZt1teZRbtoqMdQmKv5rcfwWypnvX8fbj27PSzUY+K5BjJxDYS4BrLmGtw7yD7pMYm5BuK5BjJxDYS4BrLmGtRhkx4aZXvN9XH/Gu+t/dWzdrtu7baqmsZ/p9EK9Zx4LoJMXAQhLoKsuQi1Ww5rt9vVRHtgqOfEcxFk4iIIcRFkzUWoMtqaxhfQL+I2F9/mt54T4iLImovw9HL/V2mehHpOPBdBJi6CEBdB1lyE2q3pVbe5zaGeE89FkImLIBuf1ms9J8XPMGpzzEUQz0WQiYsgxEWQNRfh7uW717nmsM2eiyATF0GIiyBrLsI9t0Wn3o65COK5CDJxEYS4CLLmItzj3PcFXs8xF0E8F0EmLoIQF0HWXIR7Jxk7y0k1xzrOcxFk4iIIcRFkzUW41/H1HnOe97qm8Y71nOcjyMRHEOIjyJqPUFPye9kTYy8xH0E8H0EmPoIQH0HWfIRnL9vmXo/1nOcjyMRHEOIjyJqPcLd51duxnvN8BJn4CEJ8BFnzEe4aZTHTYj3n+Qgy8RGE+Aiy5iPcq+seZ/pFrOc8H0EmPoIQH0HWfIR7RznToua4zV7PTXwE2V05n/v3ODl4ZsR6zvMRZOIjCPERZM1HuHt51Py8p0nMRxDPR5CJjyDER5A1H6GO+9mwpyqt51jPeT6CTHwEIT6CrPkItb/g1Ovl5tyGih6WIDpvY16CeF6CTLwEIV6CrHkJ/Qus7W2VgeM2+uT5ZazTPDdBJm6CEDdB1tyEOrRqf1erlUYh1mmemyATN0GImyBrbsJdY3+dqoVmXqzTPDdBJm6CEDdBltyEcxvWkKHnM/V2rNM8N0EmboLsPG/WOq0crzY/v4i5CeK5CTJxE4S4CbLmJlS9x7f/u9EvwjZ7boJM3AQhboIsuQlg7r16m2qOdZrnJsjETRDiJsiam1DzqDktao7b7HXaxE0Q4ibIkpvw7ChjvB/fbom5CeK5CTJxE4S4CbLkJjxz+3qhB2Kz73H0zbFO8/wEmfgJQvwEWfMT7j1t7Os802Kd5vkJMvEThPgJsuYn3DvK3euJfhG32eu0iZ8gxE+QNT/h3kXH6qKzLOYniOcnyMRPEOInyJqfcNc81jeduzE/QTw/QSZ+ghA/Qdb8hPv8rmnav2N+gnh+gkz8BCF+gqz5CXXYV6/zGjsM/SJus9dpEz9BiJ8ga35Cr5n2NBrnWKd5foJM/AQhfoKs+Qm3NinHfHLEOs3zE2TiJ8jB82Wl00gdbfM4xzrN8xNk4icI8RNkzU/oNdJuSjtJrMs8P0EmfoIQP0HW/IR+YjzjzCdHrMc8P0EmfoIQP0HW/IR+Sj4188kR6zHPT5CJnyAHz5dAj41e1vnEiPWY5ybIxE0Q4ibIkpswzizUOM/tWI95XoJMvAQhXoIseQlW47h7jFXV+2DcEMZOcyuIK9p/e2J4JOYpiOcpyMRTEOIpyJKngJp6jb2P9v4F9G4a8xTE8xRk4ikI8RRkyVMYNRPxePTBsw/EPAXxPAWZeApCPAVZ8xRuxrKMPugzdO/7v/Q+yv3fs3/h0f/u6H+X+IvjPvP6b+IqCHEVZMlVeL7k/rJjfNnzy1gHer6CTHwFIb6CLPkK1uZe8zFqpm+O9Z/nK9h/ndp+cDkfvB3r7cF6fM7ImK+AwlzNk/4jvoIs+QrnltJrvOlbY/3n+Qoy8RXk5L5b6b9zk15j7l9AtsmYryCeryATX0GIryBLvoLVNHp7m2dYrP88X0EmvoKc3HcBP8sR0P3qivWf5yvIxFcQ4ivIkq/wrKqx/un+HvMVxPMVZOIrCPEVZMlXwCrqvdxrpjfImK8gnq8gE19BiK8gS77CuZ19ZvV7Hb+XxnwF8XwFmfgKcrpylm0e6znrvKpi/ef5CjLxFYT4CrLkKzy9fPc69Xas/zxfQSa+ghBfQZZ8hefkOO/V9fwi1n+eryATX0GIryBLvgJ6t49vn+NKqyrWf56vIBNfQYivIEu+wrOTjF7n1RDrP89XkImvIMRXkCVfYezbRGqj3TPWf56vIBNfQYivIEu+wnNipKEYnp0k5iuI5yvIxFcQ4ivIkq+A9etXFZ2SMV9BPF9BJr6CEF9BlnwFnE29reOsojbHOs7zFWTiKwjxFWTJV3jm9jifSUvEfAXxfAWZ+ApCfAVZ8hVwQoz9euix5xexDvN8BZn4CkJ8BVnyFYYKevbtk8Y51mGeryATX0ES991Kh9F6PuY2xzrM8xXsL6c2kw5Lax12K4KhgrnmuM1eh018BSG+giz5Ck/N5xhn6u1Yh3m+gkx8BSG+giz5CtRWXdQct9nrsImvIMRXkCVf4Wnr3XZaz7EO83wFmfgKQnwFWfIVqM1jjm/0i7jNXodNfAUhvoIs+QpPjWMPo1My5iuI5yvIxFcQ4ivIkq/wnMvHPcfpF3GbvQ6b+ApCfAVZ8hWeGscX8MyIdZjnKsjEVRDiKsiSq0Dje8zjHOswz1WQiasgxFWQJVfhOSU1zbtnrMM8V0EmroIQV0GWXIWn5lsh0LfGOsxzFWTiKghxFWTJVXjm9K0MaG7HOsxzFWTiKghxFWTJVXjaevc67SSxDvNcBZm4CkJcBVlyFZ7T8bYZPG2OuQriuQoycRWEuAqy5Crc2lP3WwnSL8I2e66CTFwFIa6CLLkK1NuLNsc6zHMVZOIqCHEVZMlVIGtUmc7nmKsgnqsgE1dBiKsgS67CU+P4Aro/x1wF8VwFmbgKQlwFWXIVnrMqz6o35iqI5yrIxFUQ4irIkqvw6O1RM91iY66CeK6CTFwFIa6CLLkKj96+dxL61liHea6CTFwFIa6CLLkKz349an6i9iTmKojnKsjEVRDiKsiSq/DMrNvySuMc6zDPVZCJqyDEVZAlV+HchjfRIKrdHGr6ZazHPF9BJr6CEF9BlnyFcxsMt5tDXcYX0S/jPvC6bOIsCHEWZM1ZuOnPQ5OOdzQ69WLegnjegky8BSHegqx5C3reNfZ/B++MVl2s0zx3QSbuggivobVOK73XB4nrpj/TF8R6zfMXZOIvCPEXZM1fuDnTw6ox3lFrz1XdFcbe//f9enc79z5q+9b/lfG/9395f491n+c3yMRvEOI3yJLfcO79RXDvmnent6aY2yCe2yATt0GI2yBLbgP1TfJ9w7og1n+e2yATt0GEV8Ja//Vcalsdbad5E+s/z2uQidcgxGuQNa9Bx3gPbj29YsScBvGcBpk4DUKcBllyGqzGPuO6RX8nj46YzyCezyATn0GIzyBLPoON6+jle8bRL8I2ey6DTFwGIS6DLLkMT41j1dHLTcxlEM9lkInLIMRlkIDLMEh9d9vpW2P957kMMnEZRF0563FOfieiEyXmMojnMsjEZRDiMsiSy4BVNHaS/gWJfhG32eu/icsgfLovuQxWU5/T59hZHkUScxnEcxlk4jIIcRlkyWV4atzGF9C3xvrPcxlk4jKIunLWc3ucGONEod6O9Z/nMsjEZRDiMsiSy/CsJrnPMvpF3Gav/yYegxCPQZY8BlrPx7yTxLrP8xhk4jEI8RhkyWM4dxnjfLedfhG32eu9iccgyqtzaYfr+/XN/Mx0Tsc8BvE8Bpl4DEI8BlnyGJ6TovuCuBMj1neexyATj0GIxyBLHgNW0VjHY10/v4h1necxyMRjEOIxyJLHYDUVXzPdnmMeg3geg0w8BiEegyx5DM8MuxUh1RzrMc9jkInHIMRjkCWPASfE2K+HLqNfxG32OmziMQjxGGTJYxgqyGocOwnt27EO8zwGmXgMQjwGWfIYnh3k1p7U5liHeR6DTDwGIR6DLHkMNMN6zfQeGnMVxHMVZOIqCHEVZMlVeBT/XbPSL8I2e66CTFwFIa6CLLkKzx1j9DrtYTFXQTxXQSaughBXQZZcBbp3HUMJ0i/iNnsdNnEVhLgKsuQqPHP6VvrU5liHea6CTFwFIa6CLLkK94mR9/lOGXMVxHMVZOIqSOb5stRh9769z7tnzFUQz1WQiasgxFWQJVfhqfE+ObjmuM1eh01cBSGugiy5CqQ9y7yeYx3muQoycRWEuAqy5CqQGiqTJom5CuK5CjJxFYS4CrLkKjxqd8xx7qVYh3mugkxcBSGugiy5Cs8490yxblXFOsxzFWTiKghxFWTJVXj09thJ6MSIuQriuQoycRWEuAqy5Co8NY/XjMo1x232OmziKghxFWTJVXhm2Dgx6N075iqI5yrIxFUQ4irIkquAVeRrpttNzFUQz1WQiasgxFWQJVfhWc+39qQ2xzrMcxVk4ioIcRVkyVV4LDRpvkvGXAXxXAWZuApCXAVZchWecR43Oj4lYx3muQoycRWEuAqy5CrQrjnuVTTOsQ7zXAWZuApCmcVlyVV4LK63Re5pc8xTEM9TkImnIMRTkCVPgfbrNO3bMU9BPE9BJp6CEClAljyFp62jZm5zrMM8T0EmnoIQT0GWPIXH1jtsv7TfxjwF8TwFmXgKQjwFWfIUrKbe24MWOljN3PZYj3mugkxcBSGugiy5ClbzqDHxF+CL6JdxH3hdNvEVhHLZy5qvcLOaR+8PoiZ5RMacBfGcBZk4C0KcBVlyFlBTr3GwmidetcS8BfG8BZl4C0K56mXJWxg127+D2Xx/yfPLWK957oJM3AUh7oKsuQs3m/l0X3LuFPkW8xfE8xdk4i8I8RdkzV+4Gc1Dt+Xx76OiYg6DeA6DTBwGIQ6DrDkMeewD/Q15H6xP3gNjHed5DDLxGKTwvrLWcXl8weAXH/MXxHrO8xZk4i0I8RZkyVs49/56ufc3Q87jEHMWxHMWZOIsCHEWZMlZOI9x5vU3450yy8V8BfF8BZn4CkJ8BVnyFe6aj2E/pajemKsgnqsgE1dBiKsgS66CtbG4Nh9kV4t5CuJ5CjLxFIR4CrLkKdw19zYz21VijoJ4joJMHAUpPF/Wem5Y8voL/U75AWJ+gnh+gkz8BCF+giz5CVTzNc5Sxoyjtse6zvMTZOInCGdVXfITnjlex4x7fhFzE8RzE2TiJghxE2TNTRic6nuOU6/HvATxvASZeAlSXQuW433vKPN4x5wE8ZwEmTgJQpwEWXISaIalaZxj/oF4/oFM/APhPJ9L/gGNb5rHOdZznn8gE/9AiH8ga/7BwyMf48w1x232Om7iHwjnc13yD8Y4D3avrznWb55/IBP/QIh/IEv+wdjLRtvtX5phsW7z/AOZ+AfCWbiW/IN7fPc89nGqOdZrnn8gE/9AiH8gS/7BPb5jPR/0/hXzD8TzD2TiHwjxD2TJP6A9LM3rOdZnnn8gE/9AiH8gS/4BVpGr2bU51mWefyAT/0A4z9uSf/DUXMaqehRCzD8Qzz+QiX8gxD+QJf/grvmeaTzDYj3m+Qcy8Q+E88Ss+Qf3Oh7799hNy9jbuoLoXmTHMRiQ/f/eX2aPYfGnnGYxP0E8P0EmfoIQP0GW/ISn5vElvI5jPef5CTLxE4T4CbLkJ1hNvS+638PwKj/oTSnmKIjnKMjEURDiKMiSo3AeMmrs/wrXHLfd67qJoyCck2PJUXhq7haEg+4sMUdBPEdBJo6CEEdBlhwF6/VBrUvzTIv1nOcoyMRREM4DuOQo2Nzvu28ac//ubY05CuI5CjpxFJQ4CrrkKGBcey/3uf7YJjXmKKjnKOjEUVDK+qJLjsJYz88qO6jNoZ5Tz1HQiaOgxFHQJUdhjPPzBa7muM27b/NbzynxE3TJT3h6uVuCjyd6QGN+gnp+gk78BCV+gi75CVbjvYf1mbbRL+I2H77Nbz2nFHurS37CU+NYz9xLoZ5Tz0/QiZ+gxE/QJT8BO0dv65hpNLdDPaeen6ATP0EpB4ou+QnP/n2MttM4h3pOPT9BJ36CEj9Bl/yEZ06PvaxwzXGbk2/zW88pxa3pmp/QmZ6D3Yw5/vwi1HPq+Qk68ROU+Am65Cc8vXyfmrSeQz2nnp+gEz9BKXOBLvkJj2a5NQz9ItRz6vkJOvETlPgJuuQnPHN7rCqek6GeU89P0ImfoBTbo2t+ws3oljHTaFWFekw9P0EnfoISP0GX/ITnlDxvXUa/iNucfZvfekyJf6BL/sGjSe8voJpDHaaef6AT/0CJf6BL/gHVeMw7SajD1PMPdOIfKEXS6JJ/gLnsNUmiVRXqMPX8A534B0r8A13yD5623jXTt4Y6TD3/QCf+gRL/QJf8A6pxrK5nbsf8A/X8A534B0r8A13yD56aj7m3Y/6Bev6BTvwDJf6BLvkHzzjv90x7fhHrMM8/0Il/oMQ/0CX/4KlxfMHjGakx/0A9/0An/oGSL5gu+QfPiTGUAa2qmH+gnn+gE/9AiX+gS/4B7dvjxOCa4zZ7HTZxD5T8HHXJPXhqlG06MWLugXrugU7cAyXugS65B3S3GHvYRr+I2+x12MQ90N21YH3HGGfV+JdqjnWY5x7oxD1Q4h7okntAt9dxo+Oa4zZ7HTZxD5S4B7rkHjy9PW45dKOLuQfquQc6cQ+UuAe65B6QIhg107fGOsxzD3TiHujuylnr7fs+NW7wzy9iHea5BzpxD5S4B7rkHjxtHje6k2uO2+x12MQ9UOIe6Jp7MIj2t+6+75RDBafXHjf2+f6/K83IWLd5ToJOnAQlToIuOQmoqdc46O+dg0UqKuYjqOcj6MRHUOIj6JqPUJL7AoSs9S+hX8Y6zvMRdOIjKPERdMlHGDXav5351TNU+C+I+8DruYmToPS+rmtOQhnzoPuIHDf9nWZsrOs8L0EnXoISL0HXvIReo03ZPv49H6v/grgPvL6buAlKL0W65iaUMQrdM+MYFHhabTE/QT0/QSd+ghI/QZf8hFEjzOK95rL4grAPPEdBJ46C0guhLjkKR7nbXPhLYCp4fhnrPs9T0ImnoMRT0CVPATVdNd7E+94XT64rjbkK6rkKOnEVlC1MS67CqHF8gf07OMWP9o35Cur5CjrxFZT4CrrmKxzj9aN7bJzdbnNug+3a58l4Ae426VLS4kvjvvK6ceIwKHEYdMlhQNJq9yUnWVdiDoN6DoNOHAYlDoMuOQxIgdD76BotvUeLZmqsHz2PQSceg7ICXvIYRq/TKFDNsX70PAadeAxKPAZd8hjQ+D/c+yePU6wfPY9BJx6D8l16yWNA0pVrhtWJd6sxj0E9j0EnHoMSj0GXPAY4C/a29jVA98GYx6Cex6ATj0FZhy55DKPNNN5Uc6wfPY9BJx6DEo9BlzwGNLbX2NtO+jHmMajnMejEY9CDz5Oln9wzw3pv0x045jGo5zHoxGNQ4jHokseAmv5w20+6G8U8BvU8Bp14DEo8Bl3yGJDKaOxh/V/6Raz/PI9BJx6DEo9BlzwG2j3TvIvGus/zGHTiMSjxGHTJY8DO0cd3zG3q7VjveR6DTjwGJR6DrnkMY/8+u6fHudHcjnWe5zHoxGNQ4jHomscw1vG9l9EeFnMW1HMWdOIsKHEWdMlZGMze8xy2LfrWmK+gnq+gE19Bia+ga77C08tlOiVjroJ6roJOXAUlroIuuQq3drm1DL2nxnwE9XwEnfgIyqtzzUcYc/s+JWlVxVwE9VwEnbgISlwEXXIRxumI/XqMN/0ibrPXYxMXQfmcX3IRnlPy3sNobsd6zHMR7C+nNpMeW3MRHm2qi5rjNnsdNnERlLgIuuYi3DXeOwrVHOswz0XQiYugxEXQNRfh7Ha8W5PstKpiHea5CDpxEZS4CLrkIjxtHTXzqop1mOci6MRFUOIi6JqL8LR19DrN7ViHeS6CTlwEJS6CrrkIj/Jb9HaswzwXQScughIXQddchDHO467B2jPmIqjnIujERVDiIuiai3DXeH8Bze1Yh3kugk5cBCUugq65CPeJcaR5VcU6zHMRdOIiKHERdM1FuDXJ0GP0zhZzEdRzEXTiIihxEXTNRXhq1PnEiHWY5yLoxEVQ4iLomotwq93xDsPKINZhnougExdBiYugay7CrfDPsZNwzXGbvQ6buAh6uhZ82Q7umknFxFwE9VwEnbgISlwEXXMR7t7exr1qo1+EbfZcBJ24CJpcC9bjnF41PzMs5iKo5yLoxEVQ4iLomovw1JjGDZ5+EbfZ67CJi6DERdA1F2G0+b7FkhqKuQjquQg6cRGUuAi65CLcBPtSX/foe5Vtrz1u7LJjZva/7y8DZ38dPdP479T2WNd5zoJOnAUlzoKuOQtnfwU/u53+fHIvaMxZUM9Z0ImzoMRZ0DVn4dR3m2n0Yl3nOQs6cRbwWypnyQrsntWnjDY/p27MWVDPWdCJs6DEWdA1Z+EUfbWZa47b7HXdxFlQ4izomrNw1zxY7fQKFnMW1HMWdOIsKHEWdM1ZOPvL4Nl9TVxvx7rOcxZ04ixo4jWy1nVjbsui5ljXec6CTpwFJc6CrjkL99y+ZxjtxrGu85wFnTgLSpwFXXMW7t7uczwPNU2etzFvQT1vQSfeghJvQde8haft/V+lHSXWd563oBNvQYm3oGvewj3D7hlHbY71nect6MRbUOIt6Jq38LT1mNsc6zvPW9CJt6DEW9Alb+HZy8b+Ta+aMW9BPW9BJ96CEm9B17yFvrqOmrZFzXGbvb6beAtKvAVd8xb6XjbajtP4/kXMW1DPW9CJt6DEW9A1b+Ee33F+0y4a8xbU8xZ04i0o8RZ0zVt4xrf/S34UMW9BPW9BJ96CEm9B17yFZz0f0y4a8xbU8xZ04i0o8RZ0zVs49bWeuc2xvvO8BZ14C0q8BV3zFu6ab6VAMyzWY563oBNvQYm3oGvewl3zPdOot2M95nkLOvEWlHgLuuYtpGHZ6++diewvMW9BPW9BJ96CEm9B17yFUePZ722u5liPed6CTrwFJd6CrnkLaVh88qiZxjnWY563oBNvQYm3oGvewtl9Ac7umXGSH0TMWVDPWdCJs6DEWdA1ZyGN+9r4ArL8xHwF9XwFnfgKSnwFXfIVrKZe47gd0VtBzFVQz1XQiaugxFXQJVcBbXTjfJKnXsxTUM9T0ImnoMRT0CVPYXDJrcbBYqcZFuswz1HQiaOgxFHQJUeBZliZxznWYZ5/oBP/QIl/oGv+wejttI1/6RexDvP8A534B0r8A13zD9I+evtqeyI7W8w9UM890Il7oMQ90DX34Cxj99R5bsc6zHMPdOIeKHEPdM09eGZYGjONfhG32euwiXugxD3QNfcgDUvu2MPIOyjmHqjnHujEPVDiHuiae3D3st47Cv0ibLPnHujEPVDiHuiSe3BUHSeFjjn+/CLWYZ57oBP3QIl7oEvuwT23n3O60C/iNnsdNnEPlLgHuuYenN1vccywRK8UMfdAPfdAJ+6BEvdA19yDez0PuxmPc6zDPPdAJ+6BEvdA19yDs/o2n7Rvx9wD9dwDnbgHStwDXXMP7rOq+97VTG2OdZjnHujEPVDiHuiae5C2W38NPfb8ItZhnnugE/dAiXuga+7BmcfcHvdorjlus9dhE/dAiXuga+7BvYeVxaqKdZjnHujEPVDiHuiae/Bozm1eVbEO89wDnbgHStwDXXMPxn797N9Uc6zDPPdAJ+6BEvdA19yDp62L3o51mOce6MQ9UOIe6Jp70FfVfVpuq/071mOef6AT/0CJf6Br/sHYRccqc6sr1mOef6AT/0CJf6Br/sFT43zXiPkH6vkHOvEPlPgHuuYfPDps3LNoL4v1mOcf6MQ/UOIf6Jp/8CjB69+Rl9HtLLEu8xwEnTgIShwEXXMQxpk1zmu+1cYcBPUcBJ04CEocBF1zEG6FMF6lnqw7GnMQ1HMQdOIgKHEQdM1B2K5exy2Hbz2kIMZdxOv0Z/9PVEPYR56boBM3QYmboGtuwnarqb4Xdjv5xl8Q6znPT9CJn6DET9A1P+Gp8bJmyiBtui+I+8DruomjoMRR0DVHoddsX9JnaveDSd3elvr7auoWwNRfN1N/V0+D0Ef+MjF/QT1/QSf+ghJ/Qdf8hTT20G6XS0/eR435C+r5CzrxF5T4C7rmL6T+fpZk9AG1OdaDnr+gE39Bib+ga/7CXWP31EnktRLzF9TzF3TiLyjxF3TNX0gyxnnwymkfifWg5y/oxF9Q4i/omr+Quh9F6ru26+1YD3r+gk78BSX+gq75C/ecH2uAdH/MX1DPX9CJv6DEX9A1f2HrenAbqzFxzXGbvR6c+AtK/AVd8xeedX+3/flFrAc9f0En/oISf0HX/IXU7++p+0Ul8j6I+Qvq+Qs68ReU+Au65i/cNafRZprbsQ70/AWd+AtK/AVd8xfuvau/ISV6vYr5C+r5CzrxF5T4C7rmL9z7eH9bSPRKGfMX1PMXdOIvKPEXdM1fSP0lPvXXjUQvszF/QT1/QSf+ghJ/Qdf8hWcHGbsn/SLWf56/oBN/QYm/oGv+wl3zPdO45rjNXv9N/AUl/oKu+Qtjv37272ecY/6Cev6CTvwFJf6CrvkLz0kxEdI15i+o5y/oxF9Q4i/omr9wz7Dz1irPL2Id5/kLOvEXlPgLuuYvDBWUhmWQ7jgxf0E9f0En/oISf0HX/IW7zWOc6W4TcxfUcxd04i4ocRd0zV1IQ68PTjmPc6zDPG9BJ96CEm9Bl7yF51y+zyr6RazDPGdBJ86CEmdB15yFWwGO/ZuUQcxXUM9X0ImvoMRX0DVf4VZ+twal9RzrMM9V0ImroMRV0CVXgdTu3Xb6Rdxmr8MmnoJy/oElT+Gp8Va/1OZYh3mOgk4cBSWOgi45Ck+No7cpAiLmJ6jnJ+jET9DCMzXQYeNWs03nc8xNUM9N0ImboMRN0DU34VEE47TkmuM2ex02cROU8wusuQl3zWNVkTKIuQnquQk6cROUuAm65iY8vZ2m8znmJqjnJujETVDiJuiam/Aog3G/phkW6zDPTdCJm6DETdA1N+HW2bcmod6OdZjnJujETVDiJuiam3CfjuOs4lMy1mGem6ATN0GJm6BrbsKjPe/Tkn4Rt9nrsImXoMRL0DUv4W7zbS95fhHzEtTzEnTiJSjxEnTJS3hq1PkuGfMS1PMSdOIlKPESdM1LGMpg3GZdzbEO87wEnXgJSrwEXfMS7hrzrEliXoJ6XoJOvAQlXoKueQn3STGsU3R/jnkJ6nkJOvESlHgJuuQlPNaKUbNyzXGbvQ6beAlKvARd8xLSeEPqXiZbfz/byNYccxPUcxN04iYocRN0zU1Iw17S30vHF7CfcMxPUM9P0ImfoMRP0DU/YSvqvmB8UeI+iPWZ5yjoxFFQ4ijomqOQhq/e3fujT+jbY53meQo68RS08o611mmj18co9PeWjV72Yq6Ceq6CTlwFJa6CrrkKo8bxBamPinQ7mvQ3RxkWgOHF0N8epL+ObeQ3E/MY1PMYdOIxKPEYdM1jkH7+S/ePElJbMY9BPY9BJx6DEo9B1zwG6TcJ6XFJsnHNcZu9zpt4DEo8Bl3yGO4a03gVI0+OmKegnqegE09Biaega56C9LNQut5jv+OYp6Cep6ATT0Er7zNrnVfHDNS5t2Od5zkKOnEUlDgKuuYo3HN+rAHSeTFHQT1HQSeOglbeV9Z8rJt4f7heJ7KuxjwF9TwFnXgKSjwFXfMUZNwkxhdQVGDMU1DPU9CJp6DEU9A1T+HeeY6798cvcsxTUM9TyBNPIRNPIa95CqPNsm/vOZ5jnkL2PIU88RQy8RTymqdw72Hb2F2pzaHey56nkCeeQiaeQl7zFMZ+LufYRelbQ72XPU8hTzyFvHHfLfWe7KPmsa7pF6Hey56nkCeeQiaeQl7zFMZOMnaW9JxZOeYpZM9TyBNPIRNPIa95Cvceds80qjnUednzFPLEU8jEU8hrnoL0F3rZ9b2ec8xTyJ6nkCeeQt54viz13X1y7EPb0C9CXZc9TyFPPIVMPIW85imMGTY0Snp2zxzzFLLnKeSJp5CJp5CXPAXbu7wqStzmUMdlz1PIE08hE08hr3kKtx4bq4vnZKjHsucp5ImnkImnkNc8hXtmDYXANYd6LHueQp54Cpl4CnnNU7jP53FiHLSqQj2WPU8hTzyFTDyFvOQpPEpw7N+JVlWox7LnKeSJp5CJp5DXPIWhAB8tyjXHbc6+zW89lomnkNc8hUf13m1/fhHqsex5CnniKWTiKeQ1T+GucajgSm0O9Vj2PIU88RQy3fPymqdwt3m8IRQ6n0Mdlj1PIU88hUw8hbzmKYwd5N5RDq45bnP1bX7rsOx24aUOe9azTmdVzFPInqeQJ55CJp5CXvMUnjZPd8oc8xSy5ynkiaeQiaeQ1zyFcVZtNU29HfMUsucp5ImnkImnkNc8hbvG+wvoW2Md5nkKeeIpZOIp5DVP4VYG56x6Y55C9jyFPPEUMvEU8pqnkO4230qQfhG32euwiaeQiaeQ1zyFR+2OPezZSWKeQvY8hTzxFDLxFPKap3DXfCt++tZYh3meQp54Cnnnvlu/f969vVjPsQ7zPIU88RQy8RTymqfwqN7xb6JfxG32OmziKWTiKeQ1T+G+vZ5l7u1Yh3meQp54Cpl4CnnNU3huN5O9JMc8hex5CnniKWTiKeQ1T+FWBGm+P8c8hex5CnniKWTiKeQ1T+G2l4yaeZxjHeZ5CnniKWTiKeQlT8FqHG3uvNL+ArsLtT3WY56TkCdOQiZOQl5zEqS/j+2DvayjL6gPYl3mOQl54iRk4iTkJSfh3AerVUdf9NWWqA9ifeY5CXniJGTiJOQ1J0G635L018ldR59QH8Q6zXMS8sRJyMRJyEtOwl2zyBiFMr7k+WWs1zwnIU+chEychLzmJOx5czWPLxGhPoh1m+ck5ImTkHfWBUvdtvdXrPElwyOeIstzzEnInpOQJ05CJk5CXnMSxhdIt2JK9wXZH0ZAjjkJ2XMS8sRJyMRJyEtOwl2jjH2gv6+5L4j1nOck5ImTkImTkNecBBl90F/45HmpzzEfIXs+Qp74CJn4CHnJR7Caetv7q5Zwm2M957kIeeIiZOIi5DUX4SZj31/ANcdt9npu4hxk4hzkNedA+vjK2Ptox4k5B9lzDvLEOcjEOchrzsFoswyrNfd2rOc83yBPfINMfIO85htIf6mTsdPQ7hjzDbLnG+SJb5CJb5DXfIN7ho2aM9cct9nruYlvkIlvkNd8g3tO97OuDE1L+3vMOciec5AnzkEmzkFecw6eNi96PdZ1nnOQJ85BPnh3Xuu6saOUY55psa7znIM8cQ4ycQ7ymnMgefN7WaG9LNZ1nnOQJ85BPnjU1rou3zNsXtexnvOcgzxxDjJxDvKac3C3+Z5x9K2xjvOcgzxxDvLBa2VtX7v37TK3OdZvnnOQJ85BJs5BXnMO9vIe54N+EbfZ67aJc5APXiNr3TY0SznmmmO95jkHeeIcZOIc5DXn4N5F+/6989yOdZrnHOSJc5ApQ3Becw6eXh4nx6PTY85B9pyDPHEOMnEO8pJz8PTyrVHuOd6/6Jp5OmwU402hv5fp4CNs/MVhX3k+Qp74CJkyC+c1H2F8ifa7rZK1O+YjZM9HyBMfIRMfIa/5CHeNoy/I8hvzEbLnI+SJj5CJj5DXfATtNmftt2rKtpFjPkL2fIQ88REy8RHyko8AbmAf5zEPDvpF3Gav4yY+Qj5dC5ZtHi/v90yjmmMd5/kIeeIjZOIj2H9et7m8eptmWKzjTq/jJj5CJj5CXvMRpI5x7l/w+OjnmI+QPR8hT3yETHyEvOYjjF4e61vJChrzEbLnI+SJj5CJj5DXfIRBD9Z9rC5aVbF+83yEPPERMvER8pqPoJu63hZ6E475CNnzEfLER8iUazqv+QhSx8wa40xzO9Zvno+QJz5CJj5CXvMR7pk1uHT09h/zEbLnI+SJj5CJj5DXfAR9jbOrOdZvno+QJz5CJj5CXvMRBil1tFn5jIn1m+cj5ImPkImPkNd8hHvv2rb/z9m77Nqy41iWH1OdaGws2FMkm5FZUUACiYhAVmSj/v9HilMmmU0uibZvbgfcj597l+n9oChxjnENy+23yEeQgY8gxEeQOR/h3pdn+3Nuv0U+ggx8BCE+gsz5CM8I28aVJLffIh9BBj6CEB9B5nyEez7f/Ux1zu23yEeQgY8gxEeQOR/hXrf7Pk27W85HkMhHkIGPIMRHkDkfoa8gfUWxfkNL96Q5J0EiJ0EGToKQ0qDMOQmPPdb3a/oit8ciJ0EGToIQJ0HmnIR7r2o580jLOQkSOQkycBKEOAky5yTcFkLPmdbvnJMgkZMgAydBiJMgU04C5TzaYznXQCLXQAaugRw8Yud+tXvP6ueyZ3blXAOJXAMZuAZCXAOZcw26DfrMMiprbo9FroH/dajzzum82906jrDcHotcAxm4BkJcA5lzDcr2ZXfzmMztscg1kIFrIBQxJXOuwZ3zvWdRP+f2WOQayMA1EOIayJxrUJYtjO2whuX2WOQayMA1EIpoljnX4J5N62iP5VwDiVwDGbgGQlwDmXMNbqb6vVt+jfV+/urvndotdtlpJOZ2W+QfyMA/EOIfyJx/UNpbkNIJpzd7nUqQ22+RfyAD/0CIfyBz/kHPsZegdEoNecNyDoJEDoIMHASh+CaZcxB6jmXvzPUyliC35yIPQQYeghAPQeY8hJ5jL0HZOwWeZmdu10UuggxcBCEugky5CHeOpd3oN/p7LEFu30U+ggx8BCE+gsz5CJ32Xo7+Z2ewUy/kdl7kJMjASRB+mTvnJPQcy9FZ62UoQc5LkMhLkIGXIMRLkDkvoefYS1COTn9X+jJtg8hNkIGbIPwqZs5N6DmWs1O8l7EEud0X+Qky8BOE+Aky5yf0nMvZGVD9z4W+zNsg2n8DR0H4fc6co9BzLu0+vbS5UPpKVfo/73z6o5f0STm3EyNvQQbeghBvQea8hbtEN3Odeie3EyNvQQbegvBL7jlv4c6xl4BeO+S8BYm8BRl4C0K8BZnzFu5Wv3uByprbiZG3IANvQfgt4py3UNoILNpLQK2d24mRtyADb0GItyBz3kIfYc+I45zzOkc7ceAtCPEWZM5beOo6GWG5nRh5CzLwFoR4CzLnLWz3CGsrEa++uZ0YeQsy8BaEX8XMeQul70DS604rTm4nRt6CDLwFId6CzHkLpZ++emuTbZzzFiTyFmTgLQjfZU55C6hjrDO9tM95CxJ5CzLwFoR4CzLnLZSz1/Xoaxl9kdc52nsDb0H4jcKct3DXte9tnHNu50Xeggy8BSHegsx5C/d8Fp3knNc52ncDb0HOkM6cX6uhzkVohOV2XeQtyMBbEOItyJS3QOt2Gdew3J6LvAUZeAvCnqg5b+HZn+99+v4i5y1I5C3IwFsQ4i3InLdwj7C+htE8zHkLEnkLMvAWhH3bU97Cs4bd/Ux1zu22yFuQgbcgxFuQOW/hXkn6WkZrWM5bkMhbkIG3IOwbmfMW7hWkrShdTbnQm+CcuyCRuyADd0GIuyBz7sJjj/X+prrn9ljkLsjAXRD2hc25C/c+baNtknMXJHIXZOAuCHEXZM5duNfvvl+TJZhzFyRyF2TgLghxF2TOXbgtQJ3Mrtwei9wFGbgLQtwFmXMX7ta+V1POOa9ztMcG7oIQd0Hm3IXbBi2T2ZXbY5G7IAN3QYi7IHPuwj2fb6uIyprbY5G7IAN3QYi7IHPuQrEvu5vOVzl3QSJ3QQbughB3QebchTvn2/qlsZ3bY5G7IAN3QULbJfaYxvnMa1huj0Xeggy8BSHegsx5C48dNtpjOW9BIm9BBt6CEG9B5ryFvfvd+qySr7F+j/3um+htdH0n7RZUmhdVyKed8xok8hpk4DUI8RpkzmuQ5s+VdoMgFCGb8xok8hpk4DVIaPupPSdrr+vRS/B8kdtzkdMgA6dBiNMgc07D08rtT3o/k3MaJHIaZOA0CHEaZM5puBm92zLUOec0SOQ0yMBpEOI0yJzTIKvGEUZ1zrkLErkLMnAXhLgLMucu3K18tzrlnNtzkbcgA29BiLcgc97CPbbXMrZ2bs9FzoIMnAUhzoLMOQs3RXQvw3zOeQkSeQky8BKEeAky5yX0laSvLMU457zO0Y4beAlCvASZ8xL6PC7Xm5Jjudc06u/cnovcBBm4CULcBJlzE2Q54lr2cDUk5yZI5CbIwE0Q4ibInJvwrGXL2Oq5PRe5CTJwE4S4CTLnJtx1vldRau3cnovcBBm4CULcBJlzE+4c+80g1zm35yI3QQZughA3QebchHsVvfuZyprbc5GbIAM3QYibIHNuQl9R9nbHFHLO7bnITZCBmyDETZA5N+Fev9vOQZRgybkJErkJMnAThLgJMucm3K3c9yx6I5ZzEyRyE2TgJghxE2TOTZB2syvNihKyJHNugkRuggzcBCFugsy5CdLX7estybG02yyhCNmcnyCRnyADP0GInyBzfoK0u+SbYtUJutxfuX0WOQoycBSEOAoy5yj0nOXoLG5q/dw+ixwFGTgKQhwFmXMU5Gnt1gvU6rl9FjkKMnAUhDgKMucoyNmtozbmySOQcxQkchRk4CgIcRRkzlGQo+fYWn3nnNM6R46CDBwFIY6CzDkK0t4QSbsr5JU/5yhI5CjIwFEQ4ijInKNwt3J7vSC0puUcBYkcBRk4CkIcBZlzFPby1doUd55zFCRyFGTgKAhxFGTOUej93PlnPKtyjoJEjoIMHAUhjoLMOQrP2O6zir7I7bLIUZCBoyDEUZA5R+Fev/u+Tet4zlGQyFGQgaMgxFGQOUfh6d9tHGG5XRY5CjJwFIQ4CjLnKNw59lX0Yf5IzlGQyFGQgaMgyrNzbpedvZXbKkovsXKOgkSOggwcBSGOgsw5CveueUxWktwuixwFGTgKQhwFmXMUbkuhl4DuPXOOgkSOggwcBSGOgsw5Cs8aNtkxcrsschRk4CgIcRRkzlG4V817x6CxndtlkaMgA0dBiKMgc47CPbbPyRqW22WRoyADR0GIoyBzjsK9hp2jZZBzFCRyFGTgKAhxFGTOUbhtknOyV+V2WOQoyMBREOIoyJyjcFuCfT4ftJLkdljk"} |  |  | - |  | - | -
[14 empty] | {"index":137,"total":402,"filename":"Advanced_Project.ifc","data":"pX3/e61RjRCqkdgFucdYTb3QYqSH7HJs30fX265aiBweYoltxnNt3VBzplfTLrQotT41ATm1Wdfbtx053aSk9rjJ2xZlNf9CjZLbB4+XGqSULLVTdhZlndu6U62NxuhDGy1xLWypPitJTu01s2iirHOb+da7np+LthmAal6U6Q4v9i2h4FYzLhyjHE6ROc+rSRZaFH/9uLjWpTI/VOtzEuUku4co8TZ/Y5aaLik2yml2dzVaR/nJ2c3vRL3VKKY2HGRbttWECZeH62e99aqsbYJ39erTd2J4CJJizYqKM1/ZBLeaI+Eapc35e/1ePbUpPN+J/qHE62e4bVGXi7leVtMiEOV2M7YBaZ/eie6h3UH1mpPa4Q02yjq7Y5Q2FVa+fgNcorbmMmUTZZ3dFqX+X9rkh7kt+uXTQ6td5V3t+dYU36OsJjxoUWojVa5jY+LaKmXX75FV28wPrk1aZGq0mvDgGiVea6Q1Tm1grjOLp0u9/GpnIbeXJk2Uk+weotzugDYdrlzME5lW65Mot+y2+RR9mwlgF8VkdzXPwTRKvE3EVRuotlanaRlWkxy0KO42XaC2dyrrrbKPYu6A1bwG0yj+OnGZK+02NzOuBLeaymBao3WUn5jd6zR+N0rXO+nSEmzzcp7dNj/ppZrMfJ3M7fJQ+9LSPr6MbcnpLYpfzVFwzYui5VL3yr5FMTuegKxNT1YvccmuNgG3w5sdT31ByjGmNsHX9QWdq+5c7zmt7VG6T1RTo6ymGNC9S6mYWXsdv5xXQA962nTrSz3Lif90nxC3y8dqhr/rnuM5qLypu15nZSx6/SRVTJzVPA66vyKiyskVsZrNb4tjrnK3vj79chK/aZzl3eKXc/fp8d71Z3HO87yPs2qP/HKWvnm91nF+Vp6Xraxfzsenhza/xHWb75eT8M3jrAjklzPv6ZGHaxz65Wx72u2G5PbSVW1f0nXxnlwNd5vmo/Z8vZVzmubBKrQJSFZWwS/n1TvGKX5tXPxyMr2tXpuNqg3O0kb55Qx6ejB11XYYU1e0tl8mzlmeR4vp/Npi+uVcedM4S8Prl1Pl6d5+e3UncZYz5c3jrDoDfjlP3qRe4SzOT85z3XrdUfLL+fP00G1zZd1t88tJ83TXiWxfvCz7kH45U54eerQXfxbnLM0h1samdvMvsbZalVbt/IWcUq53f7svTCu2nBNP9339pCc9Sb+cCE/3Iw+1m73FyS1I/VsT5xF/cR8HKbWPsRwH8csp7/Z+p1zU70dlzO0+W5y3jfi8w5gNv4VffYexD37ZLrFdYrvEdpntMttltstsl9musF1hu8J2he0K2wnbCdsJ2wnbCdsp2ynbKdsp292e6je3y2/gt9fXnPnlYsRhXIw4HBYjDmYx4jBdjLj5Vo6MIocih6LbF3vNhfHLdp7tPNt5tvNs59kusF1gu8B2ge0C20W248x7zrznzHvOvOfMe86858x7zrznzHvOvOfMe86858x7zry3TfRy8eUwLr4cDosvB7P4cpguvmyu6X7Oy0TB+lzLeK73iy4Hs+hymC66vCnwxQ05cObZ8nrx5TAuvhwOiy8Hs/hymC6+fM96v/9sy7RcfDmMiy+Hw+LLwduWabb4sqlrOdR5vfhyGBdfDofFl4NZfDlMF1++t1n9Ss72yMs6j4svh8Piy8Esvhymiy+baz0dsr1efDmMiy+Hw+LLwSy+HKaLL291vt91weyxrrMb67xffDmYxZfDdPFlc+ROhvvdtV58OYyLL4fD4svBLL4cposvb0zqLY8zI5XrRZfDuOhyOCy6HMyiy2G66LI5ojtme7nochgXXQ6HRZeDWXQ5TBddNtwNY6trRrrWiy+HcfHlcFh8OZjFl8N08eVNwdbubw7AXOvLRZfDuOhyOCy6HMyiy2G66LIhT8+FThSscxDHHOwXXQ7BtlSzRZfvLmfLQc+JuQ6Wiy6HcdHlcFh0OZhFl8N00eW7j+otzkZto3256HIYF10Oh0WXg1l0OUwXXTYOb+8PzP2/XHQ5jIsuh8Oiy8Esuhz6ost7Bd1bbkfuzsXsuc5BHnOQDzmw3MjzHHRX271T91bmSizrHOQxB+WQg2JyMPft3Ud3zm8uzlyJaz8bRj8bDn7WzNVX/zzNQdn7yM3Z3/dc+7ww+rxw8HnB+Lww9Xmbkw29b5EmCtY5GH1eOPg8M8da/fM8B2U48uaxzbvDYe3zwujzwsHnBePzwtTndQV3l280r31eGH1eOPi8oDbOWd17P8OZN7ni2ueF0efFg8+LxufFuc8rPcu9b+jMHss6x9HnxYPPi8bnxbnP60fcFJg91j4vjj4vHnxeND4vzn3e1g/e9/JM3dd+L45+Lx78XnS2JtPzvfXAtyP3/ud9z7Xvi6PviwffF43vi3Pft/X9ew+495CL2XOdg9H/xYP/M/PA1D/Pc9BHJ3rfu/+aPdc+MI4+MB58YDQ+MM594Dau0UcL+miCycHaB8bRB8aDD4z2ip77wD7iIj37/WzcW9249oFx9IHx4AOj8YFx6gPvYz37kRFzL6x9YBx9YDz4wGi8VJz7wG2UaTtyPxv3Pdc+MI4+MB58YDQ+MM59oPZRov7bFVkF6xyMPjAefKCZmaL+edoWbuNVfUTNZH/t/+Lo/+LB/0Xj/+LU/21Hvrhjnde+L46+Lx58XzS+L0593330cBu7u++x9ntx9Hvx4Pei8Xtx6vfuo4TbOKbZY13n0efFg88z8z60xVLO6rwduY+omj3XPi+OPi8efF40Pi/Ofd52xD6i5CYK1jkYfV48+LwoNs4tB/vR9uGpXkp+/9xP2pP+exQ83yFKe6aXsqbmmkvioZ9vLxlF72PeBfHzINcHem0N+FKipnh75BdV3KUGr/2AMUicB4kPbcLDi+RyuS7B4/qDjbY2RfG7IHkaJOSHVG16qSYut7cLHosyT+0kSl8KtC0wtEttuixSG69R9OLbrBjpsSCL1NpnnO1lzv17dmOQeWqHB5NF/D5K2kWZ53YXxe3fP4y7KPPcDk+52qvMuyhhjOLmuT1GOa2Rmyd3eLBZqm8ZorRPTsco8+zax5q1wyT2wWf7DHSvZZ7d4Wmkq/5heHc27YPMk7sL4oeHnhVsu1Pk58m1DzR9u2XME8/SVt8cg8xzO56hajPHd5uT7qIsrlz7LDO3xb3H96x3QRYX7vAgs60nOb7yvQuyuG7tU8w22rJ7h32X2jBP7fDul6ttwPh22P66DfPcDm9+labFvhvmdo1CmKd2/3JcqH3I3Y7zdPZXSdsbuU5bu192JzPMUzjIzsAmaAxtobAQ91dn/CkpFDm+qDtGWbSrAz2jHul5XSE0X7I2d6TGiKW4ANiA0ihHltaQ5aF92nqJtfpmpD7FeaofBet1Nc968mr333s73pniwjU8RtnrkqPXWflcsPPJVIuxOB867rALeV00cBlycX2PIcsx5HCK0+IC1/blQ3b1kqgtRe1iPRJlcbU/GqXecHaLaEL+ZHtxOAnjQe8h8/wkPO5YTkKuTsKh4jZkPql3/sknZIw4nI+8Oh9tdbHcFtgqpX2AeB5k0RI9FuS28O62wX0kI5WfZPbc7AQsQ/4k6zdxbTXk5UalVOls+h6prM7AuMMQUtqEdichl+fjkZDDCSmrExITzbqrbZx/JIqsmqLHolTS2C3MXSALGzOa3oMBT2chf5IbD0cffRJydRL2FbchXTmL+FNPyC7icD4WncsaxN2ujdsbx/sgu7O66F0+HqW9M263MCHPbSXdB3/shJyEXJjMQ8jJhbIKuTwHu4qPl7Nfh8yLPunjIe0ZyYtOqdPKm8d2XbVA0119W8LT7LzoI5321y7tTfBdnEU3aeyx6b7Hdo2THtpEftG1Iaq7r8qLDumj3bca8Xbfa2wL2ZpTteqcPtqXOwm56Kk+1rHzbdnT3Majq6E0yxqEvOi1Pt7LW1+iiz7sIeS+y3eP2J74yd135EV/duj/1Ztt1/+7NY/+oc0cWbthbeFSE3KBhbPeYM63WzOYK3HRv633Y9h9IqS3Bm3Yednqz3YebsNFb/a6Ku+NQtH5uOuHah7b97zqzT4a5bp4/H0Lc/ZXXduzDnJx1wtqGXLZ0bW95XzoLV+XC283utRTbz+ezyc94EPXuV7bQ8qWfeBj53m366rjO3af/bH7vKuIuTMWveBH+tK3Bd8X2V70gg/XxBjyks9Crq7zx0IOF+ui53tdnffen4+PRFn3dh+Jshw3yOve7jAqsBs3aOslr8YN8rLrOwwL7IYN2qLOq3GDvOwGj0DcIfOSTpC56AbXkAO+RmRGPeHbohd8iDggM6UzZC57wSMRd8wMZ8xcdoN3Hmz3JYicMHPZKR6QGHYfhZSziEvvaYkYd5+H5BNkLnrI9S62jZMfm+HWCV+3w4se8vGD1uu7f7vmdNkX1mNbfNx52SQNUndt8aWctMXLLvB5yPF5UV52gae1Gnf9GdmMu12Xjf4j53aMsryKz6653SODvO65jrfX/l4YgvzUnuvhHh2jnPSTkq9dRsmXVqFhbpbgd12mRWf18VZtjLJswM9aW9kld9klfQwDNkpZ9kJP8RR2Qf632ByjxMlz/Op53uFJGL+e38hv5pftAtsFtgtsF9gusF28bRflVo5KWT2/kd/ML/tdiH8h/oX4F+Jf2M6xnWM7x3bmW+xi3ibcvX/QLkXz/kFh/oL7+wd1XxNHJ5nL1ChTo0yNMjXK1ChTk9xrxn6JzKTSf6lh7r/UKPXfW5xCnNLjRo4TOS7xavvIL9sJ+jiTmTPbliOmNbnX2LwNecicDpmj724y55yJM7vmtmuhZyByDs0IenHrc+fGc+cO585eA2527lLsV12/Gi9HBX6dAzfmwB9yYN566yvH7nMQBwVdUTJzSBS/zoEfc+APOfAmB36aA66n+/WFgtTv2J6j2JXx7/d3g0pY58iPOQqHHJm3ZPtKs/scjUq6spStgnWOwpijcMhRMDkK0xxdequ1HZlfP96j2z3b72WjMK5zFMYcxUOOzJewfUXavcLeTl76kfn1Zs91juKYo3jIkZlVpa84u1fQW2jfj8xvHNu13s5Jb/+MwrTOURxzlA45Mn23vjLtnnGdEb0FRtHWQl92LTUtpWVAWucwjTlMhxwmG2eew0632HPDr2mP8jpHacxRPuTIdEb7CrZ7BZ2/uR+Z316WkV693VKrcJ2jPOYoH3KUTY7yNEf97HWlvV1Ss2dZ5yiPOSqHHJkvkfsKt3sF3WP06wRymgkhSlnnoIw5KIccFFuTqefYXE8eXM+gQNY5KGMO5JAD89VGX/F24RdR0BVlM4lJkXUOZMyBHHIgJgcyvw6kH5Hf7lRNm6vrHMiYAz3kwMye01e83Z8Fst7PwuaZrYJ1DnTMgR5yYK9oneZgc+c9B/c95LKuuw51l8u+7mLeF5dpfyFv5733G6LZY1lnGf22HPy2XGwN5td+P2I+HnntV2X0q3Lwq2L8qkz9aj9iV5DNeZa1T5XRp8rBp4o9a1OfmumV5e0K23Jw33PtU2X0qXLwqWJ8qkx96tZL6L0G+n956/9dBmVdabZnZ+1jZfSxcvCxMtR0ei/sFOWtR3pvkWTtU2X0qXLwqWJ8qkx9aj9i3vrAMwXrHIw+VQ4+VYxPlblP3R25K8nmVTNZ+1AZfagcfKgYHypzH9r7/fcj0ys198rah8roQ+XgQ8X4UJn60Lz1IvsIxUTB2mfK6DPl4DPF+EyZ+sx7f5YrMvYeehx76L3Hnnqv01wna58po8+Ug88U4zNl7jO7Io6c07HnLWufKaPPlIPPFOMzZeoz+xFz73Vu/V6rYJ2D0UfKwUeK8ZEy95G9H9vPxtb/NdfJ2kfK6CPl4CPttGcy95G9F9n7s73nbWaGkrWPlNFHysFHivGRMvWR9z5a78/2fqs5C2sfKaOPlIOPFOMjZe4jZd/T6b1Co33tI2X0kXLwkTLEmeZg6wX2fkTv0Zg2c+0jZfSRcvCRYnykzH3k1n+gfUjH/oSsfaSMPlIOPlKMj5Spj9yOmLqnvhwU6NpPyugn9eAn1fhJXfhJPx65KzFjPLr2lTr6Sj34SjW+Uhe+0vcj8rv1K+57rv2ljv5SD/5Sjb/Uqb/cjpjHfsWoYJ2D0WfqwWeq8Zk695lbnyp3Jfc91v5SR3+pB3+pxl/q3F/2OufNY5s91nUefaMefKMa36hT37jVOR9dva79oo5+UQ9+UY1f1Llf7EfcFBita5+oo0/Ug0/UYONM67zVtT8L8Me6r32ijj5RDz5RjU/UqU+8u3TuttLdu7ni1j5RR5+oB5+oxifq3Cf2I5auJB8VrH2ijj5RDz5RjU/UqU/cvHE/cldSrIJ1DkYfqAcfqMYH6tQHbgoYo82lO1NzHax9oI4+UA8+UI0P1LkP3I7YvbGfKFjnYPSBevCBau+pqQ/cPDB+cHueZtYS0LUP1NEH6sEHqvGBOvWB/Yj9iV53oqOCdQ5GH6gHH6jGB+rcB6bxyF1JsgrWPlBHH6gHH6jGB+rcB/YnKdvTp/5ExdwLax+oow/Ugw9U4wN17gP7c4rugfuzHJu9tQ/U0QfqwQeq8YE69YH3Mfb+7KY/KTEsXPtAHX2gHnygqq3J3Av3MfXugbsP3O7GeFn7QB18YN1yl4O2r4kz98J9JLs/Te995Gz2XOWgBR0VlIMCG2f+PJ8j6s4TWwVLH9iCDgr2PrDta+LMfcHOA29vEkSz5zoHbszB3ge2fU2cuT/o7zT0dxn8fY+lD2zBhiPvfWDb18Q5rXt/myLbI6/r7Mc6731g29fEmde5X3Hd/5tsL31gCzYcee8D274mzrTOuutx2GwvfWALNh75UOdg6rzwgZvP73W/77H0fy3YcOS9/2v7mjindZaD942Xpe9rwcYjH+ocbZzTOvf3Xe6rkMbL0u+1YMOR936v7WviTOu8HfHwpk28LH1eCzYe+VBn2zLNfd42et97Wf3dILPn0ue1oIOCvc9r+5o4c5/X/X1/ktEVmLts6fNa0FHBIQf2+pn7vP7+0+ayL0cFS5/Xgg4K9j6v7WvizHMQRwXbG1nmrlv6vBZ0VHDIQTE5mD837gr6O2H9HTG759LntaCDgr3Pa/uaOPMc7N5Si3GiYJ0DGXOw93ltXxOHWf6ffvLsyS+effDk6dO2UYrlanfbb7r9ZsqZcqFcKAtloayU9VaWy4Vfyo6yo+wpe8qBcqAcKUfK6BP0CfoEfYI+QZ+gT+6TJcWLsarPn/zivc+efEqC9L7J7fw9e/77p09+8eHzJx+9zZ7vvP1mW+aqcuidf7pvnebZ1Cu22m+5/RbKhbJQFspK+TpNWu16XK1e+6XsKDvKnrKnHCgHypFypJwoJ8qZcqZcKBfKQlkoK+X7l+m18mWeTU33TWSezTLLZl8DeJ/N5K63aPvV269QFspKWW9lf4n8UnaUHWVP2VMOlAPlSDlSTpQT5Uw5U0afR59Hn0efR59HX0BfuH9iEu0yxjabNSn3TeIsm3XPeTbLPJuBayfE/osqroXAtRC4FgLXQuBaCFwLwVwLdmHjUX3ZNuHb2IN6fafJqjm34vtSY3vx8daMtBe7+b2JirdmIcXM32fKhXKhLJRNs+DMPKSDeBfum+Sp+NqYzcTP29h0e1UypcRdnbgubwvutt98+zX22Pl5m1UPct9k2ma11Y/ffrO98Xax4vy8yarqEHOdH7v+0EQkLovEZWHW3q7B5k1APch9k2kTUPeciQuLFuDW6W6/t2s1X26ZzC7wS/k+qWe0iyQP4sL9jgrzOyqEqbj5DZXldntnuYnLeru9s14oO8qOsqfsKQfKgXKkHCknyolyppwpF8qFslAWyujTm75yuekrlwtlR9lR9pQ95UA5UI6UI+VEOVHOlDPlQrlQFspCWSmjz6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+hz6HPoQ+8FPBSwEsBLwW8FPBSwEsBLwW8FPBSwEsBLwW8FPBSwEsBLwW8FPBSwEsBLwW8FPBSwEsBLwW8FPBSwEv9pYy+gL6AvoC+gL6AvoA+wNBeB+CXMvoC+gL6AvoC+gL6AvoC+iL6Ivoi+iL6Ivoi+iL6Ivoi+iL6Ivoi+iL6Ivoi+iL6Ivoi+iL6IvoS+hL6aKbrL2X0JfQl9CX00ZKWhL6EvoS+hL6EvoS+hL6EvoS+hD4av5LRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9FX0FfQV9BX0FfQV9BX0FfQV9BX0FfQV9BX0FfQV9BX0FfQV9BX0FfQJ+gT9An6BH2CPkGfoE/QJ+gT9An6BH2CPkGfoE/QJ+gT9MGPAj8K/Cjwo8CPAj8K/Cjwo8CPAj8K/Cjwo8CPAj8K/Cjwo8CPAj8K/Cjwo8CPAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8Ufij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FH3rjR77c+NF+KTvKjrKn7CkHyoFypBwpJ8qJcqacKRfKhbJQFspKGX0OfQ59Dn0OfQ59Dn0OfQ59Dn0OfQ59Dn0OfQ59Dn0OfQ59Dn0OfQ59Hn0efR59Hn0efR59Hn0efR59Hn0efR59Hn0efR59Hn0efR59Hn0efQF9AX0BfQF9AX0BfQF9AX0BfQF9AX0BfQF9AX0BfQF9AX0BfQF9AX0RfRF9EX0RfRF9EX0RfRF9EX0RfRF9EX0RfRF9EX0RfRF9EX0RfRF9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0FfQV9BX0FfQV9BX0FfQV9BX0FfQV9BX0FfQV9BX0FfQV9BX0FfQV9gj5Bn6BP0CfoE/QJ+gR9gj5Bn6BP0CfoE/QJ+gR9gj5Bn6BP0KfoU/Qp+hR9ij5Fn6JP0afoU/Qp+hR9ij5Fn6JP0afoU/Qp+uCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx/117xeExYvqIT7Cypx/oJK0NvrNTlm+zZAnL6hkoO7fr2TWfm2/VJWynor39ZkbL+UHWVH2VP2lAPlQDlSjpQT5UQ5U86UC2X0efR59Hn0efQF9AX0BfQF9AX0BfQF9AX0BfQF9AX0BfQF9AX0BfQF9AX0BfQF9AX0RfRF9EX0RfRF9EX0RfRF9EX0RfRF9EX0RfRF9EX0RfRF9EX0RfRF9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfQl9CX0JfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0ZfRl9GX0FfQV9BX0FfQV9BX0FfQV9BX0FfQV9BX0FfQV9BX0FfQV9BX0FfQV9An6BH2CPkGfoE/QJ+gT9An6BH2CPkGfoE/QJ+gT9An6BH2CPkGfok/Rp+hT9Cn6FH2KPkWfok/Rp+hT9Cn6FH2KPkWfok/Rp+jTm7723RO/lB1lR9lT9pQD5UA5Uo6UE+VEOVPOlAvlQlkoC2WljD6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+hz74EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4EeFHhB8RfkT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4keBHgh8JfiT4wUcHmY8OcoIfCX4k+JHgR4IfCX4k+JHgR4IfCX4k+JHgR4IfCX4k+JHgR4IfCX4k+JHgR4IfCX4k+JHgR4IfCX4k+JHgR4IfCX4k+JHgR4IfCX4k+JHgR4IfCX4k+JHgR4IfCX4k+JHgR4IfCX4k+JHgR4IfCX4k+JHgR4IfCX4k+JHgR4IfCX4k+JHgR4IfCX4k+JHgR4IfCX4k+JHgR4IfCX4k+JHgR4IfCX4k+JHgR4IfCX4k+JHgR4IfCX4k+JHgR4IfCX4k+JHgR4IfCX4k+JHgR4IfCX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX5k+JHhR4YfGX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4U+FHgR4EfBX4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPgh8APgR8CPwR+CPwQ+CHwQ+CHwA+BHwI/BH4I/BD4IfBD4IfAD4EfAj8Efgj8EPgh8EPghzgzb46Lixka4n2GhjifoSGm+dP76RQN1Yxc54tov+n2K5SFslLWW1kvF34pO8qOsqfsKQfKgXKkHCknyolyppwpo0/Rp+hT9Cn69KavyrvwS9lRdpQ9ZU85UA6UI+VIOVFOlDPlTLlQLpSFslBWyuhz6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+hz6HPo8+jz6PPo8+jz6PPo8+jz6PPo8+jz6PPo8+jz6PPo8+jz6PPo8+jz6AvoC+gL6AvoC+gL6AvoC+gL6AvoC+gL6AvoC+gL6AvoC+gL6AvoC+iL6Ivoi+iL6Ivoi+iL6Ivoi+iL6Ivoi+iL6Ivoi+iL6Ivoi+iL6IvoS+hL6EvoS+hL6EvoS+hL6EvoS+hL6EvoS+hL6EvoS+hL6EvoS+hL6Mvoy+jL6Mvoy+jL6Mvoy+jL6Mvoy+jL6Mvoy+jL6Mvoy+jL6Mvoy+gr6CvoK+gr6CvoK+gr6CvoK+gr6CvoK+gr6CvoK+gr6CvoK+gr6CvoE/QJ+gR9gj5Bn6BP0CfoE/QJ+gR9gj5Bn6APfij8UPih8EPhh8IPhR8KPxR+KPxQ+KHwQ+GHwg+FHwo/FH4o/FD4ofBD4YfCD4UfCj8UfuiNH/Xs3mY9vtz40Tq9lB1lT9lTDpQD5Ug5Uk6UE+VMOVMulAtloSyUlTL6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+jz6PPo8+jz6PPo8+jz6PPo8+jz6PPo8+jz6PPo8+jz6PPo8+jz6PPoC+gL6AvoC+gL6AvoC+gL6AvoC+gL6AvoC+gL6AvoC+gL6AvoC+gL6Ivoi+iL6Ivoi+iL6Ivoi+iL6Ivoi+iL6Ivoi+iL6Ivoi+iL6WA33EtHH2qKXhD5WYrwk9LF29CWhjxW5Lgl9rId0Sehj1vFLQh/r4VwS+liV5pLQx7zYl4Q+Zqe+JPSxfuclo4+1RC4ZfayidsnoYy7SS0ZfRl9GHzPDXzL6mJv4ktHHDKKXjD5m1bxk9DHH7SWjj1nVLwV9BX0FfQV9BX0FfQV9BX0FfQV9BX0FfQV9BX0FfQV9BX0FfQV9gj5Bn6BP0CfoE/QJ+gR9gj5Bn6BP0CfoE/QJ+gR9gj5Bn6BP0KfoU/Qp+hR9ij5Fn6JP0afoU/Qp+hR9ij5Fn6JP0afoU/Qp+uCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx8Ofjj44eCHgx/118zHmBZTHsb7lIdpPuVhmk7TWk/GrLdf3G1srQ1dO34pe8qecqAcKEfKkXKinChnyplyoVwoC2WhrJRvs9q729ha+6WMPkGfoE/QJ+gT9An6BH2CPkGfoE/QJ+gT9An6BH2CPkGfok/Rp+hT9Cn6FH2KPkWfok/Rp+hT9Cn6FH2KPkWfok/Rp+i7ja1VZtz0+dvYWnvUQNlR9pQ95UA5UI6UI+VEOVHOlDPlQrlQFspCWSmjz6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+hz6HPoc+jz6PPo8+jz6PPo8+jz6PPo8+jz6PPo8+jz6PPo8+jz6PPo8+jz6MvoC+gL6AvoC+gL6AvoC+gL6AvoC+gL6AvmLnbXVrMcZruc5ym+RynaT7NcZ5OctoeWMV3br96+/WUPeVAOVCOlCPlRDlRzpQz5UK5UBbKQlkp6618+46t/VJGX0FfQV9BX0FfQV9BX0FfQV9BX0FfQV9BX0FfQV9BX0FfQZ+gT9An6BP0CfoEfYI+QZ+gT9An6BP0CfoEfYI+QZ+gT9An6BP0KfoUfYo+RZ+iT9Gn6FP0KfoUfYo+RZ+iT9Gn6FP0KfoUfYq+23fQ1UmzrsztO+j2wJOyo8zKCLfvoOsvK+jevoNu04xSjpRZn+j2HXR7cEo5U2am/dt30PWXdS5v30G36Uopo8+hz6HPoc+hz6HPoc+hzwXz3V9eTAKc75MA5/kkwHk+rXaezgJc+K6u8F1d4bu6wnd1he/qCt/VFb6rK3xXV/iurvBdXeG7usJ3dYXv6grf1RW+qyt8V1f4rq7wXV3hu7rCd3WF7+oK39UVvqsrfFdX+K6u8F1d4bu6wnd1he/qCt/VFb6rK3xXV/iurvBdXeG7usJ3dYXv6grf1RW+qyt8V1f4rq7wXV37zeYsLr7ezPevN8v8683cv96U4SyW6debbZWvcj16YeXL4iizGmDxlFmrrwTKrNFWImXW8i2JMuvYlEyZ9S5Kocy6F0Uos9ZP0VtZWPtJ0CfoE/QJ+gR9gj5Bn6BP0CfoE/QJ+gR9gj5Bn6BP0CfoE/Qp+hR9ij5Fn6JP0afoU/Qp+hR9ij5Fn6JP0afoU/Qp+hR9ir7bggrXdbf4pewoO8qesqccKAfKkXKknCgnyplyplwoF8pCWczs6WXxVLPcn2qW+VPNkuZX9e02efbBu58+qdE+e/LsycfP333+4Scfv/1m7XK+89Z7337+41v15/uX3731zrayxZusyfAmqwm8ybz8bzLF/ZvMJv8mE7e/yRzpb/J59Js8aH2TLtibmJ83aUb7jYj0ewJYVuXd3334zH/6tKbho6o3/OLtN/M7/2SqxZoqY40+epdsCQcs996h3O7u33748S8++e3TDz/+8ONfffrZJzUnzz988uztt9y/ffT6909//Ju+/+MXv/qb/PqLbz56L/z2rRrG1dy8+/Tdj5+98cuv/vHy8zeeffXNl1+/fOO3X33z+bd//xf+yV8+euOXTz/55LM33n72wRv/zxuX//Mv7a2BS3irqd7/7y4qGlHXE/r2W5fX5flv/vHpr566L977/unvfvP8+1+//vvf/z8ouUmo10b7LqY2qNdfuf22rv311/Mb+WW72zI0LXvX33Dpv5nf27/Txa+/5f+8wymoV+Fb7VlmTG+98/DxJ89/8eSXH3785BcPu8Ivr/+/Z+Rmmz969/mTzz589+nTD589f/t6WV9H2Xz7JMhff6+tk/37y618Hf1qf+/5+8awVm5VcrWX15xF+3t/+/vraGH79+YUTJzrqFq4TXTd/lr467b8Zd8spmpsb8XMX6f7Kkm1K0xdPv3U3qgtUmjv8Nw39D/tHv3oxXffvfz8s5ffff/y1ctvXr94/dW333DPOrMkmevLJn72yS9+/f4t1x+2aNcDvH27Gm7HNfvcWpX33/3s+ZNnH7778aeffPhxTf01k/rQXiUv1/eRQpuLWh7aDDO171bt3uXBBLmdvV98+NmT96/y3/6/l4dmXqU9hfC3LywuD5quMzCLXNrKI8GGqP3zxf1/E1nPIY2GynWfNhWLkumnn7z/7tNtp7dv/9Yamesf7iv6eFZcvN13x5v/v/5/vPn/l7dsrxd1je+81UPWHvjl4R1XHfuD3v+7Vy0tbiB7xd6v6+tlfruNzDko/fpp7ePvn9W28umT37z79Ne1efroxTc/fPHiT69/+P7l961+Le3vvvfk6dtvPfvby29e/eXFG7/8z9/5/7xcfpn/83eX//zm1eu6nQGSv8gY/Mnz2ub9+r0/ffPJF1998OQ/Xv6Q//qLj36Mz578jhPw6auXr/9gD/v8x+9efvjNF99+/1fuAK7nqvteB5aWmdbh/RevX3757fc/jvpvJ+XVIJYFLAextfP4df7x09dP899ffv+7D179+9c//OqTz63YT7//9vMf/vT6s5f//cNX37/8a71VX91F2kSzpM0QPnzz9asffvzb539Lf/zy8vcfP/z662//9dl3Nvy///Dim9dfvf7x+Yu/vPzkiy9uoVvTZzo5ngVshtDjdf7u757a6/wa+paD97/96197XmvX9dbEjdFPrpB2ej568f1fxuymMCZW1gGevf72+5c/fvziry8J8fzJ76r6py//9vLrf3nDvfF/6830/avXb/zy62+/Ha+tvkrnPOqL1z+8ev/bekV+X08OF85d4Mcv//7G8K82sD+5mj5++frd71++INq7nz1596Mn7z779WdP3nbp4dLmfL7Udq/2Bd0Q0a0jfvDyqy///LrLe/Lxr55/0EPWxNXW0sbx6zi//erz13+ehqmt5y5MWIf57NsfvvzzOlZtj3ax4knV6sXx/ddfffOX4dT++fXr7/7ln//573//+8OrWyvyxbfXluPh1cvxPEyuav/7r79//eK7P30Tv3/v1x/85VV+9U//9uOnXNXv//Dq9bd//UO7uCtA37rZIPyrx+j728Ly0YMWHqAwXcI1x/wGfu+Q9yx39NmTpzdP8+y931tf6T/45rOv3v/610k++eyDp89/+9tn3/3+H3+4ifune8NVzRKN4xaYdY+WgV+///u/ffrcfR8/+Mezz//rjx9889Xz33+8DOzcPXA8DXz5+jdPvvjwP75T980/vnjfPXvv2Y9//Kev14HDPfAjqfiff/3+99997J+Gb+XLj1//7hevn1y++/U68DaW6pmFaRn4t68+/PZPn37yxyfv6r9/+q/5s//46sUff7kM7E3g21X/779+9+PnHzb73a7r+/33VrtIb3fctkec7sHdcd3hdm9tO6Rhh9Y8vP3Wrb1460X9eeOvL1+8qlT7/I2vvnnjy5ff/vXl6xuYDo3HFvHm1J48vbqcHriC49v3v/yfp7/77Rfl2/fcHz4uf/s2fl1+1V3Mi1cv4cZXL1+9ZfISuahvI3dN8P3ijnJ+qbxM//3jbz797n/cf3/xpz+9+vKXf/34X//4x2Xi4+Z4fTpp/d775A/v/unbet9+9ac3Pnz17dcvTFt9ay5C+vy9oVlIJ43gNdzrH158/cavvn7x6tUbv7WNaz0bT992Th6aAZIh5EmDWEOuYoWxKUwnTWGN8vT5P3851KyEf05lrFo6jfDrvw/7uwc37p1/Qi3e/e67r7/604s/fvV1NRVDuF89fffZszc+fPZG7cI8/fD9d997+mQMf2ID/hdMTCemoKr98JtrKz5DUD2BpU3u7to3FT4OQU88wW++/fqHzWX85pOnv/7oSQ95ebjI9UuxNqDiasfXjqrUbu2ZQ/5+pJvP4ynNp+h/8fkbP4f/2T/m8/Sf/sf6vJvHefHVZkr9bQFVzzQh16vm3gTkc1rsDvW1PdSkCcj+Hrg8KvwPE+F369ZQntx1IOM6DaVvq3sa4fpzhP/lMeHbqLIvj2f878+t8F+8eP3i7v8ZDPOMFvpE+5tof5Npf8vPSv6Xz8/rUO7JLz8h+X8c6vBV7ca8qpk3PRmG8+pty6/pIJSfl/0/PqL8nn15PPt/GAbvPvz85bW39MZ4GrK5VORnpfkvX5yLlXuaZZbmy/tPn/7bN+89148+efn1f/3XN19++qf4ArGfvP7zrVt9vbjbCzK+LaJ064CJ8Hsbwbq+4XD95UoyT6i9nOf/8tEf/iY/fvRS41/1r/E/fvv5v754/uzTdZXu+defkP8Phn7ln1+8+uqbL2+VcsWsxun15+X9g/O86z3v+vjl/Y9vrMjffPXqqzv/rsm/3JoU213Xn3VR//mbR/RuSf1/SXvXZg1uGlv4z1D1zqnatat9lfyRXCBchnBJGOALBSHcwhAmXMOvf6V+7O6lttXPTqDOqZ1knpYt2ZaXZVkrbTf45T8NuKRtEWTYfvPjd9pff/JBef/dD//+yaf8jQ9+8Oknf/+qARfp9/87m7kBKm8OuKStLjr7P+mX//jiL3/9qP62/fLb8Z8fffuj/M0/vzXgIh2DTi6CT+mTT8svf/jlJ6X+68f/yD95/xvv/fV7kb9qwCVdA077nPvwhx9/8KPf/uSD93/xrw/++Pu/pd/Gf//g/WcBlzoHXFK4mSFvCbika6jpa8YbUrhBtG+PN6RreOo/iDekcANy/7N4Q7rGufb58uF7H3yDv/nFb7n+/nv/+vg74ePPf/fun1fxhjED+8ViCv325JG0kHtCpCpwDnQc8Vu4NCh5z101lwYp1v/40kAag4aPpXF7aSDtnt+kbX1pUJQZ+DUpTZJm6qSiBalfFZzznqIEAf+U4pM7AxJ8cbkzsAKyf2Ow55b2sI60NG4MQunht8WNQSgaKH/8aDsbqc9vDEYM+HnE/6Mfy/B+8PFPHvcE+Y33BOOr/29074EkZeT67YAISro4XvTq7nU7/pdONdp/fDuQ8s3x5T/erPICXsTPP/ro809/+uffvvuLD//nX//4268+/uI773/7K29WOYAOeQUQfvaHv6cvvt3e+eD33/3pL76Mn/31nz/6Ezbz4V8+/bMMzPt/2rcY47Rr3MBb5xuP9Pa9MC+cz/az/y6/+eDP3ynlh//I/Kc/ffv9//7nB+HNe2GGxZvbwrd99utff5F/870v+LPf/fvPP/n3X/7w2999/ufne6FV/y66s96ssglbpLt4zte+HUh3IZ3/5HYg3UV5/NuBmF/1zWVW8ksK2Qi82R3vNuvrLnsX/rnZYPNVzE2Y59lmXS6b9V2M5z/crK+RngfQ/fJHP/30Jz96L/2Ff/TlJ3/49ZftV9/64g2XAz2HTudi/9s3735O76/Zeu3h3Uj9L58Lod7H8MOHP/joX7/46Lu/fff7P/yHwJq//al++xtfXg4MsvU8DgziG0/B5VZw+tYn3/jLB/GXH733z0+/+ZNP/tT+9OcPP/rcF5xPwfcRX8E+n/3qF3/9vNTvfPjt39BPyi+/V7/xM1/wecShJ9cZP9p+kT/51hf/+NZvPv0k/vJX/L+f/fv7f/EFt1Pw/SEy/uPL/OsP/vrf7Zv1X3//429+x9/4d/nHe67gAoLpDZcDGOtPxE8vBx5r6/igfc3LgavvGAJ5W98NxF9/8ucf/e6dL/74zn9/+uEf6Dff+t5f369/fXY3kHqmWuppQNLfc24fGViO3X/7w+373//uN77//q/br//2rb//JX3x+0+ia3c+oRbfR7y/4t1A4vsQ+JO7gbjRK+vjOiPyxh+++W4g8X20+/ndQOKb0PbTu4HUbmLY//ndQGo3IOCr74jXsNObrwaKNXq7wQC3twFBsJPSaOsDnLxVI/Nm+19cBrA10+1W/+Qy4Lrft1X05Ce//uZ7X/z9/T/Wb33684//m//19z/kv4zwxvPLgASJZak9uQ985yfxvW/8/gffz//8+79/84t/bJ+98+7P/+au+XYcZvO2yLNJ//pDyd/5xh9+lt/99PPv/foP//v333yuCVBf4zIg9xiY2/H2+y8/pO399/Lvfvw7pWP5PPzgF9/2Oi69PQUvLB7/vH3r088/VXakf9Sf/TN/9s7P//3TX6wuA/oT905IsHuW/rc7XG6gw73x4ze//cHnn773jfe+9bNvfvZ5+r93Pq+//db7vg6n8VdJTtuXX3z5z+//7C8ffPPTH370/q/f++3/pD/97+/9y4D+ZEAXav97xnlzuLd+/BV//Jf3/vLjP+c//fj/fv69H/zs519+/O9rjsTZ8zOVIV8jP/sx7nfvvve3n/zmr1+89/GPwnd+t31C7Z3vjKP5+jJAVjB09skcL/mbX5bfv/fH+O7vvv29/93+9KtPfvjxNcgLnT3NfM342ed4fe8Hv/q/z777R0p///JPv9x+/513Pv7TmCrry4Dt8SecVwPlkbta+gNz9SmnOvGJ7d/96T+/9/H//OzPRP/6/l8/+Pyz77770x+48Eh0OAWvbP/7d//3f//Q3nmPPv7h3//2gx/94+f/9++PP3p6EZDjE5u/++GfU/rVd8t7P3zn/e+8m7/9rf+jH/k2j6fN02pqf8b//PUvv/zvj/IH7/z+ix999rN3/v75Fx9/lYsAaeu+v7X9MX73V//8Lf/gm+23P87p/z57L/7G7W86jZrWWbglPaI5ucTW1M1pVHZ/xhW0LE7ILy1sr1oXfy9GyClCX/ntIpN4+21/adLaLnJbiszrsN9SpPz/TUun7cVv29ZeWZ9UarGDCpkmucd9nouk8JpC1ee1D9Z46fBr24nAo9Y1ZxCZ3yiy8mvcn9QpTWOjXaRy99DOPBFgnua3Dk+tr5TkMKnPX7coEuNrjluKQWuWV3Dq+a2jU8urTBn5n7JNyN68j44SrKYtaCmCU2R56+jU/ErKRRD1sryL1Ldc+hAryoCByLeOjoi8TMvwukWl9ywaOYbRKW8enavIKL0MUSeVDBTceeby5tG5Ki4im9aX01pNZER+7eGJQSeVIo8YZeRPkfXNw3OZQ5rkEnS09YlXBYFvHhx+ZWWIz0pvX8SSSY4ESomozyZbgMGpbx0cuxqTiJTBoVT3G4sNO/kVHJt1GWJIccEktiQSNwQiv4JjUySlhV3kn9Mucts5T/VNUoPVSF/BsU2TUsty7lwRYl8QuR6dIP8XFHoVeePQaT04zyX6fVwPzlIibBF5t2Rai1wPzlLkMd5a59Yfb14PzizSTEo5DLiTkt86NnaHiLtEMWco0sEizYDItw6OWd2h+Mub3zo41gXFGxfEbx0c6yjDjaNsbx0c685vvHl78+BcJLpbTnvz2FzVdjdG59XUGwbH3b7bmwfnOoM8kFG2Nw+O2SF2IBR1ym8yQHruOiW+dXCmtejBtbJ9BbdmPYYHKsv2FfzasUNQh75Ra+VwacrJDCJ70O7D7//8+x9++MP9hXjn+9vR3EuHYP1v7H9z/9t/1zPmeqU53cL73/672n9X+++o/y71/576f8/9v/eXyPK/s6c9H0VfEn/48Ufv//idDz/+weNSXJR4ef3o9fzlWVvpoQ+edcpIHLEac+9pD1zkHrDotfB09fa//Xet/649ftdr5OXS32A/+MWpMxvu22b/27+n8d97O9zb4Qg9La7GIVmN66QxTJuwHGOKtofp9NEl+rYO1tZxsjWEqUpc2rqP+tkyrJro6xytznHSGbxOiUudE5vRkfl2fpF8naPVOU06J5Sz0vlo8egBWDv5Oierc5p0TqBzWq/laNbWOTNhpmVf92R1z5PuaMO81j2aNSI9gi983bPVPU+6o2vMd7qfLYM/Kb7O2epcJp0L6FyWczxn4x8yJCqU4utcrM5l0hmyqUtZ6ny0OMYZ+lp9nYvVuU46V5Sz1vnQ1ereQPfq616t7nXSvYLuda37aHnsT2PcwcOQb4NqbUCTDQhsQEsbjBaPfWLsmDDnybcBWRvQZAMoLVFoaYNjb462B3DvUdi3AVkb8GQDRjlLG4w9c+yhB0qA1ce+DdjagCcbMNiA1za47OJ84JTzy+bbgK0N2mQDtGVb2mAgoXLpAYMNmm+DZm3QJhtASLy0pQ0ORDOw2Nnnuvm6N6N73a661w3l3Op+tBzhC1dnEWZbvupcIfG5rnHrwJ0DTdXT2tXHj9Xixzrhxwr4sTr48YJ8AcdVH8dVi+PqhOMq4Li6xnEHts5WdzrnevXxXLV4rk54rgKeq2s8NzDswLS1whe+7hbP1QnPVcBzdY3nhu5Hy6Czj+eqxXN1wnMV8Fxd4rnzJDPwPH7h62zxXJ3wXAU8V9d4brR49ACs7eO4anFcnXBcBRxXlzjuOK2N09uhO8x1H89Vi+fqhOfwqFu9e4QY95ifVpNXHvlrUDC+hCSH4VOOd3kQ4h6N3OuHahHGp3KcoLTI2a5yIKRIkxwnEh3C48wveLuoD75EBdokx4k/b3EPR3Ai1nppl4D2rJZjZg29hBQ4aJX9OkUMy1WOdwmw5UcIp4a4s4Ffgjw8ybkxs0aXlDJNizhd4k95kuOZOT4CX6RsE6FdQ2OzHMfMIT1ick3GWa1qY3aTmb3QvsxmDRa2lLSeb3oqx4vnixwNY8qKkIkX4lWtWY5j5pgeEdbMcrAvU5hvMo8Tui8aTtbYrzh1Dnt/7ofdCdjL8fdxoaNtM13jebNa3g1KfMTLWSDEbma7KsJVjhOZV/PsoXzl7lCOvGeL1InHq5z9vqZF6YCqYW905v44Zn7qDFsorxX+ByIdi0vX0lWk8Wc3Ir1J/sxqvkgnCv98QG9EereLcb8BUW5p6dV0i17uRH7dVXAj0h+emwWab23p+6B73+GKJCcO/9yt3Yj0NoAnDvdG4tfdCm5EervCs13qRqS3ET/bQH2RwduT4+MSZC+dWtPsVW9EOqPzDHXcSPy6eOhGpD86egdSZGqKyguveyPSGZ2nKNIXOSpwGYhde1C+lzHPtR9saj9idaoZ3VleOkx+6TC3/+3/vQeBag+E1B6G6FQ2irP63/67fpCq/VBR4ThDvSLXAtIrcw1AeopnIer/6j+IIKcsNO70FLoAXvqs7X9j/5v73/67MCzRe94DK7WHejr5jvr5/rf/rocGaw9KdlKeTD04LW4Cekq+xsVqzJPG520qpeUYj7HKVhOChBVKvs2TtXmabA65FZSWNg9sbFohnE3J1z1Z3dOkewLd853uZ8vQ1+zrnK3OedI5o5yVzmNljPlUIRhJ2dc5W53zpHMGnctK57PF0QPwAsXXuVidy6Qz2q6sdR5Wzpe1hF/6uhere5l0L6B7XesezaquUImHqq97tbrXSXcIKVK90/1sGVZX9XWuVuc66QzZEkTrOT48zOFz4QtfZ7I606QzhFmI1r507AaHL4UvfJ3J6kyTzgQ681LnYz/ZjO4E15zEvu5sdedJdwinEt/vI2NHG3/xS98GbG3Akw2gqDm1tQ2y6cHYWcyu33wbNGuDNtkAqhtTW875sXvXanpAELKn5tugWRu0yQaQEMfbcr1vY/c9cMTAFfClawNlooMe8Ha1AcOlNW9LG9ClB2PfJ/zStYFy4JkeXG3AUJOXwxrDDewWbQ/gUQYH3wbB2iBMNgDvzWFpgwPzHGgSvvB1D1b3MOkeQHcHv15brvCFr7PFkTzhSAYcyUsceSDlgf/g+oN9PMcWz/GE5xjwHK/x3NHi6AH01cdxbHEcTzgOc2R5ieOO0wBdsC+D7j6eY4vneMJzDHiO13huoO4DhW/wha+7xXM84TkGPMdrPHechEbL+IWvs8VzPOE5BjzHSzx3nL3GCQSSC9jHc2zxHE94jgHP8RrPHWee0QNYXT6OY4vjeMJxDDiOnUh+Y3rNyqleuSXlcLNH3e0aGmYnkt+IXuWLlFhmvPLmPJWzDhA0qq/1KucMVPI1xMxOJF/l5LbFFLeiIc9roGESs44EtEqvNdYkCpSsBDKXRNF0leNE8lXOJjuv4MyWpVOXMKRM9qscx8y1ab3P1iK1QHx9fbFNejmRfDWPsplVLUZPOV8DjnN/PDNrhipzFnDalJLPRtvy9UKJnVC+yqksOhXlwely7qaPE8pvXF+bYLrS5J/q9VXOQoxjZlkVtQheDVtVYqOrWtOwO5F8ldNSU0rW8IigPTGzE75vrbwW0gqvLSmQfzrsTsy+NXolrqKNZl+n681LnuzjBOpVzqb5+iXKsZfa02XhROdlqLXall5B71X6nq1SJyKvZlbuvCJtc7w+pRHIPclxzPzUGV7ifuBfnTD8PgNOkde3KTwFek+RzQnDPzXajURnGJ4O541IZ0hEZBGvGgXsR/Hks8O7Efl1F8GNyJvRuVmfU+wYRDph+Oeu40akt0qeOLUbiZ77f+Zub0R+3Z3gRqS3KTzbpHyR0duHn+2fNyK9Lbm+arU/5dMuyjc5+dQbkc7wPEUdNyK/Jh66keiPjrjbIjNGsFpeOF1fpFOP8TmIvBEZF8i605zmTgat++JL39f639j/9t/1OFenFMydRjV3smmFiS8d5vW//Xf9fNxJqBXm9Pb67+AU03odyAWiV2ZBQPQNEs7+q/8ggxxaaNz6HUDr3CCdvDB3wtbcaa11VF/6UHQL9J73+ErrEZ9Ojpg7IWzutNnqUV+6G+x/++96LLpBNLyl5mtMRmNIdBsan4+aWl6O8TFWVpMGyX4t+zbP1uZ5sjk8Lmh5afO0GZsyxCZb9nXPVvcy6Z5B93Kn+9ky9LX4Oherc5l0LihnpfNYGWM+MURDW/F1LlbnOukMxdlbXel8tjh6wPCFr3O1OtdJZ7RdXes8rFwvawm/9HWvVneadIe3kI3Wumezqhnir4183cnqTpPuEElsdKf70TLcJDfydSarM086Q6m2xss5TmN1HT4XvvB1ZqszTzpDyn7j5bo+Wjx8KXzh68xW5zbpDNWSWlvrPPaTaHTH4get+bo3q3ubdIeYdWu3+0gYO9r4i1/6Nmhog7Jtkw3Ocgbyf13boJoejJ2FzwiwfOnZQIXaHlxsoN+CnOWcH7s3selBOyP18qVnAxVqehC2qQdgg7Bc78eueuCIgSvgS98GwdogTDYIYIOwtoHtwdj3mfFL3wbB2iBONghgg7jGcAO7ZdODdt5Bype+DaK1QZxsEEGTuFwLB+Y50CR84esere5p0j2C7g5+vbYMc9/FkSrMtjzpnEDnJY4cSHngP24w41w8p8JMy1c8p9+ecpZ47mjx6AH01cVxKsy2POmcUc5S5+M0cMW+oLuL51So6cEVz+m3p5wlnhuoe6BwbuBpXDynwmzLk+4FdF/juUP30TJ+4etcrM5XPKffnnKWeO44e40TSAVru3hOhdmWJ50raLDGc8eZZ/QAVpeL41SYafmK4/TbU45bVycVW9sh9wjMVrjRniue8oM5t+j9ewCRXgWKq8i6vVmkV4HimciKAreUQKRXH+SZ4r7IVY5K6XT1ZXtgprI9cIN2AL707u9UqBnNa46KfgtyiqOUKHFrp1KMUiiSliJLRYEtfCWR7WuKDCmn9QTpb2W/uuI3ItNSZDXTQ2P3b5/GbT08z0Ve5hzs7yt0rPPgpQ9e/9teupngS9+DWHQcVjk353xuqf8tY37/v/PLc16f4oNJt5F/naZ0e3Q3nGk38s9vtd2b12tYoWpdl3addr3C+QxY/tm1XbCoOkyoOgCqDk5E/blS7hwLTkh9XgmzSGclBC+zfVqvX0Gkk9n+VOTFq8CYOCH154q7jiqsAP8xQWRCvPRB7BMGv8yriW+xflhlFOkAdrG1/+3NnQ+i5Z+9rAsVatvg6/yLXf6ZYVTCKsNIvcWL6dHjlK/eBb50d66Q7DK/ZhrptyBnZYvhx0bLwxYbY999WyRri2umkX57ylllGh2DfHi37u0CnLGDm3GkQk0PrhlH+i3IWduA7Dzo82Jj8CNu5pEKtT2YbJDBBqvMo3OCD09/IBnou5uBpEJND64ZSPotyFnboF3WRJ72s+BmIqlQ24PJBgVs4GQizcAwvtknO0lJC6z5VigRnPyk5yL97dBJVXqu+I3IRSkBtfBLN0v/2/1LBeTglstRoWY0r+Vy9FuQs0Zxi13hrfA10BqJLPaut4t8K8ieJ4i3w9IaZD9X3BfJa5C9QCtvnsb8VpD9ZBrDzFnl6es8eOmD1/92r0rgRd08fRVq5tyq/M85n7nvm5zG/D7bgGg7irdT+lr5R7v20j8HUW+13dvX6yq/X9elXadDr4Zf+rZr1nbX/H799pATnaSi50q5cyz6RTbzM4furIToPe6d1utXEPlWkH0V6SLi6GQVPVfcdVRx9fTgnCAdIMRtOPgNvlwdBaN5dSD/uigAowPYxeb+t/a/DOK9AjAq1LZxKQCjXXvpMkDecoVTe7E96piMzpUQ3aJHKtT05Fr0SL8FOStbDD82Wh62CAR9d4sfqVDbg8kWEeUsbTAQ8PAC3dtFiEJHtwiSCjU9uBZB0m9BztoG5TIP8vDp8KVvg2RtcC2GpN+CnJUNjgk+PP2BZKDvblEkFWp6cC2KpN+CnLUN6LIm4rSfRbcokgq1PZhskMEGTlEkv4T0w4+klxKdTTo69ZEWIrc3i3xL/f5av5LIt9Tvr/UrKV5X8yn31fx4p6y69L8ZvmR3NEs1own3IV1+AU9Z3VDpk9FU6q5DLZDnIuwnQ+nJW2EQ6fVLb81aKqNmLgaJ5n2t/OsVg8QKPXgTfcFqJjkarXJlTk3oOuaw9t2cGRVqNLrmzOi3IMc5XzydyJ5GbaXR0GT4ppKHZueXUNhz0qgZjeBOpMtngEs9s+bag97ymC3HugJbQGHPaw842x7Q1ANYyby0wWh59GTYpAJCaL4N2NqgTTaAiEd8cyH+/LZRfXMV/vy2ef/mEvxXea77TG8uwX9V+SIyg8jl6mx97raOMR73ztoB+NJdnclm96Qpuydt2IO3rs632T1tzv3aU3m+3Qe33cVItRuF+t82jAVfJtdIIRgjQaJQN9LJGSX//Bbmm12pN0325N1APJXnG2n1Nvk0To9dpjBmUoMv3ehpMm+U5V+v0dN0Zv3JP6/2ztHymNOpo9cUYJj8G4VkbxTSdKOQ4CYhLW8SjpaDnTCxgfX8m4RkbxLSdJOQ4IialjcJQ+dzHbfZBv5NQrI3CWm6SUhwk5AcXrfZScW3TVWH1G0h723+wWF0ey7Pn/oOo9tzlX2/vCqtr7Z96Tbpf/vMytAZt8S+CjXjeC2xr9+CnDWynV3EG+1enMDxU3m+3VfJUqdxHlzrpXOsq7HgS/cKO9mkqTQlTSVImkpvok3blXrbZH8TZ9pKnm+kujpzHcbpZ/fUo5vppDooqbpnLhFqjXQ9c6UKnoVW2+fR8jGn6+gJfOlvn2S3T5q2T4hKJVraYLRcLxMGbiUT+TYgawOabAA5TomXNhg652ynKtqAfRuwtQFPNmCwgVd8VCYSs8ybpITZLDMztNcse1WVycRh29/0l1fN5VCCihRgannFR8srMXGV/UVmpBY7VBIxMat2MdZHmYD8GuU/Kx82BoKTTwF2fnCVl+7kubsH6lSuWucbrb3Ko1lfq25aPCblpBICix2Ya9OiUN2OW92U/K9CaaySvMKjotPWtlLzJmCV0i6xhb22mDiARylesXXbWhavxNhH9/Ahv9f0e/m5HM92iVzaFps6l1S7xPMXh8jsHz5QK7qoTcXXO3t1Rzm9isG2JN5uzz24DA75g5OduwnKbfePohFHzTq/9PJmdLL34jnUV26hVS0+1bZp4ZS7Xq6HR+z++hjkLcjMrVxozBviRFvccoBHAdl55Zy1kHht+oiiEMV6VbbdKOvkZAV97LknbCirb7lObqp3Ih3AJSZ63QJpJzd+SGy16I7LIfQxlsWc9rKpDQU6A1LLa6JSmxh8I9XS9pHu+uisF1l18oH4Za0GoBVRVWTbdtqadvjGljaW4SJI/stOQlahqq6LqvoIcY69k2lfbHFrY9aUIpoESg1Frscmy0E26HNkkl035McKbLxfEcg/pjbcRGOBfBGIvUXkemzkiPIactMD104E+PATm/jXKDttGou6yp6hvilnFOmA4cDitLdQtiISv9pycR45766npk0xW2tap1dEBnFjuakXjqOT4wfntp6dN84sgD1KB2KVnbCly+hIP+zo1JPNUGkiPSdeKO/vukmmWesuV/SjnEVEXzmymTWtPxgBXebk7DT0KpNcS7Tr6tH6IqK3eAz5lyq6Pkqrx1eZlAIPN45ww+xyg9NrElwZiz5Py33zYlnXMteDDvFDZM1y1FN2K0KRbjaj+EYZX1k98puy2g9lcSXln68ykiDRP0LiB5NfK3ciXRyAWtWL3o/aLY7e/kESbV8vo/PwbM7oOAfJur3GKvBGdgCZM6q4ACBZ6xRZ95K03/+3V61oIWcCKjiH3Osr8wFfRCo0cEU611fSS2riumsU96b0FQaltS5RXADLXlYinHY9anCVKB+rm2lxt5yIpE0/EBTWtFL+LrIG2TVCMqPj3F7tesMHV5HlKhI2CYf+4yHyUOsKd1u8U9xZO+IaZSHqdMl7FuYKlG+vOiGbIF44tHnM4CHj73NbAl5HouPYBFFlRQOyy2wtXoFf7+KmT3C2lhhC9y4zuBgpyF4qXlCEMl/xbnqIJN6q7rYbvILyqMF3tWUXpf01VL3iXeoSjx9gJ91Nx2i1dEKO3t7VGlfddVh+rDvsNNrVHxvnAdMBJK8Q1+uYU+okJJEgQFc/1zKTqz3b6dh6PADhipMRoMqhdSmy+SmbesD0Zo8BXHao17ZX+RTXtcdDFgjX0dVjAA97cbusJao4b9O41juRHmgWIC44Meh2VGvoEFecrOgtSHooLmg/qy3AxXoly0iclQAPDf1UTWN4dFJAmEDzwDxmilI5i2kiAlLv/N90/BSWyWmdQj8SVsFLgWXbjg+J4o20Zo4crhNIXA+OAMxX0TEoeN7Loj4WnVIgy55KsY1FJ24jCDqD47rHAJ6UdKXoc2EZJn39vjoRrieiEwDIisvEz4i3iQLN4mOXbilE7Xql0Dsp2D6RTIkK4NG7eQxaISdrWQVmTVF6+2rx7x631xp1tjDtzCMzwDU/AInOCbNWRa9aGahGrUTQAS63IjutssM9+qgMlqJEhscOHgF41XQ6fc5QY61Uc7dkFqPJ4TjtZfSS"} |  |  | - |  | - | -
[14 empty] | {"index":401,"total":402,"filename":"Advanced_Project.ifc","data":"P+2vPviM/f0fOgGunABXTICrTQCApRt3eLKscU7DBMCisuMyAKcCENS3gtzoDSAMbgB9+FOV6lJHyzcoZqCSMkRB6zAD0uDHBUgEbyBhJxsPsAF7EU0fAPm2byAYZ/A/+AhIcBOwn8Ba8kKjVCv6p6CaFST1s3gBX0yBr23BMVg3HpVTwC8gCwHSqlDjgCc0BH07mP/RHtyHomHoFPhyCnwxBZU8ITAFArO74eEtHlEHUTTYcS+CgR24n4UMo6fAj5qCMHQKQjkFoZiCUJsChVwn9B+RPMILOMweCpsYnncj+tjoMJoLNQM8RN+HFIdOQCgnIBQTUPEIBWYNdZROKjzpFL9iGHoQrK3AfFT9TY/kQfs3YX6fsoqhox/L0Y/F6MfK6MNGKSx21qOXM7AQ6DTmUKzRBvaHvrZbN+Fy+es+CO2fQCmGDn4sB7+Q/2TFA5QYN9xzAX4C+kBC94GMawejhztTX+P//4UwKYaNvxTF+Euhi8dq4++lhxaBMxcYhAQsdPC4K+MGLHwfAEkxcgJG7WGyNdfJV/9d2f9iAmpSsMVMHuMguXhMVoQ7ADAyDroADBUIBn39b5OCmyxPvwyG8SDNKoaOfykEy0IIljUhGHgebcdh7Yug8MxS3ABAAsAjGh2eQN7XePv4G6/wQwXJX/L4o5IdXgJNFqa5frTNHtBfSsHlif2ZzYmtrYW5VdZqTPxGfePvA/jv99r28up/WT0SKAEcqZnRuRP+So+Gd+XJ94gCnikLrYKt7P8KHcbXuT1DG52e2V7+PTezOls0qjEb0y8kqCHVZLBHIqnh6DEJB1HolINtBHdgB7CF/w4smLJ03WkUbYDSURFIvSBKOQeBOqwWKT/vUn3A2VmkXhr67fF4aqKB6vcavdiAGumY4pmVDlN9C6KOzyMAfFNEJarmgdLpzEgxPRJQTfpK4MgcRkRRgeQZhT7mgQvsQKBIEEoFSzeD/CVzgZQAUDA4alRwfEVxwnMsWH4cQ3JSgQyxUMAzebng+AowhiEVPLdubf4nJ9MV56nzQXDSDCh4ynsD3B+7EcG2mvqMR71HLkjuPB5Io1IhCi5wtIfCk27SlUAZuvDD1CEV2D9cQAciF/jdscAelULysQZYoKNEoQDz3VyYutPCXFvb7P8agEFBgQEIHV1jpcfTuWA3c0QwEA+Ip180PUBQxtPEJQHxeMaG0XSepgEBCGYHxAY8LcLAl+yIoEIBxAlarJpSZjtMyEYE5S2vaRJgtRocH9gsaHJgN6WTHWDOKe4Zs+7idWSwcEABWohT9bx+gf+3dLYuUJqv4Cy7IcPo0pE3Irklw1iTA5/ytCij4XUSrWLhCR8gmoAQZhkHB5UJCAsgI+IQKIQlpp5SwABLhPXBzcRBKxRhPVFPtm2J7CVSTWcAK3wvwxRnGAaNlpfCAfeEB5Hu04JhKjhKbqEwIIe+V5XwALY/wgGVcAFEOr5uHN9H4wZwERVdh5/8/Sd8geEm/PAh0m9Yr4appOcDvQeGpvF9ITJuALNJvyNxHEBd4N/04UAvKW0awA4tJ6T0717S6U0IR4Q7HtazIBrS78i/FWljkVK/ALY81QcjZIhqDAIGyrgFlPrjFc0/UGepPmCNqT4tuF0tuR1ADHoOeGeq39DZdECNpvphqdJ9JvDzlrQDDpN04P3oFBWJSsLnGC2Ok8fjBwxRPOkbqCSGAF6P+gWv5whHYWEZwlVB7+VJAUPUIT4DDXzKleJElYC2hn5rqZhqvh+WD/07iL/0nPHpenBULyybdBg9U48MMlLD7XtMmYOnO3rBp2qRCItHogamge9nnxccRjoKWgM7ECgzsODfUXHaOa2pP7Bt0HuZQIY+DP9HYyQGyuK84jDiOHrAB2wXlzWuO6AS3wMpmoiigoEwTLFeoCgNkvMy4QKaJEjegHXgyf0ArQpBNiHSdoHI2eVBiJR0OBfCA8vFnIQhBgpAjwRBaFjHL1UoTUCg0RkMVbeReAy+6PlioIuStKwADfSFw07AfAgyvmhBJnigcAFAh0DMgZOEFRQbDQOAM4zIQETi964AVhB+QOIgYnHRKugKeRUGvjPSnbCtEpej6E5Y7TjsIMJ7glnhGCeRE80Fo3jr0ZZPLRcAObw9AWg7LmCywcaQ+85DPr85sVwOOR5aY7lFl5JegMSf+hBS8njAW94rAViNSgUOsYACx5lBgY3MkhcN8hiBLXAy8QlYYGYXCpwNTWp27tHSW04yg9mIqADcAEmHIK/C3c337cST0vsuz/wp39eh5cgRqyVxqQNFtSV+AjSLSB1/IrZvkH0nnhTY0ZX+dY3ojW1gXDl8TSCmp49LMsFfPuKqA4KcR0we8DDqxIgIpUhQE46WE1BJoybwvDamfB+wVEw1pUAHSmZlEZivEqh0we8Y9k1DVBr6roUmfwJgCOggL2QMiB9A/pm/cpUomSYVcqBENXOCwBnSsgD+N1H6gg3s7yJRrM8aS2GbrD5E/kIkPoM1YR7D+IjfsMQZesepXoH/4Ps8sTYoWFB/gRKfB3BP4xAs8zWwf9PSwVT6dL9nYx3CLt3nidECqonNhLFnPkVyQgh0V6bzlmExEj+DHAlRXtoRB4IpjS8sWZoXPPGXkAtAkJ5DiYAo8SVkKeDrkcYd88hQO15y1jjPx5xgVgG6Dxhbeh5ZXKJ8HBG67tDzkXhDxEaal4ihKkTJ9g29FoReaCAgvkoLmahnwCTHckBM2j8UnpJFv6Ed5rMsCWkiEveoUOtCwhy04xlbcf6BekZX5vvQMccR9sINxKcBY0awixwmURLLkNK+hVq4RAPt156YVo8Tbmk/l1gfUKVpXwchR9O+nvb7SPUTO8O/iaX3qG6h/VQHPp3XML8AlJ4HhKPfQPk39FcwpX1VSzpiHmnkfdhSPwCAmJsG9ovuZzkPKK0ntEtLqpfnEaij99OYQpTYb0F8AHC5xJ8ge0T1BasSjVQvLNREA7UbCD+RBuYHjKV6o1V8cgDxYV4zPw+LWNB4GiGpv/D6galGeRMorQugKUE37AFMveHnCTeAEm6g1ErtA6X20aWAnpeEbMDeCf6teBzQyMKUx8Fo4uOAMl8FvadxN5bOhgJqmZ+x9N0AJXkaKfEz8NnT/Bjk6IiiIwNSS/wYsGOa7+Nxgrfj9wpSBqaB3iMEzddpY/LIrlM/YuKTAI44R5yg9oEyPyUpPTNQT+vMSgru8qhIoedge6TngF+IRC3J81aRdO5R3MD24POnemEZ0Xu4yO/rIskFHhnaRGlcYZmpRGldeGFUorQuUHeYKM0LwIrn35HmEZ3ymUqaR1QW4PMYQkcUvqNEaX3H9B0h3miiNvC/U0wsUvwegiCTA1KNOBQQZ5jSaXEAv+ggDDQIctpXKC+ymsIG2tFgQCj1ARZgs2puuJ1k7bnlib8DsjYwvCRPa4I5a0j7YxnUgDnGRYeaNFwUMEUkfAJLZ1SidOgFCLXEJAKV/Jv0WVoomSkudg17AYIVUlxssPLJMojU8W/6uIFq3CR0SjyCFDcv4OrwZGiiCL468keNFDkr4Fc8TgJSy78JfOAbJHDHbxI3B/imtI5MLakIUEeJ6gDmQZHi5geUlElA+X4cFv53EuoNfM04akhJ1QCt0/0geyCnghQ3e4zmxUUFHAOmDiWKmzOseYUfM1L8+C0OP/QXPnWLwitQhx+H1ZwNwFqY6sgU+2EBQ/EjBUrcpwUmkp4HimDtQHTHNYQ08m9S6jngQ0lYB4ofD1AaL4fCGAqrAGIktMLSlyTESxLSkHrDwjsJuU4REwDUCcmUhFT49AMJn9qy0k7T++BWrug6fCu0SXkSvoFq+qiQC6HNQxjWvWCyCKIMPiADEPgBJbB0gd4XqKPNCZYLgQ4sFwJtF0hZgTwRHYSF9lj6aGET4Y9aEbcJmETCHW6O+BHqxOkCxX4EA+1GpvTRGuSiiJJeLaCGmz5iGADLlOpxMIKUrISVPqgrMfzvNN4BpX9OZmIU/bsnsAQa6LlgCbSAkrIEtnJjSSribFxA0a6DlHJ8AI2omwSops0WjyfWxE0LdHhBis6hSPE8O6Q0P6j+jPzvQfC/R34eNnn6dwBDQ5REGaCkLAFKOmmglJQ+4LLmfw+S/z1q+ncQO+l5ResfqPJUP3IbRA23rxy3rzy3r0J6PvLzWvDzWnL7WnH7ms6PBmr5/WGZ0PPac/9ZHgxoPKH6+TsPKNnQvxvFzxvDz8NnTs8bx+0bUqYBJaYx4ClmdN2SEgA/OwL5iFoDoiSaAsWjfZBSquOAp0rwvweWciwxOQE/c3reKX7ekcIVs3HSugFehdt3jtt3nAQH03vyvxMTC8uAlRaYqI+e93RkF1DSUAdMpEX1e8ftw05C7XvepABm+Pkg+XlgIun5oLn9YLj9YPn9EeiJ+vR85P5Hwe8fJb8/TjBRze1Hw8/z8RAhci7GgN7OgaU//B4ixgNYomQkwGXtWCykM+LRGxDxI6L7iSDqkXlEsRFxOKKdlP4dpTWipNpAVSo/LzU/D9sR1S9p/eGp3ty+DNy+jIbqU8SUoYjv6d8VemEg1fy8IjwCSniE+fe4fRW4fRW5fS24fZA96Xmt+Hlt+HltuX3tuH3t+f114PfXkZ9HrpOo4vc3mt8fnWSIWm7fOH4euD563oT0fOT2LSuxYFeR1C55tyGlU3KBEpMC1Dl6DuCP6kXLCVJHQl9EHRr9O2wr9O9oaSZq+Hln+XkEQKK0/oAGbt8Lbt9LRfWBOEL/zsp0oMT8RnSCo+c9MXFACX+BsmoA1TLUPgjb1H5Q3D7vH0ANPw+fMz0fHLcfArcPiEP/HgW/f5T8fFTcfxYygRp+f/iAqb8onRIN6XmyqSDLSC5cuL+oHOWrk15LU+o5LLCtBwYJE8eU3F0nNeHm2tpsP3cH/AHZO9BpGWOfGrV20oTtTiwvD/CMxM0oSjapWHlHShX0doW/Etcu+TvAX9yvtOa/uObQiIx/EW81cSWaFP4gndBf/L5QpsO/OB6w0ukv8WeC/hLGsZoQts1Alh76i2vcGP7riJ/jv7jGDOVjNqRMNoH/0lOR/xL/JegvCUDwJdBfS/wX/TXEYzGnZZHPhMVMf5HhR69M5Lxw3i3tEpYYehxo+Cv5L5kAiDcAhEfOyPBfUtVb/uvZHEp/qQYyCDnamdGqgX9JpGGBmnS2AHv0l0RXxX+z+M1CMItwLLAhJ8R/FYk4/JfUBYH/WhJp+C++VyDlSyAVQlD8FxEmaP5Lu7Phv7SzWv5LXAEZFgLNL39fyM/w7sh7En/R9L3gX0l/FSEZ45kmNDX8lxDR8l9CZcd/UQLA/IT4l1CFFDZs1cYQdCakDENXAyLkFi1UIqR4Ao6HCanVhEmE4r4AB5nQlypcIqToEp4JrS0pYiI2KQuZkM5ecv4tye1JghTATVLbka8vEJsI6RalY0KpgYGQYkuy3RbqYhxJhHBGyUTI6UYp/jfN5mpaxpgAhUmycydCPVOeSWALZ0yEgw1FIpx3RCbCauykzdYEOdokkhIM5TxD9DjbozXBpUzWcp00/DER0tcZkQhp7ZJSlT97yd+95A9f8pcPhJTsqBdB4sgiYHwipGsEUGRCOnfDsdKW45os2TmkVYlQnSye4aTQRWLCJbwQEzqGyTomnuzi5PILJJAO1RLGAG+RCFXmJBPCSWBLEiFlL7quI2HTMghrTGhNoEMEEZp+Foylo/0KjdBMaFY8Tw7sOKQY1olQHltvEiFlA7CFTGJSIRPxXFlIhLYpHxNh5XDSEfPnFFQipLAFUGDik/qZtc40rMElQntg8InQ+gwhERpPZBl/oZWcIzBkIuwQrRIhzYWkyQFiSa1qEwmkfCVxSkmad4VZZ4iQ4ZttC/AXh1UZUgSgUZ/0Hx4hBwgZy1C1RYR0IY7PaHcGOWkjyJXGCFLeG+QriSDXYgQBlGEDJQgYngk2hPI7DqFGCVIRJTxEGkgzEkWmOClAZaK0/wHVmcrI+2qmKOlrzEmdqCHNSnSZWjKXo52XqWZzvWRzu1LJbJ/M7kqze44mSRapoX/XzrDET+ZalPxJk+A0WRaB0iijd5Cg+o1kTQEwuoqTEaIkgDQwp0QSAuXu4uu0n1ByB82ByWR2xQBlwhOYBbajQIEzNEOBDwWEj0ikK7RBUcGnK0amK8bkKyFdSUfhQsHmKyFdIbaeCjZfiekKf/hYcPlKTFeCdqnAaXSNY38jLJh8hbOwGs/BXlgw+UpIV2QCVN7nqcCAC2PEZkj0VstX0vigo2YquHTFpBFLIMB+fVywuXWbW2fziUbJIdXMewUWYqqZOAgqpHdnfpwKOj0VfGo9yvQUG9iwkEY+JNMpFPjQTijwGXcmyPQWQXJOE+DeRHoqz3tQ6S2CTm8ReGfAAltMYY5VqsfYVI9JMxjSqVtQcKkel94CgCrV49JbMDtDhbR+gs9vEfJbhDQXIRl3TUhbmwmRPatMFOktokgrgVVVWJDpLaI0+UpaCVGllZAgEAshXUmuWlCw+UpMV0gopILLV2K6kt895neP+d2j0/lKWr3Rp9UbSdtKBU5pZXI+TSiYfCWtH1YhU8HmK7x6rUhGdEtxDlxIZxsKsn5QweUrKV8zPJSuqJQDTeh0FAXwcPmKT1eMSFeMyVdSGi5gmdIVa/KVkK6kNQ8Fm6/kPvvcZ5/77HOfQ+5zyH3OOabhtdKVmPosReoz2/+okPosZeqzlCZfSX2WKvVZKpOvpD5Lnfosk7MCFFKfZXKYgILNV1LgL3s7UcGlK06kK07nKz5dSW4WNtl+sZAyLcIKTVeCyVdSSLXMmX9kTlshYzosRwn+KtFhPV+J6YpU6Yp0+UrqM7rapELqs9Kpz+yERYXUZ2VSn9HBLRVSn1U+Vl5Zk6+kPiuX+gwt5Cu5zz732ec++9znkPsccp9D7nPMfY6pz1qkPmuh85XUZy1Tn7U0+Urqs1apzyAa5Supz1qnPmtt85XUZ53Qz/aYcm1Sn/GlU8HlK6nPOh/Hp13us8999rnPPvc55D6H3OeQ+xxzn2Puc0x9NiL12STxIllgsCBTn420+UrqM7t0UsHlK6nPJu16UEh9Nib12Ridr5AnAhRIJqaCyVdSFgjjUqZg40y+EtIVn87WhXWUr6TMBCak9Esm2Hwl5VwGpE5X2L8TCynVCkb7pIJLV2RKAs1GOiqkA4/xC0kFk6+kLDe4XFKBdwcopKR41qQEUWjBSoWYrtiEWslhFQsJtaxLqMW2ZizkQ39sPh8DBixdCQm1bDD5SkItGxNq2WjylYRaLiOAywjgMgK4jAAuI4DLCOAyAriMAC4jgMsI4DICuIwALiOAywjgMgK4jAAuI4DLCOAyAriMAC4jgMsI4DICuIwALiOAywjgMgK4jAA+I4DPCOAzAlCKOC6kWfYyzbJPPIBNDkZYSK17ndaY1y49ZXg3R/toSIX07sDyqVRIK9zbtMJ9Pj3as48OFkJq3avUOkttWEipI4DlS/3JuUl9TKvF5zxVyRlLo2lbpILJV9LIB5laDzJ9X+ySgAWVvq+gUj6eoNJaDXneQ573kOc9mPR1gzCa6rHpSwk2fSmsEMaCSzMYXJrBwGIxRvGk7zT4dCxGyGs+5F0vhDSGIbnxoU02PRXTFxdF+uKiyHn68vceZU6KnHf8mHf8mHf8qPJRczone9M5O5HOaTxMTn5tcp5Ym4/rsjlnWMa66NJosAsTFdJoRJ9GI/qc/cXHnF4zjUbsHRKSXBgpD1gqYL7MUvfcwStx6vf22vragOMr68Jcnydt6OBxOPN7am1lwOMQzxegtYPGG1KXBdIIoIcdXffZ44yNiUqwFlAJ/oAxnYBr6utDB2+Mmd8zyzNTv2c21leKzqDlhw1DNPDo1UjaL/jYJdOkACHnGoU+LmQ/D56doCQpv9AtgZyfjVfJWUajyIeCFt2PaV5Qb4s+4U2jQOhgalj4Pbuzudo/jui7gYoN4Gw8KctRVAZiiJAzOlpF2f0gsh5cJHU4keQfRW+KblFENJ1iBHIqjTRpq8gV6hedJkq3uKDZr4kng7yKAgYnIiEzuiDrDobOkCcO20qlkGT6J0QLkv8tsJ06sNJRpIAcnHDSEAfWkwFfT98Ouksopmy6cWRuRMqKV5+iiDwrmoFT5Bgin3xGPbPWKmncVM/Bh3Oiw4bOwUdJ3QYcHtuKAnM3qPtgJSdrsI1jqQJqo98usgoCxjkkypo9wbxHioEgTR9r/FiFCtI7AS3QyMo78p0HyqFPQIkLAbBjzZ1hrS76RfDvmHxOOVVTsGQ2BUpmCqCsXQ1Jr4r2NMmUtX2SYkuASvYFlczsRKk4BFmyaAMISO8TVeQYGc1sJNDkYyrZZ5XdzpHy/ZrHNyZ9MGahxveOiVeIzij2QTUcMuxs8kFV7MsKOy097wP3zwf2ifUc+4PeOnR/UozGtHHFtF1hrm7+d088BcjBipHFsTs+x4wAZTUkzDr5kIJcKh1T9kG1xEsgDYxIgn1PneT6mFECqrheR8pfoGRmVoJj7ZTw6bpn7y/hDQcQeMv1e1KjgtBASjhUp5BBD91iLLnz0DoDym5C0USORbEk3CIlt6FoaT6AEu+ClJ+zmp+zJj1n03M2PefScz49l9qzqT2b2nOpPZfac6k9l9pzqT2X2nOpPZfac6k9l9pzqT0XFT9HWzeGEjl6zpN7DX5upCTFU/foOU/haEANP+dNes6m51x6zqfnfHoupOdSez61F1J7IbUXUnshtRdSeyG1F1J7IbUXUnshtRdSe4HawwgX8nXFnc0QdcnHmIym6FpJJkW0GrCvMfm+o88x+XoCUBh244rJ91gY8k2OHMsjmelA317ysQVhkXw86WwLpuzrqkihhCljBO8F+TrNL0C9yTSS76qzvN050s+hMYN8NIGyL68jhT9GjrJPbEjbY0g7SCAJByjHDqFWj3xQBZlMkHo2mZIgBZQUKEhpP4Kv0yYfWDat4pdOvqvCsi+rpHH0mvYNpOxb6jhmFVhnGhd0p2G3NFLKA43sYxoiB7/AdEWZC7xDRPIsooJNBefSpgHLr7mpd7D0L/9eX17dHmCOlDQcJ4EFz0ZFw0oIheokkwox3UP+lFgghKECb41ol4mpQLwNFFikRh9RDr+VqFvGAip9dCrwSwH3S6KMUkmJpVSygGGBzZUqyVgKUEnkAm+gRhInQAWCdvRA5QBYI01I/8T6Pwzc4wjfKFlYxwIL0IK93bGQJDMB3W7ytqEDb7v8e2the2ZgtHGHpuGiAvttCBaVkB3V/E+SnIGoQNuXRKf/dE/I8cIs32PBJVuu5fDewAGQGEHMcgwWmJ0B4UfxFfY8kBTVma6kqQGZjuNbUBmtcyGmAusAYBeOTfY8dmDP05iQw0nBVgpyZEB3fDKikaMxGoXJiEaSBhDsgGENqpGkRMY8fXiLpE8ZEUURwT7DcsVhAkL+JJrdSjjgz7CDimEPFcA7ekCT4QeTEtEvGnfDFmrDHiqGLdS47i0SYlwNR7GhSTqyUwrdSbsXsFrUa0MuQgYV7sgFR1zmQDggWZDbLusB0URs2HGEftEejNH39IsQCLNnYy0cO+Y4cgy+MnICNmSTSfGmnsNaQGIgBNTEYGGIALndeg4NiIymHGCJKnTGPPK4JaUMxmqQXy25hXpH8W2wuQX6RUJojOw6xxKHRI8syZRdKQCSLVPP/+7ZcSKwswOG01mmhHeUeYWo52/UKJcor2qf3Bs8AxBmnIlMWXD1IlNCM+RJNFPFhnSXqWaDNXnQIOUwKcveAkBJmQBCS6YcPuXYEocOyWy/pvBJpIppyJQ0eoEShRNlVpDDBDA8nMOohFaJsrFbmEw5PFxYZomF5XhQeC3+zWc1R8X6/KjYhhk12YeRamaJ+T3QM5baMWz9jOw5CJRVmej5SpQj5oGyMg4dcRxTmgfYjTjVoE1hWU5x5jvHKlo87ckw5fCskPoXUpgWSCrMQvPBE+j5mahlFlllyiyq8hyepTyzzIZYdaRk5MdUJYlSuLrgLQZpYMrhVUDJ1A/4ws9bwc9ZlSk/Z3WmgVlyK5glpzBroGQuQ2qY5U4svLPMursUeOtSmL5L/XGew8ngC2TWm/N/ADRxPWxMxEhdz79jCi/jrAhAuX3MecKU6pGCvgekkn8Ti4uU3h8YlEzxa8XYX5moIs8JDtNBSuFx8NlHpuRYo2g/YcrPaZEpzRvsu5nSvCnjMqUwN8zxYH5xQDH/5nlQht8D03o4piTCoKOhZkph8c6QXgypZr8CMnog5YgFWMeGKbH0MOqOf1P7mK0k8u/AaUYss9jAiEm6zpEoSCPVy/pyoCl9gU31WM/9sIH9I2zgyAgbOf0AJj0iSgZNpJz2xAUCZ8xXQJS9+pBymhTvOW2K9yktSk5zILh99tRGyu0iEDFN6RFCptxupKh0pClNAilOHWqIqH/RcMRHNFwvh8sh5XGJId0XuJ8cfo+U2veCIgbwdFZS7gBFngxfC9ctvhaNP74e389pXTxv7A5dl/g3bbVAA6ddEORpjEkmUj2R65Wc5sFL8jxGgY36hWkKqX1JselILT2nUn2KVADotWEUU65fK76f02EATf3V5MeEWWm8Yxr5uuV+aLITuLSFurSHAo3pd0zpGwSnhzCUU5Cy2yimgdo3HLmDcX7Uf+M4LYQh1YDDuDu+jzxHUOFE/cVoVP5N5lakNK/RsH8PUL4v1YP6YBZpSXWNVLLoSOwIUmoXjwxxTGncI6uWHZ44wb9JT45U83XSwyFlERMrIkqe2bA8ZEpDQbiAy4XUfoL9fYCBJedBpCl8lfw0kBLbkhIeIOXw18iiomSHA4/aWcWU00yIlI5CpDBXwaIjATxRsuMj9fQcFphGpjJRDltFN7HIVDMlfyekFPaHUc9MWYRTbN5FSmGVStN+iJRERKUNt4suHERtoo6YL8weIZmSiKlYBYeU6+N9Gimny+DIFKQ0PrD9E/eGx4TT85a9epWlCALKRGaZcrokJ3l8HGmePZ7Owdc1hwUnERyzslL/nE3exhzui5Fk/Nun3zF7I3M6EZ/SNXnJ9bN7ElKeN094jZTCYlElys+xqgGGmfvpI2l/0UdVMOX5Z/8gpIEph2di9mh6PnCYJlBOOxI4XFMlVYBiUw5STiMVIvcjpHGLkvsR0zjFND5R8/hGUiUi9Xy/S/eRw5DHHBKOKalMdODngNJ4ao5EQ+pZk0/8L1LNvyXruVm8QYVd5Ouaw3ZBrOXrhsOSFUX4IU2adPYLN5QQDyn7g6Pgzrp1EmqQcpgvZdojGlmlopPWXXO9jsNmjYusquH9AymtO8NmJqSOVSsiqVT4+8Kw/MDUs0WCIkaRUqQRRoA6ppHdnSUxBlRgP+jICdOowMmtgLniHE0CjbZNQbSDaWb999bE6ubv2YW97TIdhnEsTXF8clIJCc3LKK3GlItGc+g5f6KaE/BYYuzwABEiLmWPSG4Fmg/2BcpWXdZUSp1dGB07U2dDN1AStb0jDR150pJGHj5P1ownDXjS3kTeZiS6gBF7zeEKiKJkTsZjuFizTfIuap6Z/VQuaYIpWwSwnZZtYCG5fwbDn43lKH5lLX8O1nN2IMuwrEWK/heSh0YoHhvMq0zLUypejhw1DouYl7sxvPzZacNT5lJaTp6z+AB3RcuQU954q1hmRa8aWmZapqhx35edLHYwdG38nprYGtDSeBtYy8dz7shxL7DREAh+npGTXIHQRWFBGK9NUQm45eAOaYiQQkuwDhv9WVnAdewAKlimRpoEZEUCIoYoEY2s4wKqWCB2/FwWtCN7lKJShD4ckZLUac4vpjSFaGLeEs5LYthGo7xkszJwwokmj30vE2WvB88rSnt2woHtmV3zHdtk0Ks+MiUBF71tAlOqj7LJMNVM2T8QOQ2yQQn2eQLGkfrhOc8ZUNIpowsa+7OnYAwv2EkF059JpukL8YmynTokrWOwrECA0SeBGmN2WXAP1G+gkQV7DuHAvOX0POevwDwopE+DXifbVOAvTrFiA5PV0BemOL4L2GPSpEXD+QhjckMCEKP3BcqCr035UCy7F6Etgyl7QUTHfnnIuJEA7VNeOM/eXtFzkALaFljgZt/nyAw+5kPh/ieFBIZaskDpWKAMnJ9EsGM55jWhkH7Me8eCpOJ8JIIEJBQkSVCHhcrpogQJMpjHhLzlJSdQVHj+AQmGKgmGSibBkfN1YZod/MJBbqANWnJyIbQppDxl5DjuMRSAGT+hmSrOF6ZJ0eLxRC1muHgD04IZNM02T68lKYyAss1AO8pahdSz7otsZ0g1UxXo3zn/JOYlYeQKzMhiZDEhW0j5RFhQR34/8EZuOd8HHyKBvteEhEYwI2nYxxTzhzASSgoDo4wCbPsg2xVS3vAVIy2mV2MLOTOoxqa8JbzPoBzBeUs4lBPzhbBF3XKIPOrcqX5veIP2bKMBhI38O3B9nvOnGHZ28ck/GZWDbEOJ5H+PGeEZFQXnj0tOq+hdlPJ/MOMBq4n6ga6nfJ9N10lgQJsJIbpVJuUJodB4zA9CiA9sCiO8YpsTGh8NUWaEUTDl36QA8ZjOSBAl5xjMkkPj6wW7SKB3Pf2WJCgBu0mh4Mh2Uj4S9GqRTD3/JpsvMCy8/vCARWZgWMDA74uvUwBEoANLiHJIumABN+B6J8bGsz8Y5cPVqZCtPtD55qbVwZCz8XtrfWpjMMEsC0xIIyt0SLGIihzF3yW/l5L8HQCleccwmSQAER6DoMbOe5jU2KYCp4YSInlUYhZVYl8ERm84LrBrgMCQY66Hw2kkMWuBCzql7uIcslhggz3axUktK9D5Lt3DHIvAfYk3Ss+J4QQJ5Vxg+z0q2QgUUcvGb4GBx1wzZm75RYYWcgihQvLW8BzIhoV+NrKDjWfr99b25taAmwxbb1JSQJT6HRHsesoRhHkC6SJlyjGSnOYw+z7ZLAQbMtgYFHzK4pXCK9APSDIly1XwefciyyT6YvOuF9jVEKhLNPJ10utD7ZZ3A03ZckiK5uuJH9SO0whqn+737HmgkzpW066I1PB1Op4c3osTUARH6jSgnPgisDiJNDAltWpI2VKRukQ54QUnMEHKiTA4oBxpUInyv9MuSNQzlYYps2vOp/pJjYLUcLv0MSJ16X6f7vfcHqmPkUa+n2IlkUqRKLdHajekmu8PRiXK7dGME033e24vpPckLoQo3x/TuJBnEFLF93OiDaTcHomtAQeCngtpHEJ638CJKELwXH8IXF8gp12k/N7A1Km08mdWp7dmpqBAxd8LW2u/0SSpfysJF/8/"} |  |  | - |  | - | -
1cFRppLhj948bTrzz_An6e | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:810826 | -1 - Garage |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:810826 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.231 | 122.13 | 272.472 | 177.94 | 94.532 | 0.34694 | 67% | In Progress
1cFRppLhj948bTrzz_An7i | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:810766 | -1 - Garage |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:810766 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 0.846 | 136.49 | 115.4705 | 83.16 | 32.3105 | 0.27982 | 75% | In Progress
1cFRppLhj948bTrzz_Ao_1 | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:811363 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:811363 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 389.7 | 1052.2812 | 810.81 | 241.4712 | 0.22947 | 78% | In Progress
1cFRppLhj948bTrzz_Aowb | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:811079 | -1 - Garage |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:811079 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.464 | 138.26 | 202.4126 | 145.94 | 56.4726 | 0.279 | 76% | In Progress
1cFRppLhj948bTrzz_AowZ | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:811073 | -1 - Garage |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:811073 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 0.92 | 134.09 | 123.3628 | 86.66 | 36.7028 | 0.29752 | 68% | In Progress
1cFRppLhj948bTrzz_AoxP | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:811067 | -1 - Garage |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:811067 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.435 | 143.97 | 206.5969 | 138.19 | 68.4069 | 0.33111 | 70% | In Progress
1cFRppLhj948bTrzz_Aoxy | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:811038 | -1 - Garage |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:811038 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.266 | 140.98 | 319.4607 | 234.34 | 85.1207 | 0.26645 | 78% | In Progress
1cFRppLhj948bTrzz_Aoxw | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:811032 | -1 - Garage |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:811032 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.049 | 127.13 | 133.3594 | 95.48 | 37.8794 | 0.28404 | 77% | In Progress
1cFRppLhj948bTrzz_Aoxm | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:811026 | -1 - Garage |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:811026 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.124 | 131.51 | 147.8172 | 112.08 | 35.7372 | 0.24177 | 73% | In Progress
1cFRppLhj948bTrzz_An7g | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:810760 | -1 - Garage |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:810760 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 0.861 | 143.27 | 123.3555 | 96.34 | 27.0155 | 0.21901 | 76% | In Progress
1cFRppLhj948bTrzz_An4w | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:810968 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:810968 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 12.13 | 88.96 | 1079.0848 | 1118.15 | -39.0652 | -0.036202 | 100% | Completed
1cFRppLhj948bTrzz_An6O | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:810874 | -1 - Garage |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:810874 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 0.809 | 131.24 | 106.1732 | 74.67 | 31.5032 | 0.29671 | 74% | In Progress
1cFRppLhj948bTrzz_An60 | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:810850 | -1 - Garage |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:810850 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.179 | 138.87 | 163.7277 | 128.89 | 34.8377 | 0.21278 | 77% | In Progress
1cFRppLhj948bTrzz_An6_ | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:810844 | -1 - Garage |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:810844 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.386 | 120.53 | 287.5846 | 211.9 | 75.6846 | 0.26317 | 71% | In Progress
1cFRppLhj948bTrzz_An6q | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:810838 | -1 - Garage |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:810838 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.49 | 136.53 | 203.4297 | 139.81 | 63.6197 | 0.31274 | 70% | In Progress
1cFRppLhj948bTrzz_An6o | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:810832 | -1 - Garage |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:810832 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 0.843 | 142.51 | 120.1359 | 83.52 | 36.6159 | 0.30479 | 75% | In Progress
2dAxltRn524vY2d5KNMrvW | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:808239 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:808239 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 12.55 | 88.94 | 1116.197 | 1084.12 | 32.077 | 0.028738 | 100% | Completed
1cFRppLhj948bTrzz_An7Q | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:810808 | -1 - Garage |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:810808 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.604 | 125.32 | 201.0133 | 138.18 | 62.8333 | 0.31258 | 70% | In Progress
1cFRppLhj948bTrzz_An5M | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:810932 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:810932 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 11.33 | 93.37 | 1057.8821 | 1101.48 | -43.5979 | -0.041212 | 100% | Completed
2dAxltRn524vY2d5KNMr$K | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:808091 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:808091 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.6 | 89.12 | 1301.152 | 1264.38 | 36.772 | 0.028261 | 100% | Completed
3GdhC2lQD5ifjmLdQ3yoT7 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:798319 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:798319 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.57 | 86.38 | 1604.0766 | 1575.05 | 29.0266 | 0.018096 | 100% | Completed
2dAxltRn524vY2d5KNMrWy | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:807795 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:807795 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 13.03 | 100.02 | 1303.2606 | 1293.33 | 9.9306 | 0.0076198 | 100% | Completed
3GzoWuxxn4WO8bCtw8H3AT | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Elavator:696920 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Elavator:696920 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.58 | 88.75 | 2092.725 | 2189.9 | -97.175 | -0.046435 | 100% | Completed
3GzoWuxxn4WO8bCtw8H3AS | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Elavator:696921 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Elavator:696921 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.01 | 85.69 | 1800.3469 | 1889.66 | -89.3131 | -0.049609 | 100% | Completed
3GzoWuxxn4WO8bCtw8H3I4 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Elavator:697409 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Elavator:697409 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.4 | 95.55 | 2044.77 | 2021.09 | 23.68 | 0.011581 | 100% | Completed
1cFRppLhj948bTrzz_AoiZ | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:812481 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:812481 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.55 | 101.12 | 1572.416 | 1529.93 | 42.486 | 0.02702 | 100% | Completed
3naw$9in55$v8L5CpxnK31 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Elavator:712947 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Elavator:712947 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 25.69 | 85.66 | 2200.6054 | 2148.35 | 52.2554 | 0.023746 | 100% | Completed
3naw$9in55$v8L5CpxnK36 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Elavator:712948 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Elavator:712948 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.83 | 100.06 | 1884.1298 | 1935.21 | -51.0802 | -0.027111 | 100% | Completed
3naw$9in55$v8L5CpxnKAh | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Elavator:713369 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Elavator:713369 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 20.01 | 101.61 | 2033.2161 | 2014.16 | 19.0561 | 0.0093724 | 100% | Completed
2v8sGyGFXDsRc80mj95kV8 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Elavator:722908 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Elavator:722908 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 25.29 | 96.67 | 2444.7843 | 2518.16 | -73.3757 | -0.030013 | 100% | Completed
3p6DR19bjD_PWb8lZMRTT8 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Elavator:734443 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Elavator:734443 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.77 | 86.24 | 1273.7648 | 1260.43 | 13.3348 | 0.010469 | 100% | Completed
3p6DR19bjD_PWb8lZMRTOE | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Elavator:734637 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Elavator:734637 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 22.78 | 94.19 | 2145.6482 | 2231.69 | -86.0418 | -0.040101 | 100% | Completed
3p6DR19bjD_PWb8lZMRTPc | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Elavator:734661 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Elavator:734661 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.55 | 89.67 | 1753.0485 | 1840.09 | -87.0415 | -0.049652 | 100% | Completed
3p6DR19bjD_PWb8lZMRTML | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Elavator:734774 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Elavator:734774 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.71 | 92.86 | 1458.8306 | 1470.81 | -11.9794 | -0.0082116 | 100% | Completed
1KMtYLyv9CyfGv8UjnMBCI | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior Garage:794609 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior Garage:794609 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 32.11 | 101.81 | 3269.1191 | 3265.99 | 3.1291 | 0.00095717 | 100% | Completed
1KMtYLyv9CyfGv8UjnMBCH | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior Garage:794610 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior Garage:794610 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 31.12 | 87.48 | 2722.3776 | 2688.51 | 33.8676 | 0.01244 | 100% | Completed
1KMtYLyv9CyfGv8UjnMBCG | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior Garage:794611 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior Garage:794611 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 26.99 | 100.02 | 2699.5398 | 2634.69 | 64.8498 | 0.024023 | 100% | Completed
1KMtYLyv9CyfGv8UjnMBCN | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior Garage:794612 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior Garage:794612 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 28.12 | 98.9 | 2781.068 | 2762.76 | 18.308 | 0.0065831 | 100% | Completed
1KMtYLyv9CyfGv8UjnMBCM | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior Garage:794613 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior Garage:794613 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 25.26 | 102.55 | 2590.413 | 2624.44 | -34.027 | -0.013136 | 100% | Completed
2dAxltRn524vY2d5KNMrcT | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:807634 | -1 - Garage |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:807634 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.223 | 140.86 | 313.1318 | 242.11 | 71.0218 | 0.22681 | 75% | In Progress
3GdhC2lQD5ifjmLdQ3ype4 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:799532 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:799532 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.12 | 92.26 | 1671.7512 | 1709.03 | -37.2788 | -0.022299 | 100% | Completed
3GdhC2lQD5ifjmLdQ3yoTZ | IFCWALL |  | Basic Wall:MockUp Storage Wall:798283 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:798283 | Includes RC walls, block walls, brick walls | Dimensions | Area | 8.2767 | m² |  |  | 91.66 | 758.6437 | 742.27 | 16.3737 | 0.021583 | 100% | Completed
3GdhC2lQD5ifjmLdQ3yoHJ | IFCDOOR |  | M_Single-Flush:Generic Door:798075 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:798075 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 375.74 | 1198.4524 | 966.16 | 232.2924 | 0.19383 | 83% | In Progress
3GdhC2lQD5ifjmLdQ3yoHF | IFCDOOR |  | M_Single-Flush:Generic Door:798055 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:798055 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 411.13 | 1311.3316 | 1045.23 | 266.1016 | 0.20292 | 81% | In Progress
3GdhC2lQD5ifjmLdQ3yoB_ | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:797654 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:797654 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 11.01 | 86.89 | 956.6589 | 944.66 | 11.9989 | 0.012543 | 100% | Completed
2dAxltRn524vY2d5KNMrzR | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:807956 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:807956 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.76 | 96.04 | 1417.5504 | 1430.04 | -12.4896 | -0.0088107 | 100% | Completed
3GdhC2lQD5ifjmLdQ3yo9v | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:797521 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:797521 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 10.91 | 92.41 | 1008.1931 | 991.85 | 16.3431 | 0.01621 | 100% | Completed
1KMtYLyv9CyfGv8UjnM8dU | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:795965 | -1 - Garage |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:795965 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.447 | 153.02 | 374.4399 | 283.69 | 90.7499 | 0.24236 | 73% | In Progress
1KMtYLyv9CyfGv8UjnM8y$ | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:795612 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:795612 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 12.57 | 90.5 | 1137.585 | 1167.95 | -30.365 | -0.026693 | 100% | Completed
1KMtYLyv9CyfGv8UjnM8_h | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:795464 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:795464 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 11.69 | 86.16 | 1007.2104 | 1050.37 | -43.1596 | -0.042851 | 100% | Completed
1KMtYLyv9CyfGv8UjnMBCR | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior Garage:794616 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior Garage:794616 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 32.38 | 93.96 | 3042.4248 | 3005.11 | 37.3148 | 0.012265 | 100% | Completed
1KMtYLyv9CyfGv8UjnMBCK | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior Garage:794615 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior Garage:794615 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 22.92 | 101.91 | 2335.7772 | 2318.54 | 17.2372 | 0.0073796 | 100% | Completed
1KMtYLyv9CyfGv8UjnMBCL | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior Garage:794614 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior Garage:794614 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 32.34 | 102.21 | 3305.4714 | 3385.42 | -79.9486 | -0.024187 | 100% | Completed
3GdhC2lQD5ifjmLdQ3yo2f | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:797057 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:797057 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.67 | 93.2 | 1646.844 | 1701.4 | -54.556 | -0.033128 | 100% | Completed
1cFRppLhj948bTrzz_AoiD | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:812527 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:812527 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 386.36 | 1043.2624 | 841.18 | 202.0824 | 0.1937 | 80% | In Progress
0ducQKkW5EGQM9rQ5zdP_b | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:819359 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:819359 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 24.76 | 94.95 | 2350.962 | 2314.56 | 36.402 | 0.015484 | 100% | Completed
1cFRppLhj948bTrzz_Ao2N | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:814709 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:814709 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 13.08 | 89.59 | 1171.8372 | 1197.05 | -25.2128 | -0.021516 | 100% | Completed
1q9pLykVT2tOtz_4XjbvBZ | IFCDOOR |  | M_Single-Flush:Generic Door:878630 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:878630 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 353.36 | 1127.0696 | 847.11 | 279.9596 | 0.2484 | 79% | In Progress
1q9pLykVT2tOtz_4XjbvqZ | IFCDOOR |  | M_Single-Flush:Generic Door:878566 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:878566 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 344.18 | 1097.7893 | 951.12 | 146.6693 | 0.1336 | 85% | In Progress
1q9pLykVT2tOtz_4XjbvqA | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:878543 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:878543 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 11.86 | 95.03 | 1127.0558 | 1141.07 | -14.0142 | -0.012434 | 100% | Completed
1q9pLykVT2tOtz_4Xjbv_z | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:877944 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:877944 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 11.2 | 98.14 | 1099.168 | 1111.3 | -12.132 | -0.011037 | 100% | Completed
1q9pLykVT2tOtz_4Xjbvw7 | IFCDOOR |  | M_Single-Flush:Generic Door:877634 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:877634 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 372.69 | 1188.7242 | 870.99 | 317.7342 | 0.26729 | 77% | In Progress
1q9pLykVT2tOtz_4XjbvWj | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:877288 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:877288 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 10.44 | 102.45 | 1069.578 | 1058.2 | 11.378 | 0.010638 | 100% | Completed
3U8bdGexDEOw9DXBmULrD3 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Elavator:873160 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Elavator:873160 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.61 | 98.87 | 1444.4907 | 1472.6 | -28.1093 | -0.01946 | 100% | Completed
3U8bdGexDEOw9DXBmULrCi | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Elavator:873127 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Elavator:873127 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 20.24 | 90.8 | 1837.792 | 1862.71 | -24.918 | -0.013559 | 100% | Completed
3U8bdGexDEOw9DXBmULq6a | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:868399 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:868399 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.24 | 88.74 | 1352.3976 | 1411.8 | -59.4024 | -0.043924 | 100% | Completed
34Ni6yH0HDjQqrjEsXb0JF | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Elavator:865874 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Elavator:865874 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.3 | 88.81 | 1358.793 | 1398.52 | -39.727 | -0.029237 | 100% | Completed
1q9pLykVT2tOtz_4XjbvA1 | IFCDOOR |  | M_Single-Flush:Generic Door:878660 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:878660 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 359.53 | 1146.7493 | 879.85 | 266.8993 | 0.23274 | 78% | In Progress
34Ni6yH0HDjQqrjEsXb0TF | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Elavator:865746 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Elavator:865746 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.86 | 91.87 | 2008.2782 | 2104.82 | -96.5418 | -0.048072 | 100% | Completed
3kW2in6T58YuHUVjUiIHHY | IFCBUILDINGELEMENTPROXY |  | M_Electric Lift-4 person wall based:MockUp A:847967 | -1 - Garage |  | Not Assigned | Not Assigned | M_Electric Lift-4 person wall based:MockUp A:847967 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.56923 | m³ |  |  | 179.91 | 102.4109 | 65.67 | 36.7409 | 0.35876 | 68% | In Progress
0ducQKkW5EGQM9rQ5zdOpb | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:824287 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:824287 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 407.98 | 1101.6415 | 932.69 | 168.9515 | 0.15336 | 82% | In Progress
0ducQKkW5EGQM9rQ5zdOtF | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:824053 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:824053 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.4 | 89.09 | 1282.896 | 1283.87 | -0.974 | -0.00075922 | 100% | Completed
0ducQKkW5EGQM9rQ5zdOvK | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:823662 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:823662 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 361.27 | 975.5135 | 713.42 | 262.0935 | 0.26867 | 78% | In Progress
0ducQKkW5EGQM9rQ5zdP1L | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:823151 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:823151 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 395.6 | 1068.2126 | 924.58 | 143.6326 | 0.13446 | 84% | In Progress
0ducQKkW5EGQM9rQ5zdP1J | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:823145 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:823145 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 20.91 | 92.53 | 1934.8023 | 2000.38 | -65.5777 | -0.033894 | 100% | Completed
0ducQKkW5EGQM9rQ5zdP9Z | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:822617 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:822617 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 25.13 | 90.18 | 2266.2234 | 2378.52 | -112.2966 | -0.049552 | 100% | Completed
0ducQKkW5EGQM9rQ5zdP8c | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:822556 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:822556 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 417.46 | 1127.2397 | 915.06 | 212.1797 | 0.18823 | 79% | In Progress
0ducQKkW5EGQM9rQ5zdPFU | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:822500 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:822500 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 401.56 | 1084.306 | 842.45 | 241.856 | 0.22305 | 81% | In Progress
0ducQKkW5EGQM9rQ5zdPFm | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:822474 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:822474 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 381.02 | 1028.8432 | 817.51 | 211.3332 | 0.20541 | 83% | In Progress
1N4ygrFWX08Q8J7Fws7pYK | IFCBUILDINGELEMENTPROXY |  | M_Electric Lift-4 person wall based:MockUp A:865497 | -1 - Garage |  | Not Assigned | Not Assigned | M_Electric Lift-4 person wall based:MockUp A:865497 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.56923 | m³ |  |  | 165.05 | 93.9521 | 58.8 | 35.1521 | 0.37415 | 68% | In Progress
1q9pLykVT2tOtz_4XjbvDJ | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:878998 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:878998 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 13.99 | 95.21 | 1331.9879 | 1383.86 | -51.8721 | -0.038943 | 100% | Completed
1q9pLykVT2tOtz_4Xjbv1L | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:879248 | -1 - Garage |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:879248 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.321 | 119.51 | 157.8727 | 113.58 | 44.2927 | 0.28056 | 73% | In Progress
1q9pLykVT2tOtz_4Xjbv1J | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:879254 | -1 - Garage |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:879254 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.242 | 121.6 | 151.0272 | 107.39 | 43.6372 | 0.28894 | 77% | In Progress
3NlCHdPGXFUvkKekQzm3CK | IFCSLAB | FLOOR | Floor:Concrete-Domestic 425mm:982103 | -1 - Garage |  | Structure | Concrete | Floor:Concrete-Domestic 425mm:982103 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 913.1432 | m² |  |  | 77.42 | 70695.5467 | 73632.65 | -2937.1033 | -0.041546 | 100% | Completed
3pFbansyD0KOHFtJHrTupl | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:883160 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:883160 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 395.33 | 1067.4835 | 837.27 | 230.2135 | 0.21566 | 77% | In Progress
3pFbansyD0KOHFtJHrTuoC | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:883131 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:883131 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 25.07 | 98.26 | 2463.3782 | 2577.9 | -114.5218 | -0.04649 | 100% | Completed
3pFbansyD0KOHFtJHrTutI | IFCDOOR |  | M_Single-Flush:Generic Door:882917 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:882917 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 398.89 | 1272.2912 | 949.52 | 322.7712 | 0.25369 | 80% | In Progress
3pFbansyD0KOHFtJHrTuq$ | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:882696 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:882696 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 12.81 | 89.03 | 1140.4743 | 1133.86 | 6.6143 | 0.0057996 | 100% | Completed
3pFbansyD0KOHFtJHrTu9y | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:882507 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:882507 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 13.93 | 98.18 | 1367.6474 | 1370.34 | -2.6926 | -0.0019688 | 100% | Completed
1q9pLykVT2tOtz_4XjbuoS | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:882265 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:882265 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 359.62 | 971.0582 | 812.17 | 158.8882 | 0.16362 | 83% | In Progress
1q9pLykVT2tOtz_4Xjbupo | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:882231 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:882231 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 22.6 | 90.95 | 2055.47 | 2139.65 | -84.18 | -0.040954 | 100% | Completed
1q9pLykVT2tOtz_4Xjbup3 | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:882182 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:882182 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 399.44 | 1078.5815 | 892.15 | 186.4315 | 0.17285 | 84% | In Progress
1q9pLykVT2tOtz_4XjbuzE | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:882059 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:882059 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.2 | 89.98 | 1907.576 | 1945.65 | -38.074 | -0.019959 | 100% | Completed
1q9pLykVT2tOtz_4XjbuwS | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:881753 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:881753 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.11 | 86.9 | 1486.859 | 1557.57 | -70.711 | -0.047557 | 100% | Completed
1q9pLykVT2tOtz_4XjbuaX | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:881636 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:881636 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 24.28 | 93.75 | 2276.25 | 2329.06 | -52.81 | -0.0232 | 100% | Completed
1q9pLykVT2tOtz_4Xjbucy | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:881529 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:881529 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 20.11 | 92.64 | 1862.9904 | 1906.65 | -43.6596 | -0.023435 | 100% | Completed
1q9pLykVT2tOtz_4Xjbudy | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:881465 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:881465 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.16 | 94.28 | 1523.5648 | 1505.94 | 17.6248 | 0.011568 | 100% | Completed
1q9pLykVT2tOtz_4XjbueK | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:880849 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:880849 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 25.87 | 96.17 | 2487.9179 | 2589.02 | -101.1021 | -0.040637 | 100% | Completed
1q9pLykVT2tOtz_4XjbvLy | IFCFLOWTERMINAL |  | M_Lavatory - Vanity:760 mmx455 mm - Private:880569 | -1 - Garage |  | MEP | MEP | M_Lavatory - Vanity:760 mmx455 mm - Private:880569 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 854.8 | 854.8 | 664.76 | 190.04 | 0.22232 | 80% | In Progress
1q9pLykVT2tOtz_4XjbvMR | IFCFLOWTERMINAL |  | M_Lavatory - Vanity:760 mmx455 mm - Private:880478 | -1 - Garage |  | MEP | MEP | M_Lavatory - Vanity:760 mmx455 mm - Private:880478 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 876.28 | 876.28 | 735.11 | 141.17 | 0.1611 | 90% | In Progress
1q9pLykVT2tOtz_4XjbvVT | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:879896 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:879896 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 13.23 | 101.57 | 1343.7711 | 1311.34 | 32.4311 | 0.024134 | 100% | Completed
1q9pLykVT2tOtz_4XjbvQm | IFCFLOWTERMINAL |  | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:879733 | -1 - Garage |  | MEP | MEP | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:879733 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 917.96 | 917.96 | 778.55 | 139.41 | 0.15187 | 84% | In Progress
1q9pLykVT2tOtz_4XjbvQn | IFCFLOWTERMINAL |  | M_Lavatory - Vanity:760 mmx455 mm - Private:879732 | -1 - Garage |  | MEP | MEP | M_Lavatory - Vanity:760 mmx455 mm - Private:879732 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 849.16 | 849.16 | 658.89 | 190.27 | 0.22407 | 82% | In Progress
1q9pLykVT2tOtz_4Xjbv7l | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:879402 | -1 - Garage |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:879402 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 0.811 | 131.91 | 106.979 | 79.66 | 27.319 | 0.25537 | 75% | In Progress
1q9pLykVT2tOtz_4Xjbv75 | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:879360 | -1 - Garage |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:879360 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.063 | 121.09 | 128.7187 | 83.66 | 45.0587 | 0.35006 | 68% | In Progress
1q9pLykVT2tOtz_4Xjbv1P | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:879260 | -1 - Garage |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:879260 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 0.93 | 130.34 | 121.2162 | 95.32 | 25.8962 | 0.21364 | 79% | In Progress
0ducQKkW5EGQM9rQ5zdPEJ | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:822441 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:822441 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.12 | 89.87 | 1628.4444 | 1694.58 | -66.1356 | -0.040613 | 100% | Completed
0ducQKkW5EGQM9rQ5zdPJh | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:822225 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:822225 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.17 | 85.89 | 1560.6213 | 1555.52 | 5.1013 | 0.0032688 | 100% | Completed
0ducQKkW5EGQM9rQ5zdPNP | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:821987 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:821987 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 419.93 | 1133.9093 | 919.48 | 214.4293 | 0.18911 | 79% | In Progress
0ducQKkW5EGQM9rQ5zdPNY | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:821976 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:821976 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 20.71 | 93 | 1926.03 | 1917.99 | 8.04 | 0.0041744 | 100% | Completed
0ducQKkW5EGQM9rQ5zdM0J | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:818985 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:818985 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.38 | 98.27 | 1609.6626 | 1678.88 | -69.2174 | -0.043001 | 100% | Completed
0ducQKkW5EGQM9rQ5zdM4W | IFCWALL |  | Basic Wall:MockUp Storage Wall:818714 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:818714 | Includes RC walls, block walls, brick walls | Dimensions | Area | 5.9392 | m² |  |  | 91.33 | 542.4291 | 550.08 | -7.6509 | -0.014105 | 100% | Completed
0ducQKkW5EGQM9rQ5zdMAQ | IFCWALL |  | Basic Wall:MockUp Storage Wall:818592 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:818592 | Includes RC walls, block walls, brick walls | Dimensions | Area | 9.1581 | m² |  |  | 93.34 | 854.8138 | 869.78 | -14.9662 | -0.017508 | 100% | Completed
0ducQKkW5EGQM9rQ5zdM8G | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:818474 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:818474 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 421.65 | 1138.5537 | 989.59 | 148.9637 | 0.13084 | 86% | In Progress
1cFRppLhj948bTrzz_ApAd | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:818245 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:818245 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 24.97 | 102.28 | 2553.9316 | 2611.73 | -57.7984 | -0.022631 | 100% | Completed
1cFRppLhj948bTrzz_ApBx | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:818201 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:818201 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 25.65 | 95.2 | 2441.88 | 2447.4 | -5.52 | -0.0022606 | 100% | Completed
1cFRppLhj948bTrzz_ApJS | IFCWALL |  | Basic Wall:MockUp Storage Wall:817726 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:817726 | Includes RC walls, block walls, brick walls | Dimensions | Area | 11.1251 | m² |  |  | 90.04 | 1001.7028 | 997.93 | 3.7728 | 0.0037663 | 100% | Completed
1cFRppLhj948bTrzz_ApSU | IFCWALL |  | Basic Wall:MockUp Storage Wall:817660 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:817660 | Includes RC walls, block walls, brick walls | Dimensions | Area | 10.6712 | m² |  |  | 101.23 | 1080.2461 | 1108.3 | -28.0539 | -0.02597 | 100% | Completed
1cFRppLhj948bTrzz_ApV0 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:817442 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:817442 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.15 | 102.55 | 1861.2825 | 1869.8 | -8.5175 | -0.0045761 | 100% | Completed
1cFRppLhj948bTrzz_ApO1 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:817379 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:817379 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.48 | 97.49 | 2289.0652 | 2220.71 | 68.3552 | 0.029862 | 100% | Completed
1cFRppLhj948bTrzz_ApRD | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:817199 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:817199 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 363.32 | 981.049 | 827.36 | 153.689 | 0.15666 | 83% | In Progress
1cFRppLhj948bTrzz_ApRW | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:817154 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:817154 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 24.61 | 96.16 | 2366.4976 | 2301.88 | 64.6176 | 0.027305 | 100% | Completed
1cFRppLhj948bTrzz_Apb_ | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:817052 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:817052 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.54 | 91.75 | 1792.795 | 1819.18 | -26.385 | -0.014717 | 100% | Completed
1cFRppLhj948bTrzz_ApdW | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:816898 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:816898 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.08 | 102.08 | 1539.3664 | 1573.1 | -33.7336 | -0.021914 | 100% | Completed
1cFRppLhj948bTrzz_ApY4 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:816742 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:816742 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.93 | 94.68 | 1697.6124 | 1749.25 | -51.6376 | -0.030418 | 100% | Completed
1cFRppLhj948bTrzz_ApiD | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:816623 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:816623 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 353.01 | 953.2096 | 753.66 | 199.5496 | 0.20934 | 85% | In Progress
1cFRppLhj948bTrzz_Apiw | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:816600 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:816600 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 387.44 | 1046.1787 | 791.69 | 254.4887 | 0.24326 | 82% | In Progress
1cFRppLhj948bTrzz_Apqc | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:816068 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:816068 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.79 | 88.98 | 1760.9142 | 1841.51 | -80.5958 | -0.045769 | 100% | Completed
1cFRppLhj948bTrzz_Apu2 | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:815328 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:815328 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 402.79 | 1087.6273 | 880.65 | 206.9773 | 0.1903 | 81% | In Progress
1cFRppLhj948bTrzz_Apug | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:815304 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:815304 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 12.71 | 99.12 | 1259.8152 | 1305.59 | -45.7748 | -0.036335 | 100% | Completed
1cFRppLhj948bTrzz_Apvj | IFCFLOWTERMINAL |  | M_Lavatory - Vanity:760 mmx455 mm - Private:815247 | -1 - Garage |  | MEP | MEP | M_Lavatory - Vanity:760 mmx455 mm - Private:815247 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 878.37 | 878.37 | 760.15 | 118.22 | 0.13459 | 88% | In Progress
1cFRppLhj948bTrzz_Apxb | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:815111 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:815111 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 380.9 | 1028.5191 | 890.15 | 138.3691 | 0.13453 | 85% | In Progress
1cFRppLhj948bTrzz_Ao4n | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:815059 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:815059 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 364.91 | 985.3424 | 775.67 | 209.6724 | 0.21279 | 82% | In Progress
0ducQKkW5EGQM9rQ5zdM1i | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:819030 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:819030 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.65 | 95.21 | 1680.4565 | 1690.47 | -10.0135 | -0.0059588 | 100% | Completed
1cFRppLhj948bTrzz_AoFF | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:814381 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:814381 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.84 | 94.44 | 1590.3696 | 1614.23 | -23.8604 | -0.015003 | 100% | Completed
0ducQKkW5EGQM9rQ5zdM1T | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:819047 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:819047 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 370.96 | 1001.6788 | 796.4 | 205.2788 | 0.20493 | 84% | In Progress
0ducQKkW5EGQM9rQ5zdM3v | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:819139 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:819139 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 416.52 | 1124.7015 | 908.44 | 216.2615 | 0.19228 | 86% | In Progress
0ducQKkW5EGQM9rQ5zdPMt | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:821901 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:821901 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.9 | 101.12 | 1506.688 | 1527.88 | -21.192 | -0.014065 | 100% | Completed
0ducQKkW5EGQM9rQ5zdPUw | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:821376 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:821376 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.15 | 87.55 | 1413.9325 | 1471.36 | -57.4275 | -0.040615 | 100% | Completed
0ducQKkW5EGQM9rQ5zdPSm | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:821258 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:821258 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.78 | 93.04 | 1654.2512 | 1648.92 | 5.3312 | 0.0032227 | 100% | Completed
0ducQKkW5EGQM9rQ5zdPdI | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:820968 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:820968 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 20.49 | 92.95 | 1904.5455 | 1960.87 | -56.3245 | -0.029574 | 100% | Completed
0ducQKkW5EGQM9rQ5zdPbh | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:820817 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:820817 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 415.94 | 1123.1353 | 915.98 | 207.1553 | 0.18444 | 83% | In Progress
0ducQKkW5EGQM9rQ5zdPaT | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:820775 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:820775 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 407.17 | 1099.4543 | 854.32 | 245.1343 | 0.22296 | 76% | In Progress
0ducQKkW5EGQM9rQ5zdPfL | IFCWALL |  | Basic Wall:MockUp Storage Wall:820591 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:820591 | Includes RC walls, block walls, brick walls | Dimensions | Area | 6.4947 | m² |  |  | 94.92 | 616.4735 | 609.51 | 6.9635 | 0.011296 | 100% | Completed
0ducQKkW5EGQM9rQ5zdPiu | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:820226 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:820226 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.47 | 97.98 | 1417.7706 | 1472.53 | -54.7594 | -0.038624 | 100% | Completed
0ducQKkW5EGQM9rQ5zdPnm | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:820042 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:820042 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 421.22 | 1137.3926 | 936.36 | 201.0326 | 0.17675 | 82% | In Progress
0ducQKkW5EGQM9rQ5zdPmG | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:820010 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:820010 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 367.46 | 992.228 | 823.79 | 168.438 | 0.16976 | 87% | In Progress
0ducQKkW5EGQM9rQ5zdPm_ | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:819972 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:819972 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 380.53 | 1027.52 | 839 | 188.52 | 0.18347 | 79% | In Progress
0ducQKkW5EGQM9rQ5zdPsI | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:819880 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:819880 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 350.41 | 946.189 | 756.31 | 189.879 | 0.20068 | 77% | In Progress
0ducQKkW5EGQM9rQ5zdPsq | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:819854 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:819854 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 370.94 | 1001.6248 | 855.16 | 146.4648 | 0.14623 | 86% | In Progress
0ducQKkW5EGQM9rQ5zdPrI | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:819816 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:819816 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 422.41 | 1140.6058 | 980.36 | 160.2458 | 0.14049 | 84% | In Progress
0ducQKkW5EGQM9rQ5zdPrq | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:819790 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:819790 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 375.78 | 1014.6939 | 793.82 | 220.8739 | 0.21768 | 85% | In Progress
0ducQKkW5EGQM9rQ5zdPrw | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:819776 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:819776 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 350.38 | 946.108 | 727.98 | 218.128 | 0.23055 | 81% | In Progress
0ducQKkW5EGQM9rQ5zdPqd | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:819741 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:819741 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 364.55 | 984.3703 | 770.81 | 213.5603 | 0.21695 | 79% | In Progress
0ducQKkW5EGQM9rQ5zdPwl | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:819605 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:819605 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 354.25 | 956.5579 | 711.19 | 245.3679 | 0.25651 | 80% | In Progress
0ducQKkW5EGQM9rQ5zdPvI | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:819560 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:819560 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 353.75 | 955.2078 | 719.24 | 235.9678 | 0.24703 | 79% | In Progress
0ducQKkW5EGQM9rQ5zdP$j | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:819415 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:819415 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 367.13 | 991.3369 | 795.15 | 196.1869 | 0.1979 | 82% | In Progress
0ducQKkW5EGQM9rQ5zdP$n | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:819403 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:819403 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 25.35 | 96.25 | 2439.9375 | 2474.06 | -34.1225 | -0.013985 | 100% | Completed
0ducQKkW5EGQM9rQ5zdPyj | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:819223 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:819223 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 395.92 | 1069.0766 | 825.86 | 243.2166 | 0.2275 | 77% | In Progress
0ducQKkW5EGQM9rQ5zdM3l | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:819157 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:819157 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 422.26 | 1140.2008 | 969.5 | 170.7008 | 0.14971 | 83% | In Progress
0ducQKkW5EGQM9rQ5zdM2q | IFCDOOR |  | M_Single-Flush:0762 x 2032mm:819086 | -1 - Garage |  | Finishes | Joinery / Metal | M_Single-Flush:0762 x 2032mm:819086 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 2.7002 | m² |  |  | 419.08 | 1131.6141 | 865.72 | 265.8941 | 0.23497 | 81% | In Progress
1KGNuJkf5FjQZDFQ6We96A | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Elavator:671215 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Elavator:671215 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.54 | 101.81 | 1887.5574 | 1845.74 | 41.8174 | 0.022154 | 100% | Completed
0ducQKkW5EGQM9rQ5zdPDs | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Storage Wall:822348 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Storage Wall:822348 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.06 | 92.48 | 1392.7488 | 1362.39 | 30.3588 | 0.021798 | 100% | Completed
0MOEoDTm9EnO9yKsXjjlj9 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Elavator:585626 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Elavator:585626 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 25.83 | 98.49 | 2543.9967 | 2481.34 | 62.6567 | 0.024629 | 100% | Completed
0MOEoDTm9EnO9yKsXjjlkV | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Elavator:585548 | -1 - Garage |  | Structure | Concrete / Masonry | Basic Wall:MockUp Elavator:585548 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15 | 101.03 | 1515.45 | 1511.25 | 4.2 | 0.0027715 | 100% | Completed
3bptS3GYj4Qv2__W5Ei$Tc | IFCBUILDINGELEMENTPROXY |  | Display-LCD-Panasonic-Standard:47, 1080p Full HD LCD w/ built-in speaker:654546 | 1 - First Floor |  | Not Assigned | Not Assigned | Display-LCD-Panasonic-Standard:47, 1080p Full HD LCD w/ built-in speaker:654546 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.065323 | m³ |  |  | 194.06 | 12.6766 | 8.03 | 4.6466 | 0.36655 | 62% | In Progress
0MgESf4zL2juYwctbhVsxF | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:575972 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:575972 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14 | 100.68 | 1409.52 | 1310.53 | 98.99 | 0.07023 | 93% | In Progress
0fjrUmmzDB4fngo1stt3Ty | IFCBUILDINGELEMENTPROXY |  | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:912449 | 1 - First Floor |  | Not Assigned | Not Assigned | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:912449 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.75803 | m³ |  |  | 177.22 | 134.3379 | 72.85 | 61.4879 | 0.45771 | 53% | In Progress
2SEl4sI2X1JhqYqQydYvln | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:973034 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:973034 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 291.28 | 291.28 | 144.96 | 146.32 | 0.50233 | 54% | In Progress
2SEl4sI2X1JhqYqQydYvlo | IFCFURNISHINGELEMENT |  | Inredning - Skrivbord:1600x800:973033 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Skrivbord:1600x800:973033 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 271.21 | 271.21 | 150.95 | 120.26 | 0.44342 | 59% | In Progress
2SEl4sI2X1JhqYqQydYvk$ | IFCFURNISHINGELEMENT |  | M_Entertainment center:1830 x 1830 x 0610mm:972964 | 1 - First Floor |  | Finishes | Furnishing | M_Entertainment center:1830 x 1830 x 0610mm:972964 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 281.98 | 281.98 | 158.41 | 123.57 | 0.43822 | 60% | In Progress
2SEl4sI2X1JhqYqQydYviP | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:972802 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:972802 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 177.62 | 0.0073046 | 0.01 | -0.0026954 | -0.36899 | 60% | In Progress
2SEl4sI2X1JhqYqQydYviQ | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:972801 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:972801 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 166.04 | 0.0068284 | 0.01 | -0.0031716 | -0.46447 | 60% | In Progress
2SEl4sI2X1JhqYqQydYviR | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:972800 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:972800 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 255.7 | 255.7 | 148.24 | 107.46 | 0.42026 | 58% | In Progress
2SEl4sI2X1JhqYqQydYvJT | IFCFURNISHINGELEMENT |  | M_Shelving:0915 x 0254 x 1830mm:972742 | 1 - First Floor |  | Finishes | Furnishing | M_Shelving:0915 x 0254 x 1830mm:972742 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 280.8 | 280.8 | 141.18 | 139.62 | 0.49722 | 54% | In Progress
2SEl4sI2X1JhqYqQydYv4D | IFCBUILDINGELEMENTPROXY |  | M_Hood-Island:1100mm:971286 | 1 - First Floor |  | Not Assigned | Not Assigned | M_Hood-Island:1100mm:971286 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.064043 | m³ |  |  | 184.92 | 11.8428 | 7.37 | 4.4728 | 0.37768 | 60% | In Progress
2SEl4sI2X1JhqYqQydYvFl | IFCFURNISHINGELEMENT |  | M_Counter Top:600mm Depth:970996 | 1 - First Floor |  | Finishes | Furnishing | M_Counter Top:600mm Depth:970996 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 269.8 | 269.8 | 157.27 | 112.53 | 0.41709 | 61% | In Progress
2SEl4sI2X1JhqYqQydYuq4 | IFCBUILDINGELEMENTPROXY |  | M_RPC Female:Florence:970271 | 1 - First Floor |  | Not Assigned | Not Assigned | M_RPC Female:Florence:970271 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.618 | 144.61 | 233.979 | 125.27 | 108.709 | 0.46461 | 55% | In Progress
2SEl4sI2X1JhqYqQydYuxc | IFCBUILDINGELEMENTPROXY |  | M_RPC Male:Jay:970237 | 1 - First Floor |  | Not Assigned | Not Assigned | M_RPC Male:Jay:970237 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.434 | 124.97 | 179.207 | 102.23 | 76.977 | 0.42954 | 58% | In Progress
3bptS3GYj4Qv2__W5Ei$UA | IFCBUILDINGELEMENTPROXY |  | Serena bench with three drawers:Serena bench with three drawers:654398 | 1 - First Floor |  | Not Assigned | Not Assigned | Serena bench with three drawers:Serena bench with three drawers:654398 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.037843 | m³ |  |  | 181.24 | 6.8587 | 4.07 | 2.7887 | 0.40659 | 59% | In Progress
3U8bdGexDEOw9DXBmULqba | IFCDOOR |  | M_Single-Flush:Generic Door:870639 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:870639 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 391.77 | 1249.5814 | 824.86 | 424.7214 | 0.33989 | 65% | In Progress
3U8bdGexDEOw9DXBmULqkr | IFCDOOR |  | M_Single-Flush:Generic Door:870974 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:870974 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 414.88 | 1323.2925 | 833.03 | 490.2625 | 0.37049 | 64% | In Progress
3U8bdGexDEOw9DXBmULr9k | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:873445 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:873445 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 13.88 | 97.5 | 1353.3 | 1266.71 | 86.59 | 0.063984 | 94% | In Progress
0MgESf4zL2juYwctbhVsl5 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:576750 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:576750 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.59 | 102.48 | 2007.5832 | 1852.6 | 154.9832 | 0.077199 | 90% | In Progress
0MOEoDTm9EnO9yKsXjjlOO | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:582347 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:582347 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 13.1 | 100.53 | 1316.943 | 1237.4 | 79.543 | 0.0604 | 92% | In Progress
0MOEoDTm9EnO9yKsXjjl4H | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:583106 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:583106 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.4 | 100.22 | 1443.168 | 1320.21 | 122.958 | 0.0852 | 89% | In Progress
0MOEoDTm9EnO9yKsXjjlBg | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:583225 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:583225 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.91 | 86.29 | 1372.8739 | 1177.88 | 194.9939 | 0.14203 | 93% | In Progress
2sG0Vcmgb1Uverjtj49Yum | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:589440 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:589440 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 111.31 | 111.31 | 61.09 | 50.22 | 0.45117 | 55% | In Progress
2sG0Vcmgb1Uverjtj49YxE | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:589438 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:589438 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 111.02 | 111.02 | 54.3 | 56.72 | 0.5109 | 50% | In Progress
2sG0Vcmgb1Uverjtj49YxC | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:589436 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:589436 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 132.49 | 132.49 | 61.36 | 71.13 | 0.53687 | 50% | In Progress
2sG0Vcmgb1Uverjtj49Yx6 | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:589430 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:589430 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 128.16 | 128.16 | 65.72 | 62.44 | 0.4872 | 50% | In Progress
2sG0Vcmgb1Uverjtj49Yx4 | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:589428 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:589428 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 125.22 | 125.22 | 73.23 | 51.99 | 0.41519 | 58% | In Progress
2sG0Vcmgb1Uverjtj49YxT | IFCFURNISHINGELEMENT |  | M_Table-Dining:0915 x 1830mm:589421 | 1 - First Floor |  | Finishes | Furnishing | M_Table-Dining:0915 x 1830mm:589421 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 549.54 | 549.54 | 309.61 | 239.93 | 0.4366 | 58% | In Progress
2sG0Vcmgb1Uverjtj49YtH | IFCDOOR |  | M_Single-Flush:Generic Door:589153 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:589153 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 367.56 | 1172.3617 | 693.85 | 478.5117 | 0.40816 | 61% | In Progress
2sG0Vcmgb1Uverjtj49YtX | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:589137 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:589137 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.4 | 100.58 | 1951.252 | 1750.58 | 200.672 | 0.10284 | 93% | In Progress
2sG0Vcmgb1Uverjtj49YsP | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:589097 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:589097 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 13.87 | 101.37 | 1406.0019 | 1212.91 | 193.0919 | 0.13733 | 84% | In Progress
3U8bdGexDEOw9DXBmULrMs | IFCDOOR |  | M_Single-Flush:Generic Door:873533 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:873533 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 348.06 | 1110.1649 | 717.94 | 392.2249 | 0.3533 | 69% | In Progress
2sG0Vcmgb1Uverjtj49YfG | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:588512 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:588512 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 10.9 | 95.78 | 1044.002 | 934.99 | 109.012 | 0.10442 | 90% | In Progress
0MOEoDTm9EnO9yKsXjjk5B | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:587160 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:587160 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 10.37 | 97.68 | 1012.9416 | 894.08 | 118.8616 | 0.11734 | 94% | In Progress
0MOEoDTm9EnO9yKsXjjk2Z | IFCDOOR |  | M_Single-Flush:Generic Door:586864 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:586864 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 377.98 | 1205.5971 | 713.44 | 492.1571 | 0.40823 | 60% | In Progress
0MOEoDTm9EnO9yKsXjjk26 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:586837 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:586837 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.21 | 100.9 | 1534.689 | 1377.72 | 156.969 | 0.10228 | 90% | In Progress
0MOEoDTm9EnO9yKsXjjk39 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:586778 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:586778 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.46 | 94.45 | 1554.647 | 1484.09 | 70.557 | 0.045385 | 94% | In Progress
0MOEoDTm9EnO9yKsXjjkTj | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:586686 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:586686 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.27 | 102.55 | 1463.3885 | 1254.65 | 208.7385 | 0.14264 | 87% | In Progress
0MOEoDTm9EnO9yKsXjjkUX | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:586610 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:586610 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.36 | 101.74 | 1867.9464 | 1712.64 | 155.3064 | 0.083143 | 90% | In Progress
0MOEoDTm9EnO9yKsXjjkL6 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:586133 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:586133 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.52 | 91.66 | 1789.2032 | 1496.19 | 293.0132 | 0.16377 | 88% | In Progress
0MOEoDTm9EnO9yKsXjjkME | IFCDOOR |  | M_Single-Flush:Generic Door:586077 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:586077 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 345.04 | 1100.5323 | 687.78 | 412.7523 | 0.37505 | 66% | In Progress
0MOEoDTm9EnO9yKsXjjkNr | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:586022 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:586022 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.96 | 100.29 | 1801.2084 | 1521.73 | 279.4784 | 0.15516 | 88% | In Progress
2sG0Vcmgb1Uverjtj49YTd | IFCDOOR |  | M_Single-Flush:Generic Door:587735 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:587735 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 385.88 | 1230.7947 | 765.74 | 465.0547 | 0.37785 | 61% | In Progress
3U8bdGexDEOw9DXBmULrIO | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:873747 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:873747 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 13.33 | 96.13 | 1281.4129 | 1054.67 | 226.7429 | 0.17695 | 84% | In Progress
3U8bdGexDEOw9DXBmULrUn | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Kitchen:874042 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Kitchen:874042 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 25.12 | 92.41 | 2321.3392 | 2340.4 | -19.0608 | -0.0082111 | 100% | Completed
2sG0Vcmgb1Uverjtj49Yuo | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:589442 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:589442 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 132.43 | 132.43 | 75.73 | 56.7 | 0.42815 | 58% | In Progress
0fjrUmmzDB4fngo1stt3Ub | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:912536 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:912536 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 185.42 | 0.0076254 | 0.01 | -0.0023746 | -0.3114 | 56% | In Progress
0qKJYWbnv5I8o6vyLfHi8K | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:893699 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:893699 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.3 | 94.61 | 1825.973 | 1500.46 | 325.513 | 0.17827 | 89% | In Progress
0qKJYWbnv5I8o6vyLfHiAM | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:893825 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:893825 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 12 | 93.64 | 1123.68 | 998.07 | 125.61 | 0.11178 | 88% | In Progress
0qKJYWbnv5I8o6vyLfHiAu | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:893871 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:893871 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.8 | 87.82 | 1651.016 | 1451.85 | 199.166 | 0.12063 | 90% | In Progress
0qKJYWbnv5I8o6vyLfHiO9 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:894750 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:894750 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.24 | 93.49 | 1518.2776 | 1397.66 | 120.6176 | 0.079444 | 94% | In Progress
0qKJYWbnv5I8o6vyLfHiOf | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:894782 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:894782 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 287.05 | 287.05 | 149.11 | 137.94 | 0.48054 | 54% | In Progress
0qKJYWbnv5I8o6vyLfHiOe | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:894783 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:894783 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 171.23 | 0.0070419 | 0.01 | -0.0029581 | -0.42008 | 54% | In Progress
0qKJYWbnv5I8o6vyLfHiPN | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:894784 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:894784 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 203.21 | 0.008357 | 0.01 | -0.001643 | -0.1966 | 53% | In Progress
0qKJYWbnv5I8o6vyLfHiPM | IFCBUILDINGELEMENTPROXY |  | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:894785 | 1 - First Floor |  | Not Assigned | Not Assigned | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:894785 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.75803 | m³ |  |  | 166.84 | 126.4695 | 76.77 | 49.6995 | 0.39298 | 60% | In Progress
0qKJYWbnv5I8o6vyLfHiPL | IFCBUILDINGELEMENTPROXY |  | Handtag kylfrys:Handtag kyl/frys:894786 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag kylfrys:Handtag kyl/frys:894786 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 2.5901e-05 | m³ |  |  | 202.23 | 0.005238 | 0.01 | -0.004762 | -0.90912 | 54% | In Progress
0qKJYWbnv5I8o6vyLfHiPJ | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Diskb\X2\00E4\X0\nk med sk\X2\00E5\X0\p:H14H:894788 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Diskb\X2\00E4\X0\nk med sk\X2\00E5\X0\p:H14H:894788 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 295.79 | 295.79 | 169.67 | 126.12 | 0.42638 | 56% | In Progress
0qKJYWbnv5I8o6vyLfHiPI | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:894789 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:894789 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 172.5 | 0.0070941 | 0.01 | -0.0029059 | -0.40963 | 60% | In Progress
0qKJYWbnv5I8o6vyLfHiPH | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:894790 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:894790 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 188.46 | 0.0077504 | 0.01 | -0.0022496 | -0.29025 | 52% | In Progress
0qKJYWbnv5I8o6vyLfHiPG | IFCFLOWTERMINAL |  | K\X2\00F6\X0\k - Diskmaskin 6m:Diskmaskin:894791 | 1 - First Floor |  | MEP | MEP | K\X2\00F6\X0\k - Diskmaskin 6m:Diskmaskin:894791 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 882.39 | 882.39 | 586.82 | 295.57 | 0.33497 | 71% | In Progress
0qKJYWbnv5I8o6vyLfHiPV | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Spish\X2\00E4\X0\ll:600 mm:894792 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Spish\X2\00E4\X0\ll:600 mm:894792 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 299.73 | 299.73 | 155.45 | 144.28 | 0.48137 | 53% | In Progress
0qKJYWbnv5I8o6vyLfHiPU | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - H\X2\00F6\X0\gsk\X2\00E5\X0\p:Ugn/Micro:894793 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - H\X2\00F6\X0\gsk\X2\00E5\X0\p:Ugn/Micro:894793 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 274.92 | 274.92 | 145.77 | 129.15 | 0.46977 | 52% | In Progress
0qKJYWbnv5I8o6vyLfHiPT | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:894794 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:894794 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 176.44 | 0.0072561 | 0.01 | -0.0027439 | -0.37815 | 61% | In Progress
0qKJYWbnv5I8o6vyLfHiQk | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:894905 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:894905 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 276.07 | 276.07 | 162.27 | 113.8 | 0.41221 | 58% | In Progress
0qKJYWbnv5I8o6vyLfHiQj | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:894906 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:894906 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 185.59 | 0.0076324 | 0.01 | -0.0023676 | -0.3102 | 52% | In Progress
0fjrUmmzDB4fngo1stt3Ua | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:912537 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:912537 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 161.46 | 0.0066401 | 0.01 | -0.0033599 | -0.50601 | 54% | In Progress
3U8bdGexDEOw9DXBmULrGs | IFCDOOR |  | M_Single-Flush:Generic Door:873917 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:873917 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 386.85 | 1233.8886 | 857.67 | 376.2186 | 0.3049 | 71% | In Progress
0fjrUmmzDB4fngo1stt3PN | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:912746 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:912746 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 258.2 | 258.2 | 149.73 | 108.47 | 0.4201 | 58% | In Progress
0HFJ4FEcn5UhECI1IyBAoJ | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:913001 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:913001 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 318.48 | 318.48 | 179.82 | 138.66 | 0.43538 | 57% | In Progress
3U8bdGexDEOw9DXBmULrR9 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Kitchen:874306 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Kitchen:874306 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.42 | 95.56 | 1569.0952 | 1463.33 | 105.7652 | 0.067405 | 94% | In Progress
3U8bdGexDEOw9DXBmULrPb | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:874478 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:874478 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 265.31 | 265.31 | 147.78 | 117.53 | 0.44299 | 57% | In Progress
3U8bdGexDEOw9DXBmULrPa | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:874479 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:874479 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 160.12 | 0.006585 | 0.01 | -0.003415 | -0.51861 | 55% | In Progress
3U8bdGexDEOw9DXBmULrPx | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:874480 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:874480 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 191.82 | 0.0078886 | 0.01 | -0.0021114 | -0.26765 | 53% | In Progress
3U8bdGexDEOw9DXBmULrX$ | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:874996 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:874996 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 287.63 | 287.63 | 144.21 | 143.42 | 0.49863 | 51% | In Progress
3U8bdGexDEOw9DXBmULrq8 | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:875651 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:875651 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 268.87 | 268.87 | 132.86 | 136.01 | 0.50586 | 53% | In Progress
3U8bdGexDEOw9DXBmULrqF | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:875652 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:875652 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 177.48 | 0.0072989 | 0 | 0.0072989 | 1 | 50% | In Progress
3U8bdGexDEOw9DXBmULrqE | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:875653 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:875653 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 206.92 | 0.0085096 | 0 | 0.0085096 | 1 | 54% | In Progress
3GzoWuxxn4WO8bCtw8H2m5 | IFCSPACE |  | 25 | 1 - First Floor | Area | (Info Only) | — | 25 | Room/zone. Not directly costed – use for rate build-up by space type | Custom_Pset | NetArea | 67.5439 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
3GzoWuxxn4WO8bCtw8H2nu | IFCSPACE |  | 24 | 1 - First Floor | 5ROK | (Info Only) | — | 24 | Room/zone. Not directly costed – use for rate build-up by space type | Custom_Pset | NetArea | 135.7537 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
3T2n8kPiTBtA2RCLGKorWP | IFCSPACE |  | 23 | 1 - First Floor | Area | (Info Only) | — | 23 | Room/zone. Not directly costed – use for rate build-up by space type | Custom_Pset | NetArea | 12.0533 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
3T2n8kPiTBtA2RCLGKoqPy | IFCSPACE |  | 20 | 1 - First Floor | 3ROK | (Info Only) | — | 20 | Room/zone. Not directly costed – use for rate build-up by space type | Custom_Pset | NetArea | 59.1362 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
3T2n8kPiTBtA2RCLGKoqPx | IFCSPACE |  | 21 | 1 - First Floor | 3ROK | (Info Only) | — | 21 | Room/zone. Not directly costed – use for rate build-up by space type | Custom_Pset | NetArea | 72.5496 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
3T2n8kPiTBtA2RCLGKoqPs | IFCSPACE |  | 22 | 1 - First Floor | 3ROK | (Info Only) | — | 22 | Room/zone. Not directly costed – use for rate build-up by space type | Custom_Pset | NetArea | 76.7944 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
2X_OhCV2r4iwXNvH5Dk$Fi | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:919957 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:919957 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 157.62 | 0.0064821 | 0.01 | -0.0035179 | -0.5427 | 53% | In Progress
2X_OhCV2r4iwXNvH5Dk$Fj | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:919956 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:919956 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 179.98 | 0.0074017 | 0 | 0.0074017 | 1 | 52% | In Progress
2X_OhCV2r4iwXNvH5Dk$Fg | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:919955 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:919955 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 296.47 | 296.47 | 164.93 | 131.54 | 0.44369 | 60% | In Progress
1gdfXOIAf8ZBJUgAp$8e1o | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:919551 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:919551 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 514.59 | 3886.2313 | 2632.68 | 1253.5513 | 0.32256 | 67% | In Progress
0HFJ4FEcn5UhECI1IyBBLe | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:915346 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:915346 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 493.1 | 2580.6335 | 1736.69 | 843.9435 | 0.32703 | 68% | In Progress
0fjrUmmzDB4fngo1stt3PM | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:912747 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:912747 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 261.55 | 261.55 | 129.56 | 131.99 | 0.50465 | 53% | In Progress
2sG0Vcmgb1Uverjtj49zLG | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:591328 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:591328 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.42 | 92.11 | 1420.3362 | 1317.99 | 102.3462 | 0.072058 | 92% | In Progress
2sG0Vcmgb1Uverjtj49zPp | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:591555 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:591555 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 11.57 | 97.51 | 1128.1907 | 1045.88 | 82.3107 | 0.072958 | 93% | In Progress
2sG0Vcmgb1Uverjtj49zPS | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:591596 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:591596 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.66 | 101.75 | 2000.405 | 1783.02 | 217.385 | 0.10867 | 87% | In Progress
3Icxn5iZD46RLnvfRjDRHb | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:731730 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:731730 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 196.62 | 0.008086 | 0.01 | -0.001914 | -0.2367 | 56% | In Progress
3Icxn5iZD46RLnvfRjDRHa | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:731731 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:731731 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 183.47 | 0.0075452 | 0.01 | -0.0024548 | -0.32534 | 61% | In Progress
3Icxn5iZD46RLnvfRjDR8d | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:732176 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:732176 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 289.17 | 289.17 | 145.76 | 143.41 | 0.49594 | 54% | In Progress
3Icxn5iZD46RLnvfRjDRA7 | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:732336 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:732336 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 318.43 | 318.43 | 173.9 | 144.53 | 0.45388 | 56% | In Progress
3Icxn5iZD46RLnvfRjDRA6 | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:732337 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:732337 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 259.94 | 259.94 | 133.52 | 126.42 | 0.48634 | 51% | In Progress
0Zs4aBjAr5AggJ3MVmSI39 | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:599256 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:599256 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 117.57 | 117.57 | 67.45 | 50.12 | 0.4263 | 57% | In Progress
0Zs4aBjAr5AggJ3MVmSI33 | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:599250 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:599250 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 134.47 | 134.47 | 82.45 | 52.02 | 0.38685 | 60% | In Progress
0Zs4aBjAr5AggJ3MVmSI31 | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:599248 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:599248 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 131.64 | 131.64 | 70.32 | 61.32 | 0.46582 | 55% | In Progress
0Zs4aBjAr5AggJ3MVmSI3O | IFCFURNISHINGELEMENT |  | M_Table-Dining:0915 x 1830mm:599241 | 1 - First Floor |  | Finishes | Furnishing | M_Table-Dining:0915 x 1830mm:599241 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 564.55 | 564.55 | 279.66 | 284.89 | 0.50463 | 52% | In Progress
3NlCHdPGXFUvkKekQzm3FC | IFCSLAB | FLOOR | Floor:Concrete-Domestic 425mm:982159 | 1 - First Floor |  | Structure | Concrete | Floor:Concrete-Domestic 425mm:982159 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 818.8261 | m² |  |  | 88.09 | 72130.3945 | 62517.56 | 9612.8345 | 0.13327 | 92% | In Progress
2elCQiqUf77O30JxVoEUXt | IFCFURNISHINGELEMENT |  | Inredning - Dubbels\X2\00E4\X0\ng:1800:787024 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Dubbels\X2\00E4\X0\ng:1800:787024 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 291.81 | 291.81 | 164.4 | 127.41 | 0.43662 | 57% | In Progress
2elCQiqUf77O30JxVoEUu4 | IFCFURNISHINGELEMENT |  | Furniture-Wieland_Healthcare-Rally-Compose-Sofa:64343HC:787491 | 1 - First Floor |  | Finishes | Furnishing | Furniture-Wieland_Healthcare-Rally-Compose-Sofa:64343HC:787491 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 949.44 | 949.44 | 482.81 | 466.63 | 0.49148 | 53% | In Progress
1KMtYLyv9CyfGv8UjnMBSF | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior:793580 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior:793580 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 36.98 | 101.79 | 3764.1942 | 3412.15 | 352.0442 | 0.093524 | 90% | In Progress
1KMtYLyv9CyfGv8UjnMBSE | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior:793581 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior:793581 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 33.52 | 93.14 | 3122.0528 | 2837.67 | 284.3828 | 0.091088 | 88% | In Progress
1KMtYLyv9CyfGv8UjnMBSD | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior:793582 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior:793582 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 31.78 | 85.86 | 2728.6308 | 2246.83 | 481.8008 | 0.17657 | 86% | In Progress
1KMtYLyv9CyfGv8UjnMBSC | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior:793583 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior:793583 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 35.44 | 99.49 | 3525.9256 | 3208.15 | 317.7756 | 0.090125 | 89% | In Progress
1KMtYLyv9CyfGv8UjnMBSJ | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior:793584 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior:793584 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 32.22 | 97.2 | 3131.784 | 2812.29 | 319.494 | 0.10202 | 89% | In Progress
1KMtYLyv9CyfGv8UjnMBSI | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior:793585 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior:793585 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 27.82 | 94.63 | 2632.6066 | 2507.47 | 125.1366 | 0.047533 | 93% | In Progress
1KMtYLyv9CyfGv8UjnMBSH | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior:793586 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior:793586 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 28.74 | 93.53 | 2688.0522 | 2324.2 | 363.8522 | 0.13536 | 89% | In Progress
3Icxn5iZD46RLnvfRjDRHc | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:731729 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:731729 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 255.53 | 255.53 | 137.18 | 118.35 | 0.46316 | 53% | In Progress
1KMtYLyv9CyfGv8UjnMBSG | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior:793587 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior:793587 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.79 | 90.49 | 2152.7571 | 1839.25 | 313.5071 | 0.14563 | 90% | In Progress
3Icxn5iZD46RLnvfRjDRGg | IFCDOOR |  | M_Single-Flush:Generic Door:731677 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:731677 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 394.16 | 1257.2045 | 739.28 | 517.9245 | 0.41197 | 60% | In Progress
3Icxn5iZD46RLnvfRjDRUz | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:731530 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:731530 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 13.56 | 95.21 | 1291.0476 | 1328.44 | -37.3924 | -0.028963 | 100% | Completed
2v8sGyGFXDsRc80mj95i21 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:729237 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:729237 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 187.6 | 0.0077151 | 0.01 | -0.0022849 | -0.29616 | 62% | In Progress
2v8sGyGFXDsRc80mj95i22 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:729238 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:729238 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 172.77 | 0.0071052 | 0.01 | -0.0028948 | -0.40742 | 53% | In Progress
2v8sGyGFXDsRc80mj95i4v | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:729389 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:729389 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 10.85 | 95.3 | 1034.005 | 883.67 | 150.335 | 0.14539 | 86% | In Progress
2v8sGyGFXDsRc80mj95i76 | IFCDOOR |  | M_Single-Flush:Generic Door:729554 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:729554 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 391.55 | 1248.8797 | 792.61 | 456.2697 | 0.36534 | 62% | In Progress
2v8sGyGFXDsRc80mj95i8j | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p:500 mm:729657 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p:500 mm:729657 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 280.18 | 280.18 | 143.06 | 137.12 | 0.4894 | 55% | In Progress
2v8sGyGFXDsRc80mj95i8k | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:729658 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:729658 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 179.48 | 0.0073811 | 0.01 | -0.0026189 | -0.35481 | 53% | In Progress
2v8sGyGFXDsRc80mj95i9$ | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Kitchen:729707 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Kitchen:729707 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 25.18 | 97.01 | 2442.7118 | 2200.48 | 242.2318 | 0.099165 | 88% | In Progress
2v8sGyGFXDsRc80mj95iBv | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:729837 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:729837 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 272.6 | 272.6 | 141.3 | 131.3 | 0.48166 | 55% | In Progress
2v8sGyGFXDsRc80mj95iGA | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:730142 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:730142 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.63 | 89.33 | 1664.2179 | 1384.81 | 279.4079 | 0.16789 | 88% | In Progress
2v8sGyGFXDsRc80mj95iGb | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:730161 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:730161 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 273.34 | 273.34 | 158.64 | 114.7 | 0.41962 | 56% | In Progress
2v8sGyGFXDsRc80mj95iGc | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:730162 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:730162 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 165.82 | 0.0068194 | 0.01 | -0.0031806 | -0.46641 | 55% | In Progress
2v8sGyGFXDsRc80mj95iGd | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:730163 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:730163 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 176.82 | 0.0072717 | 0.01 | -0.0027283 | -0.37519 | 54% | In Progress
2v8sGyGFXDsRc80mj95iGW | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:730164 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:730164 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 320.15 | 320.15 | 172.1 | 148.05 | 0.46244 | 56% | In Progress
2v8sGyGFXDsRc80mj95iGX | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:730165 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:730165 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 166.4 | 0.0068432 | 0.01 | -0.0031568 | -0.4613 | 53% | In Progress
2v8sGyGFXDsRc80mj95iGY | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:730166 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:730166 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 186.6 | 0.0076739 | 0.01 | -0.0023261 | -0.30311 | 62% | In Progress
2v8sGyGFXDsRc80mj95iIB | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:730271 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:730271 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 274.34 | 274.34 | 148.64 | 125.7 | 0.45819 | 53% | In Progress
2v8sGyGFXDsRc80mj95iIq | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:730272 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:730272 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 159.55 | 0.0065615 | 0.01 | -0.0034385 | -0.52404 | 59% | In Progress
2v8sGyGFXDsRc80mj95iIr | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:730273 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:730273 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 160.58 | 0.0066039 | 0.01 | -0.0033961 | -0.51426 | 56% | In Progress
2v8sGyGFXDsRc80mj95iJz | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:730345 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:730345 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 318.71 | 318.71 | 155.6 | 163.11 | 0.51178 | 49% | In Progress
3Icxn5iZD46RLnvfRjDRU9 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:731582 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:731582 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.93 | 90.77 | 1355.1961 | 1090.32 | 264.8761 | 0.19545 | 87% | In Progress
1KMtYLyv9CyfGv8UjnMBSN | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:793588 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:793588 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 533.44 | 5265.4239 | 3512.29 | 1753.1339 | 0.33295 | 69% | In Progress
1KMtYLyv9CyfGv8UjnMBSM | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:793589 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:793589 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 571.08 | 5636.9569 | 3923.89 | 1713.0669 | 0.3039 | 71% | In Progress
1KMtYLyv9CyfGv8UjnMBSL | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:793590 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:793590 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 525.28 | 2749.0472 | 1775.56 | 973.4872 | 0.35412 | 68% | In Progress
1KMtYLyv9CyfGv8UjnMB32 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M BATHROOM:793633 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M BATHROOM:793633 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 2.4454 | m² |  |  | 549.17 | 1342.9207 | 1005.16 | 337.7607 | 0.25151 | 72% | In Progress
0Zs4aBjAr5AggJ3MVmSI0z | IFCFURNISHINGELEMENT |  | M_Bed-Standard:0965 x 1905mm - Twin:599084 | 1 - First Floor |  | Finishes | Furnishing | M_Bed-Standard:0965 x 1905mm - Twin:599084 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 1390.99 | 1390.99 | 701.36 | 689.63 | 0.49578 | 50% | In Progress
0Zs4aBjAr5AggJ3MVmSISH | IFCDOOR |  | M_Single-Flush:Generic Door:598784 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:598784 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 366.93 | 1170.3522 | 756.24 | 414.1122 | 0.35384 | 68% | In Progress
0Zs4aBjAr5AggJ3MVmSIRv | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:598760 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:598760 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.07 | 87.34 | 1665.5738 | 1468.67 | 196.9038 | 0.11822 | 94% | In Progress
0Zs4aBjAr5AggJ3MVmSIQu | IFCDOOR |  | M_Single-Flush:Generic Door:598697 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:598697 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 395.63 | 1261.8931 | 758.23 | 503.6631 | 0.39913 | 59% | In Progress
0Zs4aBjAr5AggJ3MVmSII4 | IFCFLOWTERMINAL |  | M_Lavatory - Vanity:760 mmx455 mm - Private:598165 | 1 - First Floor |  | MEP | MEP | M_Lavatory - Vanity:760 mmx455 mm - Private:598165 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 870.38 | 870.38 | 587.16 | 283.22 | 0.3254 | 73% | In Progress
0Zs4aBjAr5AggJ3MVmSII5 | IFCFLOWTERMINAL |  | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:598164 | 1 - First Floor |  | MEP | MEP | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:598164 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 877.99 | 877.99 | 568.6 | 309.39 | 0.35238 | 67% | In Progress
0Zs4aBjAr5AggJ3MVmSIIU | IFCFLOWTERMINAL |  | M_Shower Stall with Seat - Rectangular:1220 mmx915 mm - Private:598159 | 1 - First Floor |  | MEP | MEP | M_Shower Stall with Seat - Rectangular:1220 mmx915 mm - Private:598159 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 912.79 | 912.79 | 622.17 | 290.62 | 0.31839 | 67% | In Progress
0Zs4aBjAr5AggJ3MVmSIHS | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:598093 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:598093 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.92 | 90.21 | 1526.3532 | 1422.19 | 104.1632 | 0.068243 | 93% | In Progress
0Zs4aBjAr5AggJ3MVmSHkB | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:597914 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:597914 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.59 | 95.51 | 1489.0009 | 1245.13 | 243.8709 | 0.16378 | 86% | In Progress
3DRhHSTRP15ukUYu1G74a9 | IFCFLOWTERMINAL |  | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:596032 | 1 - First Floor |  | MEP | MEP | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:596032 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 940.24 | 940.24 | 660.49 | 279.75 | 0.29753 | 69% | In Progress
3DRhHSTRP15ukUYu1G74bs | IFCFLOWTERMINAL |  | M_Lavatory - Vanity:760 mmx455 mm - Private:596031 | 1 - First Floor |  | MEP | MEP | M_Lavatory - Vanity:760 mmx455 mm - Private:596031 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 957.12 | 957.12 | 593.06 | 364.06 | 0.38037 | 64% | In Progress
3DRhHSTRP15ukUYu1G74Jn | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:595384 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:595384 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 10.07 | 99.49 | 1001.8643 | 1009.84 | -7.9757 | -0.0079609 | 100% | Completed
2sG0Vcmgb1Uverjtj49zir | IFCFLOWTERMINAL |  | M_Shower Stall with Seat - Rectangular:1220 mmx915 mm - Private:592773 | 1 - First Floor |  | MEP | MEP | M_Shower Stall with Seat - Rectangular:1220 mmx915 mm - Private:592773 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 848.61 | 848.61 | 533.34 | 315.27 | 0.37151 | 66% | In Progress
2sG0Vcmgb1Uverjtj49zb3 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:592371 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:592371 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.71 | 98.45 | 1546.6495 | 1373.77 | 172.8795 | 0.11178 | 95% | In Progress
2sG0Vcmgb1Uverjtj49za9 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:592313 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:592313 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 13.38 | 95.17 | 1273.3746 | 1245.82 | 27.5546 | 0.021639 | 100% | Completed
2sG0Vcmgb1Uverjtj49zdx | IFCDOOR |  | M_Single-Flush:Generic Door:592203 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:592203 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 371.26 | 1184.1631 | 787.35 | 396.8131 | 0.3351 | 66% | In Progress
2sG0Vcmgb1Uverjtj49zXt | IFCDOOR |  | M_Single-Flush:Generic Door:592071 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:592071 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 363.71 | 1160.0818 | 690.3 | 469.7818 | 0.40496 | 62% | In Progress
2sG0Vcmgb1Uverjtj49zSM | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:591782 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:591782 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.75 | 88.47 | 1570.3425 | 1292.33 | 278.0125 | 0.17704 | 88% | In Progress
1KMtYLyv9CyfGv8UjnMB33 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:793632 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:793632 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 571.22 | 2989.4737 | 1996.8 | 992.6737 | 0.33206 | 68% | In Progress
1KMtYLyv9CyfGv8UjnMB3$ | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:793628 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:793628 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 548.07 | 2868.3184 | 1775.07 | 1093.2484 | 0.38115 | 66% | In Progress
1KMtYLyv9CyfGv8UjnMB3u | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:793627 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:793627 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 481.65 | 2520.7101 | 1433.04 | 1087.6701 | 0.43149 | 61% | In Progress
1KMtYLyv9CyfGv8UjnMB3v | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:793626 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:793626 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 555.92 | 4198.3592 | 2914.02 | 1284.3392 | 0.30591 | 70% | In Progress
1KMtYLyv9CyfGv8UjnMBSK | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:793591 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:793591 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 485.96 | 3670.0148 | 2300.08 | 1369.9348 | 0.37328 | 66% | In Progress
1KMtYLyv9CyfGv8UjnMBSR | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:793592 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:793592 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 505.93 | 3820.8301 | 2310.31 | 1510.5201 | 0.39534 | 61% | In Progress
1KMtYLyv9CyfGv8UjnMBSQ | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:793593 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:793593 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 507.94 | 5013.7212 | 2867.29 | 2146.4312 | 0.42811 | 62% | In Progress
1KMtYLyv9CyfGv8UjnMBSP | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:793594 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:793594 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 543.56 | 4105.0154 | 2714.98 | 1390.0354 | 0.33862 | 71% | In Progress
1KMtYLyv9CyfGv8UjnMBSO | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:793595 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:793595 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 536.69 | 2808.7613 | 1819.29 | 989.4713 | 0.35228 | 70% | In Progress
1KMtYLyv9CyfGv8UjnMBSV | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:793596 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:793596 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 547.51 | 4134.8461 | 2673.56 | 1461.2861 | 0.35341 | 68% | In Progress
1KMtYLyv9CyfGv8UjnMBSU | IFCWINDOW |  | BALANS Fixed Single Window:BALANS TRAPPHUS:793597 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS TRAPPHUS:793597 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 24.9655 | m² |  |  | 565.15 | 14109.2798 | 8956.19 | 5153.0898 | 0.36523 | 63% | In Progress
1KMtYLyv9CyfGv8UjnMBST | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:793598 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:793598 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 550.98 | 4161.0519 | 2568.44 | 1592.6119 | 0.38274 | 67% | In Progress
1KMtYLyv9CyfGv8UjnMB3Z | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:793600 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:793600 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 504.29 | 2639.1963 | 1554.89 | 1084.3063 | 0.41085 | 60% | In Progress
0qKJYWbnv5I8o6vyLfHiQi | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:894907 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:894907 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 163.83 | 0.0067375 | 0 | 0.0067375 | 1 | 52% | In Progress
1KMtYLyv9CyfGv8UjnMB3Y | IFCWINDOW |  | BALANS Fixed Single Window:BALANS TRAPPHUS:793601 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS TRAPPHUS:793601 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 24.9655 | m² |  |  | 530.83 | 13252.4622 | 9280.34 | 3972.1222 | 0.29973 | 70% | In Progress
1KMtYLyv9CyfGv8UjnMB3d | IFCWINDOW |  | BALANS Fixed Single Window:BALANS TRAPPHUS:793604 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS TRAPPHUS:793604 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 24.9655 | m² |  |  | 536.34 | 13390.0224 | 9506.7 | 3883.3224 | 0.29002 | 69% | In Progress
1KMtYLyv9CyfGv8UjnMB3b | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:793606 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:793606 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 480.31 | 3627.3455 | 2430.66 | 1196.6855 | 0.32991 | 67% | In Progress
1KMtYLyv9CyfGv8UjnMB3e | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:793611 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:793611 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 532.86 | 4024.208 | 2843.79 | 1180.418 | 0.29333 | 70% | In Progress
1KMtYLyv9CyfGv8UjnMB3i | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:793615 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:793615 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 492.33 | 3718.1217 | 2349.73 | 1368.3917 | 0.36803 | 68% | In Progress
1KMtYLyv9CyfGv8UjnMB3p | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:793616 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:793616 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 554.63 | 5474.584 | 3530.58 | 1944.004 | 0.3551 | 63% | In Progress
1KMtYLyv9CyfGv8UjnMB3o | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M BATHROOM:793617 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M BATHROOM:793617 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 2.4454 | m² |  |  | 568.99 | 1391.3879 | 845.45 | 545.9379 | 0.39237 | 60% | In Progress
1KMtYLyv9CyfGv8UjnMB3n | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:793618 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:793618 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 513.45 | 2687.135 | 1522.31 | 1164.825 | 0.43348 | 61% | In Progress
1KMtYLyv9CyfGv8UjnMB3m | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:793619 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:793619 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 557.45 | 4209.9139 | 2901.43 | 1308.4839 | 0.31081 | 70% | In Progress
1KMtYLyv9CyfGv8UjnMB3x | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:793624 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:793624 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 548.2 | 5411.1154 | 3726.77 | 1684.3454 | 0.31128 | 71% | In Progress
1KMtYLyv9CyfGv8UjnMB3X | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:793602 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:793602 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 491.33 | 4849.7689 | 2980.78 | 1868.9889 | 0.38538 | 62% | In Progress
2v8sGyGFXDsRc80mj95i20 | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:729236 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:729236 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 315.4 | 315.4 | 191.35 | 124.05 | 0.39331 | 59% | In Progress
0qKJYWbnv5I8o6vyLfHiZW | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:895479 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:895479 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.03 | 97.44 | 1854.2832 | 1606.46 | 247.8232 | 0.13365 | 85% | In Progress
0qKJYWbnv5I8o6vyLfHipI | IFCFURNISHINGELEMENT |  | Inredning - Enkels\X2\00E4\X0\ng:900:896453 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Enkels\X2\00E4\X0\ng:900:896453 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 267.1 | 267.1 | 134 | 133.1 | 0.49832 | 49% | In Progress
3XuKtrI0jD5PlAb3LVW6Hv | IFCFLOWTERMINAL |  | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:905751 | 1 - First Floor |  | MEP | MEP | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:905751 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 860.59 | 860.59 | 606.81 | 253.78 | 0.29489 | 68% | In Progress
0pHBx4qSPCfPLZRKuUIKTa | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:906450 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:906450 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 516.5 | 2703.0972 | 1856.94 | 846.1572 | 0.31303 | 72% | In Progress
0pHBx4qSPCfPLZRKuUIKQ9 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:906559 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:906559 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 500.61 | 3780.653 | 2397.95 | 1382.703 | 0.36573 | 68% | In Progress
0pHBx4qSPCfPLZRKuUIKRO | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:906606 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:906606 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 520.73 | 2725.2348 | 1806.43 | 918.8048 | 0.33715 | 70% | In Progress
0pHBx4qSPCfPLZRKuUIKOJ | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:906661 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:906661 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 498.54 | 3765.0202 | 2302.68 | 1462.3402 | 0.3884 | 66% | In Progress
0pHBx4qSPCfPLZRKuUIKPy | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:906698 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:906698 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 551.69 | 5445.5641 | 3397.29 | 2048.2741 | 0.37614 | 60% | In Progress
0pHBx4qSPCfPLZRKuUIKNz | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:906827 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:906827 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 487.51 | 2551.3783 | 1617.6 | 933.7783 | 0.36599 | 61% | In Progress
0pHBx4qSPCfPLZRKuUIKG1 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:907191 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:907191 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 507.48 | 2655.8911 | 1666.36 | 989.5311 | 0.37258 | 68% | In Progress
0pHBx4qSPCfPLZRKuUIKhq | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M BATHROOM:907586 | 1 - First Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M BATHROOM:907586 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 2.4454 | m² |  |  | 497.89 | 1217.5224 | 743.29 | 474.2324 | 0.38951 | 63% | In Progress
0fjrUmmzDB4fngo1stt0Lp | IFCBUILDINGELEMENTPROXY |  | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:908878 | 1 - First Floor |  | Not Assigned | Not Assigned | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:908878 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.75803 | m³ |  |  | 170.17 | 128.9938 | 72.23 | 56.7638 | 0.44005 | 55% | In Progress
0fjrUmmzDB4fngo1stt0Lo | IFCBUILDINGELEMENTPROXY |  | Handtag kylfrys:Handtag kyl/frys:908879 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag kylfrys:Handtag kyl/frys:908879 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 2.5901e-05 | m³ |  |  | 159.18 | 0.004123 | 0 | 0.004123 | 1 | 61% | In Progress
0fjrUmmzDB4fngo1stt0Lj | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Vinkel:K\X2\00F6\X0\k vinkel:908880 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Vinkel:K\X2\00F6\X0\k vinkel:908880 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 305.8 | 305.8 | 193.38 | 112.42 | 0.36763 | 61% | In Progress
0fjrUmmzDB4fngo1stt0Li | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Diskb\X2\00E4\X0\nk med sk\X2\00E5\X0\p:H14H:908881 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Diskb\X2\00E4\X0\nk med sk\X2\00E5\X0\p:H14H:908881 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 267.65 | 267.65 | 154.32 | 113.33 | 0.42343 | 56% | In Progress
0fjrUmmzDB4fngo1stt0Ll | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:908882 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:908882 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 174.53 | 0.0071776 | 0.01 | -0.0028224 | -0.39323 | 60% | In Progress
0fjrUmmzDB4fngo1stt0Lk | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:908883 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:908883 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 171.91 | 0.0070698 | 0.01 | -0.0029302 | -0.41446 | 53% | In Progress
0fjrUmmzDB4fngo1stt0Lf | IFCFLOWTERMINAL |  | K\X2\00F6\X0\k - Diskmaskin 6m:Diskmaskin:908884 | 1 - First Floor |  | MEP | MEP | K\X2\00F6\X0\k - Diskmaskin 6m:Diskmaskin:908884 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 989.75 | 989.75 | 687.01 | 302.74 | 0.30588 | 70% | In Progress
0fjrUmmzDB4fngo1stt0Le | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - H\X2\00F6\X0\gsk\X2\00E5\X0\p:Ugn/Micro:908885 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - H\X2\00F6\X0\gsk\X2\00E5\X0\p:Ugn/Micro:908885 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 272.33 | 272.33 | 144.34 | 127.99 | 0.46998 | 53% | In Progress
0fjrUmmzDB4fngo1stt0Lh | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:908886 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:908886 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 174.12 | 0.0071607 | 0.01 | -0.0028393 | -0.39651 | 62% | In Progress
0fjrUmmzDB4fngo1stt0Lg | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:908887 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:908887 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 312.37 | 312.37 | 171.88 | 140.49 | 0.44976 | 54% | In Progress
3XuKtrI0jD5PlAb3LVW6Sm | IFCDOOR |  | M_Single-Flush:Generic Door:905566 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:905566 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 423.51 | 1350.8186 | 935.95 | 414.8686 | 0.30712 | 70% | In Progress
0fjrUmmzDB4fngo1stt0Lb | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:908888 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:908888 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 170.34 | 0.0070053 | 0.01 | -0.0029947 | -0.4275 | 54% | In Progress
3XuKtrI0jD5PlAb3LVW6T0 | IFCFLOWTERMINAL |  | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:905518 | 1 - First Floor |  | MEP | MEP | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:905518 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 955.04 | 955.04 | 632.15 | 322.89 | 0.33809 | 64% | In Progress
2IzmleSW1Dlx86K0hfkLkU | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:905060 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:905060 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 266.93 | 266.93 | 129.79 | 137.14 | 0.51377 | 50% | In Progress
0qdpkovdH5RgxJU7gsxr5T | IFCFURNISHINGELEMENT |  | M_Base Cabinet-Double Door & 2 Drawer:600mm:903898 | 1 - First Floor |  | Finishes | Furnishing | M_Base Cabinet-Double Door & 2 Drawer:600mm:903898 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 702.26 | 702.26 | 355.54 | 346.72 | 0.49372 | 50% | In Progress
0qdpkovdH5RgxJU7gsxr5v | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:903934 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:903934 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 318.93 | 318.93 | 152.87 | 166.06 | 0.52068 | 50% | In Progress
0qdpkovdH5RgxJU7gsxr5u | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:903935 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:903935 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 179.63 | 0.0073873 | 0.01 | -0.0026127 | -0.35367 | 59% | In Progress
0qdpkovdH5RgxJU7gsxr27 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:903936 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:903936 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 202.35 | 0.0083217 | 0.01 | -0.0016783 | -0.20168 | 51% | In Progress
0qdpkovdH5RgxJU7gsxr26 | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:903937 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:903937 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 265.57 | 265.57 | 156.43 | 109.14 | 0.41097 | 57% | In Progress
0qdpkovdH5RgxJU7gsxr25 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:903938 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:903938 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 177.15 | 0.0072853 | 0.01 | -0.0027147 | -0.37262 | 54% | In Progress
0qdpkovdH5RgxJU7gsxr24 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:903939 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:903939 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 189.11 | 0.0077772 | 0.01 | -0.0022228 | -0.28582 | 62% | In Progress
0qdpkovdH5RgxJU7gsxr23 | IFCFURNISHINGELEMENT |  | Inredning - Skrivbord:1600x800:903940 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Skrivbord:1600x800:903940 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 294.9 | 294.9 | 174.78 | 120.12 | 0.40732 | 57% | In Progress
0qdpkovdH5RgxJU7gsxr22 | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:903941 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:903941 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 268.02 | 268.02 | 149.97 | 118.05 | 0.44045 | 55% | In Progress
2IzmleSW1Dlx86K0hfkL$P | IFCFURNISHINGELEMENT |  | fixa_bench:Colour - (Light grey-S2000-N):903971 | 1 - First Floor |  | Finishes | Furnishing | fixa_bench:Colour - (Light grey-S2000-N):903971 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 296.67 | 296.67 | 157.44 | 139.23 | 0.46931 | 52% | In Progress
2IzmleSW1Dlx86K0hfkLXl | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:904341 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:904341 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 271.04 | 271.04 | 159.28 | 111.76 | 0.41234 | 61% | In Progress
2IzmleSW1Dlx86K0hfkLXi | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:904342 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:904342 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 186.55 | 0.0076719 | 0 | 0.0076719 | 1 | 51% | In Progress
2IzmleSW1Dlx86K0hfkLXj | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:904343 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:904343 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 183.04 | 0.0075275 | 0.01 | -0.0024725 | -0.32846 | 55% | In Progress
2IzmleSW1Dlx86K0hfkLgD | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p:500 mm:904823 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p:500 mm:904823 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 261.23 | 261.23 | 134.11 | 127.12 | 0.48662 | 51% | In Progress
2IzmleSW1Dlx86K0hfkLg2 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:904824 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:904824 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 171.99 | 0.0070731 | 0.01 | -0.0029269 | -0.41381 | 53% | In Progress
2IzmleSW1Dlx86K0hfkLfI | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p:500 mm:904872 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p:500 mm:904872 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 286.56 | 286.56 | 166.59 | 119.97 | 0.41866 | 60% | In Progress
2IzmleSW1Dlx86K0hfkLfJ | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:904873 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:904873 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 160.15 | 0.0065862 | 0.01 | -0.0034138 | -0.51833 | 57% | In Progress
2IzmleSW1Dlx86K0hfkLev | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p:500 mm:904899 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p:500 mm:904899 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 288.21 | 288.21 | 168.66 | 119.55 | 0.4148 | 59% | In Progress
2IzmleSW1Dlx86K0hfkLe_ | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:904900 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:904900 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 201.58 | 0.00829 | 0.01 | -0.00171 | -0.20627 | 51% | In Progress
3XuKtrI0jD5PlAb3LVW6T3 | IFCFLOWTERMINAL |  | M_Lavatory - Vanity:760 mmx455 mm - Private:905517 | 1 - First Floor |  | MEP | MEP | M_Lavatory - Vanity:760 mmx455 mm - Private:905517 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 941.71 | 941.71 | 638.55 | 303.16 | 0.32193 | 66% | In Progress
0fjrUmmzDB4fngo1stt0La | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:908889 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:908889 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 183.68 | 0.0075539 | 0 | 0.0075539 | 1 | 51% | In Progress
0fjrUmmzDB4fngo1stt0Ld | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:908890 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:908890 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 263.62 | 263.62 | 137.14 | 126.48 | 0.47978 | 54% | In Progress
0fjrUmmzDB4fngo1stt0Lc | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:908891 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:908891 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 166.35 | 0.0068412 | 0.01 | -0.0031588 | -0.46174 | 57% | In Progress
0fjrUmmzDB4fngo1stt3qX | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:910876 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:910876 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 304.83 | 304.83 | 144.94 | 159.89 | 0.52452 | 50% | In Progress
0fjrUmmzDB4fngo1stt3q0 | IFCFURNISHINGELEMENT |  | Inredning - Skrivbord:1600x800:910909 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Skrivbord:1600x800:910909 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 280.01 | 280.01 | 152.26 | 127.75 | 0.45623 | 54% | In Progress
0fjrUmmzDB4fngo1stt3q3 | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:910910 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:910910 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 293.21 | 293.21 | 146.1 | 147.11 | 0.50172 | 53% | In Progress
0fjrUmmzDB4fngo1stt3q2 | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:910911 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:910911 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 273.47 | 273.47 | 138.28 | 135.19 | 0.49435 | 53% | In Progress
0fjrUmmzDB4fngo1stt3rz | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:910912 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:910912 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 176.13 | 0.0072434 | 0.01 | -0.0027566 | -0.38057 | 59% | In Progress
0fjrUmmzDB4fngo1stt3ry | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:910913 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:910913 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 173.27 | 0.0071257 | 0.01 | -0.0028743 | -0.40336 | 62% | In Progress
0fjrUmmzDB4fngo1stt3Fj | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p:500 mm:911568 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p:500 mm:911568 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 265.3 | 265.3 | 146.62 | 118.68 | 0.44734 | 55% | In Progress
0fjrUmmzDB4fngo1stt3Fi | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:911569 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:911569 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 176.91 | 0.0072754 | 0.01 | -0.0027246 | -0.37449 | 60% | In Progress
0fjrUmmzDB4fngo1stt3FQ | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p:600 mm:911591 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p:600 mm:911591 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 285.94 | 285.94 | 133.11 | 152.83 | 0.53448 | 50% | In Progress
0fjrUmmzDB4fngo1stt3FL | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:911592 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:911592 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 166.94 | 0.0068654 | 0.01 | -0.0031346 | -0.45657 | 56% | In Progress
0fjrUmmzDB4fngo1stt38$ | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p:500 mm:911618 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p:500 mm:911618 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 279.86 | 279.86 | 157.79 | 122.07 | 0.43618 | 60% | In Progress
0fjrUmmzDB4fngo1stt38_ | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:911619 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:911619 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 199.34 | 0.0081979 | 0 | 0.0081979 | 1 | 51% | In Progress
0fjrUmmzDB4fngo1stt38O | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Kitchen:911653 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Kitchen:911653 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 20.51 | 97.49 | 1999.5199 | 1649.67 | 349.8499 | 0.17497 | 89% | In Progress
0fjrUmmzDB4fngo1stt390 | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:911741 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:911741 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 279.89 | 279.89 | 139.07 | 140.82 | 0.50313 | 51% | In Progress
0fjrUmmzDB4fngo1stt393 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:911742 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:911742 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 155.72 | 0.006404 | 0.01 | -0.003596 | -0.56152 | 61% | In Progress
0fjrUmmzDB4fngo1stt392 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:911743 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:911743 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 160.51 | 0.006601 | 0.01 | -0.003399 | -0.51492 | 61% | In Progress
0fjrUmmzDB4fngo1stt3AF | IFCBUILDINGELEMENTPROXY |  | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:911794 | 1 - First Floor |  | Not Assigned | Not Assigned | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:911794 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.75803 | m³ |  |  | 160.1 | 121.3604 | 74.58 | 46.7804 | 0.38547 | 60% | In Progress
0fjrUmmzDB4fngo1stt3AE | IFCBUILDINGELEMENTPROXY |  | Handtag kylfrys:Handtag kyl/frys:911795 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag kylfrys:Handtag kyl/frys:911795 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 2.5901e-05 | m³ |  |  | 175.51 | 0.0045459 | 0 | 0.0045459 | 1 | 62% | In Progress
0fjrUmmzDB4fngo1stt34i | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Kitchen:911889 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Kitchen:911889 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.66 | 102.54 | 2015.9364 | 1796.21 | 219.7264 | 0.10899 | 90% | In Progress
0fjrUmmzDB4fngo1stt3xR | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:910822 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:910822 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 314.45 | 314.45 | 160.98 | 153.47 | 0.48806 | 54% | In Progress
0fjrUmmzDB4fngo1stt3xO | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:910821 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:910821 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 264.1 | 264.1 | 151.27 | 112.83 | 0.42722 | 57% | In Progress
0fjrUmmzDB4fngo1stt3xm | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:910797 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:910797 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 266.68 | 266.68 | 150.37 | 116.31 | 0.43614 | 61% | In Progress
0fjrUmmzDB4fngo1stt3xn | IFCFURNISHINGELEMENT |  | Inredning - Skrivbord:1600x800:910796 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Skrivbord:1600x800:910796 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 294.02 | 294.02 | 171.82 | 122.2 | 0.41562 | 59% | In Progress
0fjrUmmzDB4fngo1stt0LX | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:908892 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:908892 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 201 | 0.0082661 | 0.01 | -0.0017339 | -0.20975 | 57% | In Progress
0fjrUmmzDB4fngo1stt0Ma | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:908953 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:908953 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 291.8 | 291.8 | 148.91 | 142.89 | 0.48968 | 55% | In Progress
0fjrUmmzDB4fngo1stt0Md | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:908954 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:908954 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 175.75 | 0.0072277 | 0.01 | -0.0027723 | -0.38356 | 54% | In Progress
0fjrUmmzDB4fngo1stt0Mc | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:908955 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:908955 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 159.28 | 0.0065504 | 0 | 0.0065504 | 1 | 50% | In Progress
0fjrUmmzDB4fngo1stt0Nb | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:909016 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:909016 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 286.82 | 286.82 | 171.73 | 115.09 | 0.40126 | 59% | In Progress
0fjrUmmzDB4fngo1stt0Na | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:909017 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:909017 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 196.94 | 0.0080992 | 0.01 | -0.0019008 | -0.23469 | 57% | In Progress
0fjrUmmzDB4fngo1stt0Nd | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:909018 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:909018 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 195.69 | 0.0080478 | 0.01 | -0.0019522 | -0.24258 | 62% | In Progress
0fjrUmmzDB4fngo1stt0Nc | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Spish\X2\00E4\X0\ll:600 mm:909019 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Spish\X2\00E4\X0\ll:600 mm:909019 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 290.12 | 290.12 | 167.04 | 123.08 | 0.42424 | 59% | In Progress
0fjrUmmzDB4fngo1stt0NX | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:909020 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:909020 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 256.89 | 256.89 | 128.8 | 128.09 | 0.49862 | 51% | In Progress
0qdpkovdH5RgxJU7gsxrDr | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:903410 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:903410 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 321.82 | 321.82 | 159.95 | 161.87 | 0.50298 | 54% | In Progress
0fjrUmmzDB4fngo1stt0NW | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:909021 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:909021 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 178.82 | 0.007354 | 0.01 | -0.002646 | -0.35981 | 57% | In Progress
0fjrUmmzDB4fngo1stt0NY | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:909023 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:909023 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 282.84 | 282.84 | 152.54 | 130.3 | 0.46068 | 52% | In Progress
0fjrUmmzDB4fngo1stt0NT | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:909024 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:909024 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 185.64 | 0.0076345 | 0.01 | -0.0023655 | -0.30985 | 57% | In Progress
0fjrUmmzDB4fngo1stt0NS | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:909025 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:909025 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 198.82 | 0.0081765 | 0.01 | -0.0018235 | -0.22302 | 51% | In Progress
0fjrUmmzDB4fngo1stt3fd | IFCFURNISHINGELEMENT |  | Furniture-Wieland_Healthcare-Rally-Compose-Sofa:64143(L)HC:909658 | 1 - First Floor |  | Finishes | Furnishing | Furniture-Wieland_Healthcare-Rally-Compose-Sofa:64143(L)HC:909658 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 799.74 | 799.74 | 441.71 | 358.03 | 0.44768 | 58% | In Progress
0fjrUmmzDB4fngo1stt3f6 | IFCFURNISHINGELEMENT |  | Furniture-Wieland_Healthcare-Rally-Compose-Sofa:64143(R)HC:909691 | 1 - First Floor |  | Finishes | Furnishing | Furniture-Wieland_Healthcare-Rally-Compose-Sofa:64143(R)HC:909691 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 812.41 | 812.41 | 415.05 | 397.36 | 0.48911 | 51% | In Progress
0fjrUmmzDB4fngo1stt3an | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p:600 mm:909836 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p:600 mm:909836 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 279.32 | 279.32 | 132.1 | 147.22 | 0.52707 | 50% | In Progress
0fjrUmmzDB4fngo1stt3am | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:909837 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:909837 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 202.77 | 0.0083389 | 0.01 | -0.0016611 | -0.19919 | 59% | In Progress
0fjrUmmzDB4fngo1stt3Z5 | IFCBUILDINGELEMENTPROXY |  | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:910328 | 1 - First Floor |  | Not Assigned | Not Assigned | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:910328 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.75803 | m³ |  |  | 204.3 | 154.8653 | 91.55 | 63.3153 | 0.40884 | 59% | In Progress
0fjrUmmzDB4fngo1stt3Z4 | IFCBUILDINGELEMENTPROXY |  | Handtag kylfrys:Handtag kyl/frys:910329 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag kylfrys:Handtag kyl/frys:910329 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 2.5901e-05 | m³ |  |  | 178.4 | 0.0046208 | 0 | 0.0046208 | 1 | 54% | In Progress
0fjrUmmzDB4fngo1stt0NZ | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:909022 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:909022 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 166.9 | 0.0068638 | 0.01 | -0.0031362 | -0.45692 | 56% | In Progress
0qKJYWbnv5I8o6vyLfHipJ | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:896452 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:896452 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 316.39 | 316.39 | 156.79 | 159.6 | 0.50444 | 50% | In Progress
0qdpkovdH5RgxJU7gsxrD5 | IFCDOOR |  | M_Single-Flush:Generic Door:903362 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:903362 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 377.67 | 1204.6083 | 750.05 | 454.5583 | 0.37735 | 65% | In Progress
0qdpkovdH5RgxJU7gsxrn$ | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:903160 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:903160 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 311.47 | 311.47 | 168.75 | 142.72 | 0.45821 | 56% | In Progress
0qKJYWbnv5I8o6vyLfHjJv | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:898542 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:898542 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.26 | 89.75 | 1728.585 | 1512.37 | 216.215 | 0.12508 | 85% | In Progress
0qKJYWbnv5I8o6vyLfHjJW | IFCDOOR |  | M_Single-Flush:Generic Door:898551 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:898551 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 352.82 | 1125.3473 | 738.23 | 387.1173 | 0.344 | 69% | In Progress
0qKJYWbnv5I8o6vyLfHjQF | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:898968 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:898968 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 12.34 | 93.17 | 1149.7178 | 1167.24 | -17.5222 | -0.01524 | 100% | Completed
0qKJYWbnv5I8o6vyLfHjRu | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:899055 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:899055 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 13.42 | 85.94 | 1153.3148 | 922.97 | 230.3448 | 0.19972 | 85% | In Progress
0qKJYWbnv5I8o6vyLfHjc9 | IFCFURNISHINGELEMENT |  | M_Table-Dining:0915 x 1830mm:899230 | 1 - First Floor |  | Finishes | Furnishing | M_Table-Dining:0915 x 1830mm:899230 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 502.09 | 502.09 | 282.63 | 219.46 | 0.43709 | 61% | In Progress
0qKJYWbnv5I8o6vyLfHjco | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:899237 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:899237 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 119.08 | 119.08 | 66.93 | 52.15 | 0.43794 | 57% | In Progress
0qKJYWbnv5I8o6vyLfHjcm | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:899239 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:899239 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 128.83 | 128.83 | 70.37 | 58.46 | 0.45378 | 57% | In Progress
0qKJYWbnv5I8o6vyLfHjcw | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:899245 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:899245 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 121.28 | 121.28 | 64.22 | 57.06 | 0.47048 | 55% | In Progress
0qKJYWbnv5I8o6vyLfHjcu | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:899247 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:899247 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 120.06 | 120.06 | 57.59 | 62.47 | 0.52032 | 51% | In Progress
0qKJYWbnv5I8o6vyLfHjcc | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:899249 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:899249 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 112.07 | 112.07 | 64.33 | 47.74 | 0.42598 | 57% | In Progress
0qKJYWbnv5I8o6vyLfHjca | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:899251 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:899251 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 125.59 | 125.59 | 70.43 | 55.16 | 0.43921 | 60% | In Progress
0qKJYWbnv5I8o6vyLfHjXL | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:899394 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:899394 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.66 | 97.91 | 1533.2706 | 1392.23 | 141.0406 | 0.091987 | 88% | In Progress
0qKJYWbnv5I8o6vyLfHjis | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:899617 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:899617 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 252.92 | 252.92 | 150.17 | 102.75 | 0.40625 | 60% | In Progress
0qKJYWbnv5I8o6vyLfHjir | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:899618 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:899618 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 205.11 | 0.0084352 | 0.01 | -0.0015648 | -0.18551 | 53% | In Progress
0qKJYWbnv5I8o6vyLfHjiq | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:899619 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:899619 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 175.5 | 0.0072175 | 0 | 0.0072175 | 1 | 52% | In Progress
0qKJYWbnv5I8o6vyLfHjip | IFCBUILDINGELEMENTPROXY |  | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:899620 | 1 - First Floor |  | Not Assigned | Not Assigned | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:899620 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.75803 | m³ |  |  | 196.07 | 148.6267 | 79.1 | 69.5267 | 0.46779 | 55% | In Progress
0qKJYWbnv5I8o6vyLfHjio | IFCBUILDINGELEMENTPROXY |  | Handtag kylfrys:Handtag kyl/frys:899621 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag kylfrys:Handtag kyl/frys:899621 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 2.5901e-05 | m³ |  |  | 191.75 | 0.0049666 | 0 | 0.0049666 | 1 | 59% | In Progress
0qKJYWbnv5I8o6vyLfHjin | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Vinkel:K\X2\00F6\X0\k vinkel:899622 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Vinkel:K\X2\00F6\X0\k vinkel:899622 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 273.74 | 273.74 | 138.39 | 135.35 | 0.49445 | 53% | In Progress
0qKJYWbnv5I8o6vyLfHjim | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Diskb\X2\00E4\X0\nk med sk\X2\00E5\X0\p:H14H:899623 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Diskb\X2\00E4\X0\nk med sk\X2\00E5\X0\p:H14H:899623 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 260.16 | 260.16 | 126.63 | 133.53 | 0.51326 | 52% | In Progress
0qKJYWbnv5I8o6vyLfHjIN | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:898432 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:898432 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 156.96 | 0.006455 | 0.01 | -0.003545 | -0.54919 | 55% | In Progress
0qKJYWbnv5I8o6vyLfHji$ | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:899624 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:899624 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 200.41 | 0.0082419 | 0.01 | -0.0017581 | -0.21332 | 61% | In Progress
0qKJYWbnv5I8o6vyLfHjHe | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:898431 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:898431 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 183.26 | 0.0075366 | 0.01 | -0.0024634 | -0.32686 | 54% | In Progress
0qKJYWbnv5I8o6vyLfHjHg | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:898429 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:898429 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 198.57 | 0.0081662 | 0.01 | -0.0018338 | -0.22456 | 57% | In Progress
0qKJYWbnv5I8o6vyLfHip8 | IFCFURNISHINGELEMENT |  | Inredning - Skrivbord:1600x800:896479 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Skrivbord:1600x800:896479 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 260.15 | 260.15 | 121.93 | 138.22 | 0.53131 | 49% | In Progress
0qKJYWbnv5I8o6vyLfHipt | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:896480 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:896480 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 308.38 | 308.38 | 150.97 | 157.41 | 0.51044 | 53% | In Progress
0qKJYWbnv5I8o6vyLfHipd | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:896496 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:896496 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 301.26 | 301.26 | 146.83 | 154.43 | 0.51261 | 51% | In Progress
0qKJYWbnv5I8o6vyLfHipc | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:896497 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:896497 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 185.77 | 0.0076398 | 0 | 0.0076398 | 1 | 52% | In Progress
0qKJYWbnv5I8o6vyLfHipb | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:896498 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:896498 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 178.78 | 0.0073523 | 0 | 0.0073523 | 1 | 51% | In Progress
0qKJYWbnv5I8o6vyLfHiyf | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:896574 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:896574 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 318.51 | 318.51 | 173.64 | 144.87 | 0.45484 | 53% | In Progress
0qKJYWbnv5I8o6vyLfHiut | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:896800 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:896800 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 13.83 | 92.05 | 1273.0515 | 1202.31 | 70.7415 | 0.055568 | 94% | In Progress
0qKJYWbnv5I8o6vyLfHj8U | IFCDOOR |  | M_Single-Flush:Generic Door:897801 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:897801 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 370.15 | 1180.6227 | 784.01 | 396.6127 | 0.33594 | 66% | In Progress
0qKJYWbnv5I8o6vyLfHj8w | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:897837 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:897837 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 12.59 | 95.06 | 1196.8054 | 1255.56 | -58.7546 | -0.049093 | 100% | Completed
0qKJYWbnv5I8o6vyLfHjMt | IFCFLOWTERMINAL |  | M_Lavatory - Vanity:760 mmx455 mm - Private:898208 | 1 - First Floor |  | MEP | MEP | M_Lavatory - Vanity:760 mmx455 mm - Private:898208 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 886.99 | 886.99 | 664.73 | 222.26 | 0.25058 | 73% | In Progress
0qKJYWbnv5I8o6vyLfHjMs | IFCFLOWTERMINAL |  | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:898209 | 1 - First Floor |  | MEP | MEP | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:898209 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 863.71 | 863.71 | 586.51 | 277.2 | 0.32094 | 67% | In Progress
0qKJYWbnv5I8o6vyLfHjMr | IFCFLOWTERMINAL |  | M_Shower Stall with Seat - Rectangular:1220 mmx915 mm - Private:898210 | 1 - First Floor |  | MEP | MEP | M_Shower Stall with Seat - Rectangular:1220 mmx915 mm - Private:898210 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 925.97 | 925.97 | 586.08 | 339.89 | 0.36706 | 68% | In Progress
0qKJYWbnv5I8o6vyLfHjMq | IFCFURNISHINGELEMENT |  | M_Base Cabinet-Double Door & 2 Drawer:600mm:898211 | 1 - First Floor |  | Finishes | Furnishing | M_Base Cabinet-Double Door & 2 Drawer:600mm:898211 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 677.43 | 677.43 | 394.43 | 283 | 0.41776 | 57% | In Progress
0qKJYWbnv5I8o6vyLfHjMo | IFCFURNISHINGELEMENT |  | M_Base Cabinet-Double Door & 2 Drawer:600mm:898213 | 1 - First Floor |  | Finishes | Furnishing | M_Base Cabinet-Double Door & 2 Drawer:600mm:898213 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 629.46 | 629.46 | 350.74 | 278.72 | 0.44279 | 59% | In Progress
0qKJYWbnv5I8o6vyLfHjHl | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:898424 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:898424 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 296.35 | 296.35 | 162.24 | 134.11 | 0.45254 | 53% | In Progress
0qKJYWbnv5I8o6vyLfHjHk | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:898425 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:898425 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 156.46 | 0.0064344 | 0.01 | -0.0035656 | -0.55414 | 56% | In Progress
0qKJYWbnv5I8o6vyLfHjHj | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:898426 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:898426 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 176.98 | 0.0072783 | 0.01 | -0.0027217 | -0.37394 | 50% | In Progress
0qKJYWbnv5I8o6vyLfHjHi | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:898427 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:898427 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 278.4 | 278.4 | 153.76 | 124.64 | 0.4477 | 56% | In Progress
0qKJYWbnv5I8o6vyLfHjHh | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:898428 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:898428 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 167.12 | 0.0068728 | 0.01 | -0.0031272 | -0.45501 | 54% | In Progress
0qKJYWbnv5I8o6vyLfHjHf | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:898430 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:898430 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 260.81 | 260.81 | 138.84 | 121.97 | 0.46766 | 53% | In Progress
0qKJYWbnv5I8o6vyLfHji_ | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:899625 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:899625 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 181.4 | 0.0074601 | 0.01 | -0.0025399 | -0.34047 | 52% | In Progress
0qKJYWbnv5I8o6vyLfHjiz | IFCFLOWTERMINAL |  | K\X2\00F6\X0\k - Diskmaskin 6m:Diskmaskin:899626 | 1 - First Floor |  | MEP | MEP | K\X2\00F6\X0\k - Diskmaskin 6m:Diskmaskin:899626 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 976.85 | 976.85 | 607.23 | 369.62 | 0.37838 | 67% | In Progress
0qKJYWbnv5I8o6vyLfHjiy | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Spish\X2\00E4\X0\ll:600 mm:899627 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Spish\X2\00E4\X0\ll:600 mm:899627 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 301.89 | 301.89 | 174.3 | 127.59 | 0.42264 | 57% | In Progress
0qKJYWbnv5I8o6vyLfHg6w | IFCDOOR |  | M_Single-Flush:Generic Door:901293 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:901293 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 359.01 | 1145.0908 | 649.18 | 495.9108 | 0.43308 | 61% | In Progress
0qKJYWbnv5I8o6vyLfHg1B | IFCFLOWTERMINAL |  | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:901468 | 1 - First Floor |  | MEP | MEP | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:901468 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 981.36 | 981.36 | 610.78 | 370.58 | 0.37762 | 62% | In Progress
0qKJYWbnv5I8o6vyLfHg2K | IFCFLOWTERMINAL |  | M_Lavatory - Vanity:760 mmx455 mm - Private:901507 | 1 - First Floor |  | MEP | MEP | M_Lavatory - Vanity:760 mmx455 mm - Private:901507 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 918.95 | 918.95 | 681.5 | 237.45 | 0.25839 | 74% | In Progress
0qKJYWbnv5I8o6vyLfHg2z | IFCFLOWTERMINAL |  | M_Shower Stall with Seat - Rectangular:1220 mmx915 mm - Private:901546 | 1 - First Floor |  | MEP | MEP | M_Shower Stall with Seat - Rectangular:1220 mmx915 mm - Private:901546 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 953.03 | 953.03 | 588.52 | 364.51 | 0.38247 | 65% | In Progress
0qKJYWbnv5I8o6vyLfHgDX | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:901750 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:901750 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.15 | 95.56 | 1352.174 | 1152.61 | 199.564 | 0.14759 | 88% | In Progress
0qdpkovdH5RgxJU7gsxrW0 | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:902023 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:902023 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 109.41 | 109.41 | 55.19 | 54.22 | 0.49557 | 53% | In Progress
0qdpkovdH5RgxJU7gsxrWE | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:902025 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:902025 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 123.6 | 123.6 | 73.45 | 50.15 | 0.40574 | 60% | In Progress
0qdpkovdH5RgxJU7gsxrWM | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:902033 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:902033 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 126.14 | 126.14 | 68.96 | 57.18 | 0.45331 | 59% | In Progress
0qdpkovdH5RgxJU7gsxrWK | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:902035 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:902035 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 134.12 | 134.12 | 61.82 | 72.3 | 0.53907 | 49% | In Progress
0qdpkovdH5RgxJU7gsxrs$ | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:902712 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:902712 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 308.13 | 308.13 | 157.74 | 150.39 | 0.48807 | 52% | In Progress
0qdpkovdH5RgxJU7gsxrs_ | IFCFURNISHINGELEMENT |  | Inredning - Enkels\X2\00E4\X0\ng:900:902713 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Enkels\X2\00E4\X0\ng:900:902713 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 252.77 | 252.77 | 148.26 | 104.51 | 0.41346 | 58% | In Progress
0qdpkovdH5RgxJU7gsxrtm | IFCDOOR |  | M_Single-Flush:Generic Door:902775 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:902775 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 363.11 | 1158.168 | 789.24 | 368.928 | 0.31854 | 68% | In Progress
0qdpkovdH5RgxJU7gsxrr1 | IFCBUILDINGELEMENTPROXY |  | Serena bench with three drawers:Serena bench with three drawers:902854 | 1 - First Floor |  | Not Assigned | Not Assigned | Serena bench with three drawers:Serena bench with three drawers:902854 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.037843 | m³ |  |  | 181.73 | 6.8772 | 4.05 | 2.8272 | 0.4111 | 58% | In Progress
0qdpkovdH5RgxJU7gsxrr0 | IFCFURNISHINGELEMENT |  | Furniture-Wieland_Healthcare-Rally-Compose-Sofa:64343HC:902855 | 1 - First Floor |  | Finishes | Furnishing | Furniture-Wieland_Healthcare-Rally-Compose-Sofa:64343HC:902855 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 799.29 | 799.29 | 410.52 | 388.77 | 0.48639 | 55% | In Progress
0qdpkovdH5RgxJU7gsxroD | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:902922 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:902922 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 285.93 | 285.93 | 170.29 | 115.64 | 0.40443 | 60% | In Progress
0qdpkovdH5RgxJU7gsxrnM | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:903121 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:903121 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 308.64 | 308.64 | 153.38 | 155.26 | 0.50305 | 54% | In Progress
0qdpkovdH5RgxJU7gsxrnL | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:903122 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:903122 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 174.33 | 0.0071693 | 0.01 | -0.0028307 | -0.39483 | 61% | In Progress
0qdpkovdH5RgxJU7gsxrnK | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:903123 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:903123 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 177.82 | 0.0073129 | 0.01 | -0.0026871 | -0.36745 | 59% | In Progress
0qdpkovdH5RgxJU7gsxrnm | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:903159 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:903159 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 254.3 | 254.3 | 144.59 | 109.71 | 0.43142 | 59% | In Progress
0qKJYWbnv5I8o6vyLfHg6D | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:901274 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:901274 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 10.93 | 97.84 | 1069.3912 | 936.07 | 133.3212 | 0.12467 | 86% | In Progress
0qKJYWbnv5I8o6vyLfHg5$ | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:901224 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:901224 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 10.08 | 96.89 | 976.6512 | 832.64 | 144.0112 | 0.14745 | 90% | In Progress
0qKJYWbnv5I8o6vyLfHj$0 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:900823 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:900823 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 158.48 | 0.0065175 | 0 | 0.0065175 | 1 | 52% | In Progress
0qKJYWbnv5I8o6vyLfHj$1 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:900822 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:900822 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 186.92 | 0.0076871 | 0.01 | -0.0023129 | -0.30088 | 53% | In Progress
0qKJYWbnv5I8o6vyLfHjix | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - H\X2\00F6\X0\gsk\X2\00E5\X0\p:Ugn/Micro:899628 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - H\X2\00F6\X0\gsk\X2\00E5\X0\p:Ugn/Micro:899628 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 267.44 | 267.44 | 152.15 | 115.29 | 0.43109 | 59% | In Progress
0qKJYWbnv5I8o6vyLfHjiw | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:899629 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:899629 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 174.08 | 0.0071591 | 0 | 0.0071591 | 1 | 50% | In Progress
0qKJYWbnv5I8o6vyLfHjiv | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:899630 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:899630 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 261.83 | 261.83 | 144.77 | 117.06 | 0.44708 | 58% | In Progress
0qKJYWbnv5I8o6vyLfHjiu | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:899631 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:899631 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 179.69 | 0.0073898 | 0.01 | -0.0026102 | -0.35322 | 60% | In Progress
0qKJYWbnv5I8o6vyLfHjid | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:899632 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:899632 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 192.23 | 0.0079055 | 0.01 | -0.0020945 | -0.26495 | 55% | In Progress
0qKJYWbnv5I8o6vyLfHje7 | IFCBUILDINGELEMENTPROXY |  | Serena bench with three drawers:Serena bench with three drawers:899856 | 1 - First Floor |  | Not Assigned | Not Assigned | Serena bench with three drawers:Serena bench with three drawers:899856 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.037843 | m³ |  |  | 189.2 | 7.1599 | 4.27 | 2.8899 | 0.40363 | 61% | In Progress
0fjrUmmzDB4fngo1stt3Ug | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:912535 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:912535 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 283.34 | 283.34 | 150.49 | 132.85 | 0.46887 | 57% | In Progress
0qKJYWbnv5I8o6vyLfHje4 | IFCFURNISHINGELEMENT |  | Furniture-Wieland_Healthcare-Rally-Compose-Sofa:64343HC:899859 | 1 - First Floor |  | Finishes | Furnishing | Furniture-Wieland_Healthcare-Rally-Compose-Sofa:64343HC:899859 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 778.56 | 778.56 | 405.43 | 373.13 | 0.47926 | 56% | In Progress
0qKJYWbnv5I8o6vyLfHjfZ | IFCFURNISHINGELEMENT |  | Inredning - Skrivbord:1600x800:899956 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Skrivbord:1600x800:899956 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 317.99 | 317.99 | 187.33 | 130.66 | 0.41089 | 59% | In Progress
0qdpkovdH5RgxJU7gsxrEl | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:903208 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:903208 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 296.72 | 296.72 | 155.82 | 140.9 | 0.47486 | 53% | In Progress
0qKJYWbnv5I8o6vyLfHjfY | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:899957 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:899957 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 281.54 | 281.54 | 168.02 | 113.52 | 0.40321 | 59% | In Progress
0qKJYWbnv5I8o6vyLfHjn9 | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:900446 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:900446 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 297.87 | 297.87 | 172.83 | 125.04 | 0.41978 | 58% | In Progress
0qKJYWbnv5I8o6vyLfHjn8 | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:900447 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:900447 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 267.17 | 267.17 | 140.61 | 126.56 | 0.47371 | 51% | In Progress
0qKJYWbnv5I8o6vyLfHjnq | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:900451 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:900451 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 254.21 | 254.21 | 139.18 | 115.03 | 0.4525 | 53% | In Progress
0qKJYWbnv5I8o6vyLfHjnp | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:900452 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:900452 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 182.73 | 0.0075148 | 0.01 | -0.0024852 | -0.33071 | 61% | In Progress
0qKJYWbnv5I8o6vyLfHjno | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:900453 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:900453 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 192.09 | 0.0078997 | 0.01 | -0.0021003 | -0.26587 | 61% | In Progress
0qKJYWbnv5I8o6vyLfHjzs | IFCDOOR |  | M_Single-Flush:Generic Door:900705 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:900705 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 402.32 | 1283.2314 | 783.53 | 499.7014 | 0.38941 | 66% | In Progress
0qKJYWbnv5I8o6vyLfHj_A | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:900765 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:900765 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 280.52 | 280.52 | 134.15 | 146.37 | 0.52178 | 51% | In Progress
0qKJYWbnv5I8o6vyLfHj_9 | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:900766 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:900766 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 260.5 | 260.5 | 145.25 | 115.25 | 0.44242 | 57% | In Progress
0qKJYWbnv5I8o6vyLfHj$2 | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:900821 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:900821 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 312.76 | 312.76 | 183.97 | 128.79 | 0.41179 | 61% | In Progress
0qKJYWbnv5I8o6vyLfHjnA | IFCFURNISHINGELEMENT |  | Inredning - Dubbels\X2\00E4\X0\ng:1800:900445 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Dubbels\X2\00E4\X0\ng:1800:900445 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 311.99 | 311.99 | 188.43 | 123.56 | 0.39604 | 61% | In Progress
2v8sGyGFXDsRc80mj95i27 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:729235 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:729235 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 170.65 | 0.007018 | 0 | 0.007018 | 1 | 53% | In Progress
0fjrUmmzDB4fngo1stt3T$ | IFCBUILDINGELEMENTPROXY |  | Handtag kylfrys:Handtag kyl/frys:912450 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag kylfrys:Handtag kyl/frys:912450 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 2.5901e-05 | m³ |  |  | 164.25 | 0.0042543 | 0 | 0.0042543 | 1 | 57% | In Progress
2v8sGyGFXDsRc80mj95i25 | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:729233 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:729233 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 277.41 | 277.41 | 145.92 | 131.49 | 0.47399 | 54% | In Progress
11MreptMzBDAizZWBG8_Z1 | IFCFURNISHINGELEMENT |  | Furniture-Wieland_Healthcare-Rally-Compose-Sofa:64343HC:687698 | 1 - First Floor |  | Finishes | Furnishing | Furniture-Wieland_Healthcare-Rally-Compose-Sofa:64343HC:687698 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 916.35 | 916.35 | 444.84 | 471.51 | 0.51455 | 51% | In Progress
2sG0Vcmgb1Uverjtj49YU1 | IFCSPACE |  | 19 | 1 - First Floor | 3ROK | (Info Only) | — | 19 | Room/zone. Not directly costed – use for rate build-up by space type | Custom_Pset | NetArea | 66.303 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
11MreptMzBDAizZWBG8_ZS | IFCBUILDINGELEMENTPROXY |  | Serena bench with three drawers:Serena bench with three drawers:687695 | 1 - First Floor |  | Not Assigned | Not Assigned | Serena bench with three drawers:Serena bench with three drawers:687695 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.037843 | m³ |  |  | 197.07 | 7.4578 | 3.93 | 3.5278 | 0.47303 | 53% | In Progress
11MreptMzBDAizZWBG8_fj | IFCDOOR |  | M_Single-Flush:Generic Door:687358 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:687358 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 415.4 | 1324.9511 | 831.96 | 492.9911 | 0.37208 | 63% | In Progress
11MreptMzBDAizZWBG8_si | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:686911 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:686911 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 177.29 | 0.0072911 | 0.01 | -0.0027089 | -0.37154 | 54% | In Progress
11MreptMzBDAizZWBG8_sj | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - H\X2\00F6\X0\gsk\X2\00E5\X0\p:Ugn/Micro:686910 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - H\X2\00F6\X0\gsk\X2\00E5\X0\p:Ugn/Micro:686910 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 276.36 | 276.36 | 147.69 | 128.67 | 0.46559 | 55% | In Progress
11MreptMzBDAizZWBG8_sk | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Spish\X2\00E4\X0\ll:600 mm:686909 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Spish\X2\00E4\X0\ll:600 mm:686909 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 313.53 | 313.53 | 157.27 | 156.26 | 0.49839 | 51% | In Progress
11MreptMzBDAizZWBG8_sl | IFCFLOWTERMINAL |  | K\X2\00F6\X0\k - Diskmaskin 6m:Diskmaskin:686908 | 1 - First Floor |  | MEP | MEP | K\X2\00F6\X0\k - Diskmaskin 6m:Diskmaskin:686908 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 823.98 | 823.98 | 629.35 | 194.63 | 0.23621 | 74% | In Progress
11MreptMzBDAizZWBG8_Wt | IFCDOOR |  | M_Single-Flush:Generic Door:687780 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:687780 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 408.53 | 1303.0387 | 916.06 | 386.9787 | 0.29698 | 71% | In Progress
11MreptMzBDAizZWBG8_se | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:686907 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:686907 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 199.92 | 0.0082217 | 0.01 | -0.0017783 | -0.21629 | 62% | In Progress
11MreptMzBDAizZWBG8_sg | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Diskb\X2\00E4\X0\nk med sk\X2\00E5\X0\p:G12H:686905 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Diskb\X2\00E4\X0\nk med sk\X2\00E5\X0\p:G12H:686905 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 305.49 | 305.49 | 163.97 | 141.52 | 0.46326 | 56% | In Progress
0X2$ayW0v5dBNxK3e4nxzq | IFCFURNISHINGELEMENT |  | Furniture-Wieland_Healthcare-Rally-Compose-Sofa:64343HC:686533 | 1 - First Floor |  | Finishes | Furnishing | Furniture-Wieland_Healthcare-Rally-Compose-Sofa:64343HC:686533 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 792.62 | 792.62 | 413.26 | 379.36 | 0.47862 | 52% | In Progress
0X2$ayW0v5dBNxK3e4nxzp | IFCBUILDINGELEMENTPROXY |  | Serena bench with three drawers:Serena bench with three drawers:686530 | 1 - First Floor |  | Not Assigned | Not Assigned | Serena bench with three drawers:Serena bench with three drawers:686530 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.037843 | m³ |  |  | 155.84 | 5.8975 | 3.26 | 2.6375 | 0.44722 | 57% | In Progress
0X2$ayW0v5dBNxK3e4nxvW | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:686289 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:686289 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 278.82 | 278.82 | 161.88 | 116.94 | 0.41941 | 56% | In Progress
0X2$ayW0v5dBNxK3e4nxvX | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:686288 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:686288 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 280.87 | 280.87 | 140.62 | 140.25 | 0.49934 | 54% | In Progress
0X2$ayW0v5dBNxK3e4nxu_ | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:686223 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:686223 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 319.43 | 319.43 | 195.44 | 123.99 | 0.38816 | 60% | In Progress
0X2$ayW0v5dBNxK3e4nxu$ | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:686222 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:686222 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 294.62 | 294.62 | 161.46 | 133.16 | 0.45197 | 57% | In Progress
0X2$ayW0v5dBNxK3e4nxwB | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:686138 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:686138 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 267.79 | 267.79 | 143.44 | 124.35 | 0.46436 | 57% | In Progress
11MreptMzBDAizZWBG8_sf | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:686906 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:686906 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 204.16 | 0.0083961 | 0 | 0.0083961 | 1 | 52% | In Progress
11MreptMzBDAizZWBG8nOS | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:688271 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:688271 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 304.94 | 304.94 | 158.03 | 146.91 | 0.48177 | 55% | In Progress
11MreptMzBDAizZWBG8nOY | IFCFURNISHINGELEMENT |  | Inredning - Skrivbord:1600x800:688305 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Skrivbord:1600x800:688305 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 281.61 | 281.61 | 147.85 | 133.76 | 0.47498 | 51% | In Progress
11MreptMzBDAizZWBG8nOX | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:688306 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:688306 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 302.73 | 302.73 | 160.75 | 141.98 | 0.469 | 56% | In Progress
11MreptMzBDAizZWBG8n$m | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Kitchen:690531 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Kitchen:690531 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.76 | 87.2 | 2071.872 | 1767.44 | 304.432 | 0.14694 | 88% | In Progress
11MreptMzBDAizZWBG8nuM | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:690309 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:690309 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 172.39 | 0.0070896 | 0.01 | -0.0029104 | -0.41053 | 54% | In Progress
11MreptMzBDAizZWBG8nuN | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:690308 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:690308 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 165.9 | 0.0068227 | 0 | 0.0068227 | 1 | 52% | In Progress
11MreptMzBDAizZWBG8nuG | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:690307 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:690307 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 275.76 | 275.76 | 139.03 | 136.73 | 0.49583 | 53% | In Progress
11MreptMzBDAizZWBG8n79 | IFCDOOR |  | M_Single-Flush:Generic Door:690010 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:690010 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 345.57 | 1102.2228 | 712.66 | 389.5628 | 0.35343 | 70% | In Progress
11MreptMzBDAizZWBG8n15 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:689878 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:689878 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.79 | 88.86 | 1669.6794 | 1407.34 | 262.3394 | 0.15712 | 87% | In Progress
11MreptMzBDAizZWBG8nDY | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:689649 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:689649 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 118.91 | 118.91 | 59.96 | 58.95 | 0.49575 | 54% | In Progress
11MreptMzBDAizZWBG8nDy | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:689647 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:689647 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 122.25 | 122.25 | 62.85 | 59.4 | 0.48589 | 53% | In Progress
11MreptMzBDAizZWBG8nD_ | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:689645 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:689645 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 112.25 | 112.25 | 60.98 | 51.27 | 0.45675 | 59% | In Progress
11MreptMzBDAizZWBG8nDu | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:689643 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:689643 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 126.59 | 126.59 | 72.67 | 53.92 | 0.42594 | 56% | In Progress
11MreptMzBDAizZWBG8nDs | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:689637 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:689637 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 132.04 | 132.04 | 73.17 | 58.87 | 0.44585 | 55% | In Progress
11MreptMzBDAizZWBG8nDm | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:689635 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:689635 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 132.3 | 132.3 | 69.06 | 63.24 | 0.478 | 54% | In Progress
11MreptMzBDAizZWBG8nDF | IFCFURNISHINGELEMENT |  | M_Table-Dining:0915 x 1830mm:689628 | 1 - First Floor |  | Finishes | Furnishing | M_Table-Dining:0915 x 1830mm:689628 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 524.16 | 524.16 | 296.44 | 227.72 | 0.43445 | 55% | In Progress
11MreptMzBDAizZWBG8nTq | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:688615 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:688615 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 191.76 | 0.0078861 | 0.01 | -0.0021139 | -0.26805 | 54% | In Progress
11MreptMzBDAizZWBG8nTr | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:688614 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:688614 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 162.15 | 0.0066684 | 0.01 | -0.0033316 | -0.4996 | 52% | In Progress
11MreptMzBDAizZWBG8nTs | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:688613 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:688613 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 296.96 | 296.96 | 183.16 | 113.8 | 0.38322 | 60% | In Progress
11MreptMzBDAizZWBG8nSG | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:688515 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:688515 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 287.59 | 287.59 | 161.44 | 126.15 | 0.43865 | 55% | In Progress
11MreptMzBDAizZWBG8nSH | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:688514 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:688514 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 320.45 | 320.45 | 175.93 | 144.52 | 0.45099 | 59% | In Progress
11MreptMzBDAizZWBG8nSI | IFCFURNISHINGELEMENT |  | Inredning - Dubbels\X2\00E4\X0\ng:1800:688513 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Dubbels\X2\00E4\X0\ng:1800:688513 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 305.55 | 305.55 | 150.99 | 154.56 | 0.50584 | 49% | In Progress
0X2$ayW0v5dBNxK3e4nx5W | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:686033 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:686033 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 295.8 | 295.8 | 160.32 | 135.48 | 0.45801 | 55% | In Progress
0X2$ayW0v5dBNxK3e4nx4O | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:685993 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:685993 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 294.9 | 294.9 | 145.46 | 149.44 | 0.50675 | 53% | In Progress
0X2$ayW0v5dBNxK3e4nx7c | IFCDOOR |  | M_Single-Flush:Generic Door:685911 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:685911 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 383.07 | 1221.832 | 763.38 | 458.452 | 0.37522 | 63% | In Progress
0X2$ayW0v5dBNxK3e4nxDQ | IFCFURNISHINGELEMENT |  | M_Base Cabinet-Double Door & 2 Drawer:600mm:685547 | 1 - First Floor |  | Finishes | Furnishing | M_Base Cabinet-Double Door & 2 Drawer:600mm:685547 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 606.5 | 606.5 | 305.69 | 300.81 | 0.49598 | 51% | In Progress
1KGNuJkf5FjQZDFQ6WeFhN | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:677554 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:677554 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 153.33 | 0.0063057 | 0.01 | -0.0036943 | -0.58586 | 58% | In Progress
1KGNuJkf5FjQZDFQ6WeFhK | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:677553 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:677553 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 184.77 | 0.0075987 | 0.01 | -0.0024013 | -0.31602 | 53% | In Progress
1KGNuJkf5FjQZDFQ6WeFhL | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:677552 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:677552 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 314.61 | 314.61 | 159.54 | 155.07 | 0.4929 | 51% | In Progress
1KGNuJkf5FjQZDFQ6WeFqg | IFCFURNISHINGELEMENT |  | M_Base Cabinet-Double Door & 2 Drawer:600mm:676175 | 1 - First Floor |  | Finishes | Furnishing | M_Base Cabinet-Double Door & 2 Drawer:600mm:676175 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 616.94 | 616.94 | 348.81 | 268.13 | 0.43461 | 59% | In Progress
1KGNuJkf5FjQZDFQ6WeFrl | IFCFURNISHINGELEMENT |  | M_Base Cabinet-Double Door & 2 Drawer:600mm:676106 | 1 - First Floor |  | Finishes | Furnishing | M_Base Cabinet-Double Door & 2 Drawer:600mm:676106 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 743.05 | 743.05 | 411.54 | 331.51 | 0.44615 | 58% | In Progress
1KGNuJkf5FjQZDFQ6WeEFB | IFCFLOWTERMINAL |  | M_Shower Stall with Seat - Rectangular:1220 mmx915 mm - Private:675758 | 1 - First Floor |  | MEP | MEP | M_Shower Stall with Seat - Rectangular:1220 mmx915 mm - Private:675758 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 957.3 | 957.3 | 630.35 | 326.95 | 0.34153 | 65% | In Progress
1KGNuJkf5FjQZDFQ6WeEBX | IFCFLOWTERMINAL |  | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:675460 | 1 - First Floor |  | MEP | MEP | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:675460 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 911.76 | 911.76 | 640.1 | 271.66 | 0.29795 | 71% | In Progress
1KGNuJkf5FjQZDFQ6WeEBc | IFCFLOWTERMINAL |  | M_Lavatory - Vanity:760 mmx455 mm - Private:675459 | 1 - First Floor |  | MEP | MEP | M_Lavatory - Vanity:760 mmx455 mm - Private:675459 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 928.41 | 928.41 | 623.12 | 305.29 | 0.32883 | 71% | In Progress
1KGNuJkf5FjQZDFQ6WeE57 | IFCFURNISHINGELEMENT |  | Furniture-Wieland_Healthcare-Rally-Compose-Sofa:64343HC:675106 | 1 - First Floor |  | Finishes | Furnishing | Furniture-Wieland_Healthcare-Rally-Compose-Sofa:64343HC:675106 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 929.57 | 929.57 | 508.3 | 421.27 | 0.45319 | 59% | In Progress
1KGNuJkf5FjQZDFQ6WeE5w | IFCBUILDINGELEMENTPROXY |  | Serena bench with three drawers:Serena bench with three drawers:675103 | 1 - First Floor |  | Not Assigned | Not Assigned | Serena bench with three drawers:Serena bench with three drawers:675103 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.037843 | m³ |  |  | 173.35 | 6.5601 | 3.77 | 2.7901 | 0.42532 | 62% | In Progress
1KGNuJkf5FjQZDFQ6WeEQM | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:674547 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:674547 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 129.63 | 129.63 | 68.47 | 61.16 | 0.4718 | 57% | In Progress
1KGNuJkf5FjQZDFQ6WeEQK | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:674545 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:674545 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 121.82 | 121.82 | 77.17 | 44.65 | 0.36652 | 61% | In Progress
1KGNuJkf5FjQZDFQ6WeEQA | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:674543 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:674543 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 117.39 | 117.39 | 64.76 | 52.63 | 0.44833 | 58% | In Progress
1KGNuJkf5FjQZDFQ6WeEQ8 | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:674541 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:674541 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 136.47 | 136.47 | 76.59 | 59.88 | 0.43878 | 56% | In Progress
1KGNuJkf5FjQZDFQ6WeEQ2 | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:674535 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:674535 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 137.87 | 137.87 | 77.17 | 60.7 | 0.44027 | 59% | In Progress
1KGNuJkf5FjQZDFQ6WeEQ0 | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:674533 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:674533 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 127.66 | 127.66 | 70.7 | 56.96 | 0.44619 | 58% | In Progress
1KGNuJkf5FjQZDFQ6WeEQx | IFCFURNISHINGELEMENT |  | M_Table-Dining:0915 x 1830mm:674526 | 1 - First Floor |  | Finishes | Furnishing | M_Table-Dining:0915 x 1830mm:674526 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 549.29 | 549.29 | 258.74 | 290.55 | 0.52896 | 50% | In Progress
1KGNuJkf5FjQZDFQ6WeERB | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:674478 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:674478 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 301.93 | 301.93 | 148.91 | 153.02 | 0.50681 | 53% | In Progress
1KGNuJkf5FjQZDFQ6WeEO1 | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:674404 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:674404 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 268.97 | 268.97 | 148.94 | 120.03 | 0.44626 | 60% | In Progress
1KGNuJkf5FjQZDFQ6WeFjc | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Kitchen:677635 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Kitchen:677635 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.95 | 96.93 | 1449.1035 | 1304.95 | 144.1535 | 0.099478 | 95% | In Progress
11MreptMzBDAizZWBG8nzD | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Kitchen:690654 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Kitchen:690654 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 24.58 | 88.9 | 2185.162 | 1899.9 | 285.262 | 0.13055 | 93% | In Progress
1KGNuJkf5FjQZDFQ6WeFl3 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Kitchen:677798 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Kitchen:677798 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.24 | 95.99 | 1654.8676 | 1549.21 | 105.6576 | 0.063847 | 95% | In Progress
1KGNuJkf5FjQZDFQ6WeFH7 | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:677922 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:677922 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 274.12 | 274.12 | 146.6 | 127.52 | 0.4652 | 52% | In Progress
0X2$ayW0v5dBNxK3e4nxFl | IFCFURNISHINGELEMENT |  | M_Base Cabinet-Double Door & 2 Drawer:600mm:685406 | 1 - First Floor |  | Finishes | Furnishing | M_Base Cabinet-Double Door & 2 Drawer:600mm:685406 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 637.54 | 637.54 | 382.39 | 255.15 | 0.40021 | 58% | In Progress
0X2$ayW0v5dBNxK3e4nxMV | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:684846 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:684846 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 186.76 | 0.0076805 | 0.01 | -0.0023195 | -0.30199 | 54% | In Progress
0X2$ayW0v5dBNxK3e4nxMS | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:684845 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:684845 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 155.39 | 0.0063904 | 0.01 | -0.0036096 | -0.56484 | 57% | In Progress
0X2$ayW0v5dBNxK3e4nxMT | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:684844 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:684844 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 263.92 | 263.92 | 133.34 | 130.58 | 0.49477 | 52% | In Progress
0X2$ayW0v5dBNxK3e4nxGo | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:684675 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:684675 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 257.4 | 257.4 | 145.37 | 112.03 | 0.43524 | 58% | In Progress
0X2$ayW0v5dBNxK3e4nxGp | IFCFURNISHINGELEMENT |  | Inredning - Skrivbord:1600x800:684674 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Skrivbord:1600x800:684674 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 302.03 | 302.03 | 154.82 | 147.21 | 0.4874 | 52% | In Progress
3GzoWuxxn4WO8bCtw8H3Gq | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:697585 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:697585 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 12.72 | 97.41 | 1239.0552 | 1051.07 | 187.9852 | 0.15172 | 84% | In Progress
0X2$ayW0v5dBNxK3e4nwvt | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Kitchen:682182 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Kitchen:682182 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.37 | 99.64 | 1431.8268 | 1267.04 | 164.7868 | 0.11509 | 88% | In Progress
0X2$ayW0v5dBNxK3e4nw7b | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Spish\X2\00E4\X0\ll:600 mm:681812 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Spish\X2\00E4\X0\ll:600 mm:681812 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 272.73 | 272.73 | 147.2 | 125.53 | 0.46027 | 57% | In Progress
0X2$ayW0v5dBNxK3e4nw7Y | IFCFLOWTERMINAL |  | K\X2\00F6\X0\k - Diskmaskin 6m:Diskmaskin:681811 | 1 - First Floor |  | MEP | MEP | K\X2\00F6\X0\k - Diskmaskin 6m:Diskmaskin:681811 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 945.82 | 945.82 | 613.48 | 332.34 | 0.35138 | 67% | In Progress
0X2$ayW0v5dBNxK3e4nw7Z | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:681810 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:681810 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 155.06 | 0.0063769 | 0.01 | -0.0036231 | -0.56817 | 54% | In Progress
0X2$ayW0v5dBNxK3e4nw7W | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:681809 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:681809 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 153.55 | 0.0063148 | 0.01 | -0.0036852 | -0.58359 | 61% | In Progress
0X2$ayW0v5dBNxK3e4nw7X | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Diskb\X2\00E4\X0\nk med sk\X2\00E5\X0\p:G12H:681808 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Diskb\X2\00E4\X0\nk med sk\X2\00E5\X0\p:G12H:681808 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 298 | 298 | 161.88 | 136.12 | 0.45678 | 56% | In Progress
0X2$ayW0v5dBNxK3e4nw7_ | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Vinkel:K\X2\00F6\X0\k vinkel:681807 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Vinkel:K\X2\00F6\X0\k vinkel:681807 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 259.33 | 259.33 | 133.51 | 125.82 | 0.48517 | 52% | In Progress
0X2$ayW0v5dBNxK3e4nw7$ | IFCBUILDINGELEMENTPROXY |  | Handtag kylfrys:Handtag kyl/frys:681806 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag kylfrys:Handtag kyl/frys:681806 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 2.5901e-05 | m³ |  |  | 196.36 | 0.005086 | 0.01 | -0.004914 | -0.96619 | 51% | In Progress
0X2$ayW0v5dBNxK3e4nw7y | IFCBUILDINGELEMENTPROXY |  | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:681805 | 1 - First Floor |  | Not Assigned | Not Assigned | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:681805 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.75803 | m³ |  |  | 179.25 | 135.8767 | 79.35 | 56.5267 | 0.41601 | 61% | In Progress
0X2$ayW0v5dBNxK3e4nwCn | IFCFURNISHINGELEMENT |  | fixa_bench:Colour - (Light grey-S2000-N):681344 | 1 - First Floor |  | Finishes | Furnishing | fixa_bench:Colour - (Light grey-S2000-N):681344 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 305.59 | 305.59 | 165.79 | 139.8 | 0.45748 | 54% | In Progress
0X2$ayW0v5dBNxK3e4nw9G | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:681185 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:681185 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 283.46 | 283.46 | 134.77 | 148.69 | 0.52455 | 50% | In Progress
0X2$ayW0v5dBNxK3e4nwKj | IFCFURNISHINGELEMENT |  | fixa_bench:Colour - (Light grey-S2000-N):680860 | 1 - First Floor |  | Finishes | Furnishing | fixa_bench:Colour - (Light grey-S2000-N):680860 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 289.46 | 289.46 | 144.15 | 145.31 | 0.502 | 54% | In Progress
1KGNuJkf5FjQZDFQ6WeFH4 | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:677921 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:677921 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 316.91 | 316.91 | 162.69 | 154.22 | 0.48664 | 53% | In Progress
11MreptMzBDAizZWBG8npA | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Vinkel:K\X2\00F6\X0\k vinkel:690777 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Vinkel:K\X2\00F6\X0\k vinkel:690777 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 291.78 | 291.78 | 154.57 | 137.21 | 0.47025 | 51% | In Progress
11MreptMzBDAizZWBG8nhd | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Kitchen:691316 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Kitchen:691316 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.42 | 98.85 | 2117.367 | 1962.88 | 154.487 | 0.072962 | 90% | In Progress
11MreptMzBDAizZWBG8mO0 | IFCFLOWTERMINAL |  | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:692371 | 1 - First Floor |  | MEP | MEP | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:692371 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 821.74 | 821.74 | 552.24 | 269.5 | 0.32796 | 68% | In Progress
3GzoWuxxn4WO8bCtw8H3GI | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Vinkel:K\X2\00F6\X0\k vinkel:697559 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Vinkel:K\X2\00F6\X0\k vinkel:697559 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 289.31 | 289.31 | 146 | 143.31 | 0.49535 | 53% | In Progress
3GzoWuxxn4WO8bCtw8H3GJ | IFCBUILDINGELEMENTPROXY |  | Handtag kylfrys:Handtag kyl/frys:697558 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag kylfrys:Handtag kyl/frys:697558 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 2.5901e-05 | m³ |  |  | 161.18 | 0.0041748 | 0 | 0.0041748 | 1 | 58% | In Progress
3GzoWuxxn4WO8bCtw8H3GG | IFCBUILDINGELEMENTPROXY |  | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:697557 | 1 - First Floor |  | Not Assigned | Not Assigned | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:697557 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.75803 | m³ |  |  | 199.97 | 151.583 | 88.05 | 63.533 | 0.41913 | 58% | In Progress
3GzoWuxxn4WO8bCtw8H3GH | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:697556 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:697556 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 201.89 | 0.0083027 | 0.01 | -0.0016973 | -0.20442 | 60% | In Progress
3GzoWuxxn4WO8bCtw8H3GM | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:697555 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:697555 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 189.74 | 0.0078031 | 0.01 | -0.0021969 | -0.28155 | 55% | In Progress
3GzoWuxxn4WO8bCtw8H3G$ | IFCFURNISHINGELEMENT |  | Furniture-Wieland_Healthcare-Rally-Compose-Sofa:64343HC:697594 | 1 - First Floor |  | Finishes | Furnishing | Furniture-Wieland_Healthcare-Rally-Compose-Sofa:64343HC:697594 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 976.42 | 976.42 | 574.23 | 402.19 | 0.4119 | 61% | In Progress
3GzoWuxxn4WO8bCtw8H3GN | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:697554 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:697554 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 310.81 | 310.81 | 160.27 | 150.54 | 0.48435 | 51% | In Progress
3GzoWuxxn4WO8bCtw8H3GB | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:697550 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:697550 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 126.01 | 126.01 | 76.5 | 49.51 | 0.39291 | 60% | In Progress
3GzoWuxxn4WO8bCtw8H3G9 | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:697548 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:697548 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 126.95 | 126.95 | 59.45 | 67.5 | 0.53171 | 49% | In Progress
3GzoWuxxn4WO8bCtw8H3GF | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:697546 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:697546 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 134.33 | 134.33 | 72.61 | 61.72 | 0.45947 | 54% | In Progress
3GzoWuxxn4WO8bCtw8H3GD | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:697544 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:697544 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 119.22 | 119.22 | 58.7 | 60.52 | 0.50763 | 52% | In Progress
3GzoWuxxn4WO8bCtw8H3Gv | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:697596 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:697596 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.56 | 87.75 | 1716.39 | 1502.36 | 214.03 | 0.1247 | 91% | In Progress
3GzoWuxxn4WO8bCtw8H3Gu | IFCFLOWTERMINAL |  | M_Lavatory - Vanity:760 mmx455 mm - Private:697597 | 1 - First Floor |  | MEP | MEP | M_Lavatory - Vanity:760 mmx455 mm - Private:697597 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 847.07 | 847.07 | 548.44 | 298.63 | 0.35254 | 63% | In Progress
3GzoWuxxn4WO8bCtw8H3Gx | IFCFLOWTERMINAL |  | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:697598 | 1 - First Floor |  | MEP | MEP | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:697598 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 909.16 | 909.16 | 572.75 | 336.41 | 0.37002 | 66% | In Progress
3GzoWuxxn4WO8bCtw8H3Gw | IFCFLOWTERMINAL |  | M_Shower Stall with Seat - Rectangular:1220 mmx915 mm - Private:697599 | 1 - First Floor |  | MEP | MEP | M_Shower Stall with Seat - Rectangular:1220 mmx915 mm - Private:697599 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 830.02 | 830.02 | 511.25 | 318.77 | 0.38405 | 66% | In Progress
3GzoWuxxn4WO8bCtw8H3N5 | IFCFURNISHINGELEMENT |  | M_Base Cabinet-Double Door & 2 Drawer:600mm:697600 | 1 - First Floor |  | Finishes | Furnishing | M_Base Cabinet-Double Door & 2 Drawer:600mm:697600 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 659.74 | 659.74 | 303.17 | 356.57 | 0.54047 | 49% | In Progress
3GzoWuxxn4WO8bCtw8H3N7 | IFCFURNISHINGELEMENT |  | M_Base Cabinet-Double Door & 2 Drawer:600mm:697602 | 1 - First Floor |  | Finishes | Furnishing | M_Base Cabinet-Double Door & 2 Drawer:600mm:697602 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 718.15 | 718.15 | 356.58 | 361.57 | 0.50347 | 49% | In Progress
3GzoWuxxn4WO8bCtw8H3N2 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Kitchen:697607 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Kitchen:697607 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.95 | 93.4 | 1583.13 | 1499.78 | 83.35 | 0.052649 | 94% | In Progress
3GzoWuxxn4WO8bCtw8H3NC | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:697609 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:697609 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 296.93 | 296.93 | 148.47 | 148.46 | 0.49998 | 53% | In Progress
3GzoWuxxn4WO8bCtw8H3GT | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Diskb\X2\00E4\X0\nk med sk\X2\00E5\X0\p:H14H:697560 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Diskb\X2\00E4\X0\nk med sk\X2\00E5\X0\p:H14H:697560 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 286.64 | 286.64 | 141.78 | 144.86 | 0.50537 | 50% | In Progress
3GzoWuxxn4WO8bCtw8H3NF | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:697610 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:697610 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 309.08 | 309.08 | 145.76 | 163.32 | 0.52841 | 50% | In Progress
3GzoWuxxn4WO8bCtw8H3GS | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:697561 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:697561 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 186.12 | 0.0076542 | 0 | 0.0076542 | 1 | 50% | In Progress
3GzoWuxxn4WO8bCtw8H3GU | IFCFLOWTERMINAL |  | K\X2\00F6\X0\k - Diskmaskin 6m:Diskmaskin:697563 | 1 - First Floor |  | MEP | MEP | K\X2\00F6\X0\k - Diskmaskin 6m:Diskmaskin:697563 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 988.74 | 988.74 | 686.93 | 301.81 | 0.30525 | 69% | In Progress
3GzoWuxxn4WO8bCtw8H3Ge | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:697581 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:697581 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 192.54 | 0.0079182 | 0.01 | -0.0020818 | -0.26291 | 54% | In Progress
3GzoWuxxn4WO8bCtw8H3Gp | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:697590 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:697590 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 263.47 | 263.47 | 135.25 | 128.22 | 0.48666 | 52% | In Progress
3GzoWuxxn4WO8bCtw8H3Gf | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:697580 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:697580 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 171.67 | 0.0070599 | 0.01 | -0.0029401 | -0.41644 | 57% | In Progress
3GzoWuxxn4WO8bCtw8H3Gk | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:697579 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:697579 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 311.36 | 311.36 | 180.02 | 131.34 | 0.42183 | 56% | In Progress
3GzoWuxxn4WO8bCtw8H3Gl | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:697578 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:697578 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 278.47 | 278.47 | 144.8 | 133.67 | 0.48002 | 54% | In Progress
3GzoWuxxn4WO8bCtw8H3Gi | IFCFURNISHINGELEMENT |  | Inredning - Skrivbord:1600x800:697577 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Skrivbord:1600x800:697577 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 275.28 | 275.28 | 164.27 | 111.01 | 0.40326 | 58% | In Progress
3GzoWuxxn4WO8bCtw8H3Gj | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:697576 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:697576 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 271.75 | 271.75 | 144.47 | 127.28 | 0.46837 | 57% | In Progress
3GzoWuxxn4WO8bCtw8H3GY | IFCFURNISHINGELEMENT |  | Inredning - Enkels\X2\00E4\X0\ng:900:697575 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Enkels\X2\00E4\X0\ng:900:697575 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 290.32 | 290.32 | 140.93 | 149.39 | 0.51457 | 49% | In Progress
3GzoWuxxn4WO8bCtw8H3Go | IFCBUILDINGELEMENTPROXY |  | Serena bench with three drawers:Serena bench with three drawers:697591 | 1 - First Floor |  | Not Assigned | Not Assigned | Serena bench with three drawers:Serena bench with three drawers:697591 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.037843 | m³ |  |  | 185.42 | 7.0169 | 3.66 | 3.3569 | 0.4784 | 55% | In Progress
3GzoWuxxn4WO8bCtw8H3GZ | IFCFURNISHINGELEMENT |  | Inredning - Dubbels\X2\00E4\X0\ng:1800:697574 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Dubbels\X2\00E4\X0\ng:1800:697574 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 319.15 | 319.15 | 166.49 | 152.66 | 0.47833 | 51% | In Progress
3GzoWuxxn4WO8bCtw8H3GW | IFCDOOR |  | M_Single-Flush:Generic Door:697573 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:697573 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 421.43 | 1344.1843 | 813.11 | 531.0743 | 0.39509 | 60% | In Progress
3GzoWuxxn4WO8bCtw8H3GX | IFCDOOR |  | M_Single-Flush:Generic Door:697572 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:697572 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 388.17 | 1238.0989 | 810 | 428.0989 | 0.34577 | 69% | In Progress
3GzoWuxxn4WO8bCtw8H3Gd | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:697570 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:697570 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.82 | 93.82 | 1578.0524 | 1301.87 | 276.1824 | 0.17501 | 87% | In Progress
3GzoWuxxn4WO8bCtw8H3Ga | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:697569 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:697569 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 182.01 | 0.0074852 | 0.01 | -0.0025148 | -0.33597 | 61% | In Progress
3GzoWuxxn4WO8bCtw8H3Gb | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:697568 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:697568 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 202.7 | 0.0083361 | 0.01 | -0.0016639 | -0.19961 | 54% | In Progress
3GzoWuxxn4WO8bCtw8H3GQ | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:697567 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:697567 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 265.22 | 265.22 | 151.93 | 113.29 | 0.42715 | 57% | In Progress
3GzoWuxxn4WO8bCtw8H3GR | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:697566 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:697566 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 177.36 | 0.0072939 | 0.01 | -0.0027061 | -0.371 | 57% | In Progress
3GzoWuxxn4WO8bCtw8H3GO | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - H\X2\00F6\X0\gsk\X2\00E5\X0\p:Ugn/Micro:697565 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - H\X2\00F6\X0\gsk\X2\00E5\X0\p:Ugn/Micro:697565 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 272.18 | 272.18 | 153.34 | 118.84 | 0.43662 | 57% | In Progress
3GzoWuxxn4WO8bCtw8H3GP | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Spish\X2\00E4\X0\ll:600 mm:697564 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Spish\X2\00E4\X0\ll:600 mm:697564 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 282.08 | 282.08 | 152.9 | 129.18 | 0.45796 | 54% | In Progress
3GzoWuxxn4WO8bCtw8H3GV | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:697562 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:697562 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 153.58 | 0.006316 | 0.01 | -0.003684 | -0.58328 | 59% | In Progress
1KGNuJkf5FjQZDFQ6WeElF | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:673706 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:673706 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 11.11 | 86.23 | 958.0153 | 859.94 | 98.0753 | 0.10237 | 89% | In Progress
3GzoWuxxn4WO8bCtw8H3NE | IFCFURNISHINGELEMENT |  | fixa_bench:Colour - (Light grey-S2000-N):697611 | 1 - First Floor |  | Finishes | Furnishing | fixa_bench:Colour - (Light grey-S2000-N):697611 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 297.17 | 297.17 | 150.85 | 146.32 | 0.49238 | 51% | In Progress
3GzoWuxxn4WO8bCtw8H3Pm | IFCDOOR |  | M_Single-Flush:Generic Door:698037 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:698037 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 402.68 | 1284.3797 | 805.37 | 479.0097 | 0.37295 | 62% | In Progress
02b4vxvtD5HBo2EeUI64uz | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:634753 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:634753 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 186.87 | 0.007685 | 0 | 0.007685 | 1 | 53% | In Progress
02b4vxvtD5HBo2EeUI64u_ | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:634754 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:634754 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 153.14 | 0.0062979 | 0.01 | -0.0037021 | -0.58783 | 61% | In Progress
02b4vxvtD5HBo2EeUI65Me | IFCFLOWTERMINAL |  | K\X2\00F6\X0\k - Diskmaskin 6m:Diskmaskin:635924 | 1 - First Floor |  | MEP | MEP | K\X2\00F6\X0\k - Diskmaskin 6m:Diskmaskin:635924 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 926.36 | 926.36 | 630.11 | 296.25 | 0.3198 | 68% | In Progress
02b4vxvtD5HBo2EeUI62mU | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - H\X2\00F6\X0\gsk\X2\00E5\X0\p:Ugn/Micro:642466 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - H\X2\00F6\X0\gsk\X2\00E5\X0\p:Ugn/Micro:642466 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 256.33 | 256.33 | 124.92 | 131.41 | 0.51266 | 50% | In Progress
02b4vxvtD5HBo2EeUI62mV | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:642467 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:642467 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 185.97 | 0.007648 | 0.01 | -0.002352 | -0.30753 | 58% | In Progress
3GzoWuxxn4WO8bCtw8H0zf | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:696236 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:696236 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 160.17 | 0.006587 | 0 | 0.006587 | 1 | 51% | In Progress
3GzoWuxxn4WO8bCtw8H0zk | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:696235 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:696235 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 188.84 | 0.0077661 | 0.01 | -0.0022339 | -0.28765 | 57% | In Progress
3GzoWuxxn4WO8bCtw8H0zl | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:696234 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:696234 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 268.46 | 268.46 | 143.05 | 125.41 | 0.46715 | 56% | In Progress
3GzoWuxxn4WO8bCtw8H0_M | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Spish\X2\00E4\X0\ll:600 mm:696147 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Spish\X2\00E4\X0\ll:600 mm:696147 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 259.03 | 259.03 | 163.79 | 95.24 | 0.36768 | 61% | In Progress
3GzoWuxxn4WO8bCtw8H0$q | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:696113 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:696113 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 184.53 | 0.0075888 | 0.01 | -0.0024112 | -0.31773 | 55% | In Progress
3GzoWuxxn4WO8bCtw8H0$r | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:696112 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:696112 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 201.09 | 0.0082698 | 0.01 | -0.0017302 | -0.20921 | 53% | In Progress
3GzoWuxxn4WO8bCtw8H0$g | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:696111 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:696111 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 293.99 | 293.99 | 147.41 | 146.58 | 0.49859 | 52% | In Progress
3GzoWuxxn4WO8bCtw8H0xc | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:695843 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:695843 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 314.46 | 314.46 | 188.76 | 125.7 | 0.39973 | 60% | In Progress
11MreptMzBDAizZWBG8mns | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:695013 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:695013 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 304.45 | 304.45 | 172.79 | 131.66 | 0.43245 | 60% | In Progress
11MreptMzBDAizZWBG8m1P | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:693962 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:693962 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 154.34 | 0.0063472 | 0.01 | -0.0036528 | -0.57549 | 60% | In Progress
11MreptMzBDAizZWBG8m1Q | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:693961 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:693961 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 198.84 | 0.0081773 | 0.01 | -0.0018227 | -0.2229 | 52% | In Progress
11MreptMzBDAizZWBG8m1R | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:693960 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:693960 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 276.36 | 276.36 | 142.52 | 133.84 | 0.4843 | 54% | In Progress
11MreptMzBDAizZWBG8mFz | IFCDOOR |  | M_Single-Flush:Generic Door:693614 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:693614 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 351.08 | 1119.7974 | 707.14 | 412.6574 | 0.36851 | 62% | In Progress
11MreptMzBDAizZWBG8mO7 | IFCFLOWTERMINAL |  | M_Lavatory - Vanity:760 mmx455 mm - Private:692372 | 1 - First Floor |  | MEP | MEP | M_Lavatory - Vanity:760 mmx455 mm - Private:692372 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 876.7 | 876.7 | 595.19 | 281.51 | 0.3211 | 66% | In Progress
02b4vxvtD5HBo2EeUI64uy | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Diskb\X2\00E4\X0\nk med sk\X2\00E5\X0\p:H14H:634752 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Diskb\X2\00E4\X0\nk med sk\X2\00E5\X0\p:H14H:634752 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 303.47 | 303.47 | 163.99 | 139.48 | 0.45962 | 58% | In Progress
3GzoWuxxn4WO8bCtw8H3Q3 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:697926 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:697926 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 11.38 | 86.62 | 985.7356 | 878.89 | 106.8456 | 0.10839 | 91% | In Progress
02b4vxvtD5HBo2EeUI67uA | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Vinkel:K\X2\00F6\X0\k vinkel:630710 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Vinkel:K\X2\00F6\X0\k vinkel:630710 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 276.1 | 276.1 | 126.44 | 149.66 | 0.54205 | 49% | In Progress
02b4vxvtD5HBo2EeUI66Ue | IFCBUILDINGELEMENTPROXY |  | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:624148 | 1 - First Floor |  | Not Assigned | Not Assigned | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:624148 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.75803 | m³ |  |  | 188.34 | 142.7671 | 88.59 | 54.1771 | 0.37948 | 61% | In Progress
3GzoWuxxn4WO8bCtw8H3Vj | IFCWALL |  | Basic Wall:MockUp Interior between App:698152 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:698152 | Includes RC walls, block walls, brick walls | Dimensions | Area | 24.3511 | m² |  |  | 91.31 | 2223.5015 | 1762.82 | 460.6815 | 0.20719 | 85% | In Progress
3GzoWuxxn4WO8bCtw8H3G7 | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:697538 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:697538 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 130.08 | 130.08 | 78.88 | 51.2 | 0.3936 | 61% | In Progress
3GzoWuxxn4WO8bCtw8H3G5 | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:697536 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:697536 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 133.94 | 133.94 | 65.41 | 68.53 | 0.51165 | 51% | In Progress
3GzoWuxxn4WO8bCtw8H3UC | IFCDOOR |  | M_Single-Flush:Generic Door:698185 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:698185 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 351.1 | 1119.8612 | 725.6 | 394.2612 | 0.35206 | 63% | In Progress
3GzoWuxxn4WO8bCtw8H3XD | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Kitchen:698504 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Kitchen:698504 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 25.57 | 95.58 | 2443.9806 | 2368.02 | 75.9606 | 0.031081 | 95% | In Progress
3GzoWuxxn4WO8bCtw8H3Hy | IFCFURNISHINGELEMENT |  | M_Table-Dining:0915 x 1830mm:697529 | 1 - First Floor |  | Finishes | Furnishing | M_Table-Dining:0915 x 1830mm:697529 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 504.31 | 504.31 | 256.27 | 248.04 | 0.49184 | 51% | In Progress
2v8sGyGFXDsRc80mj95i26 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:729234 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:729234 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 206.17 | 0.0084788 | 0.01 | -0.0015212 | -0.17942 | 54% | In Progress
3GzoWuxxn4WO8bCtw8H3Ho | IFCDOOR |  | M_Single-Flush:Generic Door:697527 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:697527 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 367.65 | 1172.6487 | 672.84 | 499.8087 | 0.42622 | 62% | In Progress
3GzoWuxxn4WO8bCtw8H3Hp | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:697526 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:697526 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.15 | 88.96 | 1347.744 | 1250.98 | 96.764 | 0.071797 | 93% | In Progress
3GzoWuxxn4WO8bCtw8H3WJ | IFCFURNISHINGELEMENT |  | fixa_bench:Colour - (Light grey-S2000-N):698582 | 1 - First Floor |  | Finishes | Furnishing | fixa_bench:Colour - (Light grey-S2000-N):698582 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 259.1 | 259.1 | 151.88 | 107.22 | 0.41382 | 58% | In Progress
3GzoWuxxn4WO8bCtw8H3Hm | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:697525 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:697525 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.13 | 92.45 | 1768.5685 | 1714.35 | 54.2185 | 0.030657 | 94% | In Progress
3GzoWuxxn4WO8bCtw8H3Hn | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:697524 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:697524 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.43 | 92.96 | 1620.2928 | 1515.55 | 104.7428 | 0.064644 | 91% | In Progress
38dG_uU_12$ex4EhqaBX1_ | IFCFURNISHINGELEMENT |  | Inredning - Skrivbord:1600x800:619972 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Skrivbord:1600x800:619972 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 300.08 | 300.08 | 178.31 | 121.77 | 0.40579 | 59% | In Progress
3GzoWuxxn4WO8bCtw8H3D2 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:697223 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:697223 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.8 | 98.44 | 1850.672 | 1500.2 | 350.472 | 0.18938 | 86% | In Progress
3GzoWuxxn4WO8bCtw8H3ES | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:697177 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:697177 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.97 | 95.79 | 1721.3463 | 1533.11 | 188.2363 | 0.10935 | 91% | In Progress
38dG_uU_12$ex4EhqaBX1$ | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:619973 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:619973 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 309.71 | 309.71 | 143.3 | 166.41 | 0.53731 | 50% | In Progress
02b4vxvtD5HBo2EeUI69y2 | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:622270 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:622270 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 312.25 | 312.25 | 162.04 | 150.21 | 0.48106 | 52% | In Progress
02b4vxvtD5HBo2EeUI69y3 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:622271 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:622271 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 204.03 | 0.0083908 | 0.01 | -0.0016092 | -0.19179 | 61% | In Progress
02b4vxvtD5HBo2EeUI69zy | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:622272 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:622272 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 179.44 | 0.0073795 | 0.01 | -0.0026205 | -0.35511 | 54% | In Progress
02b4vxvtD5HBo2EeUI66Uf | IFCBUILDINGELEMENTPROXY |  | Handtag kylfrys:Handtag kyl/frys:624149 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag kylfrys:Handtag kyl/frys:624149 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 2.5901e-05 | m³ |  |  | 194.71 | 0.0050432 | 0.01 | -0.0049568 | -0.98286 | 60% | In Progress
1KGNuJkf5FjQZDFQ6WeEa4 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:673121 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:673121 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 166.57 | 0.0068502 | 0.01 | -0.0031498 | -0.45981 | 58% | In Progress
0X2$ayW0v5dBNxK3e4nwfs | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Kitchen:683207 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Kitchen:683207 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.87 | 91.39 | 1450.3593 | 1177.37 | 272.9893 | 0.18822 | 87% | In Progress
1KGNuJkf5FjQZDFQ6WeEaw | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:673119 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:673119 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 263.66 | 263.66 | 154.7 | 108.96 | 0.41326 | 59% | In Progress
2m6FhmO0r2OgRBRP7hD4OV | IFCBUILDINGELEMENTPROXY |  | Serena bench with three drawers:Serena bench with three drawers:712690 | 1 - First Floor |  | Not Assigned | Not Assigned | Serena bench with three drawers:Serena bench with three drawers:712690 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.037843 | m³ |  |  | 157.64 | 5.9656 | 3.06 | 2.9056 | 0.48706 | 54% | In Progress
38dG_uU_12$ex4EhqaBXN8 | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:618610 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:618610 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 312.35 | 312.35 | 191.99 | 120.36 | 0.38534 | 60% | In Progress
38dG_uU_12$ex4EhqaBZAY | IFCFURNISHINGELEMENT |  | Inredning - Dubbels\X2\00E4\X0\ng:1800:612120 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Dubbels\X2\00E4\X0\ng:1800:612120 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 308.11 | 308.11 | 160.03 | 148.08 | 0.48061 | 53% | In Progress
07FRR7rH17tO$Mh0aewlOz | IFCFURNISHINGELEMENT |  | Inredning - Enkels\X2\00E4\X0\ng:900:606367 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Enkels\X2\00E4\X0\ng:900:606367 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 270.34 | 270.34 | 144.56 | 125.78 | 0.46527 | 53% | In Progress
0Zs4aBjAr5AggJ3MVmSIoU | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:600207 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:600207 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 13.45 | 97.42 | 1310.299 | 1137.43 | 172.869 | 0.13193 | 90% | In Progress
0Zs4aBjAr5AggJ3MVmSIn8 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:600153 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:600153 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.38 | 85.53 | 1572.0414 | 1386.48 | 185.5614 | 0.11804 | 93% | In Progress
0Zs4aBjAr5AggJ3MVmSImG | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:600065 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:600065 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.3 | 97.57 | 1492.821 | 1268.58 | 224.241 | 0.15021 | 91% | In Progress
0Zs4aBjAr5AggJ3MVmSIFT | IFCFURNISHINGELEMENT |  | M_Base Cabinet-Double Door & 2 Drawer:600mm:600012 | 1 - First Floor |  | Finishes | Furnishing | M_Base Cabinet-Double Door & 2 Drawer:600mm:600012 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 701.44 | 701.44 | 394.11 | 307.33 | 0.43814 | 56% | In Progress
0Zs4aBjAr5AggJ3MVmSIFR | IFCFURNISHINGELEMENT |  | M_Base Cabinet-Double Door & 2 Drawer:600mm:600010 | 1 - First Floor |  | Finishes | Furnishing | M_Base Cabinet-Double Door & 2 Drawer:600mm:600010 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 650.62 | 650.62 | 334.73 | 315.89 | 0.48552 | 55% | In Progress
0Zs4aBjAr5AggJ3MVmSIFO | IFCFLOWTERMINAL |  | M_Shower Stall with Seat - Rectangular:1220 mmx915 mm - Private:600009 | 1 - First Floor |  | MEP | MEP | M_Shower Stall with Seat - Rectangular:1220 mmx915 mm - Private:600009 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 895.78 | 895.78 | 617.42 | 278.36 | 0.31075 | 73% | In Progress
0Zs4aBjAr5AggJ3MVmSIAn | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:599712 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:599712 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.89 | 90.59 | 1348.8851 | 1203.4 | 145.4851 | 0.10786 | 86% | In Progress
0Zs4aBjAr5AggJ3MVmSI9v | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:599656 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:599656 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.58 | 89.6 | 1485.568 | 1289.9 | 195.668 | 0.13171 | 94% | In Progress
0Zs4aBjAr5AggJ3MVmSI5l | IFCFURNISHINGELEMENT |  | M_Bed-Standard:0965 x 1905mm - Twin:599422 | 1 - First Floor |  | Finishes | Furnishing | M_Bed-Standard:0965 x 1905mm - Twin:599422 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 1538.56 | 1538.56 | 755.05 | 783.51 | 0.50925 | 51% | In Progress
0Zs4aBjAr5AggJ3MVmSI3F | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:599262 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:599262 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 128.97 | 128.97 | 69.37 | 59.6 | 0.46212 | 56% | In Progress
3naw$9in55$v8L5CpxnK7f | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:713179 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:713179 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.39 | 99.51 | 1630.9689 | 1509.17 | 121.7989 | 0.074679 | 91% | In Progress
3naw$9in55$v8L5CpxnK9t | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:713285 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:713285 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 10.29 | 89.12 | 917.0448 | 830.5 | 86.5448 | 0.094374 | 94% | In Progress
0Zs4aBjAr5AggJ3MVmSI3D | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:599260 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:599260 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 137.46 | 137.46 | 69.91 | 67.55 | 0.49142 | 50% | In Progress
3naw$9in55$v8L5CpxnKbi | IFCDOOR |  | M_Single-Flush:Generic Door:715102 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:715102 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 397.6 | 1268.1766 | 851.47 | 416.7066 | 0.32859 | 66% | In Progress
0Zs4aBjAr5AggJ3MVmSI3B | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:599258 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:599258 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 121.71 | 121.71 | 61.58 | 60.13 | 0.49404 | 50% | In Progress
2v8sGyGFXDsRc80mj95kax | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:723247 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:723247 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 12.08 | 101.22 | 1222.7376 | 1053.23 | 169.5076 | 0.13863 | 89% | In Progress
2v8sGyGFXDsRc80mj95kjH | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:723781 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:723781 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.96 | 100.34 | 1601.4264 | 1331.19 | 270.2364 | 0.16875 | 87% | In Progress
2m6FhmO0r2OgRBRP7hD4V1 | IFCBUILDINGELEMENTPROXY |  | Handtag kylfrys:Handtag kyl/frys:712236 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag kylfrys:Handtag kyl/frys:712236 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 2.5901e-05 | m³ |  |  | 186.85 | 0.0048396 | 0 | 0.0048396 | 1 | 55% | In Progress
2m6FhmO0r2OgRBRP7hD4V6 | IFCBUILDINGELEMENTPROXY |  | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:712235 | 1 - First Floor |  | Not Assigned | Not Assigned | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:712235 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.75803 | m³ |  |  | 193.24 | 146.4815 | 86.51 | 59.9715 | 0.40941 | 58% | In Progress
2m6FhmO0r2OgRBRP7hD4GE | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:712163 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:712163 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 13.39 | 88.24 | 1181.5336 | 1034.81 | 146.7236 | 0.12418 | 93% | In Progress
2m6FhmO0r2OgRBRP7hD4Iw | IFCFLOWTERMINAL |  | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:712023 | 1 - First Floor |  | MEP | MEP | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:712023 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 843 | 843 | 554.43 | 288.57 | 0.34231 | 65% | In Progress
2m6FhmO0r2OgRBRP7hD456 | IFCDOOR |  | M_Single-Flush:Generic Door:710827 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:710827 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 413.67 | 1319.4331 | 856.09 | 463.3431 | 0.35117 | 66% | In Progress
2m6FhmO0r2OgRBRP7hD44Y | IFCDOOR |  | M_Single-Flush:Generic Door:710863 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:710863 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 423.04 | 1349.3195 | 800.15 | 549.1695 | 0.407 | 62% | In Progress
2m6FhmO0r2OgRBRP7hD42C | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:711009 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:711009 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 281.31 | 281.31 | 151.03 | 130.28 | 0.46312 | 58% | In Progress
2m6FhmO0r2OgRBRP7hD42F | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:711010 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:711010 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 183.97 | 0.0075658 | 0.01 | -0.0024342 | -0.32174 | 51% | In Progress
2m6FhmO0r2OgRBRP7hD42E | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:711011 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:711011 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 184.41 | 0.0075839 | 0.01 | -0.0024161 | -0.31859 | 57% | In Progress
2m6FhmO0r2OgRBRP7hD429 | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:711012 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:711012 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 295.97 | 295.97 | 175.2 | 120.77 | 0.40805 | 59% | In Progress
2m6FhmO0r2OgRBRP7hD428 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:711013 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:711013 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 172.46 | 0.0070924 | 0.01 | -0.0029076 | -0.40995 | 60% | In Progress
2m6FhmO0r2OgRBRP7hD42B | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:711014 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:711014 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 183.25 | 0.0075362 | 0.01 | -0.0024638 | -0.32693 | 58% | In Progress
2m6FhmO0r2OgRBRP7hD42A | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:711015 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:711015 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 292.72 | 292.72 | 137.61 | 155.11 | 0.52989 | 51% | In Progress
2m6FhmO0r2OgRBRP7hD425 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:711016 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:711016 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 173.46 | 0.0071336 | 0.01 | -0.0028664 | -0.40182 | 54% | In Progress
2v8sGyGFXDsRc80mj95klY | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:723958 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:723958 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.39 | 97.64 | 1697.9596 | 1528 | 169.9596 | 0.1001 | 95% | In Progress
2m6FhmO0r2OgRBRP7hD424 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:711017 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:711017 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 180.93 | 0.0074408 | 0.01 | -0.0025592 | -0.34395 | 54% | In Progress
2m6FhmO0r2OgRBRP7hD42V | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:711026 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:711026 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 165.51 | 0.0068066 | 0.01 | -0.0031934 | -0.46916 | 62% | In Progress
2m6FhmO0r2OgRBRP7hD42U | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:711027 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:711027 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 190.87 | 0.0078495 | 0.01 | -0.0021505 | -0.27396 | 55% | In Progress
2m6FhmO0r2OgRBRP7hD41n | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Kitchen:711068 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Kitchen:711068 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 22.45 | 90.1 | 2022.745 | 1659.7 | 363.045 | 0.17948 | 89% | In Progress
2m6FhmO0r2OgRBRP7hD4D3 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:711342 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:711342 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 13.71 | 93.58 | 1282.9818 | 1155.49 | 127.4918 | 0.099371 | 90% | In Progress
2m6FhmO0r2OgRBRP7hD4CZ | IFCDOOR |  | M_Single-Flush:Generic Door:711374 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:711374 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 424.96 | 1355.4435 | 933.99 | 421.4535 | 0.31093 | 70% | In Progress
2m6FhmO0r2OgRBRP7hD4Bu | IFCBUILDINGELEMENTPROXY |  | Serena bench with three drawers:Serena bench with three drawers:711445 | 1 - First Floor |  | Not Assigned | Not Assigned | Serena bench with three drawers:Serena bench with three drawers:711445 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.037843 | m³ |  |  | 179.4 | 6.7891 | 4.11 | 2.6791 | 0.39462 | 61% | In Progress
28WUkjJ1r5wPzZDX9W1jHd | IFCFURNISHINGELEMENT |  | Inredning - Skrivbord:1600x800:664471 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Skrivbord:1600x800:664471 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 255.27 | 255.27 | 129.59 | 125.68 | 0.49234 | 51% | In Progress
2m6FhmO0r2OgRBRP7hD4MO | IFCFURNISHINGELEMENT |  | Inredning - Enkels\X2\00E4\X0\ng:900:711797 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Enkels\X2\00E4\X0\ng:900:711797 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 274.98 | 274.98 | 148.67 | 126.31 | 0.45934 | 55% | In Progress
2m6FhmO0r2OgRBRP7hD4J_ | IFCFURNISHINGELEMENT |  | Inredning - Enkels\X2\00E4\X0\ng:900:711955 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Enkels\X2\00E4\X0\ng:900:711955 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 271.11 | 271.11 | 143.49 | 127.62 | 0.47073 | 55% | In Progress
2m6FhmO0r2OgRBRP7hD4Ix | IFCFLOWTERMINAL |  | M_Lavatory - Vanity:760 mmx455 mm - Private:712022 | 1 - First Floor |  | MEP | MEP | M_Lavatory - Vanity:760 mmx455 mm - Private:712022 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 879.53 | 879.53 | 512.48 | 367.05 | 0.41733 | 63% | In Progress
1KGNuJkf5FjQZDFQ6WeEa5 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:673120 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:673120 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 195.57 | 0.0080428 | 0.01 | -0.0019572 | -0.24334 | 61% | In Progress
2v8sGyGFXDsRc80mj95koT | IFCFURNISHINGELEMENT |  | Inredning - Dubbels\X2\00E4\X0\ng:1800:724105 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Dubbels\X2\00E4\X0\ng:1800:724105 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 271.27 | 271.27 | 156.01 | 115.26 | 0.42489 | 59% | In Progress
2v8sGyGFXDsRc80mj95koU | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:724106 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:724106 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 309.08 | 309.08 | 176.67 | 132.41 | 0.4284 | 57% | In Progress
2v8sGyGFXDsRc80mj95koV | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:724107 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:724107 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 258.5 | 258.5 | 138.75 | 119.75 | 0.46325 | 55% | In Progress
28WUkjJ1r5wPzZDX9W1kB_ | IFCFURNISHINGELEMENT |  | Furniture-Wieland_Healthcare-Rally-Compose-Sofa:64343HC:660750 | 1 - First Floor |  | Finishes | Furnishing | Furniture-Wieland_Healthcare-Rally-Compose-Sofa:64343HC:660750 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 960.29 | 960.29 | 540.71 | 419.58 | 0.43693 | 60% | In Progress
2v8sGyGFXDsRc80mj95l5H | IFCBUILDINGELEMENTPROXY |  | Serena bench with three drawers:Serena bench with three drawers:725317 | 1 - First Floor |  | Not Assigned | Not Assigned | Serena bench with three drawers:Serena bench with three drawers:725317 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.037843 | m³ |  |  | 198.94 | 7.5285 | 3.84 | 3.6885 | 0.48994 | 54% | In Progress
2v8sGyGFXDsRc80mj95l9U | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:725578 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:725578 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 10.11 | 97.21 | 982.7931 | 870 | 112.7931 | 0.11477 | 93% | In Progress
2v8sGyGFXDsRc80mj95lAg | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:725694 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:725694 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 316.55 | 316.55 | 156.74 | 159.81 | 0.50485 | 52% | In Progress
2v8sGyGFXDsRc80mj95lAh | IFCFURNISHINGELEMENT |  | Inredning - Skrivbord:1600x800:725695 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Skrivbord:1600x800:725695 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 300.14 | 300.14 | 159.99 | 140.15 | 0.46695 | 56% | In Progress
2v8sGyGFXDsRc80mj95lBK | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:725696 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:725696 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 266.36 | 266.36 | 155 | 111.36 | 0.41808 | 58% | In Progress
2v8sGyGFXDsRc80mj95lBL | IFCFURNISHINGELEMENT |  | Inredning - Enkels\X2\00E4\X0\ng:900:725697 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Enkels\X2\00E4\X0\ng:900:725697 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 263.8 | 263.8 | 151.46 | 112.34 | 0.42585 | 57% | In Progress
2v8sGyGFXDsRc80mj95lCR | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:725775 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:725775 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 254.64 | 254.64 | 137.11 | 117.53 | 0.46155 | 53% | In Progress
2v8sGyGFXDsRc80mj95lC6 | IFCFURNISHINGELEMENT |  | Inredning - Enkels\X2\00E4\X0\ng:900:725778 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Enkels\X2\00E4\X0\ng:900:725778 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 312.47 | 312.47 | 190.39 | 122.08 | 0.39069 | 60% | In Progress
2v8sGyGFXDsRc80mj95lD8 | IFCDOOR |  | M_Single-Flush:Generic Door:725852 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:725852 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 370.68 | 1182.3131 | 798.42 | 383.8931 | 0.3247 | 66% | In Progress
2v8sGyGFXDsRc80mj95l5K | IFCBUILDINGELEMENTPROXY |  | Serena bench with three drawers:Serena bench with three drawers:725312 | 1 - First Floor |  | Not Assigned | Not Assigned | Serena bench with three drawers:Serena bench with three drawers:725312 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.037843 | m³ |  |  | 163.03 | 6.1696 | 3.3 | 2.8696 | 0.46512 | 53% | In Progress
2v8sGyGFXDsRc80mj95lE_ | IFCDOOR |  | M_Single-Flush:Generic Door:725930 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:725930 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 367.67 | 1172.7125 | 747.95 | 424.7625 | 0.36221 | 64% | In Progress
2v8sGyGFXDsRc80mj95lIw | IFCFLOWTERMINAL |  | M_Shower Stall with Seat - Rectangular:1220 mmx915 mm - Public:726190 | 1 - First Floor |  | MEP | MEP | M_Shower Stall with Seat - Rectangular:1220 mmx915 mm - Public:726190 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 980.95 | 980.95 | 692.54 | 288.41 | 0.29401 | 69% | In Progress
2v8sGyGFXDsRc80mj95lSb | IFCFURNISHINGELEMENT |  | M_Base Cabinet-Double Door & 2 Drawer:600mm:726833 | 1 - First Floor |  | Finishes | Furnishing | M_Base Cabinet-Double Door & 2 Drawer:600mm:726833 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 621.26 | 621.26 | 317.33 | 303.93 | 0.48922 | 51% | In Progress
2v8sGyGFXDsRc80mj95lXN | IFCFURNISHINGELEMENT |  | M_Base Cabinet-Double Door & 2 Drawer:600mm:727107 | 1 - First Floor |  | Finishes | Furnishing | M_Base Cabinet-Double Door & 2 Drawer:600mm:727107 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 733.92 | 733.92 | 439.71 | 294.21 | 0.40087 | 59% | In Progress
2v8sGyGFXDsRc80mj95lnq | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:728160 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:728160 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.91 | 102.11 | 2033.0101 | 1723.29 | 309.7201 | 0.15235 | 86% | In Progress
2v8sGyGFXDsRc80mj95luL | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:728577 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:728577 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.49 | 86.73 | 1343.4477 | 1189.55 | 153.8977 | 0.11455 | 86% | In Progress
2v8sGyGFXDsRc80mj95lu5 | IFCDOOR |  | M_Single-Flush:Generic Door:728593 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:728593 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 361.26 | 1152.2673 | 730.2 | 422.0673 | 0.36629 | 68% | In Progress
2v8sGyGFXDsRc80mj95lyz | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Kitchen:728873 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Kitchen:728873 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 20.87 | 98.66 | 2059.0342 | 1926.7 | 132.3342 | 0.06427 | 90% | In Progress
2v8sGyGFXDsRc80mj95i01 | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:729109 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:729109 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 259.71 | 259.71 | 130.53 | 129.18 | 0.4974 | 50% | In Progress
2v8sGyGFXDsRc80mj95i02 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:729110 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:729110 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 204.91 | 0.0084269 | 0 | 0.0084269 | 1 | 51% | In Progress
2v8sGyGFXDsRc80mj95i03 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:729111 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:729111 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 167.28 | 0.0068794 | 0.01 | -0.0031206 | -0.45361 | 56% | In Progress
2v8sGyGFXDsRc80mj95lHO | IFCFLOWTERMINAL |  | M_Lavatory - Vanity:760 mmx455 mm - Private:726092 | 1 - First Floor |  | MEP | MEP | M_Lavatory - Vanity:760 mmx455 mm - Private:726092 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 902.86 | 902.86 | 588.99 | 313.87 | 0.34764 | 70% | In Progress
2m6FhmO0r2OgRBRP7hD461 | IFCDOOR |  | M_Single-Flush:Generic Door:710764 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:710764 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 342.62 | 1092.8136 | 737.07 | 355.7436 | 0.32553 | 68% | In Progress
2v8sGyGFXDsRc80mj95l2Z | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:725175 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:725175 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.33 | 88.23 | 1440.7959 | 1400.72 | 40.0759 | 0.027815 | 100% | Completed
2v8sGyGFXDsRc80mj95kzZ | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:724855 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:724855 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.38 | 89.18 | 1282.4084 | 1157.79 | 124.6184 | 0.097175 | 94% | In Progress
28WUkjJ1r5wPzZDX9W1jI_ | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Kitchen:664398 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Kitchen:664398 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.62 | 100.68 | 2378.0616 | 2247.91 | 130.1516 | 0.05473 | 92% | In Progress
28WUkjJ1r5wPzZDX9W1jK5 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:664309 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:664309 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 173.43 | 0.0071323 | 0.01 | -0.0028677 | -0.40207 | 54% | In Progress
28WUkjJ1r5wPzZDX9W1jK4 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:664308 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:664308 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 174.95 | 0.0071948 | 0.01 | -0.0028052 | -0.38989 | 60% | In Progress
2v8sGyGFXDsRc80mj95ko2 | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:724118 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:724118 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 254.89 | 254.89 | 139.54 | 115.35 | 0.45255 | 58% | In Progress
28WUkjJ1r5wPzZDX9W1jK3 | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:664307 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:664307 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 293.23 | 293.23 | 140.95 | 152.28 | 0.51932 | 49% | In Progress
28WUkjJ1r5wPzZDX9W1jKw | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Kitchen:664266 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Kitchen:664266 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 22.12 | 91.99 | 2034.8188 | 1822.72 | 212.0988 | 0.10423 | 90% | In Progress
28WUkjJ1r5wPzZDX9W1jMB | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:664187 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:664187 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 182.92 | 0.0075226 | 0.01 | -0.0024774 | -0.32933 | 58% | In Progress
28WUkjJ1r5wPzZDX9W1jMA | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:664186 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:664186 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 174.69 | 0.0071841 | 0 | 0.0071841 | 1 | 50% | In Progress
28WUkjJ1r5wPzZDX9W1jM9 | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:664185 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:664185 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 308.27 | 308.27 | 187.2 | 121.07 | 0.39274 | 59% | In Progress
2v8sGyGFXDsRc80mj95krb | IFCFURNISHINGELEMENT |  | M_Table-Dining:0915 x 1830mm:724337 | 1 - First Floor |  | Finishes | Furnishing | M_Table-Dining:0915 x 1830mm:724337 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 477.66 | 477.66 | 259.13 | 218.53 | 0.4575 | 53% | In Progress
2v8sGyGFXDsRc80mj95k$a | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:724976 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:724976 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 12.78 | 93.29 | 1192.2462 | 1044.24 | 148.0062 | 0.12414 | 93% | In Progress
28WUkjJ1r5wPzZDX9W1kx8 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:661816 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:661816 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 193.46 | 0.0079561 | 0.01 | -0.0020439 | -0.2569 | 58% | In Progress
28WUkjJ1r5wPzZDX9W1kx6 | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:661814 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:661814 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 285.64 | 285.64 | 168.73 | 116.91 | 0.40929 | 60% | In Progress
28WUkjJ1r5wPzZDX9W1kzj | IFCFURNISHINGELEMENT |  | M_Base Cabinet-Double Door & 2 Drawer:600mm:661661 | 1 - First Floor |  | Finishes | Furnishing | M_Base Cabinet-Double Door & 2 Drawer:600mm:661661 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 724.27 | 724.27 | 386.93 | 337.34 | 0.46577 | 58% | In Progress
28WUkjJ1r5wPzZDX9W1k25 | IFCFURNISHINGELEMENT |  | M_Base Cabinet-Double Door & 2 Drawer:600mm:661365 | 1 - First Floor |  | Finishes | Furnishing | M_Base Cabinet-Double Door & 2 Drawer:600mm:661365 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 737.63 | 737.63 | 363.85 | 373.78 | 0.50673 | 52% | In Progress
28WUkjJ1r5wPzZDX9W1k71 | IFCDOOR |  | M_Single-Flush:Generic Door:661041 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:661041 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 360.52 | 1149.907 | 732.99 | 416.917 | 0.36257 | 65% | In Progress
2v8sGyGFXDsRc80mj95kri | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:724344 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:724344 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 125.17 | 125.17 | 69 | 56.17 | 0.44875 | 57% | In Progress
2v8sGyGFXDsRc80mj95krk | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:724346 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:724346 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 120.61 | 120.61 | 64.81 | 55.8 | 0.46265 | 54% | In Progress
2v8sGyGFXDsRc80mj95ksK | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:724352 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:724352 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 130.05 | 130.05 | 73.71 | 56.34 | 0.43322 | 59% | In Progress
2v8sGyGFXDsRc80mj95ksM | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:724354 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:724354 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 131.41 | 131.41 | 74.43 | 56.98 | 0.4336 | 58% | In Progress
2v8sGyGFXDsRc80mj95ksG | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:724356 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:724356 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 121.09 | 121.09 | 58.99 | 62.1 | 0.51284 | 51% | In Progress
2v8sGyGFXDsRc80mj95ksI | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:724358 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:724358 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 108.04 | 108.04 | 53.29 | 54.75 | 0.50676 | 50% | In Progress
28WUkjJ1r5wPzZDX9W1kx7 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:661815 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:661815 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 187.17 | 0.0076974 | 0.01 | -0.0023026 | -0.29914 | 60% | In Progress
2m6FhmO0r2OgRBRP7hD47b | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:710664 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:710664 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 12.26 | 94.88 | 1163.2288 | 999.31 | 163.9188 | 0.14092 | 89% | In Progress
2m6FhmO0r2OgRBRP7hD42S | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:711025 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:711025 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 256.08 | 256.08 | 146.82 | 109.26 | 0.42666 | 61% | In Progress
28WUkjJ1r5wPzZDX9W1iyS | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:669932 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:669932 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 294.49 | 294.49 | 148.69 | 145.8 | 0.49509 | 51% | In Progress
1KGNuJkf5FjQZDFQ6We996 | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Diskb\X2\00E4\X0\nk med sk\X2\00E5\X0\p:H14H:671267 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Diskb\X2\00E4\X0\nk med sk\X2\00E5\X0\p:H14H:671267 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 311.42 | 311.42 | 156.59 | 154.83 | 0.49717 | 50% | In Progress
1KGNuJkf5FjQZDFQ6We997 | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Vinkel:K\X2\00F6\X0\k vinkel:671266 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Vinkel:K\X2\00F6\X0\k vinkel:671266 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 260.99 | 260.99 | 121.55 | 139.44 | 0.53427 | 49% | In Progress
1KGNuJkf5FjQZDFQ6We994 | IFCBUILDINGELEMENTPROXY |  | Handtag kylfrys:Handtag kyl/frys:671265 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag kylfrys:Handtag kyl/frys:671265 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 2.5901e-05 | m³ |  |  | 202.22 | 0.0052377 | 0.01 | -0.0047623 | -0.90922 | 54% | In Progress
1KGNuJkf5FjQZDFQ6We995 | IFCBUILDINGELEMENTPROXY |  | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:671264 | 1 - First Floor |  | Not Assigned | Not Assigned | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:671264 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.75803 | m³ |  |  | 173.12 | 131.2299 | 63.29 | 67.9399 | 0.51772 | 52% | In Progress
1KGNuJkf5FjQZDFQ6We99w | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:671263 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:671263 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 181.37 | 0.0074589 | 0.01 | -0.0025411 | -0.34069 | 57% | In Progress
1KGNuJkf5FjQZDFQ6We99x | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:671262 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:671262 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 167.79 | 0.0069004 | 0.01 | -0.0030996 | -0.4492 | 59% | In Progress
1KGNuJkf5FjQZDFQ6We99u | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:671261 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:671261 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 257.98 | 257.98 | 147 | 110.98 | 0.43019 | 59% | In Progress
02b4vxvtD5HBo2EeUI63Px | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Kitchen:645063 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Kitchen:645063 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.89 | 96.61 | 1728.3529 | 1444.56 | 283.7929 | 0.1642 | 90% | In Progress
28WUkjJ1r5wPzZDX9W1ixN | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:669991 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:669991 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 267.59 | 267.59 | 134.99 | 132.6 | 0.49553 | 50% | In Progress
28WUkjJ1r5wPzZDX9W1iEk | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:668766 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:668766 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 13.95 | 93.21 | 1300.2795 | 1249.07 | 51.2095 | 0.039383 | 94% | In Progress
28WUkjJ1r5wPzZDX9W1jtY | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:666130 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:666130 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 185.42 | 0.0076254 | 0.01 | -0.0023746 | -0.3114 | 56% | In Progress
28WUkjJ1r5wPzZDX9W1jtX | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:666129 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:666129 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 161.84 | 0.0066557 | 0.01 | -0.0033443 | -0.50247 | 62% | In Progress
28WUkjJ1r5wPzZDX9W1jtW | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:666128 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:666128 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 285.1 | 285.1 | 166.57 | 118.53 | 0.41575 | 60% | In Progress
2m6FhmO0r2OgRBRP7hD4gW | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:709453 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:709453 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 295.38 | 295.38 | 167.85 | 127.53 | 0.43175 | 58% | In Progress
2m6FhmO0r2OgRBRP7hD4gO | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:709493 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:709493 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 317.42 | 317.42 | 184.75 | 132.67 | 0.41796 | 60% | In Progress
28WUkjJ1r5wPzZDX9W1jxA | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Kitchen:665914 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Kitchen:665914 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.45 | 98.85 | 2318.0325 | 2130.44 | 187.5925 | 0.080927 | 94% | In Progress
28WUkjJ1r5wPzZDX9W1jHe | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:664472 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:664472 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 273.16 | 273.16 | 131.94 | 141.22 | 0.51699 | 51% | In Progress
2m6FhmO0r2OgRBRP7hD4gR | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:709494 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:709494 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 156.77 | 0.0064472 | 0.01 | -0.0035528 | -0.55107 | 62% | In Progress
2m6FhmO0r2OgRBRP7hD4gQ | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:709495 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:709495 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 165.53 | 0.0068074 | 0.01 | -0.0031926 | -0.46898 | 52% | In Progress
2m6FhmO0r2OgRBRP7hD4gL | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:709496 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:709496 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 278.91 | 278.91 | 151.05 | 127.86 | 0.45843 | 57% | In Progress
2m6FhmO0r2OgRBRP7hD4gK | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:709497 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:709497 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 201.22 | 0.0082752 | 0.01 | -0.0017248 | -0.20843 | 54% | In Progress
2m6FhmO0r2OgRBRP7hD4gN | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:709498 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:709498 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 156.23 | 0.006425 | 0.01 | -0.003575 | -0.55643 | 61% | In Progress
2m6FhmO0r2OgRBRP7hD4rX | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:709772 | 1 - First Floor |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:709772 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 300.8 | 300.8 | 180.9 | 119.9 | 0.3986 | 59% | In Progress
2m6FhmO0r2OgRBRP7hD4rW | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:709773 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:709773 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 191.47 | 0.0078742 | 0.01 | -0.0021258 | -0.26997 | 60% | In Progress
2m6FhmO0r2OgRBRP7hD4rZ | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:709774 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:709774 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 164.26 | 0.0067552 | 0.01 | -0.0032448 | -0.48034 | 59% | In Progress
1KGNuJkf5FjQZDFQ6We991 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:671268 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:671268 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 155 | 0.0063744 | 0.01 | -0.0036256 | -0.56878 | 51% | In Progress
2m6FhmO0r2OgRBRP7hD4pv | IFCFURNISHINGELEMENT |  | Inredning - Skrivbord:1600x800:709908 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Skrivbord:1600x800:709908 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 255.2 | 255.2 | 126.5 | 128.7 | 0.50431 | 50% | In Progress
1KGNuJkf5FjQZDFQ6We990 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:671269 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:671269 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 197.43 | 0.0081193 | 0.01 | -0.0018807 | -0.23163 | 57% | In Progress
1KGNuJkf5FjQZDFQ6We992 | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Spish\X2\00E4\X0\ll:600 mm:671271 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Spish\X2\00E4\X0\ll:600 mm:671271 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 274.4 | 274.4 | 143.57 | 130.83 | 0.47679 | 51% | In Progress
1KGNuJkf5FjQZDFQ6WeEYu | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:672989 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:672989 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 282.89 | 282.89 | 164.43 | 118.46 | 0.41875 | 59% | In Progress
1KGNuJkf5FjQZDFQ6WeEYv | IFCFURNISHINGELEMENT |  | Inredning - Skrivbord:1600x800:672988 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Skrivbord:1600x800:672988 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 320.72 | 320.72 | 150.66 | 170.06 | 0.53024 | 49% | In Progress
3GzoWuxxn4WO8bCtw8H3fu | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:699069 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:699069 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.62 | 89.16 | 1749.3192 | 1451.51 | 297.8092 | 0.17024 | 85% | In Progress
3GzoWuxxn4WO8bCtw8H2Hb | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:701600 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:701600 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 287.97 | 287.97 | 148.46 | 139.51 | 0.48446 | 55% | In Progress
1KGNuJkf5FjQZDFQ6WeEWj | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:672840 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:672840 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 275.34 | 275.34 | 130.82 | 144.52 | 0.52488 | 50% | In Progress
3GzoWuxxn4WO8bCtw8H2Pa | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:702113 | 1 - First Floor |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:702113 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 252.21 | 252.21 | 138.6 | 113.61 | 0.45046 | 59% | In Progress
2m6FhmO0r2OgRBRP7hD2KW | IFCFLOWTERMINAL |  | M_Lavatory - Vanity:760 mmx455 mm - Private:703693 | 1 - First Floor |  | MEP | MEP | M_Lavatory - Vanity:760 mmx455 mm - Private:703693 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 825.61 | 825.61 | 539.31 | 286.3 | 0.34677 | 66% | In Progress
2m6FhmO0r2OgRBRP7hD2KZ | IFCFLOWTERMINAL |  | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:703694 | 1 - First Floor |  | MEP | MEP | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:703694 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 939.33 | 939.33 | 646.5 | 292.83 | 0.31174 | 67% | In Progress
2m6FhmO0r2OgRBRP7hD2KY | IFCFLOWTERMINAL |  | M_Shower Stall with Seat - Rectangular:1220 mmx915 mm - Private:703695 | 1 - First Floor |  | MEP | MEP | M_Shower Stall with Seat - Rectangular:1220 mmx915 mm - Private:703695 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 820.83 | 820.83 | 586.64 | 234.19 | 0.28531 | 69% | In Progress
2m6FhmO0r2OgRBRP7hD2Ky | IFCFURNISHINGELEMENT |  | M_Base Cabinet-Double Door & 2 Drawer:600mm:703697 | 1 - First Floor |  | Finishes | Furnishing | M_Base Cabinet-Double Door & 2 Drawer:600mm:703697 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 618.58 | 618.58 | 320.16 | 298.42 | 0.48243 | 56% | In Progress
2m6FhmO0r2OgRBRP7hD2K_ | IFCFURNISHINGELEMENT |  | M_Base Cabinet-Double Door & 2 Drawer:600mm:703699 | 1 - First Floor |  | Finishes | Furnishing | M_Base Cabinet-Double Door & 2 Drawer:600mm:703699 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 644.17 | 644.17 | 376.94 | 267.23 | 0.41484 | 57% | In Progress
2m6FhmO0r2OgRBRP7hD2Hh | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:703878 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:703878 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.91 | 88.65 | 1587.7215 | 1417.97 | 169.7515 | 0.10692 | 86% | In Progress
2m6FhmO0r2OgRBRP7hD2GT | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:703984 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:703984 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 315.59 | 315.59 | 174.71 | 140.88 | 0.4464 | 58% | In Progress
2m6FhmO0r2OgRBRP7hD4gc | IFCFURNISHINGELEMENT |  | Inredning - Dubbels\X2\00E4\X0\ng:1800:709451 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Dubbels\X2\00E4\X0\ng:1800:709451 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 298.38 | 298.38 | 154.39 | 143.99 | 0.48257 | 52% | In Progress
1KGNuJkf5FjQZDFQ6WeEWY | IFCFURNISHINGELEMENT |  | Inredning - Enkels\X2\00E4\X0\ng:900:672839 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Enkels\X2\00E4\X0\ng:900:672839 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 255.56 | 255.56 | 123.22 | 132.34 | 0.51784 | 52% | In Progress
1KGNuJkf5FjQZDFQ6WeEyP | IFCFURNISHINGELEMENT |  | Inredning - Dubbels\X2\00E4\X0\ng:1800:672636 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Dubbels\X2\00E4\X0\ng:1800:672636 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 253.22 | 253.22 | 122.18 | 131.04 | 0.51749 | 50% | In Progress
1KGNuJkf5FjQZDFQ6WeEzz | IFCDOOR |  | M_Single-Flush:Generic Door:672536 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:672536 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 380.83 | 1214.6874 | 768.97 | 445.7174 | 0.36694 | 65% | In Progress
2m6FhmO0r2OgRBRP7hD4gX | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:709452 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:709452 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 313.59 | 313.59 | 157.62 | 155.97 | 0.49737 | 49% | In Progress
1KGNuJkf5FjQZDFQ6WeEw3 | IFCDOOR |  | M_Single-Flush:Generic Door:672486 | 1 - First Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:672486 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 393.23 | 1254.2382 | 713.03 | 541.2082 | 0.4315 | 61% | In Progress
1KGNuJkf5FjQZDFQ6WeExu | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:672413 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:672413 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.55 | 99.21 | 1741.1355 | 1390.81 | 350.3255 | 0.20121 | 86% | In Progress
1KGNuJkf5FjQZDFQ6We999 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:671276 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:671276 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 198.69 | 0.0081711 | 0.01 | -0.0018289 | -0.22382 | 62% | In Progress
1KGNuJkf5FjQZDFQ6We99E | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:671275 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:671275 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 181.37 | 0.0074589 | 0.01 | -0.0025411 | -0.34069 | 58% | In Progress
1KGNuJkf5FjQZDFQ6We99F | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:671274 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:671274 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 307.15 | 307.15 | 186.26 | 120.89 | 0.39359 | 59% | In Progress
1KGNuJkf5FjQZDFQ6We99C | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:671273 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:671273 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 176.74 | 0.0072685 | 0 | 0.0072685 | 1 | 50% | In Progress
1KGNuJkf5FjQZDFQ6We99D | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - H\X2\00F6\X0\gsk\X2\00E5\X0\p:Ugn/Micro:671272 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - H\X2\00F6\X0\gsk\X2\00E5\X0\p:Ugn/Micro:671272 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 304.49 | 304.49 | 151.39 | 153.1 | 0.50281 | 50% | In Progress
1KGNuJkf5FjQZDFQ6We993 | IFCFLOWTERMINAL |  | K\X2\00F6\X0\k - Diskmaskin 6m:Diskmaskin:671270 | 1 - First Floor |  | MEP | MEP | K\X2\00F6\X0\k - Diskmaskin 6m:Diskmaskin:671270 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 846.27 | 846.27 | 611.47 | 234.8 | 0.27745 | 70% | In Progress
2m6FhmO0r2OgRBRP7hD4pu | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:709909 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:709909 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 317.98 | 317.98 | 179.44 | 138.54 | 0.43569 | 60% | In Progress
3GzoWuxxn4WO8bCtw8H3Gm | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:697589 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:697589 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 316.5 | 316.5 | 160 | 156.5 | 0.49447 | 50% | In Progress
2m6FhmO0r2OgRBRP7hD4nd | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Diskb\X2\00E4\X0\nk med sk\X2\00E5\X0\p:H14H:710026 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Diskb\X2\00E4\X0\nk med sk\X2\00E5\X0\p:H14H:710026 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 264.24 | 264.24 | 149.34 | 114.9 | 0.43483 | 55% | In Progress
2m6FhmO0r2OgRBRP7hD4na | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Vinkel:K\X2\00F6\X0\k vinkel:710025 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Vinkel:K\X2\00F6\X0\k vinkel:710025 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 278.17 | 278.17 | 173.2 | 104.97 | 0.37736 | 60% | In Progress
2m6FhmO0r2OgRBRP7hD4v8 | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:710565 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:710565 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 284.36 | 284.36 | 147.73 | 136.63 | 0.48048 | 52% | In Progress
2m6FhmO0r2OgRBRP7hD4v9 | IFCFURNISHINGELEMENT |  | Inredning - Skrivbord:1600x800:710564 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Skrivbord:1600x800:710564 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 313.42 | 313.42 | 175.95 | 137.47 | 0.43861 | 59% | In Progress
2m6FhmO0r2OgRBRP7hD4vi | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:710529 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:710529 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 10.15 | 97.88 | 993.482 | 862.23 | 131.252 | 0.13211 | 93% | In Progress
2m6FhmO0r2OgRBRP7hD4wq | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:710489 | 1 - First Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:710489 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.85 | 86.88 | 1637.688 | 1490.98 | 146.708 | 0.089582 | 94% | In Progress
2m6FhmO0r2OgRBRP7hD4yl | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Spish\X2\00E4\X0\ll:600 mm:710338 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - Spish\X2\00E4\X0\ll:600 mm:710338 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 291.5 | 291.5 | 148.47 | 143.03 | 0.49067 | 53% | In Progress
2m6FhmO0r2OgRBRP7hD4z$ | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:710290 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:710290 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 127.89 | 127.89 | 65.62 | 62.27 | 0.4869 | 54% | In Progress
2m6FhmO0r2OgRBRP7hD4zz | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:710288 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:710288 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 135.43 | 135.43 | 65.33 | 70.1 | 0.51761 | 50% | In Progress
2m6FhmO0r2OgRBRP7hD4zZ | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:710286 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:710286 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 130.02 | 130.02 | 59.75 | 70.27 | 0.54046 | 49% | In Progress
2m6FhmO0r2OgRBRP7hD4vE | IFCFURNISHINGELEMENT |  | Inredning - Nattduksbord:400x400:710563 | 1 - First Floor |  | Finishes | Furnishing | Inredning - Nattduksbord:400x400:710563 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 302.07 | 302.07 | 184.13 | 117.94 | 0.39044 | 61% | In Progress
2m6FhmO0r2OgRBRP7hD4zh | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:710278 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:710278 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 111.73 | 111.73 | 52.27 | 59.46 | 0.53218 | 50% | In Progress
2m6FhmO0r2OgRBRP7hD4zf | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:710276 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:710276 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 110.14 | 110.14 | 59.45 | 50.69 | 0.46023 | 57% | In Progress
2m6FhmO0r2OgRBRP7hD4_G | IFCFURNISHINGELEMENT |  | M_Table-Dining:0915 x 1830mm:710269 | 1 - First Floor |  | Finishes | Furnishing | M_Table-Dining:0915 x 1830mm:710269 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 534.08 | 534.08 | 289.49 | 244.59 | 0.45797 | 58% | In Progress
2m6FhmO0r2OgRBRP7hD4nY | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:710031 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:710031 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 190.07 | 0.0078166 | 0.01 | -0.0021834 | -0.27932 | 52% | In Progress
2m6FhmO0r2OgRBRP7hD4nZ | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - H\X2\00F6\X0\gsk\X2\00E5\X0\p:Ugn/Micro:710030 | 1 - First Floor |  | Finishes | Furnishing | K\X2\00F6\X0\k - H\X2\00F6\X0\gsk\X2\00E5\X0\p:Ugn/Micro:710030 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 309.59 | 309.59 | 164.24 | 145.35 | 0.46949 | 56% | In Progress
2m6FhmO0r2OgRBRP7hD4nW | IFCFLOWTERMINAL |  | K\X2\00F6\X0\k - Diskmaskin 6m:Diskmaskin:710029 | 1 - First Floor |  | MEP | MEP | K\X2\00F6\X0\k - Diskmaskin 6m:Diskmaskin:710029 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 950.44 | 950.44 | 641.08 | 309.36 | 0.32549 | 65% | In Progress
2m6FhmO0r2OgRBRP7hD4nX | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:710028 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:710028 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 204.12 | 0.0083945 | 0.01 | -0.0016055 | -0.19126 | 57% | In Progress
2m6FhmO0r2OgRBRP7hD4zX | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:710284 | 1 - First Floor |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:710284 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 117.57 | 117.57 | 60.46 | 57.11 | 0.48575 | 53% | In Progress
2m6FhmO0r2OgRBRP7hD4nc | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:710027 | 1 - First Floor |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:710027 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 161.34 | 0.0066351 | 0.01 | -0.0033649 | -0.50713 | 56% | In Progress
3ktY1kg3rAwgNBX_XWRS7h | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:944999 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:944999 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 508.26 | 5016.8798 | 2909.81 | 2107.0698 | 0.42 | 63% | In Progress
3ktY1kg3rAwgNBX_XWRS7g | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:944998 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:944998 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 497.08 | 3753.9941 | 2264.91 | 1489.0841 | 0.39667 | 64% | In Progress
3ktY1kg3rAwgNBX_XWRS7e | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:944996 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:944996 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 490.02 | 3700.6763 | 2332.79 | 1367.8863 | 0.36963 | 62% | In Progress
3ktY1kg3rAwgNBX_XWRS7l | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:944995 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:944995 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 484.45 | 3658.6112 | 2044.03 | 1614.5812 | 0.44131 | 55% | In Progress
3ktY1kg3rAwgNBX_XWRS7k | IFCWINDOW |  | BALANS Fixed Single Window:BALANS TRAPPHUS:944994 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS TRAPPHUS:944994 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 24.9655 | m² |  |  | 479.06 | 11959.9958 | 7097.73 | 4862.2658 | 0.40654 | 60% | In Progress
3ktY1kg3rAwgNBX_XWRS7V | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:944979 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:944979 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 522.21 | 5154.576 | 2621.54 | 2533.036 | 0.49142 | 54% | In Progress
3ktY1kg3rAwgNBX_XWRS7O | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:944980 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:944980 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 570.01 | 5626.3953 | 2817.34 | 2809.0553 | 0.49926 | 53% | In Progress
3ktY1kg3rAwgNBX_XWRS7L | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:944985 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:944985 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 509.55 | 3848.1687 | 2231.1 | 1617.0687 | 0.42022 | 57% | In Progress
3ktY1kg3rAwgNBX_XWRS7R | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:944983 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:944983 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 515.21 | 3890.9136 | 2114.28 | 1776.6336 | 0.45661 | 57% | In Progress
3ktY1kg3rAwgNBX_XWRS7K | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:944984 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:944984 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 485.21 | 4789.3603 | 2741.77 | 2047.5903 | 0.42753 | 56% | In Progress
3ktY1kg3rAwgNBX_XWRS7M | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:944986 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:944986 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 481.42 | 2519.5064 | 1479.19 | 1040.3164 | 0.4129 | 62% | In Progress
3ktY1kg3rAwgNBX_XWRS7N | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:944987 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:944987 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 488.51 | 3689.2727 | 2201.23 | 1488.0427 | 0.40334 | 62% | In Progress
3ktY1kg3rAwgNBX_XWRS7G | IFCWINDOW |  | BALANS Fixed Single Window:BALANS TRAPPHUS:944988 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS TRAPPHUS:944988 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 24.9655 | m² |  |  | 493.71 | 12325.741 | 6732.21 | 5593.531 | 0.45381 | 59% | In Progress
3ktY1kg3rAwgNBX_XWRS7a | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M BATHROOM:945000 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M BATHROOM:945000 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 2.4454 | m² |  |  | 543.33 | 1328.6398 | 799.88 | 528.7598 | 0.39797 | 61% | In Progress
3ktY1kg3rAwgNBX_XWRS7H | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:944989 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:944989 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 558.19 | 4215.5025 | 2327.39 | 1888.1125 | 0.4479 | 55% | In Progress
3ktY1kg3rAwgNBX_XWRS7I | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:944990 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:944990 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 548.63 | 2871.2492 | 1663.9 | 1207.3492 | 0.4205 | 57% | In Progress
3ktY1kg3rAwgNBX_XWRS7Q | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:944982 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:944982 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 551.94 | 4168.3019 | 2298.38 | 1869.9219 | 0.44861 | 57% | In Progress
3ktY1kg3rAwgNBX_XWRS7b | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:945001 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:945001 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 478.88 | 2506.2133 | 1525.22 | 980.9933 | 0.39142 | 59% | In Progress
3ktY1kg3rAwgNBX_XWRS7P | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:944981 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:944981 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 507.89 | 2658.0368 | 1376.72 | 1281.3168 | 0.48205 | 56% | In Progress
3ktY1kg3rAwgNBX_XWRS7d | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:945003 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:945003 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 539.18 | 5322.0817 | 2733.7 | 2588.3817 | 0.48635 | 55% | In Progress
3NlCHdPGXFUvkKekQzm3FY | IFCSLAB | FLOOR | Floor:Concrete-Domestic 425mm:982177 | 2 - Second Floor |  | Structure | Concrete | Floor:Concrete-Domestic 425mm:982177 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 818.8261 | m² |  |  | 90.02 | 73710.7289 | 58085.06 | 15625.6689 | 0.21199 | 80% | In Progress
3ktY1kg3rAwgNBX_XWRS7i | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:944992 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:944992 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 570.72 | 5633.4035 | 2963.19 | 2670.2135 | 0.474 | 56% | In Progress
3ktY1kg3rAwgNBX_XWRS7p | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:945023 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:945023 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 498.84 | 3767.2858 | 2152.81 | 1614.4758 | 0.42855 | 60% | In Progress
3ktY1kg3rAwgNBX_XWRS7o | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:945022 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:945022 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 539.79 | 2824.9851 | 1709.88 | 1115.1051 | 0.39473 | 61% | In Progress
3ktY1kg3rAwgNBX_XWRS7t | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M BATHROOM:945019 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M BATHROOM:945019 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 2.4454 | m² |  |  | 482.16 | 1179.0569 | 603.73 | 575.3269 | 0.48796 | 54% | In Progress
3ktY1kg3rAwgNBX_XWRS7s | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:945018 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:945018 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 501.53 | 2624.7518 | 1404.54 | 1220.2118 | 0.46489 | 52% | In Progress
3ktY1kg3rAwgNBX_XWRS7r | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:945017 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:945017 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 562.34 | 2943.0003 | 1572.92 | 1370.0803 | 0.46554 | 55% | In Progress
3ktY1kg3rAwgNBX_XWRS7c | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:945002 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:945002 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 544.53 | 4112.3409 | 2072.49 | 2039.8509 | 0.49603 | 53% | In Progress
3ktY1kg3rAwgNBX_XWRS7q | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:945016 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:945016 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 564.18 | 5568.8491 | 3257.73 | 2311.1191 | 0.41501 | 63% | In Progress
3ktY1kg3rAwgNBX_XWRS7J | IFCWINDOW |  | BALANS Fixed Single Window:BALANS TRAPPHUS:944991 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS TRAPPHUS:944991 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 24.9655 | m² |  |  | 508.76 | 12701.4725 | 6879.27 | 5822.2025 | 0.45839 | 54% | In Progress
3ktY1kg3rAwgNBX_XWRS7x | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:945015 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:945015 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 494.82 | 3736.9264 | 1877.72 | 1859.2064 | 0.49752 | 54% | In Progress
3ktY1kg3rAwgNBX_XWRS7W | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:945004 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:945004 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 505.03 | 3814.0333 | 2234.59 | 1579.4433 | 0.41411 | 59% | In Progress
3ktY1kg3rAwgNBX_XWRS7X | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:945005 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:945005 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 529.92 | 2773.3306 | 1641.17 | 1132.1606 | 0.40823 | 64% | In Progress
3ktY1kg3rAwgNBX_XWRS7Y | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:945006 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:945006 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 553.45 | 2896.4746 | 1481.79 | 1414.6846 | 0.48842 | 54% | In Progress
3ktY1kg3rAwgNBX_XWRS7z | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:945009 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:945009 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 523.29 | 2738.6326 | 1425.03 | 1313.6026 | 0.47966 | 55% | In Progress
3ktY1kg3rAwgNBX_XWRS7_ | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M BATHROOM:945010 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M BATHROOM:945010 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 2.4454 | m² |  |  | 550.31 | 1345.7084 | 766.59 | 579.1184 | 0.43034 | 57% | In Progress
3ktY1kg3rAwgNBX_XWRS7u | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:945012 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:945012 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 532.35 | 2786.048 | 1627.16 | 1158.888 | 0.41596 | 58% | In Progress
3ktY1kg3rAwgNBX_XWRS7v | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:945013 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:945013 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 567.22 | 4283.6979 | 2476.06 | 1807.6379 | 0.42198 | 61% | In Progress
3ktY1kg3rAwgNBX_XWRS7w | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:945014 | 2 - Second Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:945014 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 530.55 | 2776.6277 | 1503.59 | 1273.0377 | 0.45848 | 55% | In Progress
3ktY1kg3rAwgNBX_XWRV07 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940683 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940683 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 542.84 | 2840.9473 | 1474.97 | 1365.9773 | 0.48082 | 52% | In Progress
3ktY1kg3rAwgNBX_XWRV06 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940682 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940682 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 529.59 | 3999.5126 | 1983.17 | 2016.3426 | 0.50415 | 50% | In Progress
3ktY1kg3rAwgNBX_XWRV05 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS TRAPPHUS:940681 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS TRAPPHUS:940681 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 24.9655 | m² |  |  | 517.45 | 12918.4232 | 5832.97 | 7085.4532 | 0.54848 | 45% | In Progress
3ktY1kg3rAwgNBX_XWRV04 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940680 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940680 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 527.4 | 3982.9736 | 2125.12 | 1857.8536 | 0.46645 | 54% | In Progress
3ktY1kg3rAwgNBX_XWRV0B | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940679 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940679 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 510.28 | 2670.5449 | 1488.27 | 1182.2749 | 0.44271 | 54% | In Progress
3ktY1kg3rAwgNBX_XWRV0A | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940678 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940678 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 503.2 | 3800.2129 | 2079.05 | 1721.1629 | 0.45291 | 54% | In Progress
3ktY1kg3rAwgNBX_XWRV0E | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940674 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940674 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 510.38 | 2671.0682 | 1318.85 | 1352.2182 | 0.50625 | 52% | In Progress
3ktY1kg3rAwgNBX_XWRV08 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940676 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940676 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 531.92 | 4017.109 | 1977.75 | 2039.359 | 0.50767 | 52% | In Progress
3ktY1kg3rAwgNBX_XWRV0F | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940675 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940675 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 510.65 | 3856.476 | 1954.24 | 1902.236 | 0.49326 | 50% | In Progress
3ktY1kg3rAwgNBX_XWRV00 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS TRAPPHUS:940684 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS TRAPPHUS:940684 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 24.9655 | m² |  |  | 541.68 | 13523.3384 | 7289.75 | 6233.5884 | 0.46095 | 56% | In Progress
3ktY1kg3rAwgNBX_XWRV0D | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:940673 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:940673 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 499.63 | 4931.6957 | 2072.69 | 2859.0057 | 0.57972 | 45% | In Progress
3ktY1kg3rAwgNBX_XWRV0C | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:940672 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:940672 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 544.8 | 5377.555 | 2729.22 | 2648.335 | 0.49248 | 50% | In Progress
3NlCHdPGXFUvkKekQzm3Fi | IFCSLAB | FLOOR | Floor:Concrete-Domestic 425mm:982191 | 3 - Third Floor |  | Structure | Concrete | Floor:Concrete-Domestic 425mm:982191 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 818.8261 | m² |  |  | 86.27 | 70640.1309 | 45799.52 | 24840.6109 | 0.35165 | 68% | In Progress
3ktY1kg3rAwgNBX_XWRV09 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:940677 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:940677 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 509.61 | 5030.2052 | 2409.08 | 2621.1252 | 0.52108 | 48% | In Progress
3ktY1kg3rAwgNBX_XWRV0W | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940716 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940716 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 513.43 | 3877.4708 | 1936.16 | 1941.3108 | 0.50066 | 53% | In Progress
3ktY1kg3rAwgNBX_XWRV03 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS TRAPPHUS:940687 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS TRAPPHUS:940687 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 24.9655 | m² |  |  | 525.4 | 13116.8993 | 7008.57 | 6108.3293 | 0.46568 | 55% | In Progress
3ktY1kg3rAwgNBX_XWRV0S | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940688 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940688 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 487.08 | 3678.4732 | 1818.77 | 1859.7032 | 0.50556 | 53% | In Progress
3ktY1kg3rAwgNBX_XWRV0d | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940715 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940715 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 563.97 | 2951.5309 | 1304.07 | 1647.4609 | 0.55817 | 47% | In Progress
3ktY1kg3rAwgNBX_XWRV0a | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M BATHROOM:940712 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M BATHROOM:940712 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 2.4454 | m² |  |  | 506.8 | 1239.3106 | 617.67 | 621.6406 | 0.5016 | 53% | In Progress
3ktY1kg3rAwgNBX_XWRV0h | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940711 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940711 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 506.52 | 2650.8669 | 1164.07 | 1486.7969 | 0.56087 | 46% | In Progress
3ktY1kg3rAwgNBX_XWRV0g | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940710 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940710 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 528.79 | 2767.4167 | 1401.06 | 1366.3567 | 0.49373 | 50% | In Progress
3ktY1kg3rAwgNBX_XWRV0f | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:940709 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:940709 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 547.91 | 5408.2529 | 2651.17 | 2757.0829 | 0.50979 | 52% | In Progress
3ktY1kg3rAwgNBX_XWRV0e | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940708 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940708 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 552.24 | 4170.5675 | 2349.2 | 1821.3675 | 0.43672 | 55% | In Progress
3ktY1kg3rAwgNBX_XWRV0l | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940707 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940707 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 500.44 | 2619.0473 | 1170.81 | 1448.2373 | 0.55296 | 47% | In Progress
3ktY1kg3rAwgNBX_XWRV0k | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940706 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940706 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 556.68 | 4204.0988 | 2003.16 | 2200.9388 | 0.52352 | 49% | In Progress
3ktY1kg3rAwgNBX_XWRV0j | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940705 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940705 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 494.78 | 2589.4258 | 1141.66 | 1447.7658 | 0.55911 | 44% | In Progress
3ktY1kg3rAwgNBX_XWRV01 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:940685 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:940685 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 524.21 | 5174.3174 | 2309.39 | 2864.9274 | 0.55368 | 47% | In Progress
3ktY1kg3rAwgNBX_XWRV0J | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M BATHROOM:940703 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M BATHROOM:940703 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 2.4454 | m² |  |  | 553.92 | 1354.5362 | 732.73 | 621.8062 | 0.45905 | 54% | In Progress
3ktY1kg3rAwgNBX_XWRV0N | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940699 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940699 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 542.32 | 2838.2259 | 1438.38 | 1399.8459 | 0.49321 | 52% | In Progress
3ktY1kg3rAwgNBX_XWRV0M | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940698 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940698 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 505.87 | 2647.4652 | 1358.89 | 1288.5752 | 0.48672 | 53% | In Progress
3ktY1kg3rAwgNBX_XWRV0L | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940697 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940697 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 559.24 | 4223.4322 | 1776.51 | 2446.9222 | 0.57937 | 45% | In Progress
3ktY1kg3rAwgNBX_XWRV0K | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:940696 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:940696 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 540.82 | 5338.2697 | 2819.52 | 2518.7497 | 0.47183 | 54% | In Progress
3ktY1kg3rAwgNBX_XWRV0R | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940695 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940695 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 564.83 | 4265.6484 | 1939.64 | 2326.0084 | 0.54529 | 45% | In Progress
3ktY1kg3rAwgNBX_XWRV0Q | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940694 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940694 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 489.02 | 2559.2809 | 1168.37 | 1390.9109 | 0.54348 | 46% | In Progress
3ktY1kg3rAwgNBX_XWRV0O | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:940692 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:940692 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 483.84 | 4775.8374 | 2111.96 | 2663.8774 | 0.55778 | 47% | In Progress
3ktY1kg3rAwgNBX_XWRV0V | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940691 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940691 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 485.96 | 3670.0148 | 1855.51 | 1814.5048 | 0.49441 | 52% | In Progress
3ktY1kg3rAwgNBX_XWRV0T | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940689 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940689 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 543.05 | 4101.1638 | 1884.92 | 2216.2438 | 0.54039 | 45% | In Progress
3ktY1kg3rAwgNBX_XWRV0I | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940702 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940702 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 488.62 | 2557.1875 | 1296.98 | 1260.2075 | 0.49281 | 55% | In Progress
3ktY1kg3rAwgNBX_XWRV0P | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M BATHROOM:940693 | 3 - Third Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M BATHROOM:940693 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 2.4454 | m² |  |  | 496.03 | 1212.9741 | 624.4 | 588.5741 | 0.48523 | 52% | In Progress
3ktY1kg3rAwgNBX_XWRV1c | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940778 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940778 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 526.68 | 2756.3741 | 1119.56 | 1636.8141 | 0.59383 | 42% | In Progress
3ktY1kg3rAwgNBX_XWRV1R | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940759 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940759 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 541.55 | 2834.1961 | 1070.4 | 1763.7961 | 0.62233 | 39% | In Progress
3ktY1kg3rAwgNBX_XWRV1$ | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940787 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940787 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 529.42 | 2770.7138 | 1308.66 | 1462.0538 | 0.52768 | 46% | In Progress
3ktY1kg3rAwgNBX_XWRV1_ | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940786 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940786 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 567.66 | 2970.8425 | 1399.35 | 1571.4925 | 0.52897 | 46% | In Progress
3ktY1kg3rAwgNBX_XWRV1z | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:940785 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:940785 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 570.43 | 5630.541 | 2192.34 | 3438.201 | 0.61063 | 42% | In Progress
3ktY1kg3rAwgNBX_XWRV1y | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940784 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940784 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 557.84 | 4212.8593 | 1909.73 | 2303.1293 | 0.54669 | 47% | In Progress
3ktY1kg3rAwgNBX_XWRV1Z | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940783 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940783 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 571.71 | 2992.0381 | 1265.92 | 1726.1181 | 0.5769 | 45% | In Progress
3ktY1kg3rAwgNBX_XWRV1Y | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940782 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940782 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 487.1 | 3678.6242 | 1644.73 | 2033.8942 | 0.5529 | 43% | In Progress
3ktY1kg3rAwgNBX_XWRV1X | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940781 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940781 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 528.87 | 2767.8354 | 1243.14 | 1524.6954 | 0.55086 | 48% | In Progress
3ktY1kg3rAwgNBX_XWRV1d | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M BATHROOM:940779 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M BATHROOM:940779 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 2.4454 | m² |  |  | 485.78 | 1187.9091 | 456.64 | 731.2691 | 0.61559 | 39% | In Progress
3ktY1kg3rAwgNBX_XWRV1h | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940775 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940775 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 545.95 | 2857.2234 | 1094.37 | 1762.8534 | 0.61698 | 37% | In Progress
3ktY1kg3rAwgNBX_XWRV10 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:940748 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:940748 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 483.69 | 4774.3568 | 2147.44 | 2626.9168 | 0.55021 | 47% | In Progress
3ktY1kg3rAwgNBX_XWRV11 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:940749 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:940749 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 485.38 | 4791.0383 | 2149.93 | 2641.1083 | 0.55126 | 48% | In Progress
3ktY1kg3rAwgNBX_XWRV12 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940750 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940750 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 507.25 | 2654.6874 | 1114.78 | 1539.9074 | 0.58007 | 41% | In Progress
3ktY1kg3rAwgNBX_XWRV13 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940751 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940751 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 547.73 | 4136.5076 | 1518.57 | 2617.9376 | 0.63289 | 38% | In Progress
3ktY1kg3rAwgNBX_XWRV1S | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940752 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940752 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 529.08 | 3995.6611 | 1434.29 | 2561.3711 | 0.64104 | 37% | In Progress
3ktY1kg3rAwgNBX_XWRV1T | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:940753 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:940753 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 558.09 | 5508.7366 | 2246.41 | 3262.3266 | 0.59221 | 43% | In Progress
3ktY1kg3rAwgNBX_XWRV1U | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940754 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940754 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 530.03 | 4002.8356 | 1659.49 | 2343.3456 | 0.58542 | 44% | In Progress
3ktY1kg3rAwgNBX_XWRV1V | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940755 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940755 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 538 | 2815.6172 | 1200.57 | 1615.0472 | 0.5736 | 44% | In Progress
3ktY1kg3rAwgNBX_XWRV1k | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940770 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940770 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 547.99 | 2867.8997 | 1349.48 | 1518.4197 | 0.52945 | 46% | In Progress
3ktY1kg3rAwgNBX_XWRV1j | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M BATHROOM:940769 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M BATHROOM:940769 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 2.4454 | m² |  |  | 512.22 | 1252.5645 | 544.57 | 707.9945 | 0.56524 | 44% | In Progress
3ktY1kg3rAwgNBX_XWRV1i | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:940768 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:940768 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 485.15 | 4788.768 | 1954.62 | 2834.148 | 0.59183 | 41% | In Progress
3ktY1kg3rAwgNBX_XWRV1J | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940767 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940767 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 481.64 | 3637.3898 | 1548.48 | 2088.9098 | 0.57429 | 43% | In Progress
3ktY1kg3rAwgNBX_XWRV1H | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940765 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940765 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 527 | 3979.9527 | 1785.17 | 2194.7827 | 0.55146 | 48% | In Progress
3ktY1kg3rAwgNBX_XWRV1G | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940764 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940764 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 521.39 | 3937.5855 | 1822.69 | 2114.8955 | 0.5371 | 45% | In Progress
3ktY1kg3rAwgNBX_XWRV1u | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M BATHROOM:940788 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M BATHROOM:940788 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 2.4454 | m² |  |  | 513.03 | 1254.5453 | 501.1 | 753.4453 | 0.60057 | 41% | In Progress
3ktY1kg3rAwgNBX_XWRV1N | IFCWINDOW |  | BALANS Fixed Single Window:BALANS TRAPPHUS:940763 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS TRAPPHUS:940763 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 24.9655 | m² |  |  | 495.16 | 12361.9411 | 4511.85 | 7850.0911 | 0.63502 | 39% | In Progress
3ktY1kg3rAwgNBX_XWRV1K | IFCWINDOW |  | BALANS Fixed Single Window:BALANS TRAPPHUS:940760 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS TRAPPHUS:940760 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 24.9655 | m² |  |  | 498.66 | 12449.3205 | 6024.68 | 6424.6405 | 0.51606 | 48% | In Progress
3ktY1kg3rAwgNBX_XWRV1f | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940773 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940773 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 483.87 | 3654.231 | 1414.24 | 2239.991 | 0.61299 | 41% | In Progress
3ktY1kg3rAwgNBX_XWRV1Q | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940758 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940758 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 480.2 | 3626.5148 | 1725.43 | 1901.0848 | 0.52422 | 48% | In Progress
3ktY1kg3rAwgNBX_XWRV1P | IFCWINDOW |  | BALANS Fixed Single Window:BALANS TRAPPHUS:940757 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS TRAPPHUS:940757 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 24.9655 | m² |  |  | 567.18 | 14159.9599 | 5208.53 | 8951.4299 | 0.63216 | 39% | In Progress
3ktY1kg3rAwgNBX_XWRV1g | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940774 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940774 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 567.7 | 2971.0518 | 1375.58 | 1595.4718 | 0.53701 | 49% | In Progress
3ktY1kg3rAwgNBX_XWRV1O | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940756 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940756 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 532.75 | 4023.3773 | 1699.66 | 2323.7173 | 0.57755 | 44% | In Progress
3ktY1kg3rAwgNBX_XWRV1L | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:940761 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:940761 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 490.18 | 4838.4176 | 2073.33 | 2765.0876 | 0.57149 | 45% | In Progress
3ktY1kg3rAwgNBX_XWRV1l | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940771 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940771 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 537.32 | 4057.8903 | 1599.24 | 2458.6503 | 0.60589 | 39% | In Progress
3ktY1kg3rAwgNBX_XWRV1x | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940791 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940791 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 501.99 | 2627.1592 | 1157.09 | 1470.0692 | 0.55957 | 44% | In Progress
3ktY1kg3rAwgNBX_XWRV1e | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:940772 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:940772 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 524.01 | 5172.3433 | 1997.43 | 3174.9133 | 0.61382 | 40% | In Progress
3NlCHdPGXFUvkKekQzm3F_ | IFCSLAB | FLOOR | Floor:Concrete-Domestic 425mm:982205 | 4 - Fourth Floor |  | Structure | Concrete | Floor:Concrete-Domestic 425mm:982205 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 818.8261 | m² |  |  | 87.05 | 71278.8153 | 42742.53 | 28536.2853 | 0.40035 | 62% | In Progress
3ktY1kg3rAwgNBX_XWRV1q | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940792 | 4 - Fourth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940792 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 562.09 | 4244.9556 | 1575.6 | 2669.3556 | 0.62883 | 37% | In Progress
3ktY1kg3rAwgNBX_XWRV47 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940939 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940939 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 519.93 | 3926.5594 | 1453.67 | 2472.8894 | 0.62979 | 40% | In Progress
3ktY1kg3rAwgNBX_XWRV46 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940938 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940938 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 553.99 | 2899.3007 | 1042.39 | 1856.9107 | 0.64047 | 35% | In Progress
3ktY1kg3rAwgNBX_XWRV44 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M BATHROOM:940936 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M BATHROOM:940936 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 2.4454 | m² |  |  | 531.12 | 1298.7819 | 515.04 | 783.7419 | 0.60344 | 40% | In Progress
3ktY1kg3rAwgNBX_XWRV4B | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940935 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940935 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 495.66 | 2594.0312 | 977.32 | 1616.7112 | 0.62324 | 40% | In Progress
3ktY1kg3rAwgNBX_XWRV48 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940932 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940932 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 521.63 | 2729.945 | 985.22 | 1744.725 | 0.63911 | 35% | In Progress
3ktY1kg3rAwgNBX_XWRV7m | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940924 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940924 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 536 | 4047.9216 | 1546.62 | 2501.3016 | 0.61792 | 37% | In Progress
3ktY1kg3rAwgNBX_XWRV4E | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940930 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940930 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 570.95 | 4311.8672 | 1345.48 | 2966.3872 | 0.68796 | 32% | In Progress
3ktY1kg3rAwgNBX_XWRV4D | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:940929 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:940929 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 510.49 | 5038.8915 | 2154.2 | 2884.6915 | 0.57249 | 42% | In Progress
3ktY1kg3rAwgNBX_XWRV4C | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940928 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940928 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 481.47 | 3636.106 | 1204.42 | 2431.686 | 0.66876 | 33% | In Progress
3ktY1kg3rAwgNBX_XWRV41 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940941 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940941 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 557.58 | 4210.8957 | 1556.41 | 2654.4857 | 0.63039 | 38% | In Progress
3ktY1kg3rAwgNBX_XWRV7p | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940927 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940927 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 568.08 | 2973.0405 | 1165.21 | 1807.8305 | 0.60807 | 40% | In Progress
3ktY1kg3rAwgNBX_XWRV7o | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M BATHROOM:940926 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M BATHROOM:940926 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 2.4454 | m² |  |  | 483.13 | 1181.4289 | 425.16 | 756.2689 | 0.64013 | 36% | In Progress
3ktY1kg3rAwgNBX_XWRV7n | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:940925 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:940925 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 537.34 | 5303.9196 | 1823.47 | 3480.4496 | 0.6562 | 34% | In Progress
3ktY1kg3rAwgNBX_XWRV40 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940940 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940940 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 501.28 | 2623.4435 | 890.94 | 1732.5035 | 0.66039 | 34% | In Progress
3ktY1kg3rAwgNBX_XWRV4F | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940931 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940931 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 569.43 | 2980.1057 | 981.37 | 1998.7357 | 0.67069 | 32% | In Progress
3ktY1kg3rAwgNBX_XWRV7s | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940922 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940922 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 495.95 | 3745.4603 | 1158.28 | 2587.1803 | 0.69075 | 32% | In Progress
3ktY1kg3rAwgNBX_XWRV7q | IFCWINDOW |  | BALANS Fixed Single Window:BALANS TRAPPHUS:940920 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS TRAPPHUS:940920 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 24.9655 | m² |  |  | 502.07 | 12534.453 | 4878.39 | 7656.063 | 0.6108 | 38% | In Progress
3ktY1kg3rAwgNBX_XWRV4T | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M BATHROOM:940945 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M BATHROOM:940945 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 2.4454 | m² |  |  | 495.34 | 1211.2868 | 462.8 | 748.4868 | 0.61793 | 37% | In Progress
3ktY1kg3rAwgNBX_XWRV7c | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:940906 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:940906 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 562.85 | 5555.7211 | 1891.08 | 3664.6411 | 0.65962 | 33% | In Progress
3ktY1kg3rAwgNBX_XWRV7d | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940907 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940907 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 485 | 2538.2423 | 980.45 | 1557.7923 | 0.61373 | 40% | In Progress
3ktY1kg3rAwgNBX_XWRV7W | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940908 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940908 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 561.77 | 4242.539 | 1499.87 | 2742.669 | 0.64647 | 35% | In Progress
3ktY1kg3rAwgNBX_XWRV7X | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940909 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940909 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 483.33 | 3650.1528 | 1126.86 | 2523.2928 | 0.69128 | 32% | In Progress
3ktY1kg3rAwgNBX_XWRV7Y | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:940910 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:940910 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 512.99 | 5063.5682 | 1663.76 | 3399.8082 | 0.67143 | 35% | In Progress
3ktY1kg3rAwgNBX_XWRV7r | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940921 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940921 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 527.92 | 3986.9006 | 1467.51 | 2519.3906 | 0.63192 | 38% | In Progress
3ktY1kg3rAwgNBX_XWRV7Z | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940911 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940911 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 546.73 | 4128.9555 | 1563.29 | 2565.6655 | 0.62138 | 38% | In Progress
3ktY1kg3rAwgNBX_XWRV7z | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940913 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940913 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 564.3 | 4261.6458 | 1583.13 | 2678.5158 | 0.62852 | 39% | In Progress
3ktY1kg3rAwgNBX_XWRV7_ | IFCWINDOW |  | BALANS Fixed Single Window:BALANS TRAPPHUS:940914 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS TRAPPHUS:940914 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 24.9655 | m² |  |  | 549.83 | 13726.8076 | 5065.32 | 8661.4876 | 0.63099 | 37% | In Progress
3ktY1kg3rAwgNBX_XWRV7$ | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940915 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940915 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 486.21 | 3671.9029 | 1254.16 | 2417.7429 | 0.65844 | 35% | In Progress
3ktY1kg3rAwgNBX_XWRV7u | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940916 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940916 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 543.99 | 2846.9658 | 1125.93 | 1721.0358 | 0.60452 | 41% | In Progress
3ktY1kg3rAwgNBX_XWRV7v | IFCWINDOW |  | BALANS Fixed Single Window:BALANS TRAPPHUS:940917 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS TRAPPHUS:940917 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 24.9655 | m² |  |  | 504.81 | 12602.8586 | 4118.55 | 8484.3086 | 0.67321 | 35% | In Progress
3ktY1kg3rAwgNBX_XWRV7w | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:940918 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:940918 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 504.14 | 4976.2125 | 1820.52 | 3155.6925 | 0.63416 | 38% | In Progress
3ktY1kg3rAwgNBX_XWRV4S | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940944 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940944 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 518.92 | 2715.7622 | 868.91 | 1846.8522 | 0.68005 | 31% | In Progress
3ktY1kg3rAwgNBX_XWRV7b | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:940905 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:940905 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 570.19 | 5628.172 | 2247.72 | 3380.452 | 0.60063 | 39% | In Progress
3ktY1kg3rAwgNBX_XWRV7y | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940912 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940912 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 553.28 | 2895.5849 | 881.61 | 2013.9749 | 0.69553 | 33% | In Progress
3ktY1kg3rAwgNBX_XWRV4O | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940948 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940948 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 553.99 | 2899.3007 | 1035.86 | 1863.4407 | 0.64272 | 37% | In Progress
3NlCHdPGXFUvkKekQzm3EP | IFCSLAB | FLOOR | Floor:Concrete-Domestic 425mm:982234 | 5 - Fifth Floor |  | Structure | Concrete | Floor:Concrete-Domestic 425mm:982234 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 818.8261 | m² |  |  | 77.23 | 63237.9426 | 39346.19 | 23891.7526 | 0.37781 | 64% | In Progress
3ktY1kg3rAwgNBX_XWRV42 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 20M PRIVATE:940942 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 20M PRIVATE:940942 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 9.8707 | m² |  |  | 565.73 | 5584.1487 | 2192.36 | 3391.7887 | 0.6074 | 41% | In Progress
3ktY1kg3rAwgNBX_XWRV43 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M PRIVATE:940943 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M PRIVATE:940943 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 5.2335 | m² |  |  | 548.99 | 2873.1332 | 1101.55 | 1771.5832 | 0.6166 | 38% | In Progress
3ktY1kg3rAwgNBX_XWRV4P | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:940949 | 5 - Fifth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:940949 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 495.61 | 3742.8925 | 1343.92 | 2398.9725 | 0.64094 | 35% | In Progress
3ktY1kg3rAwgNBX_XWRSHc | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Roof Wall:945898 | 6 - Sixth Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Roof Wall:945898 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.15 | 88.4 | 1427.66 | 785 | 642.66 | 0.45015 | 54% | In Progress
0Um_J2ClP45uPRcRbJqhtx | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958576 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958576 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 1.7114 | m³ |  |  | 197.37 | 337.7862 | 40.51 | 297.2762 | 0.88007 | 13% | In Progress
0Um_J2ClP45uPRcRbJqhts | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958589 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958589 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 3.2213 | m³ |  |  | 196.99 | 634.5568 | 135.4 | 499.1568 | 0.78662 | 23% | In Progress
0Um_J2ClP45uPRcRbJqhrc | IFCSITE |  | M_Park Bench:1800mm:958701 | 6 - Sixth Floor |  | (Info Only) | — | M_Park Bench:1800mm:958701 |  | Custom_Pset | NetArea | 2.3396 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
0Um_J2ClP45uPRcRbJqhor | IFCSITE |  | M_Park Bench:1800mm:958782 | 6 - Sixth Floor |  | (Info Only) | — | M_Park Bench:1800mm:958782 |  | Custom_Pset | NetArea | 2.3396 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
0Um_J2ClP45uPRcRbJqhpS | IFCSITE |  | M_Park Bench:1800mm:958807 | 6 - Sixth Floor |  | (Info Only) | — | M_Park Bench:1800mm:958807 |  | Custom_Pset | NetArea | 2.3396 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
0Um_J2ClP45uPRcRbJqhmP | IFCSITE |  | M_Park Bench:1800mm:958866 | 6 - Sixth Floor |  | (Info Only) | — | M_Park Bench:1800mm:958866 |  | Custom_Pset | NetArea | 2.3396 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
0Um_J2ClP45uPRcRbJqhmO | IFCSITE |  | M_Park Bench:1800mm:958867 | 6 - Sixth Floor |  | (Info Only) | — | M_Park Bench:1800mm:958867 |  | Custom_Pset | NetArea | 2.3396 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
0Um_J2ClP45uPRcRbJqhta | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958575 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958575 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 1.7114 | m³ |  |  | 175.82 | 300.9047 | 51.96 | 248.9447 | 0.82732 | 17% | In Progress
0Um_J2ClP45uPRcRbJqhmV | IFCSITE |  | M_Park Bench:1800mm:958868 | 6 - Sixth Floor |  | (Info Only) | — | M_Park Bench:1800mm:958868 |  | Custom_Pset | NetArea | 2.3396 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
0Um_J2ClP45uPRcRbJqhvg | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:959457 | 6 - Sixth Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:959457 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.83 | 102.03 | 1921.2249 | 878.35 | 1042.8749 | 0.54282 | 49% | In Progress
0Um_J2ClP45uPRcRbJqhce | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:959523 | 6 - Sixth Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:959523 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.54 | 85.73 | 1589.4342 | 697.37 | 892.0642 | 0.56125 | 47% | In Progress
0Um_J2ClP45uPRcRbJqhdp | IFCDOOR |  | M_Single-Flush:Generic Door:959608 | 6 - Sixth Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:959608 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 380.1 | 1212.359 | 301.54 | 910.819 | 0.75128 | 25% | In Progress
0Um_J2ClP45uPRcRbJqhbu | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M BATHROOM:959731 | 6 - Sixth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M BATHROOM:959731 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 2.4454 | m² |  |  | 549.83 | 1344.5347 | 286.31 | 1058.2247 | 0.78706 | 22% | In Progress
0Um_J2ClP45uPRcRbJqhis | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 10M BATHROOM:960189 | 6 - Sixth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 10M BATHROOM:960189 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 2.4454 | m² |  |  | 479.98 | 1173.726 | 389.05 | 784.676 | 0.66853 | 32% | In Progress
0Um_J2ClP45uPRcRbJqhfw | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:960497 | 6 - Sixth Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:960497 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 11.26 | 99.47 | 1120.0322 | 559.27 | 560.7622 | 0.50067 | 50% | In Progress
2I1hX40SDEbAFJeZO_2_Pq | IFCSLAB | FLOOR | Floor:MockuUp Terrace:962748 | 6 - Sixth Floor |  | Structure | Concrete | Floor:MockuUp Terrace:962748 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 165.7822 | m² |  |  | 89.43 | 14825.9005 | 8138.19 | 6687.7105 | 0.45108 | 55% | In Progress
0Um_J2ClP45uPRcRbJqfyP | IFCRAILING | NOTDEFINED | Railing:Glass Panel - Bottom Fill:950930 | 6 - Sixth Floor |  | Finishes | Metal / Timber | Railing:Glass Panel - Bottom Fill:950930 | Balustrades, handrails, guard rails | Custom_Pset | Length | 47098.5242 | m |  |  | 254.18 | 11971502.8819 | 3609973.52 | 8361529.3619 | 0.69845 | 32% | In Progress
0Um_J2ClP45uPRcRbJqhxe | IFCWINDOW |  | BALANS Fixed Single Window:BALANS TRAPPHUS TOP:959331 | 6 - Sixth Floor |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS TRAPPHUS TOP:959331 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 15.3834 | m² |  |  | 480.57 | 7392.782 | 2314.72 | 5078.062 | 0.68689 | 31% | In Progress
0Um_J2ClP45uPRcRbJqhtf | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958562 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958562 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 1.7114 | m³ |  |  | 176.16 | 301.4866 | 60.79 | 240.6966 | 0.79837 | 20% | In Progress
0Um_J2ClP45uPRcRbJqhtg | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958561 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958561 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 1.7114 | m³ |  |  | 189.86 | 324.9333 | 51.31 | 273.6233 | 0.84209 | 16% | In Progress
0Um_J2ClP45uPRcRbJqhtV | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958548 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958548 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 1.7114 | m³ |  |  | 157.58 | 269.6881 | 53.38 | 216.3081 | 0.80207 | 21% | In Progress
3ktY1kg3rAwgNBX_XWRSMp | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Roof Wall:945983 | 6 - Sixth Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Roof Wall:945983 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.76 | 92.37 | 2009.9712 | 943.49 | 1066.4812 | 0.5306 | 48% | In Progress
0Um_J2ClP45uPRcRbJqf_I | IFCDOOR |  | M_Single-Flush:Generic Door:950809 | 6 - Sixth Floor |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:950809 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 366.93 | 1170.3522 | 360.42 | 809.9322 | 0.69204 | 31% | In Progress
0Um_J2ClP45uPRcRbJqe3T | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:957782 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:957782 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 2.4664 | m³ |  |  | 172.46 | 425.3467 | 94.93 | 330.4167 | 0.77682 | 22% | In Progress
0Um_J2ClP45uPRcRbJqeCt | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958140 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958140 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 2.4664 | m³ |  |  | 191.5 | 472.306 | 88.93 | 383.376 | 0.81171 | 19% | In Progress
0Um_J2ClP45uPRcRbJqeAt | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958268 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958268 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 2.4664 | m³ |  |  | 198.94 | 490.6557 | 92.68 | 397.9757 | 0.81111 | 20% | In Progress
0Um_J2ClP45uPRcRbJqeBQ | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958289 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958289 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 2.4664 | m³ |  |  | 193.43 | 477.0661 | 55.08 | 421.9861 | 0.88454 | 12% | In Progress
0Um_J2ClP45uPRcRbJqeBj | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958310 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958310 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 2.4664 | m³ |  |  | 165.78 | 408.8715 | 61.58 | 347.2915 | 0.84939 | 16% | In Progress
0Um_J2ClP45uPRcRbJqeBm | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958331 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958331 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 2.4664 | m³ |  |  | 159.74 | 393.9748 | 77.44 | 316.5348 | 0.80344 | 20% | In Progress
0Um_J2ClP45uPRcRbJqe8R | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958352 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958352 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 2.4664 | m³ |  |  | 200.14 | 493.6153 | 78.76 | 414.8553 | 0.84044 | 16% | In Progress
0Um_J2ClP45uPRcRbJqe8k | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958373 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958373 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 2.4664 | m³ |  |  | 192.82 | 475.5616 | 59.95 | 415.6116 | 0.87394 | 13% | In Progress
0Um_J2ClP45uPRcRbJqe8n | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958394 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958394 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 1.7114 | m³ |  |  | 172.82 | 295.7704 | 44.51 | 251.2604 | 0.84951 | 15% | In Progress
0Um_J2ClP45uPRcRbJqhsP | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958482 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958482 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 1.7114 | m³ |  |  | 159.55 | 273.0597 | 48.52 | 224.5397 | 0.82231 | 18% | In Progress
0Um_J2ClP45uPRcRbJqhsw | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958513 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958513 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 1.7114 | m³ |  |  | 195.86 | 335.2019 | 75.66 | 259.5419 | 0.77429 | 23% | In Progress
0Um_J2ClP45uPRcRbJqhsv | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958514 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958514 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 1.7114 | m³ |  |  | 174.87 | 299.2789 | 51.67 | 247.6089 | 0.82735 | 18% | In Progress
0Um_J2ClP45uPRcRbJqhsm | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958523 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958523 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 1.7114 | m³ |  |  | 153.22 | 262.2263 | 37.22 | 225.0063 | 0.85806 | 15% | In Progress
0Um_J2ClP45uPRcRbJqhst | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958524 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958524 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 1.7114 | m³ |  |  | 157.14 | 268.9351 | 44.7 | 224.2351 | 0.83379 | 16% | In Progress
0Um_J2ClP45uPRcRbJqhtE | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958533 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958533 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 1.7114 | m³ |  |  | 179.07 | 306.4669 | 65.92 | 240.5469 | 0.7849 | 21% | In Progress
0Um_J2ClP45uPRcRbJqhtD | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958534 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958534 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 1.7114 | m³ |  |  | 180.04 | 308.127 | 61.84 | 246.287 | 0.7993 | 21% | In Progress
3ktY1kg3rAwgNBX_XWRSTN | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Roof Wall:945627 | 6 - Sixth Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Roof Wall:945627 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.02 | 94.84 | 1424.4968 | 714.66 | 709.8368 | 0.49831 | 50% | In Progress
3ktY1kg3rAwgNBX_XWRSGL | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Roof Wall:945817 | 6 - Sixth Floor |  | Structure | Concrete / Masonry | Basic Wall:MockUp Roof Wall:945817 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.93 | 85.96 | 1885.1028 | 979.41 | 905.6928 | 0.48045 | 54% | In Progress
0Um_J2ClP45uPRcRbJqhtO | IFCBUILDINGELEMENTPROXY |  | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958547 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | Electrical_Solar-Panels_Soprema_Soprasolar_Fix-Evo-Tilt_EN:REC PE 260 HD:958547 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 1.7114 | m³ |  |  | 176.58 | 302.2054 | 56.8 | 245.4054 | 0.81205 | 19% | In Progress
0Um_J2ClP45uPRcRbJqf_0 | IFCDOOR |  | Swedoor_Interior_Door_SD4220_P65_EI60_Single-LeftRightOver_1.0:1990 mm (M10) x 2390 mm (M21) - EI60 - Right-handed:950795 | 6 - Sixth Floor |  | Finishes | Joinery / Metal | Swedoor_Interior_Door_SD4220_P65_EI60_Single-LeftRightOver_1.0:1990 mm (M10) x 2390 mm (M21) - EI60 - Right-handed:950795 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 9.6873 | m² |  |  | 363.97 | 3525.8715 | 1008.2 | 2517.6715 | 0.71406 | 31% | In Progress
0ifV7awIzBlRVUTYG1zp3l | IFCBUILDINGELEMENTPROXY |  | M_RPC Male:LaRon:976978 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | M_RPC Male:LaRon:976978 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 0.848 | 145.28 | 123.1974 | 26.16 | 97.0374 | 0.78766 | 23% | In Progress
0ifV7awIzBlRVUTYG1zp3a | IFCBUILDINGELEMENTPROXY |  | M_RPC Male:Dwayne:976985 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | M_RPC Male:Dwayne:976985 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 0.954 | 152.32 | 145.3133 | 33.72 | 111.5933 | 0.76795 | 24% | In Progress
0ifV7awIzBlRVUTYG1zp3s | IFCBUILDINGELEMENTPROXY |  | M_RPC Female:Cynthia:976971 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | M_RPC Female:Cynthia:976971 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.224 | 120.53 | 147.5287 | 25.67 | 121.8587 | 0.826 | 17% | In Progress
0ifV7awIzBlRVUTYG1zp3v | IFCBUILDINGELEMENTPROXY |  | M_RPC Female:Cathy:976964 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | M_RPC Female:Cathy:976964 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.799 | 128.84 | 231.7832 | 43.3 | 188.4832 | 0.81319 | 20% | In Progress
0ifV7awIzBlRVUTYG1zp29 | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Gray Birch - 3.1 Meters:976948 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Gray Birch - 3.1 Meters:976948 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.067 | 120.8 | 128.8936 | 22.31 | 106.5836 | 0.82691 | 17% | In Progress
0ifV7awIzBlRVUTYG1zp2K | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Gray Birch - 3.1 Meters:976937 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Gray Birch - 3.1 Meters:976937 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.39 | 160.62 | 223.2618 | 52.2 | 171.0618 | 0.76619 | 23% | In Progress
0ifV7awIzBlRVUTYG1zp7Z | IFCBUILDINGELEMENTPROXY |  | M_RPC Female:YinYin:977246 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | M_RPC Female:YinYin:977246 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.145 | 138.42 | 296.9109 | 35.12 | 261.7909 | 0.88172 | 12% | In Progress
0ifV7awIzBlRVUTYG1zp4Y | IFCSITE |  | M_Trash Can:M_Trash Can:977311 | 6 - Sixth Floor |  | (Info Only) | — | M_Trash Can:M_Trash Can:977311 |  | Custom_Pset | NetArea | 2.1332 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
0ifV7awIzBlRVUTYG1zp0F | IFCBUILDINGELEMENTPROXY |  | M_RPC Male:LaRon:977074 | 6 - Sixth Floor |  | Not Assigned | Not Assigned | M_RPC Male:LaRon:977074 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.876 | 150.87 | 283.0321 | 70.5 | 212.5321 | 0.75091 | 24% | In Progress
2fypDDb212M80XzLYYLej3 | IFCBUILDINGELEMENTPROXY |  | kappa_cycle_shelter_5_5m:Default:968306 | Level 1 |  | Not Assigned | Not Assigned | kappa_cycle_shelter_5_5m:Default:968306 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 26.3634 | m³ |  |  | 162.08 | 4272.9843 | 2625.62 | 1647.3643 | 0.38553 | 66% | In Progress
2I1hX40SDEbAFJeZO_2_Dy | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Largetooth Aspen - 7.6 Meters:964020 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Largetooth Aspen - 7.6 Meters:964020 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.088 | 159.03 | 332.0546 | 212.24 | 119.8146 | 0.36083 | 65% | In Progress
0cRoQU_sD5R8MkkMkeodFT | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:309817 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:309817 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.52 | 99.25 | 2135.86 | 2101.35 | 34.51 | 0.016157 | 100% | Completed
2I1hX40SDEbAFJeZO_2_Dt | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Largetooth Aspen - 7.6 Meters:964031 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Largetooth Aspen - 7.6 Meters:964031 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 0.899 | 145.43 | 130.7416 | 66.7 | 64.0416 | 0.48983 | 54% | In Progress
0cRoQU_sD5R8MkkMkeodzx | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:308895 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:308895 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.15 | 90.41 | 1460.1215 | 1531.09 | -70.9685 | -0.048605 | 100% | Completed
2I1hX40SDEbAFJeZO_2_C2 | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Largetooth Aspen - 7.6 Meters:964042 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Largetooth Aspen - 7.6 Meters:964042 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.213 | 131.23 | 290.412 | 176.74 | 113.672 | 0.39142 | 61% | In Progress
2I1hX40SDEbAFJeZO_2_CV | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Largetooth Aspen - 7.6 Meters:964055 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Largetooth Aspen - 7.6 Meters:964055 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.417 | 134.24 | 324.4581 | 202.09 | 122.3681 | 0.37715 | 63% | In Progress
0cRoQU_sD5R8MkkMkeodFw | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:309790 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:309790 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 20.94 | 91.19 | 1909.5186 | 1971.42 | -61.9014 | -0.032417 | 100% | Completed
2SEl4sI2X1JhqYqQydYuvW | IFCBUILDINGELEMENTPROXY |  | M_RPC Female:Cynthia:970107 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Female:Cynthia:970107 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.493 | 122.24 | 304.7443 | 184.46 | 120.2843 | 0.39471 | 59% | In Progress
0cRoQU_sD5R8MkkMkeod06 | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:309730 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:309730 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 24.65 | 98.98 | 2439.857 | 2105.19 | 334.667 | 0.13717 | 91% | In Progress
0cRoQU_sD5R8MkkMkeod1I | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:309686 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:309686 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.73 | 88.51 | 1923.3223 | 1996.32 | -72.9977 | -0.037954 | 100% | Completed
0cRoQU_sD5R8MkkMkeod2T | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:309625 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:309625 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 24.24 | 100.73 | 2441.6952 | 2336.68 | 105.0152 | 0.043009 | 93% | In Progress
2fypDDb212M80XzLYYLlJg | IFCDOOR |  | Swedoor_Interior_Door_SD4220_P65_EI60_Single-LeftRightOver_1.0:1990 mm (M10) x 2390 mm (M21) - EI60 - Left-handed:965083 | Level 1 |  | Finishes | Joinery / Metal | Swedoor_Interior_Door_SD4220_P65_EI60_Single-LeftRightOver_1.0:1990 mm (M10) x 2390 mm (M21) - EI60 - Left-handed:965083 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 9.6873 | m² |  |  | 379.34 | 3674.7646 | 2333.98 | 1340.7846 | 0.36486 | 68% | In Progress
0cRoQU_sD5R8MkkMkeod2W | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:309572 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:309572 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.22 | 97.58 | 1582.7476 | 1479.8 | 102.9476 | 0.065044 | 92% | In Progress
0cRoQU_sD5R8MkkMkeod5P | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:309437 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:309437 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.06 | 100.35 | 1912.671 | 1672.28 | 240.391 | 0.12568 | 95% | In Progress
0cRoQU_sD5R8MkkMkeod5q | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:309392 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:309392 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 22.56 | 93.12 | 2100.7872 | 2184.76 | -83.9728 | -0.039972 | 100% | Completed
0cRoQU_sD5R8MkkMkeod7U | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:309306 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:309306 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.7 | 100.03 | 2370.711 | 2061.12 | 309.591 | 0.13059 | 90% | In Progress
2fypDDb212M80XzLYYLlIb | IFCDOOR |  | Swedoor_Interior_Door_SD4220_P65_EI60_Single-LeftRightOver_1.0:1990 mm (M10) x 2390 mm (M21) - EI60 - Left-handed:965012 | Level 1 |  | Finishes | Joinery / Metal | Swedoor_Interior_Door_SD4220_P65_EI60_Single-LeftRightOver_1.0:1990 mm (M10) x 2390 mm (M21) - EI60 - Left-handed:965012 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 9.6873 | m² |  |  | 415.4 | 4024.0872 | 2677.28 | 1346.8072 | 0.33469 | 67% | In Progress
2SEl4sI2X1JhqYqQydYuuW | IFCBUILDINGELEMENTPROXY |  | M_RPC Male:Dwayne:970043 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Male:Dwayne:970043 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.502 | 149.9 | 225.1498 | 137.38 | 87.7698 | 0.38983 | 60% | In Progress
2SEl4sI2X1JhqYqQydYuun | IFCBUILDINGELEMENTPROXY |  | M_RPC Male:Jay:970026 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Male:Jay:970026 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.853 | 141.24 | 261.7177 | 145.7 | 116.0177 | 0.44329 | 57% | In Progress
0cRoQU_sD5R8MkkMkeod7v | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:309277 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:309277 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.42 | 95.64 | 1857.3288 | 1866.47 | -9.1412 | -0.0049217 | 100% | Completed
2SEl4sI2X1JhqYqQydYu$f | IFCBUILDINGELEMENTPROXY |  | M_RPC Male:LaRon:969970 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Male:LaRon:969970 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 0.893 | 120.49 | 107.5976 | 59.87 | 47.7276 | 0.44357 | 56% | In Progress
2SEl4sI2X1JhqYqQydYu$M | IFCBUILDINGELEMENTPROXY |  | M_RPC Male:Dwayne:969933 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Male:Dwayne:969933 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.385 | 121.39 | 289.5151 | 160.32 | 129.1951 | 0.44625 | 58% | In Progress
2SEl4sI2X1JhqYqQydYudQ | IFCBUILDINGELEMENTPROXY |  | M_RPC Female:YinYin:969409 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Female:YinYin:969409 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.609 | 150.54 | 242.2189 | 146.93 | 95.2889 | 0.3934 | 62% | In Progress
2SEl4sI2X1JhqYqQydYucp | IFCBUILDINGELEMENTPROXY |  | M_RPC Female:Tina:969384 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Female:Tina:969384 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.245 | 129.34 | 290.3683 | 152.88 | 137.4883 | 0.4735 | 57% | In Progress
0cRoQU_sD5R8MkkMkeod4L | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:309489 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:309489 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.18 | 100.01 | 1418.1418 | 1482.27 | -64.1282 | -0.04522 | 100% | Completed
2SEl4sI2X1JhqYqQydYuv1 | IFCBUILDINGELEMENTPROXY |  | M_RPC Female:Lisa:970074 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Female:Lisa:970074 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.275 | 157.15 | 200.3662 | 131.1 | 69.2662 | 0.3457 | 64% | In Progress
2SEl4sI2X1JhqYqQydYux7 | IFCBUILDINGELEMENTPROXY |  | M_RPC Male:Alex:970204 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Male:Alex:970204 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.131 | 159.95 | 340.8534 | 179.68 | 161.1734 | 0.47285 | 54% | In Progress
2I1hX40SDEbAFJeZO_2_DX | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Largetooth Aspen - 7.6 Meters:964009 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Largetooth Aspen - 7.6 Meters:964009 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.385 | 120.4 | 166.754 | 87.78 | 78.974 | 0.4736 | 56% | In Progress
2SEl4sI2X1JhqYqQydYurV | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:970308 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:970308 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.183 | 141.19 | 167.0278 | 96.19 | 70.8378 | 0.42411 | 57% | In Progress
2SEl4sI2X1JhqYqQydYvfU | IFCSITE |  | M_Park Bench:2400mm:973125 | Level 1 |  | (Info Only) | — | M_Park Bench:2400mm:973125 |  | Custom_Pset | NetArea | 3.0219 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
2SEl4sI2X1JhqYqQydYvfh | IFCSITE |  | M_Park Bench:2400mm:973168 | Level 1 |  | (Info Only) | — | M_Park Bench:2400mm:973168 |  | Custom_Pset | NetArea | 3.0219 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
2SEl4sI2X1JhqYqQydYvgl | IFCSITE |  | M_Park Bench:2400mm:973236 | Level 1 |  | (Info Only) | — | M_Park Bench:2400mm:973236 |  | Custom_Pset | NetArea | 3.0219 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
0ifV7awIzBlRVUTYG1zpXj | IFCSITE |  | M_Park Bench:2400mm:975056 | Level 1 |  | (Info Only) | — | M_Park Bench:2400mm:975056 |  | Custom_Pset | NetArea | 3.0219 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
0ifV7awIzBlRVUTYG1zpXi | IFCSITE |  | M_Park Bench:2400mm:975057 | Level 1 |  | (Info Only) | — | M_Park Bench:2400mm:975057 |  | Custom_Pset | NetArea | 3.0219 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
2SEl4sI2X1JhqYqQydYuwW | IFCBUILDINGELEMENTPROXY |  | M_RPC Male:Jay:970171 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Male:Jay:970171 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.548 | 139.67 | 216.2092 | 131.74 | 84.4692 | 0.39068 | 60% | In Progress
2SEl4sI2X1JhqYqQydYvhp | IFCBUILDINGELEMENTPROXY |  | M_RPC Female:Florence:973288 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Female:Florence:973288 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.92 | 134.94 | 259.0848 | 165.82 | 93.2648 | 0.35998 | 62% | In Progress
2SEl4sI2X1JhqYqQydYva7 | IFCBUILDINGELEMENTPROXY |  | M_RPC Female:Cynthia:973340 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Female:Cynthia:973340 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.918 | 146.86 | 281.6775 | 174.49 | 107.1875 | 0.38053 | 62% | In Progress
2SEl4sI2X1JhqYqQydYvzP | IFCSITE |  | M_Trash Can:M_Trash Can:973890 | Level 1 |  | (Info Only) | — | M_Trash Can:M_Trash Can:973890 |  | Custom_Pset | NetArea | 2.1332 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
2SEl4sI2X1JhqYqQydYv$9 | IFCSITE |  | M_Trash Can:M_Trash Can:974034 | Level 1 |  | (Info Only) | — | M_Trash Can:M_Trash Can:974034 |  | Custom_Pset | NetArea | 2.1332 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
0ifV7awIzBlRVUTYG1zpXl | IFCSITE |  | M_Trash Can:M_Trash Can:975058 | Level 1 |  | (Info Only) | — | M_Trash Can:M_Trash Can:975058 |  | Custom_Pset | NetArea | 2.1332 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
0cRoQU_sD5R8MkkMkeoduF | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:309227 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:309227 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.98 | 100.97 | 2421.2606 | 2277.47 | 143.7906 | 0.059387 | 92% | In Progress
0ifV7awIzBlRVUTYG1zpXk | IFCSITE |  | M_Trash Can:M_Trash Can:975059 | Level 1 |  | (Info Only) | — | M_Trash Can:M_Trash Can:975059 |  | Custom_Pset | NetArea | 2.1332 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
0ifV7awIzBlRVUTYG1zpXQ | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Kousa Dogwood - 3.0 Meters:975079 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Kousa Dogwood - 3.0 Meters:975079 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.66 | 147.66 | 245.1156 | 150.57 | 94.5456 | 0.38572 | 64% | In Progress
0ifV7awIzBlRVUTYG1zpcr | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Kousa Dogwood - 3.0 Meters:975112 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Kousa Dogwood - 3.0 Meters:975112 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.314 | 155.95 | 204.9183 | 114.9 | 90.0183 | 0.43929 | 60% | In Progress
0ifV7awIzBlRVUTYG1zpc8 | IFCBUILDINGELEMENTPROXY |  | M_RPC Male:Alex:975157 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Male:Alex:975157 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.865 | 128.2 | 239.093 | 135.07 | 104.023 | 0.43507 | 55% | In Progress
0ifV7awIzBlRVUTYG1zpd3 | IFCBUILDINGELEMENTPROXY |  | M_RPC Female:YinYin:975230 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Female:YinYin:975230 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.393 | 135.76 | 324.8737 | 207.69 | 117.1837 | 0.36071 | 66% | In Progress
0ifV7awIzBlRVUTYG1zpa9 | IFCBUILDINGELEMENTPROXY |  | M_RPC Male:Dwayne:975284 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Male:Dwayne:975284 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.418 | 160.65 | 227.8017 | 150.03 | 77.7717 | 0.3414 | 66% | In Progress
0ifV7awIzBlRVUTYG1zpbQ | IFCBUILDINGELEMENTPROXY |  | M_RPC Female:Cathy:975335 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Female:Cathy:975335 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.006 | 140.84 | 141.685 | 74.4 | 67.285 | 0.47489 | 57% | In Progress
0ifV7awIzBlRVUTYG1zpbL | IFCBUILDINGELEMENTPROXY |  | M_RPC Male:Alex:975336 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Male:Alex:975336 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.559 | 120.94 | 188.5455 | 109.64 | 78.9055 | 0.4185 | 62% | In Progress
0ifV7awIzBlRVUTYG1zpg5 | IFCBUILDINGELEMENTPROXY |  | M_RPC Male:Alex:975416 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Male:Alex:975416 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.021 | 127.97 | 258.6274 | 159.23 | 99.3974 | 0.38433 | 62% | In Progress
0ifV7awIzBlRVUTYG1zpg4 | IFCBUILDINGELEMENTPROXY |  | M_RPC Female:Florence:975417 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Female:Florence:975417 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.368 | 131.01 | 310.2317 | 180.16 | 130.0717 | 0.41927 | 56% | In Progress
0ifV7awIzBlRVUTYG1zpuT | IFCBUILDINGELEMENTPROXY |  | M_RPC Female:Cynthia:976544 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Female:Cynthia:976544 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.362 | 147.61 | 201.0448 | 117.17 | 83.8748 | 0.41719 | 59% | In Progress
0ifV7awIzBlRVUTYG1zpvk | IFCBUILDINGELEMENTPROXY |  | M_RPC Male:Alex:976595 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Male:Alex:976595 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.146 | 130.99 | 150.1145 | 93.35 | 56.7645 | 0.37814 | 62% | In Progress
2SEl4sI2X1JhqYqQydYuw7 | IFCBUILDINGELEMENTPROXY |  | M_RPC Male:Dwayne:970140 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Male:Dwayne:970140 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 0.804 | 135.98 | 109.3279 | 60.36 | 48.9679 | 0.4479 | 58% | In Progress
2SEl4sI2X1JhqYqQydYv$Y | IFCBUILDINGELEMENTPROXY |  | M_RPC Male:Dwayne:974073 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Male:Dwayne:974073 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.027 | 129.72 | 133.2224 | 78.3 | 54.9224 | 0.41226 | 61% | In Progress
2I1hX40SDEbAFJeZO_2_Ev | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Siberian Crab Apple - 6.1 Meters:963953 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Siberian Crab Apple - 6.1 Meters:963953 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.071 | 119.11 | 246.6768 | 133.87 | 112.8068 | 0.45731 | 54% | In Progress
0cRoQU_sD5R8MkkMkeodVk | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:310794 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:310794 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.86 | 93.07 | 1662.2302 | 1463.79 | 198.4402 | 0.11938 | 92% | In Progress
2I1hX40SDEbAFJeZO_2_EE | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Lombardy Poplar - 12.2 Meters:963910 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Lombardy Poplar - 12.2 Meters:963910 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.77 | 152.07 | 269.1639 | 160.06 | 109.1039 | 0.40534 | 61% | In Progress
0t7TVxPGL1fBrLXU9rUqSH | IFCSLAB | FLOOR | Floor:MockUp 300mm:923894 | Level 1 |  | Structure | Concrete | Floor:MockUp 300mm:923894 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 815.6581 | m² |  |  | 86.58 | 70619.6807 | 60389.08 | 10230.6007 | 0.14487 | 89% | In Progress
1k8pVOGqX51f_yJjFvAcSa | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:312482 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:312482 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.25 | 97.94 | 1395.645 | 1289.45 | 106.195 | 0.07609 | 94% | In Progress
1k8pVOGqX51f_yJjFvAcS4 | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:312450 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:312450 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.99 | 91.85 | 1560.5315 | 1475.31 | 85.2215 | 0.054611 | 94% | In Progress
0cRoQU_sD5R8MkkMkeodIb | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:310593 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:310593 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.49 | 88.53 | 1548.3897 | 1411.8 | 136.5897 | 0.088214 | 92% | In Progress
1k8pVOGqX51f_yJjFvAcVr | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:312435 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:312435 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.26 | 88.28 | 1258.8728 | 1195.01 | 63.8628 | 0.05073 | 92% | In Progress
1k8pVOGqX51f_yJjFvAcVO | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:312414 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:312414 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.71 | 99.12 | 2350.1352 | 2437.52 | -87.3848 | -0.037183 | 100% | Completed
1k8pVOGqX51f_yJjFvAcUe | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:312366 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:312366 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.03 | 96.23 | 2023.7169 | 2097.46 | -73.7431 | -0.036439 | 100% | Completed
1k8pVOGqX51f_yJjFvAc1t | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:312305 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:312305 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 25.71 | 86.27 | 2218.0017 | 2153.1 | 64.9017 | 0.029261 | 100% | Completed
1k8pVOGqX51f_yJjFvAc0s | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:312240 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:312240 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.5 | 90.01 | 2115.235 | 2110.85 | 4.385 | 0.0020731 | 100% | Completed
1k8pVOGqX51f_yJjFvAc3i | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:312170 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:312170 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 24.04 | 90.51 | 2175.8604 | 2133.72 | 42.1404 | 0.019367 | 100% | Completed
1k8pVOGqX51f_yJjFvAc5u | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:312062 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:312062 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.42 | 87.91 | 1443.4822 | 1418.08 | 25.4022 | 0.017598 | 100% | Completed
1k8pVOGqX51f_yJjFvAc54 | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:312002 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:312002 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.69 | 88.48 | 1565.2112 | 1371.25 | 193.9612 | 0.12392 | 92% | In Progress
1k8pVOGqX51f_yJjFvAc4P | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:311967 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:311967 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.83 | 97.11 | 1731.4713 | 1790.54 | -59.0687 | -0.034115 | 100% | Completed
0cRoQU_sD5R8MkkMkeodIA | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:310638 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:310638 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.9 | 96.76 | 1538.484 | 1476.68 | 61.804 | 0.040172 | 95% | In Progress
1k8pVOGqX51f_yJjFvAc65 | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:311811 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:311811 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.98 | 90.77 | 2176.6646 | 2269.5 | -92.8354 | -0.04265 | 100% | Completed
1k8pVOGqX51f_yJjFvAc9J | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:311765 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:311765 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.96 | 98.52 | 2163.4992 | 1975.32 | 188.1792 | 0.086979 | 94% | In Progress
1k8pVOGqX51f_yJjFvAc8g | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:311724 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:311724 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.3 | 90.66 | 2112.378 | 2098.39 | 13.988 | 0.0066219 | 100% | Completed
0cRoQU_sD5R8MkkMkeodVM | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:310834 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:310834 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.29 | 86.31 | 2010.1599 | 2091.99 | -81.8301 | -0.040708 | 100% | Completed
0cRoQU_sD5R8MkkMkeodUY | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:310854 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:310854 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 25.13 | 101.08 | 2540.1404 | 2216.72 | 323.4204 | 0.12732 | 93% | In Progress
0cRoQU_sD5R8MkkMkeodUx | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:310879 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:310879 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.97 | 87.53 | 1747.9741 | 1740.19 | 7.7841 | 0.0044532 | 100% | Completed
0cRoQU_sD5R8MkkMkeodUV | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:310907 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:310907 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 22.02 | 94.51 | 2081.1102 | 1782.01 | 299.1002 | 0.14372 | 92% | In Progress
0cRoQU_sD5R8MkkMkeodTg | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:310926 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:310926 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.56 | 98.39 | 1727.7284 | 1773.93 | -46.2016 | -0.026741 | 100% | Completed
0cRoQU_sD5R8MkkMkeodGm | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:310740 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:310740 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 24.11 | 97.38 | 2347.8318 | 2036.8 | 311.0318 | 0.13248 | 92% | In Progress
0cRoQU_sD5R8MkkMkeodJz | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:310553 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:310553 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.02 | 94.38 | 1795.1076 | 1801.27 | -6.1624 | -0.0034329 | 100% | Completed
0cRoQU_sD5R8MkkMkeodT3 | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:310951 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:310951 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.52 | 85.92 | 1419.3984 | 1465.33 | -45.9316 | -0.03236 | 100% | Completed
0cRoQU_sD5R8MkkMkeodOr | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:311249 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:311249 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.78 | 90.58 | 1972.8324 | 1679.49 | 293.3424 | 0.14869 | 91% | In Progress
0cRoQU_sD5R8MkkMkeoWdX | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:311301 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:311301 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.57 | 88.41 | 1553.3637 | 1370.18 | 183.1837 | 0.11793 | 95% | In Progress
0cRoQU_sD5R8MkkMkeoWcq | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:311376 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:311376 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.84 | 88.88 | 2118.8992 | 1906.77 | 212.1292 | 0.10011 | 90% | In Progress
0cRoQU_sD5R8MkkMkeoWcS | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:311416 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:311416 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.78 | 91.91 | 1726.0698 | 1676.61 | 49.4598 | 0.028655 | 100% | Completed
0cRoQU_sD5R8MkkMkeoWbM | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:311474 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:311474 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.81 | 89.14 | 1320.1634 | 1342.19 | -22.0266 | -0.016685 | 100% | Completed
1k8pVOGqX51f_yJjFvAcBx | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:311677 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:311677 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.79 | 87.19 | 1899.8701 | 1858.33 | 41.5401 | 0.021865 | 100% | Completed
0cRoQU_sD5R8MkkMkeodS1 | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:311013 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:311013 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.2 | 97.52 | 1482.304 | 1377.39 | 104.914 | 0.070778 | 94% | In Progress
2I1hX40SDEbAFJeZO_2_EP | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Lombardy Poplar - 12.2 Meters:963921 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Lombardy Poplar - 12.2 Meters:963921 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.874 | 158.37 | 296.7854 | 173.64 | 123.1454 | 0.41493 | 57% | In Progress
0cRoQU_sD5R8MkkMkeodKz | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:310489 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:310489 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.3 | 97.22 | 1487.466 | 1418.82 | 68.646 | 0.04615 | 95% | In Progress
0cRoQU_sD5R8MkkMkeodM9 | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:310381 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:310381 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.67 | 95.06 | 2059.9502 | 1771.25 | 288.7002 | 0.14015 | 93% | In Progress
2I1hX40SDEbAFJeZO_2_Fu | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Kousa Dogwood - 3.0 Meters:963888 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Kousa Dogwood - 3.0 Meters:963888 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.663 | 141.46 | 235.248 | 149.65 | 85.598 | 0.36386 | 64% | In Progress
2I1hX40SDEbAFJeZO_2_F7 | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Kousa Dogwood - 3.0 Meters:963855 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Kousa Dogwood - 3.0 Meters:963855 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.536 | 125.25 | 192.384 | 105.22 | 87.164 | 0.45307 | 56% | In Progress
2I1hX40SDEbAFJeZO_2_F8 | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Kousa Dogwood - 3.0 Meters:963840 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Kousa Dogwood - 3.0 Meters:963840 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.177 | 143.44 | 168.8289 | 99.44 | 69.3889 | 0.411 | 62% | In Progress
2I1hX40SDEbAFJeZO_2_8M | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963806 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963806 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.503 | 131.83 | 198.1405 | 119.84 | 78.3005 | 0.39518 | 64% | In Progress
2I1hX40SDEbAFJeZO_2_8R | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963795 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963795 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.869 | 121.06 | 226.2611 | 130.68 | 95.5811 | 0.42244 | 60% | In Progress
2I1hX40SDEbAFJeZO_2_80 | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963784 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963784 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.087 | 120.11 | 130.5596 | 68.79 | 61.7696 | 0.47311 | 57% | In Progress
2I1hX40SDEbAFJeZO_2_9r | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963773 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963773 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.262 | 124.01 | 280.5106 | 189.25 | 91.2606 | 0.32534 | 66% | In Progress
2I1hX40SDEbAFJeZO_2_9W | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963752 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963752 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.462 | 151.51 | 373.0176 | 208.79 | 164.2276 | 0.44027 | 56% | In Progress
2I1hX40SDEbAFJeZO_2_9L | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963741 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963741 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.406 | 145.1 | 349.1106 | 205.22 | 143.8906 | 0.41216 | 57% | In Progress
2I1hX40SDEbAFJeZO_2_9Q | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963730 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963730 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.165 | 133.38 | 155.3877 | 93.5 | 61.8877 | 0.39828 | 61% | In Progress
2I1hX40SDEbAFJeZO_2_99 | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963713 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963713 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.402 | 138.94 | 333.7339 | 213.12 | 120.6139 | 0.36141 | 62% | In Progress
2I1hX40SDEbAFJeZO_2_AY | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963690 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963690 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.216 | 123.38 | 150.0301 | 91.62 | 58.4101 | 0.38932 | 61% | In Progress
2I1hX40SDEbAFJeZO_2_AT | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963669 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963669 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 0.956 | 121.1 | 115.7716 | 68.24 | 47.5316 | 0.41056 | 57% | In Progress
2I1hX40SDEbAFJeZO_2_A2 | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963658 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963658 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.248 | 122.9 | 276.2792 | 142.8 | 133.4792 | 0.48313 | 55% | In Progress
2I1hX40SDEbAFJeZO_2_Bt | IFCBUILDINGELEMENTPROXY |  | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963647 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Tree - Deciduous:Fraxinus - 5.6 Meters:963647 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.949 | 138.78 | 270.4822 | 160.15 | 110.3322 | 0.40791 | 60% | In Progress
0cRoQU_sD5R8MkkMkeodCe | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:309964 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:309964 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 25.54 | 98.42 | 2513.6468 | 2134.57 | 379.0768 | 0.15081 | 91% | In Progress
0cRoQU_sD5R8MkkMkeodyq | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:308944 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:308944 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 20.67 | 94.24 | 1947.9408 | 1637.68 | 310.2608 | 0.15928 | 88% | In Progress
1k8pVOGqX51f_yJjFvAcT5 | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:312515 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:312515 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 20.58 | 94.53 | 1945.4274 | 1666.39 | 279.0374 | 0.14343 | 89% | In Progress
0HFJ4FEcn5UhECI1IyBq6E | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:918388 | Level 1 |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:918388 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 494.41 | 3733.83 | 2737.82 | 996.01 | 0.26675 | 74% | In Progress
0HFJ4FEcn5UhECI1IyBq0G | IFCDOOR |  | M_Single-Flush:Generic Door:918250 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:918250 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 366.69 | 1169.5867 | 828.31 | 341.2767 | 0.29179 | 72% | In Progress
0HFJ4FEcn5UhECI1IyBq10 | IFCDOOR |  | M_Single-Flush:Generic Door:918202 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:918202 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 372.33 | 1187.5759 | 798.07 | 389.5059 | 0.32798 | 67% | In Progress
0HFJ4FEcn5UhECI1IyBq1W | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:918170 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:918170 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.29 | 85.83 | 1655.6607 | 1467.23 | 188.4307 | 0.11381 | 94% | In Progress
0HFJ4FEcn5UhECI1IyBBqj | IFCWINDOW |  | BALANS Fixed Single Window:BALANS GROUND SMALL B:917463 | Level 1 |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS GROUND SMALL B:917463 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 2.4454 | m² |  |  | 481.66 | 1177.8342 | 736.23 | 441.6042 | 0.37493 | 65% | In Progress
0cRoQU_sD5R8MkkMkeodLp | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:310423 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:310423 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 20.2 | 87.03 | 1758.006 | 1601.76 | 156.246 | 0.088877 | 93% | In Progress
0HFJ4FEcn5UhECI1IyBBr8 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS GROUND SMALL A:917426 | Level 1 |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS GROUND SMALL A:917426 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 3.7877 | m² |  |  | 481.36 | 1823.2416 | 1186.01 | 637.2316 | 0.3495 | 69% | In Progress
0HFJ4FEcn5UhECI1IyBBXX | IFCWINDOW |  | BALANS Fixed Single Window:BALANS GROUND SMALL B:916123 | Level 1 |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS GROUND SMALL B:916123 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 2.4454 | m² |  |  | 500.32 | 1223.4647 | 830.8 | 392.6647 | 0.32094 | 67% | In Progress
0cRoQU_sD5R8MkkMkeodNN | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:310323 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:310323 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 22.32 | 94.97 | 2119.7304 | 2174.31 | -54.5796 | -0.025748 | 100% | Completed
0cRoQU_sD5R8MkkMkeod8d | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:310211 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:310211 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.28 | 85.89 | 1655.9592 | 1693.09 | -37.1308 | -0.022423 | 100% | Completed
0cRoQU_sD5R8MkkMkeodwY | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:309062 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:309062 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 25.68 | 96.01 | 2465.5368 | 2471.94 | -6.4032 | -0.0025971 | 100% | Completed
0cRoQU_sD5R8MkkMkeodxk | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:309002 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:309002 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.94 | 87.5 | 1394.75 | 1192.34 | 202.41 | 0.14512 | 89% | In Progress
0cRoQU_sD5R8MkkMkeodGL | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:310769 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:310769 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.05 | 86.14 | 1468.687 | 1481.75 | -13.063 | -0.0088943 | 100% | Completed
0HFJ4FEcn5UhECI1IyBBWG | IFCWINDOW |  | BALANS Fixed Single Window:BALANS GROUND SMALL A:916202 | Level 1 |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS GROUND SMALL A:916202 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 3.7877 | m² |  |  | 498.82 | 1889.3747 | 1236.65 | 652.7247 | 0.34547 | 65% | In Progress
0ifV7awIzBlRVUTYG1zpXo | IFCSITE |  | M_Park Bench:2400mm:975055 | Level 1 |  | (Info Only) | — | M_Park Bench:2400mm:975055 |  | Custom_Pset | NetArea | 3.0219 | m² |  |  | 0 | 0 | 0 | 0 | - | 0% | Not Started
1k8pVOGqX51f_yJjFvAcxy | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:314746 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:314746 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 22.9 | 86.92 | 1990.468 | 1861.13 | 129.338 | 0.064979 | 91% | In Progress
3pFbansyD0KOHFtJHrTsPR | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:889708 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:889708 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 202.25 | 0.0083176 | 0.01 | -0.0016824 | -0.20228 | 56% | In Progress
2BLn4xX2vF_gM9G5wfbUdp | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833247 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833247 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 137.49 | 137.49 | 78.33 | 59.16 | 0.43029 | 58% | In Progress
2BLn4xX2vF_gM9G5wfbUdD | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833249 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833249 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 137.5 | 137.5 | 71.22 | 66.28 | 0.48204 | 53% | In Progress
2BLn4xX2vF_gM9G5wfbUdF | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833251 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833251 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 117.52 | 117.52 | 71.25 | 46.27 | 0.39372 | 62% | In Progress
2BLn4xX2vF_gM9G5wfbUWw | IFCFURNISHINGELEMENT |  | M_Table-Dining:0915 x 1830mm:833302 | Level 1 |  | Finishes | Furnishing | M_Table-Dining:0915 x 1830mm:833302 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 522.12 | 522.12 | 260.7 | 261.42 | 0.50069 | 54% | In Progress
2BLn4xX2vF_gM9G5wfbUWn | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833309 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833309 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 108.25 | 108.25 | 59.31 | 48.94 | 0.4521 | 55% | In Progress
2BLn4xX2vF_gM9G5wfbUWp | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833311 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833311 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 119.02 | 119.02 | 76.72 | 42.3 | 0.3554 | 65% | In Progress
2BLn4xX2vF_gM9G5wfbUW9 | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833317 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833317 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 114.96 | 114.96 | 72.89 | 42.07 | 0.36595 | 64% | In Progress
2BLn4xX2vF_gM9G5wfbUWB | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833319 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833319 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 114.58 | 114.58 | 67.44 | 47.14 | 0.41142 | 58% | In Progress
2BLn4xX2vF_gM9G5wfbUdn | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833245 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833245 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 135.6 | 135.6 | 81.24 | 54.36 | 0.40088 | 58% | In Progress
2BLn4xX2vF_gM9G5wfbUW5 | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833321 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833321 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 125.16 | 125.16 | 70.95 | 54.21 | 0.43313 | 61% | In Progress
2BLn4xX2vF_gM9G5wfbUO2 | IFCFURNISHINGELEMENT |  | M_Table-Dining:0915 x 1830mm:833838 | Level 1 |  | Finishes | Furnishing | M_Table-Dining:0915 x 1830mm:833838 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 450.69 | 450.69 | 285.23 | 165.46 | 0.36713 | 65% | In Progress
2BLn4xX2vF_gM9G5wfbUOP | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833845 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833845 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 108.9 | 108.9 | 68.02 | 40.88 | 0.37539 | 61% | In Progress
2BLn4xX2vF_gM9G5wfbUOR | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833847 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833847 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 124.18 | 124.18 | 83.51 | 40.67 | 0.32751 | 65% | In Progress
2BLn4xX2vF_gM9G5wfbUOH | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833853 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833853 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 121.59 | 121.59 | 67.64 | 53.95 | 0.4437 | 56% | In Progress
2BLn4xX2vF_gM9G5wfbUOJ | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833855 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833855 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 132.26 | 132.26 | 83.66 | 48.6 | 0.36746 | 64% | In Progress
2BLn4xX2vF_gM9G5wfbUPj | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833857 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833857 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 125.88 | 125.88 | 77.89 | 47.99 | 0.38124 | 64% | In Progress
2BLn4xX2vF_gM9G5wfbUPl | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833859 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833859 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 137.99 | 137.99 | 84.23 | 53.76 | 0.38959 | 59% | In Progress
2BLn4xX2vF_gM9G5wfbUPg | IFCFURNISHINGELEMENT |  | M_Table-Dining:0915 x 1830mm:833862 | Level 1 |  | Finishes | Furnishing | M_Table-Dining:0915 x 1830mm:833862 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 458.88 | 458.88 | 254.74 | 204.14 | 0.44487 | 60% | In Progress
2BLn4xX2vF_gM9G5wfbUW7 | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833323 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833323 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 118.11 | 118.11 | 73.5 | 44.61 | 0.3777 | 64% | In Progress
2BLn4xX2vF_gM9G5wfbUPX | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833869 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833869 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 137.53 | 137.53 | 82.79 | 54.74 | 0.39802 | 63% | In Progress
2BLn4xX2vF_gM9G5wfbUdx | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833239 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833239 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 108.14 | 108.14 | 62.47 | 45.67 | 0.42232 | 58% | In Progress
2BLn4xX2vF_gM9G5wfbUdY | IFCFURNISHINGELEMENT |  | M_Table-Dining:0915 x 1830mm:833230 | Level 1 |  | Finishes | Furnishing | M_Table-Dining:0915 x 1830mm:833230 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 549.74 | 549.74 | 327.1 | 222.64 | 0.40499 | 62% | In Progress
114bk7BJ1AQATn9feajBs3 | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:315274 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:315274 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.49 | 87.38 | 1266.1362 | 1115.43 | 150.7062 | 0.11903 | 92% | In Progress
114bk7BJ1AQATn9feajBrC | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:315205 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:315205 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 20.15 | 97.33 | 1961.1995 | 2055.55 | -94.3505 | -0.048109 | 100% | Completed
1k8pVOGqX51f_yJjFvAcrl | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:315113 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:315113 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.92 | 88.42 | 1584.4864 | 1614.39 | -29.9036 | -0.018873 | 100% | Completed
1k8pVOGqX51f_yJjFvAcqu | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:315070 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:315070 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.6 | 101.35 | 2391.86 | 2031.9 | 359.96 | 0.15049 | 90% | In Progress
1k8pVOGqX51f_yJjFvAcqU | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:315032 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:315032 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.23 | 92.69 | 1411.6687 | 1313.5 | 98.1687 | 0.069541 | 94% | In Progress
1k8pVOGqX51f_yJjFvActY | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:314980 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:314980 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.82 | 95.43 | 1509.7026 | 1540.55 | -30.8474 | -0.020433 | 100% | Completed
1k8pVOGqX51f_yJjFvActC | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:314954 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:314954 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 24.03 | 92 | 2210.76 | 2251.79 | -41.03 | -0.018559 | 100% | Completed
1k8pVOGqX51f_yJjFvAcsf | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:314927 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:314927 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.77 | 85.55 | 1862.4235 | 1602.17 | 260.2535 | 0.13974 | 93% | In Progress
2BLn4xX2vF_gM9G5wfbUdv | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833237 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833237 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 118.89 | 118.89 | 68.78 | 50.11 | 0.42148 | 58% | In Progress
1k8pVOGqX51f_yJjFvAcvS | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:314842 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:314842 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 24.74 | 95.56 | 2364.1544 | 2098.35 | 265.8044 | 0.11243 | 91% | In Progress
0ducQKkW5EGQM9rQ5zdOcN | IFCDOOR |  | Swedoor_Interior_Door_SD4220_P65_EI60_Single-LeftRightOver_1.0:1990 mm (M10) x 2390 mm (M21) - EI60 - Right-handed:825005 | Level 1 |  | Finishes | Joinery / Metal | Swedoor_Interior_Door_SD4220_P65_EI60_Single-LeftRightOver_1.0:1990 mm (M10) x 2390 mm (M21) - EI60 - Right-handed:825005 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 9.6873 | m² |  |  | 410.95 | 3980.9789 | 2784.92 | 1196.0589 | 0.30044 | 73% | In Progress
0ducQKkW5EGQM9rQ5zdOTG | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:825450 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:825450 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 10.58 | 95.7 | 1012.506 | 989.4 | 23.106 | 0.022821 | 100% | Completed
0ducQKkW5EGQM9rQ5zdOVk | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:825556 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:825556 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 10.54 | 92.39 | 973.7906 | 921.8 | 51.9906 | 0.05339 | 93% | In Progress
0ducQKkW5EGQM9rQ5zdOOx | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:825601 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:825601 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.97 | 91.63 | 1463.3311 | 1523.48 | -60.1489 | -0.041104 | 100% | Completed
1k8pVOGqX51f_yJjFvAcuQ | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:314780 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:314780 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.94 | 102.15 | 1628.271 | 1461.36 | 166.911 | 0.10251 | 93% | In Progress
2BLn4xX2vF_gM9G5wfbVWH | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:829245 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:829245 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.753 | 137.63 | 241.2654 | 140.7 | 100.5654 | 0.41682 | 58% | In Progress
2BLn4xX2vF_gM9G5wfbV3X | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:831437 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:831437 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.098 | 145.72 | 305.7206 | 170.93 | 134.7906 | 0.44089 | 60% | In Progress
2BLn4xX2vF_gM9G5wfbUn3 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:832367 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:832367 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.08 | 95.25 | 1531.62 | 1466.18 | 65.44 | 0.042726 | 93% | In Progress
1k8pVOGqX51f_yJjFvAcv6 | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:314816 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:314816 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.36 | 86.65 | 1590.894 | 1381.27 | 209.624 | 0.13176 | 89% | In Progress
2BLn4xX2vF_gM9G5wfbUPZ | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833871 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833871 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 134.93 | 134.93 | 68.98 | 65.95 | 0.48877 | 53% | In Progress
2BLn4xX2vF_gM9G5wfbUPv | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833877 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833877 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 124.46 | 124.46 | 69.14 | 55.32 | 0.44448 | 56% | In Progress
2BLn4xX2vF_gM9G5wfbUPx | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833879 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833879 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 129.03 | 129.03 | 69.61 | 59.42 | 0.46051 | 54% | In Progress
2BLn4xX2vF_gM9G5wfbU9G | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834940 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834940 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 109.81 | 109.81 | 65.46 | 44.35 | 0.40388 | 61% | In Progress
2BLn4xX2vF_gM9G5wfbU9J | IFCFURNISHINGELEMENT |  | M_Table-Dining:0915 x 1830mm:834943 | Level 1 |  | Finishes | Furnishing | M_Table-Dining:0915 x 1830mm:834943 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 538.66 | 538.66 | 312.58 | 226.08 | 0.41971 | 61% | In Progress
2BLn4xX2vF_gM9G5wfbUAg | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834950 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834950 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 111.38 | 111.38 | 68.45 | 42.93 | 0.38544 | 61% | In Progress
2BLn4xX2vF_gM9G5wfbUAa | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834952 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834952 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 112.66 | 112.66 | 66.28 | 46.38 | 0.41168 | 59% | In Progress
2BLn4xX2vF_gM9G5wfbUAY | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834958 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834958 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 137.18 | 137.18 | 67.64 | 69.54 | 0.50693 | 53% | In Progress
2BLn4xX2vF_gM9G5wfbUAy | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834960 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834960 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 128.75 | 128.75 | 70.06 | 58.69 | 0.45584 | 54% | In Progress
2BLn4xX2vF_gM9G5wfbUA_ | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834962 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834962 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 134.55 | 134.55 | 81.92 | 52.63 | 0.39116 | 64% | In Progress
2BLn4xX2vF_gM9G5wfbUAu | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834964 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834964 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 109.55 | 109.55 | 65.73 | 43.82 | 0.4 | 58% | In Progress
2BLn4xX2vF_gM9G5wfbU9M | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834938 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834938 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 117.02 | 117.02 | 66.98 | 50.04 | 0.42762 | 56% | In Progress
2BLn4xX2vF_gM9G5wfbUBM | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:835066 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:835066 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.43 | 93.22 | 1531.6046 | 1363.44 | 168.1646 | 0.1098 | 91% | In Progress
2BLn4xX2vF_gM9G5wfbU5X | IFCDOOR |  | M_Single-Flush:Generic Door:835149 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:835149 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 375.4 | 1197.368 | 728.09 | 469.278 | 0.39192 | 65% | In Progress
2BLn4xX2vF_gM9G5wfbU7b | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:835273 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:835273 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 11.42 | 90.33 | 1031.5686 | 860.28 | 171.2886 | 0.16605 | 90% | In Progress
2BLn4xX2vF_gM9G5wfbU0j | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:835329 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:835329 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 10.54 | 98.5 | 1038.19 | 1042.82 | -4.63 | -0.0044597 | 100% | Completed
2BLn4xX2vF_gM9G5wfbPwA | IFCDOOR |  | M_Single-Flush:Generic Door:836006 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:836006 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 398.57 | 1271.2705 | 977.04 | 294.2305 | 0.23145 | 75% | In Progress
2BLn4xX2vF_gM9G5wfbPmS | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:836400 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:836400 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.06 | 98.27 | 1381.6762 | 1446.09 | -64.4138 | -0.04662 | 100% | Completed
2BLn4xX2vF_gM9G5wfbPnV | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:836467 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:836467 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 12.05 | 89.99 | 1084.3795 | 923.28 | 161.0995 | 0.14856 | 90% | In Progress
2BLn4xX2vF_gM9G5wfbPoz | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:836497 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:836497 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 12.33 | 100.25 | 1236.0825 | 1054.16 | 181.9225 | 0.14718 | 89% | In Progress
2BLn4xX2vF_gM9G5wfbPe3 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:836911 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:836911 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.85 | 101.13 | 1805.1705 | 1796.16 | 9.0105 | 0.0049915 | 100% | Completed
2BLn4xX2vF_gM9G5wfbU4T | IFCDOOR |  | M_Single-Flush:Generic Door:835121 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:835121 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 374.21 | 1193.5724 | 787.91 | 405.6624 | 0.33987 | 67% | In Progress
2BLn4xX2vF_gM9G5wfbU9K | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834936 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834936 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 122.56 | 122.56 | 70.63 | 51.93 | 0.42371 | 58% | In Progress
2BLn4xX2vF_gM9G5wfbU9Q | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834934 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834934 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 135.44 | 135.44 | 74.66 | 60.78 | 0.44876 | 58% | In Progress
2BLn4xX2vF_gM9G5wfbU9S | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834928 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834928 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 126 | 126 | 71.01 | 54.99 | 0.43643 | 56% | In Progress
2BLn4xX2vF_gM9G5wfbUPr | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833881 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833881 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 114.8 | 114.8 | 68.11 | 46.69 | 0.40671 | 63% | In Progress
2BLn4xX2vF_gM9G5wfbUPt | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:833883 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:833883 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 114.93 | 114.93 | 59.78 | 55.15 | 0.47986 | 53% | In Progress
2BLn4xX2vF_gM9G5wfbU8d | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:834827 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:834827 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.76 | 98.88 | 1657.2288 | 1680.13 | -22.9012 | -0.013819 | 100% | Completed
2BLn4xX2vF_gM9G5wfbU8R | IFCFURNISHINGELEMENT |  | M_Table-Dining:0915 x 1830mm:834871 | Level 1 |  | Finishes | Furnishing | M_Table-Dining:0915 x 1830mm:834871 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 560.22 | 560.22 | 358.53 | 201.69 | 0.36002 | 62% | In Progress
2BLn4xX2vF_gM9G5wfbU8I | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834878 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834878 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 119.39 | 119.39 | 59.84 | 59.55 | 0.49879 | 54% | In Progress
2BLn4xX2vF_gM9G5wfbU9i | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834880 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834880 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 110.53 | 110.53 | 70.88 | 39.65 | 0.35873 | 63% | In Progress
2BLn4xX2vF_gM9G5wfbU9g | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834886 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834886 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 130.16 | 130.16 | 67.03 | 63.13 | 0.48502 | 54% | In Progress
2BLn4xX2vF_gM9G5wfbU9a | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834888 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834888 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 112.16 | 112.16 | 58.86 | 53.3 | 0.47521 | 55% | In Progress
2BLn4xX2vF_gM9G5wfbU9c | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834890 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834890 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 119.29 | 119.29 | 74.49 | 44.8 | 0.37556 | 61% | In Progress
2BLn4xX2vF_gM9G5wfbU9W | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834892 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834892 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 120.59 | 120.59 | 70.29 | 50.3 | 0.41712 | 60% | In Progress
2BLn4xX2vF_gM9G5wfbU9Z | IFCFURNISHINGELEMENT |  | M_Table-Dining:0915 x 1830mm:834895 | Level 1 |  | Finishes | Furnishing | M_Table-Dining:0915 x 1830mm:834895 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 452.18 | 452.18 | 252.35 | 199.83 | 0.44193 | 55% | In Progress
2BLn4xX2vF_gM9G5wfbU9w | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834902 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834902 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 112.2 | 112.2 | 69.6 | 42.6 | 0.37968 | 63% | In Progress
2BLn4xX2vF_gM9G5wfbU9q | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834904 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834904 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 126.58 | 126.58 | 67.71 | 58.87 | 0.46508 | 56% | In Progress
2BLn4xX2vF_gM9G5wfbU9o | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834910 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834910 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 108.35 | 108.35 | 64.66 | 43.69 | 0.40323 | 64% | In Progress
2BLn4xX2vF_gM9G5wfbU9C | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834912 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834912 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 121.04 | 121.04 | 65.15 | 55.89 | 0.46175 | 55% | In Progress
2BLn4xX2vF_gM9G5wfbU9E | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834914 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834914 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 124.86 | 124.86 | 71.52 | 53.34 | 0.4272 | 56% | In Progress
2BLn4xX2vF_gM9G5wfbU98 | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834916 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834916 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 127.46 | 127.46 | 81.35 | 46.11 | 0.36176 | 63% | In Progress
2BLn4xX2vF_gM9G5wfbU9B | IFCFURNISHINGELEMENT |  | M_Table-Dining:0915 x 1830mm:834919 | Level 1 |  | Finishes | Furnishing | M_Table-Dining:0915 x 1830mm:834919 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 528.97 | 528.97 | 325.52 | 203.45 | 0.38462 | 60% | In Progress
2BLn4xX2vF_gM9G5wfbU92 | IFCFURNISHINGELEMENT |  | M_Chair-Breuer:M_Chair-Breuer:834926 | Level 1 |  | Finishes | Furnishing | M_Chair-Breuer:M_Chair-Breuer:834926 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 113.17 | 113.17 | 69.83 | 43.34 | 0.38296 | 61% | In Progress
114bk7BJ1AQATn9feajBst | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:315326 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:315326 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.67 | 86.69 | 1878.5723 | 1688.93 | 189.6423 | 0.10095 | 92% | In Progress
114bk7BJ1AQATn9feajA8O | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:315409 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:315409 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.27 | 95.82 | 2038.0914 | 2133.65 | -95.5586 | -0.046886 | 100% | Completed
114bk7BJ1AQATn9feajA9X | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:315496 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:315496 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.46 | 101.3 | 1869.998 | 1685.87 | 184.128 | 0.098464 | 92% | In Progress
114bk7BJ1AQATn9feajAAY | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:315563 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:315563 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.01 | 87.51 | 2013.6051 | 1816.88 | 196.7251 | 0.097698 | 92% | In Progress
3WghND$tL64OKayb9VHFRW | IFCBUILDINGELEMENTPROXY |  | M_RPC Male:Jay:482560 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Male:Jay:482560 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 2.077 | 139.4 | 289.5338 | 173.69 | 115.8438 | 0.4001 | 65% | In Progress
3WghND$tL64OKayb9VHFSn | IFCBUILDINGELEMENTPROXY |  | M_RPC Female:Florence:482513 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Female:Florence:482513 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.483 | 128.21 | 190.1354 | 108.83 | 81.3054 | 0.42762 | 62% | In Progress
1_jeQ1u6XFwed$AhVCoJi$ | IFCDOOR |  | Swedoor_Interior_Door_SD4220_P65_EI60_Single-LeftRightOver_1.0:1990 mm (M10) x 2390 mm (M21) - EI60 - Right-handed:473744 | Level 1 |  | Finishes | Joinery / Metal | Swedoor_Interior_Door_SD4220_P65_EI60_Single-LeftRightOver_1.0:1990 mm (M10) x 2390 mm (M21) - EI60 - Right-handed:473744 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 9.6873 | m² |  |  | 369.19 | 3576.439 | 2454.56 | 1121.879 | 0.31369 | 73% | In Progress
2V6UQJFc92sfDYeuDKgYFi | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior Ground Floor:451915 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior Ground Floor:451915 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 31.09 | 101.11 | 3143.5099 | 2665.01 | 478.4999 | 0.15222 | 92% | In Progress
2V6UQJFc92sfDYeuDKgYBU | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior Ground Floor:451705 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior Ground Floor:451705 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 34.24 | 89.07 | 3049.7568 | 2624.5 | 425.2568 | 0.13944 | 92% | In Progress
2V6UQJFc92sfDYeuDKgYAW | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior Ground Floor:451591 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior Ground Floor:451591 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 22.99 | 100.96 | 2321.0704 | 2023.86 | 297.2104 | 0.12805 | 93% | In Progress
1NL4ZXkFP2thNiMT9sECsi | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior Ground Floor:379538 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior Ground Floor:379538 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 22.22 | 91.79 | 2039.5738 | 2000.09 | 39.4838 | 0.019359 | 100% | Completed
1p5u6RKD9AXOYfaTdtdJom | IFCSLAB | FLOOR | Floor:Generic 150mm:318670 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:318670 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 319.8957 | m² |  |  | 91.72 | 29340.8361 | 27343.04 | 1997.7961 | 0.068089 | 92% | In Progress
0qPq0uZ5vABQlKT8FAVXQn | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior Ground Floor:525446 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior Ground Floor:525446 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.59 | 91.03 | 2147.3977 | 2052.44 | 94.9577 | 0.04422 | 93% | In Progress
1p5u6RKD9AXOYfaTdtdJp6 | IFCSLAB | FLOOR | Floor:Generic 150mm:318648 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:318648 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 687.4244 | m² |  |  | 80.28 | 55186.428 | 49689.56 | 5496.868 | 0.099605 | 92% | In Progress
1p5u6RKD9AXOYfaTdtdJla | IFCSLAB | FLOOR | Floor:Generic 150mm:318362 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:318362 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 272.4306 | m² |  |  | 88.91 | 24221.8052 | 23645.53 | 576.2752 | 0.023792 | 100% | Completed
1p5u6RKD9AXOYfaTdtdJlw | IFCSLAB | FLOOR | Floor:Generic 150mm:318340 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:318340 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 315.3513 | m² |  |  | 85.05 | 26820.632 | 27963.07 | -1142.438 | -0.042595 | 100% | Completed
1p5u6RKD9AXOYfaTdtdJi4 | IFCSLAB | FLOOR | Floor:Generic 150mm:318330 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:318330 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 220.4364 | m² |  |  | 77.6 | 17105.8619 | 16797.26 | 308.6019 | 0.018041 | 100% | Completed
1p5u6RKD9AXOYfaTdtdJiq | IFCSLAB | FLOOR | Floor:Generic 150mm:318282 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:318282 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 351.1437 | m² |  |  | 82.13 | 28839.4351 | 23880.67 | 4958.7651 | 0.17194 | 90% | In Progress
1p5u6RKD9AXOYfaTdtdJgC | IFCSLAB | FLOOR | Floor:Generic 150mm:318194 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:318194 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 130.1083 | m² |  |  | 90.9 | 11826.8464 | 10809.3 | 1017.5464 | 0.086037 | 93% | In Progress
1p5u6RKD9AXOYfaTdtdJgh | IFCSLAB | FLOOR | Floor:Generic 150mm:318165 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:318165 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 212.2408 | m² |  |  | 79.38 | 16847.6758 | 17150.22 | -302.5442 | -0.017958 | 100% | Completed
1p5u6RKD9AXOYfaTdtdJh7 | IFCSLAB | FLOOR | Floor:Generic 150mm:318137 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:318137 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 68.2683 | m² |  |  | 91.33 | 6234.9464 | 5773.55 | 461.3964 | 0.074002 | 90% | In Progress
1p5u6RKD9AXOYfaTdtdJhh | IFCSLAB | FLOOR | Floor:Generic 150mm:318101 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:318101 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 1208.7815 | m² |  |  | 83.71 | 101187.101 | 94891.68 | 6295.421 | 0.062216 | 92% | In Progress
1p5u6RKD9AXOYfaTdtdJpe | IFCSLAB | FLOOR | Floor:Generic 150mm:318614 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:318614 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 271.2952 | m² |  |  | 84.23 | 22851.1945 | 21497.68 | 1353.5145 | 0.059232 | 95% | In Progress
31F6eMknj99vYl9fb0Qb7F | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior Ground Floor:526491 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior Ground Floor:526491 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.41 | 88.38 | 2068.9758 | 1804.25 | 264.7258 | 0.12795 | 92% | In Progress
0MOEoDTm9EnO9yKsXjjie3 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior Ground Floor:581328 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior Ground Floor:581328 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 34.94 | 98.01 | 3424.4694 | 3473.34 | -48.8706 | -0.014271 | 100% | Completed
0MOEoDTm9EnO9yKsXjjiky | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Exterior Ground Floor:581487 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Exterior Ground Floor:581487 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.45 | 98.23 | 2303.4935 | 1997.25 | 306.2435 | 0.13295 | 94% | In Progress
3GzoWuxxn4WO8bCtw8H3Bx | IFCBUILDINGELEMENTPROXY |  | M_Electric Lift-4 person:1000 x 880mm:696894 | Level 1 |  | Not Assigned | Not Assigned | M_Electric Lift-4 person:1000 x 880mm:696894 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.46421 | m³ |  |  | 181.4 | 84.2077 | 46.74 | 37.4677 | 0.44494 | 54% | In Progress
3p6DR19bjD_PWb8lZMRTI1 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:735010 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:735010 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 10.94 | 96.67 | 1057.5698 | 1009.13 | 48.4398 | 0.045803 | 94% | In Progress
3p6DR19bjD_PWb8lZMRTIN | IFCDOOR |  | M_Single-Flush:Generic Door:735028 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:735028 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 372.05 | 1186.6829 | 911.41 | 275.2729 | 0.23197 | 74% | In Progress
3p6DR19bjD_PWb8lZMRTlD | IFCDOOR |  | Swedoor_Interior_Door_SD4220_P65_EI60_Single-LeftRightOver_1.0:1990 mm (M10) x 2390 mm (M21) - EI60 - Left-handed:735342 | Level 1 |  | Finishes | Joinery / Metal | Swedoor_Interior_Door_SD4220_P65_EI60_Single-LeftRightOver_1.0:1990 mm (M10) x 2390 mm (M21) - EI60 - Left-handed:735342 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 9.6873 | m² |  |  | 373.16 | 3614.8974 | 2545.88 | 1069.0174 | 0.29573 | 72% | In Progress
3p6DR19bjD_PWb8lZMRThy | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:735583 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:735583 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 12.66 | 91.55 | 1159.023 | 1049.36 | 109.663 | 0.094617 | 93% | In Progress
3p6DR19bjD_PWb8lZMRTs5 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:736806 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:736806 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 10.58 | 90.18 | 954.1044 | 939.41 | 14.6944 | 0.015401 | 100% | Completed
0Pw4h9cu11p8EzOFUdpSRt | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:738337 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:738337 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.87 | 99.94 | 1985.8078 | 1702.53 | 283.2778 | 0.14265 | 91% | In Progress
0Pw4h9cu11p8EzOFUdpSlP | IFCDOOR |  | Swedoor_Interior_Door_SD4220_P65_EI60_Single-LeftRightOver_1.0:1990 mm (M10) x 2390 mm (M21) - EI60 - Right-handed:739599 | Level 1 |  | Finishes | Joinery / Metal | Swedoor_Interior_Door_SD4220_P65_EI60_Single-LeftRightOver_1.0:1990 mm (M10) x 2390 mm (M21) - EI60 - Right-handed:739599 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 9.6873 | m² |  |  | 365.65 | 3542.1461 | 2326.44 | 1215.7061 | 0.34321 | 67% | In Progress
0Pw4h9cu11p8EzOFUdpSqt | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:741345 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:741345 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 11.27 | 99.72 | 1123.8444 | 1162.72 | -38.8756 | -0.034592 | 100% | Completed
0Pw4h9cu11p8EzOFUdpTBE | IFCDOOR |  | Swedoor_Interior_Door_SD4220_P65_EI60_Single-LeftRightOver_1.0:1990 mm (M10) x 2390 mm (M21) - EI60 - Right-handed:741400 | Level 1 |  | Finishes | Joinery / Metal | Swedoor_Interior_Door_SD4220_P65_EI60_Single-LeftRightOver_1.0:1990 mm (M10) x 2390 mm (M21) - EI60 - Right-handed:741400 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 9.6873 | m² |  |  | 353.5 | 3424.4459 | 2498.18 | 926.2659 | 0.27049 | 73% | In Progress
0xKelnDbLBsf$3TAffmU3X | IFCBUILDINGELEMENTPROXY |  | M_RPC Beetle:M_RPC Beetle:746861 | Level 1 |  | Not Assigned | Not Assigned | M_RPC Beetle:M_RPC Beetle:746861 | Catch-all. Check Name/Description/ObjectType for actual element type | Not Found | Not Found |  | m³ |  | 1.782 | 121.71 | 216.8872 | 123.63 | 93.2572 | 0.42998 | 59% | In Progress
0xKelnDbLBsf$3TAffmUEN | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:747035 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:747035 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.71 | 88.2 | 1562.022 | 1545.59 | 16.432 | 0.01052 | 100% | Completed
0xKelnDbLBsf$3TAffmU$u | IFCDOOR |  | Swedoor_Interior_Door_SD4220_P65_EI60_Single-LeftRightOver_1.0:1990 mm (M10) x 2390 mm (M21) - EI60 - Right-handed:748148 | Level 1 |  | Finishes | Joinery / Metal | Swedoor_Interior_Door_SD4220_P65_EI60_Single-LeftRightOver_1.0:1990 mm (M10) x 2390 mm (M21) - EI60 - Right-handed:748148 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 9.6873 | m² |  |  | 421.06 | 4078.9171 | 2766.41 | 1312.5071 | 0.32178 | 71% | In Progress
0xKelnDbLBsf$3TAffmUXs | IFCDOOR |  | Swedoor_Interior_Door_SD4220_P65_EI60_Single-LeftRightOver_1.0:1990 mm (M10) x 2390 mm (M21) - EI60 - Right-handed:749050 | Level 1 |  | Finishes | Joinery / Metal | Swedoor_Interior_Door_SD4220_P65_EI60_Single-LeftRightOver_1.0:1990 mm (M10) x 2390 mm (M21) - EI60 - Right-handed:749050 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 9.6873 | m² |  |  | 391.17 | 3789.3649 | 2440.82 | 1348.5449 | 0.35588 | 69% | In Progress
1ebX2H7F12su$wtPbeYAP4 | IFCWINDOW |  | BALANS Fixed Single Window:BALANS TRAPPHUS GROUND:773888 | Level 1 |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS TRAPPHUS GROUND:773888 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 10.5923 | m² |  |  | 523.13 | 5541.133 | 4192.8 | 1348.333 | 0.24333 | 75% | In Progress
1ebX2H7F12su$wtPbeYBaq | IFCWINDOW |  | BALANS Fixed Single Window:BALANS TRAPPHUS GROUND:774256 | Level 1 |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS TRAPPHUS GROUND:774256 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 10.5923 | m² |  |  | 557.6 | 5906.2485 | 4212.68 | 1693.5685 | 0.28674 | 69% | In Progress
0xyFL4ySP5TexORi78qE5c | IFCDOOR |  | M_Door-Overhead-Sectional:2400 x 2000mm:776665 | Level 1 |  | Finishes | Joinery / Metal | M_Door-Overhead-Sectional:2400 x 2000mm:776665 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 8.24 | m² |  |  | 411.71 | 3392.4904 | 2488.49 | 904.0004 | 0.26647 | 71% | In Progress
0xyFL4ySP5TexORi78qEFc | IFCWINDOW |  | BALANS Fixed Single Window:BALANS TRAPPHUS GROUND:777049 | Level 1 |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS TRAPPHUS GROUND:777049 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 10.5923 | m² |  |  | 564.75 | 5981.9832 | 4141.23 | 1840.7532 | 0.30772 | 75% | In Progress
0xyFL4ySP5TexORi78qEKF | IFCWINDOW |  | BALANS Fixed Single Window:BALANS GROUND SMALL A:777648 | Level 1 |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS GROUND SMALL A:777648 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 3.7877 | m² |  |  | 485.93 | 1840.5514 | 1234.63 | 605.9214 | 0.32921 | 69% | In Progress
1p5u6RKD9AXOYfaTdtdJhr | IFCSLAB | FLOOR | Floor:Generic 150mm:318091 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:318091 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 545.2677 | m² |  |  | 79 | 43076.146 | 37942.84 | 5133.306 | 0.11917 | 88% | In Progress
2BLn4xX2vF_gM9G5wfbPhn | IFCDOOR |  | M_Single-Flush:Generic Door:837085 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:837085 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 413.17 | 1317.8384 | 965.32 | 352.5184 | 0.2675 | 72% | In Progress
1p5u6RKD9AXOYfaTdtdJe3 | IFCSLAB | FLOOR | Floor:Generic 150mm:318077 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:318077 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 286.9266 | m² |  |  | 86.02 | 24681.4258 | 25685.03 | -1003.6042 | -0.040662 | 100% | Completed
1p5u6RKD9AXOYfaTdtdJeQ | IFCSLAB | FLOOR | Floor:Generic 150mm:318052 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:318052 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 320.0453 | m² |  |  | 78.47 | 25113.9522 | 20580.11 | 4533.8422 | 0.18053 | 89% | In Progress
0SYs3s__10NgRHjGtRj2ZW | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:316200 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:316200 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.86 | 102.04 | 2434.6744 | 2445.97 | -11.2956 | -0.0046395 | 100% | Completed
0SYs3s__10NgRHjGtRj2ZO | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:316176 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:316176 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 22.97 | 97.18 | 2232.2246 | 2280.13 | -47.9054 | -0.021461 | 100% | Completed
0SYs3s__10NgRHjGtRj2ax | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:316147 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:316147 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.29 | 102.4 | 1872.896 | 1622.3 | 250.596 | 0.1338 | 88% | In Progress
0SYs3s__10NgRHjGtRj2aH | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:316121 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:316121 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.7 | 101.75 | 1800.975 | 1885.26 | -84.285 | -0.0468 | 100% | Completed
0SYs3s__10NgRHjGtRj2bX | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:316073 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:316073 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 20.87 | 101.32 | 2114.5484 | 2178.65 | -64.1016 | -0.030315 | 100% | Completed
0SYs3s__10NgRHjGtRj2b4 | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:316044 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:316044 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 22.11 | 88.24 | 1950.9864 | 1774.89 | 176.0964 | 0.09026 | 89% | In Progress
0SYs3s__10NgRHjGtRj2cm | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:316024 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:316024 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.99 | 89.64 | 1971.1836 | 1821.47 | 149.7136 | 0.075951 | 91% | In Progress
0SYs3s__10NgRHjGtRj2cf | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:316001 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:316001 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.05 | 90.75 | 2091.7875 | 1842.63 | 249.1575 | 0.11911 | 94% | In Progress
0SYs3s__10NgRHjGtRj2X7 | IFCSLAB | FLOOR | Floor:Generic 150mm:316303 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:316303 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 353.0526 | m² |  |  | 77.26 | 27276.84 | 23137.1 | 4139.74 | 0.15177 | 88% | In Progress
0SYs3s__10NgRHjGtRj2d7 | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:315919 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:315919 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.79 | 102.46 | 2232.6034 | 2026.95 | 205.6534 | 0.092114 | 93% | In Progress
0SYs3s__10NgRHjGtRj2ei | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:315876 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:315876 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 20.26 | 93.2 | 1888.232 | 1682.64 | 205.592 | 0.10888 | 93% | In Progress
0SYs3s__10NgRHjGtRj2eO | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:315856 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:315856 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.22 | 94.32 | 2001.4704 | 1783.46 | 218.0104 | 0.10893 | 93% | In Progress
0SYs3s__10NgRHjGtRj2fJ | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:315803 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:315803 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.61 | 87.81 | 1721.9541 | 1773.33 | -51.3759 | -0.029836 | 100% | Completed
0SYs3s__10NgRHjGtRj2gr | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:315773 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:315773 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 24.28 | 92.17 | 2237.8876 | 1925.82 | 312.0676 | 0.13945 | 90% | In Progress
0SYs3s__10NgRHjGtRj2gk | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:315750 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:315750 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 24.24 | 89.18 | 2161.7232 | 1947.82 | 213.9032 | 0.09895 | 92% | In Progress
0SYs3s__10NgRHjGtRj2g3 | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:315723 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:315723 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 22.55 | 93.85 | 2116.3175 | 2004.81 | 111.5075 | 0.052689 | 95% | In Progress
114bk7BJ1AQATn9feajACD | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:315652 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:315652 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.7 | 89.03 | 1931.951 | 1679.57 | 252.381 | 0.13064 | 89% | In Progress
114bk7BJ1AQATn9feajABR | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:315602 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:315602 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.05 | 99.71 | 1500.6355 | 1460.83 | 39.8055 | 0.026526 | 100% | Completed
0SYs3s__10NgRHjGtRj2ez | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:315893 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:315893 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.71 | 98.09 | 1737.1739 | 1618.24 | 118.9339 | 0.068464 | 93% | In Progress
0SYs3s__10NgRHjGtRj2W7 | IFCSLAB | FLOOR | Floor:Generic 150mm:316367 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:316367 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 327.799 | m² |  |  | 86.51 | 28357.8876 | 25536.72 | 2821.1676 | 0.099484 | 90% | In Progress
0SYs3s__10NgRHjGtRj2WI | IFCSLAB | FLOOR | Floor:Generic 150mm:316378 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:316378 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 383.118 | m² |  |  | 88.89 | 34055.3596 | 34332.49 | -277.1304 | -0.0081376 | 100% | Completed
0SYs3s__10NgRHjGtRj2ub | IFCSLAB | FLOOR | Floor:Generic 150mm:316909 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:316909 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 464.3618 | m² |  |  | 83.09 | 38583.8249 | 37930.97 | 652.8549 | 0.01692 | 100% | Completed
0o1QfH3m18FQ$FuQf8VgdV | IFCSLAB | FLOOR | Floor:Generic 150mm:318004 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:318004 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 197.7583 | m² |  |  | 84.17 | 16645.3175 | 14664.29 | 1981.0275 | 0.11901 | 92% | In Progress
0o1QfH3m18FQ$FuQf8VgeR | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:317936 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:317936 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.54 | 98.14 | 1623.2356 | 1460.06 | 163.1756 | 0.10052 | 92% | In Progress
0o1QfH3m18FQ$FuQf8VgfQ | IFCSLAB | FLOOR | Floor:Generic 150mm:317873 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:317873 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 114.901 | m² |  |  | 88.8 | 10203.2068 | 8955.35 | 1247.8568 | 0.1223 | 90% | In Progress
0o1QfH3m18FQ$FuQf8VgfX | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:317834 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:317834 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 25.38 | 93.53 | 2373.7914 | 2075.91 | 297.8814 | 0.12549 | 95% | In Progress
0o1QfH3m18FQ$FuQf8Vgg3 | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:317800 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:317800 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.26 | 95.59 | 2032.2434 | 1916.14 | 116.1034 | 0.057131 | 91% | In Progress
0o1QfH3m18FQ$FuQf8Vgh_ | IFCSLAB | FLOOR | Floor:Generic 150mm:317717 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:317717 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 203.2689 | m² |  |  | 78.99 | 16056.2125 | 14509.91 | 1546.3025 | 0.096306 | 90% | In Progress
0o1QfH3m18FQ$FuQf8VgiA | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:317665 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:317665 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 22.96 | 101.33 | 2326.5368 | 2063.08 | 263.4568 | 0.11324 | 92% | In Progress
0o1QfH3m18FQ$FuQf8VgjP | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:317618 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:317618 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 25.86 | 92.4 | 2389.464 | 2389.35 | 0.114 | 4.7709e-05 | 100% | Completed
0o1QfH3m18FQ$FuQf8Vgjk | IFCSLAB | FLOOR | Floor:Generic 150mm:317573 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:317573 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 306.5504 | m² |  |  | 88.19 | 27034.68 | 26797.28 | 237.4 | 0.0087813 | 100% | Completed
0o1QfH3m18FQ$FuQf8VgGm | IFCSLAB | FLOOR | Floor:Generic 150mm:317403 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:317403 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 322.3307 | m² |  |  | 81.14 | 26153.9106 | 23613.32 | 2540.5906 | 0.09714 | 88% | In Progress
0o1QfH3m18FQ$FuQf8VgJQ | IFCSLAB | FLOOR | Floor:Generic 150mm:317233 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:317233 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 320.3001 | m² |  |  | 86.73 | 27779.6299 | 27550.44 | 229.1899 | 0.0082503 | 100% | Completed
0o1QfH3m18FQ$FuQf8VgJg | IFCSLAB | FLOOR | Floor:Generic 150mm:317185 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:317185 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 200.1538 | m² |  |  | 88 | 17613.5354 | 17534.28 | 79.2554 | 0.0044997 | 100% | Completed
0o1QfH3m18FQ$FuQf8VgK2 | IFCSLAB | FLOOR | Floor:Generic 150mm:317161 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:317161 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 53.3912 | m² |  |  | 78.74 | 4204.0224 | 3586.94 | 617.0824 | 0.14678 | 91% | In Progress
0o1QfH3m18FQ$FuQf8VgKi | IFCSLAB | FLOOR | Floor:Generic 150mm:317127 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:317127 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 121.7913 | m² |  |  | 82.4 | 10035.6008 | 8858.19 | 1177.4108 | 0.11732 | 93% | In Progress
0o1QfH3m18FQ$FuQf8VgL$ | IFCSLAB | FLOOR | Floor:Generic 150mm:317076 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:317076 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 142.7759 | m² |  |  | 88.91 | 12694.2016 | 13023.94 | -329.7384 | -0.025976 | 100% | Completed
0o1QfH3m18FQ$FuQf8VgMN | IFCSLAB | FLOOR | Floor:Generic 150mm:317052 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:317052 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 289.2668 | m² |  |  | 78.11 | 22594.6322 | 22975.8 | -381.1678 | -0.01687 | 100% | Completed
0SYs3s__10NgRHjGtRj2sh | IFCSLAB | FLOOR | Floor:Generic 150mm:317027 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:317027 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 352.2184 | m² |  |  | 90.74 | 31960.3011 | 28688.93 | 3271.3711 | 0.10236 | 89% | In Progress
0SYs3s__10NgRHjGtRj2t6 | IFCSLAB | FLOOR | Floor:Generic 150mm:316942 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:316942 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 142.982 | m² |  |  | 78.53 | 11228.3725 | 10415.7 | 812.6725 | 0.072377 | 94% | In Progress
0SYs3s__10NgRHjGtRj2u$ | IFCSLAB | FLOOR | Floor:Generic 150mm:316919 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:316919 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 282.3167 | m² |  |  | 81.65 | 23051.1623 | 19374.58 | 3676.5823 | 0.1595 | 89% | In Progress
1p5u6RKD9AXOYfaTdtdJeC | IFCSLAB | FLOOR | Floor:Generic 150mm:318066 | Level 1 |  | Structure | Concrete | Floor:Generic 150mm:318066 | Floors, roofs, ramps. Check PredefinedType: FLOOR/ROOF/LANDING | Custom_Pset | NetArea | 258.1715 | m² |  |  | 83.12 | 21459.2136 | 18818.3 | 2640.9136 | 0.12307 | 89% | In Progress
2BLn4xX2vF_gM9G5wfbPbw | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:837206 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:837206 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 10.5 | 86.95 | 912.975 | 853.13 | 59.845 | 0.065549 | 92% | In Progress
2BLn4xX2vF_gM9G5wfbPiL | IFCDOOR |  | M_Single-Flush:Generic Door:836665 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:836665 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 357.44 | 1140.0831 | 789.04 | 351.0431 | 0.30791 | 75% | In Progress
2BLn4xX2vF_gM9G5wfbPb7 | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:837227 | Level 1 |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:837227 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 252.21 | 252.21 | 145.84 | 106.37 | 0.42175 | 61% | In Progress
3pFbansyD0KOHFtJHrTtaZ | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:887828 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:887828 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 194.25 | 0.0079886 | 0.01 | -0.0020114 | -0.25179 | 57% | In Progress
3pFbansyD0KOHFtJHrTtaY | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:887829 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:887829 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 161.79 | 0.0066536 | 0.01 | -0.0033464 | -0.50294 | 64% | In Progress
3pFbansyD0KOHFtJHrTtde | IFCDOOR |  | M_Single-Flush:Generic Door:888031 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:888031 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 352.66 | 1124.8369 | 762.24 | 362.5969 | 0.32236 | 67% | In Progress
3pFbansyD0KOHFtJHrTtYf | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:888222 | Level 1 |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:888222 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 305.17 | 305.17 | 159.47 | 145.7 | 0.47744 | 54% | In Progress
3pFbansyD0KOHFtJHrTtYe | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888223 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888223 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 202.34 | 0.0083213 | 0.01 | -0.0016787 | -0.20174 | 56% | In Progress
3pFbansyD0KOHFtJHrTtYN | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888224 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888224 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 177.68 | 0.0073071 | 0.01 | -0.0026929 | -0.36853 | 56% | In Progress
3pFbansyD0KOHFtJHrTtYM | IFCBUILDINGELEMENTPROXY |  | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:888225 | Level 1 |  | Not Assigned | Not Assigned | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:888225 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.75803 | m³ |  |  | 171.4 | 129.9261 | 72.75 | 57.1761 | 0.44007 | 58% | In Progress
3pFbansyD0KOHFtJHrTtYL | IFCBUILDINGELEMENTPROXY |  | Handtag kylfrys:Handtag kyl/frys:888226 | Level 1 |  | Not Assigned | Not Assigned | Handtag kylfrys:Handtag kyl/frys:888226 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 2.5901e-05 | m³ |  |  | 175.41 | 0.0045433 | 0 | 0.0045433 | 1 | 58% | In Progress
3pFbansyD0KOHFtJHrTtaa | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:887827 | Level 1 |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:887827 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 316.77 | 316.77 | 168.28 | 148.49 | 0.46876 | 55% | In Progress
3pFbansyD0KOHFtJHrTtYK | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Vinkel:K\X2\00F6\X0\k vinkel:888227 | Level 1 |  | Finishes | Furnishing | K\X2\00F6\X0\k - Vinkel:K\X2\00F6\X0\k vinkel:888227 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 317.98 | 317.98 | 167.24 | 150.74 | 0.47405 | 54% | In Progress
3pFbansyD0KOHFtJHrTtYI | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888229 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888229 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 205.99 | 0.0084714 | 0.01 | -0.0015286 | -0.18045 | 54% | In Progress
3pFbansyD0KOHFtJHrTtYH | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888230 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888230 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 165.16 | 0.0067922 | 0.01 | -0.0032078 | -0.47227 | 66% | In Progress
3pFbansyD0KOHFtJHrTtYG | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - H\X2\00F6\X0\gsk\X2\00E5\X0\p:Ugn/Micro:888231 | Level 1 |  | Finishes | Furnishing | K\X2\00F6\X0\k - H\X2\00F6\X0\gsk\X2\00E5\X0\p:Ugn/Micro:888231 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 268.52 | 268.52 | 163.74 | 104.78 | 0.39021 | 62% | In Progress
3pFbansyD0KOHFtJHrTtYV | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888232 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888232 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 204.78 | 0.0084216 | 0.01 | -0.0015784 | -0.18742 | 61% | In Progress
3pFbansyD0KOHFtJHrTtYU | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:888233 | Level 1 |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:600 mm:888233 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 261.75 | 261.75 | 167.67 | 94.08 | 0.35943 | 62% | In Progress
3pFbansyD0KOHFtJHrTtYT | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888234 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888234 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 176.89 | 0.0072746 | 0.01 | -0.0027254 | -0.37464 | 60% | In Progress
3pFbansyD0KOHFtJHrTtYS | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888235 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888235 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 195.51 | 0.0080404 | 0.01 | -0.0019596 | -0.24372 | 65% | In Progress
3pFbansyD0KOHFtJHrTtYR | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:888236 | Level 1 |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:888236 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 288.85 | 288.85 | 170.87 | 117.98 | 0.40845 | 61% | In Progress
3pFbansyD0KOHFtJHrTtYJ | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Diskb\X2\00E4\X0\nk med sk\X2\00E5\X0\p:H14H:888228 | Level 1 |  | Finishes | Furnishing | K\X2\00F6\X0\k - Diskb\X2\00E4\X0\nk med sk\X2\00E5\X0\p:H14H:888228 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 313.83 | 313.83 | 158.24 | 155.59 | 0.49578 | 53% | In Progress
3pFbansyD0KOHFtJHrTtxg | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:887773 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:887773 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 175.92 | 0.0072347 | 0.01 | -0.0027653 | -0.38222 | 57% | In Progress
3pFbansyD0KOHFtJHrTtxh | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:887772 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:887772 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 205.11 | 0.0084352 | 0.01 | -0.0015648 | -0.18551 | 65% | In Progress
3pFbansyD0KOHFtJHrTtxi | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:887771 | Level 1 |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:887771 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 269.27 | 269.27 | 157.68 | 111.59 | 0.41442 | 57% | In Progress
2BLn4xX2vF_gM9G5wfbPb6 | IFCFURNISHINGELEMENT |  | Inredning - Skrivbord:1600x800:837226 | Level 1 |  | Finishes | Furnishing | Inredning - Skrivbord:1600x800:837226 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 308.83 | 308.83 | 179.69 | 129.14 | 0.41816 | 56% | In Progress
3pFbansyD0KOHFtJHrTulz | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:884426 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:884426 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 11.24 | 89.39 | 1004.7436 | 1010.7 | -5.9564 | -0.0059283 | 100% | Completed
3pFbansyD0KOHFtJHrTulG | IFCDOOR |  | M_Single-Flush:Generic Door:884455 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:884455 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 397.61 | 1268.2085 | 778.59 | 489.6185 | 0.38607 | 65% | In Progress
3pFbansyD0KOHFtJHrTugv | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:884622 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:884622 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.78 | 102.11 | 1611.2958 | 1673.05 | -61.7542 | -0.038326 | 100% | Completed
3pFbansyD0KOHFtJHrTugD | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:884666 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:884666 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.57 | 91.69 | 1794.3733 | 1678.05 | 116.3233 | 0.064827 | 92% | In Progress
3pFbansyD0KOHFtJHrTuhb | IFCDOOR |  | M_Single-Flush:Generic Door:884690 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:884690 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 371.44 | 1184.7372 | 815.12 | 369.6172 | 0.31198 | 68% | In Progress
3pFbansyD0KOHFtJHrTtNs | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:884929 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:884929 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.02 | 98.14 | 1866.6228 | 1769.83 | 96.7928 | 0.051855 | 94% | In Progress
3pFbansyD0KOHFtJHrTtNC | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:884987 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:884987 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 12.29 | 89.08 | 1094.7932 | 974.67 | 120.1232 | 0.10972 | 93% | In Progress
3pFbansyD0KOHFtJHrTtSF | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:885304 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:885304 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 11.56 | 96.78 | 1118.7768 | 1114.42 | 4.3568 | 0.0038943 | 100% | Completed
3pFbansyD0KOHFtJHrTtO7 | IFCDOOR |  | M_Single-Flush:Generic Door:885552 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:885552 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 409.02 | 1304.6016 | 784.55 | 520.0516 | 0.39863 | 63% | In Progress
3pFbansyD0KOHFtJHrTt4i | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:885787 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:885787 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 12.04 | 98.77 | 1189.1908 | 1097.36 | 91.8308 | 0.077221 | 90% | In Progress
3pFbansyD0KOHFtJHrTt4G | IFCDOOR |  | M_Single-Flush:Generic Door:885799 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:885799 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 399.88 | 1275.4489 | 812.11 | 463.3389 | 0.36328 | 69% | In Progress
3pFbansyD0KOHFtJHrTtDE | IFCDOOR |  | M_Single-Flush:Generic Door:886393 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:886393 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 390.84 | 1246.6151 | 847.41 | 399.2051 | 0.32023 | 70% | In Progress
3pFbansyD0KOHFtJHrTtyw | IFCFLOWTERMINAL |  | M_Lavatory - Vanity:760 mmx455 mm - Private:887309 | Level 1 |  | MEP | MEP | M_Lavatory - Vanity:760 mmx455 mm - Private:887309 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 868.11 | 868.11 | 623.52 | 244.59 | 0.28175 | 76% | In Progress
3pFbansyD0KOHFtJHrTtyv | IFCFLOWTERMINAL |  | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:887310 | Level 1 |  | MEP | MEP | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:887310 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 921.54 | 921.54 | 659.48 | 262.06 | 0.28437 | 76% | In Progress
3pFbansyD0KOHFtJHrTt_f | IFCFLOWTERMINAL |  | M_Lavatory - Vanity:760 mmx455 mm - Private:887454 | Level 1 |  | MEP | MEP | M_Lavatory - Vanity:760 mmx455 mm - Private:887454 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 958.09 | 958.09 | 648.59 | 309.5 | 0.32304 | 69% | In Progress
3pFbansyD0KOHFtJHrTt_e | IFCFLOWTERMINAL |  | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:887455 | Level 1 |  | MEP | MEP | M_Water Closet - Flush Tank:Public - Flushing Greater than 6.1 Lpf:887455 |  | Default (count unit) | 1 per element | 1 | ea |  |  | 982.66 | 982.66 | 762.42 | 220.24 | 0.22413 | 75% | In Progress
3pFbansyD0KOHFtJHrTtwh | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:887708 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:887708 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.89 | 96.17 | 1816.6513 | 1833.88 | -17.2287 | -0.0094838 | 100% | Completed
3pFbansyD0KOHFtJHrTtwA | IFCDOOR |  | M_Single-Flush:Generic Door:887741 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:887741 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 353.01 | 1125.9533 | 721.23 | 404.7233 | 0.35945 | 67% | In Progress
3pFbansyD0KOHFtJHrTtYQ | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888237 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888237 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 154.32 | 0.0063464 | 0.01 | -0.0036536 | -0.57569 | 60% | In Progress
3pFbansyD0KOHFtJHrTuY0 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:884151 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:884151 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 10.48 | 98.04 | 1027.4592 | 906.14 | 121.3192 | 0.11808 | 88% | In Progress
3pFbansyD0KOHFtJHrTtYP | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888238 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888238 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 156.76 | 0.0064468 | 0.01 | -0.0035532 | -0.55116 | 63% | In Progress
3pFbansyD0KOHFtJHrTtZC | IFCFURNISHINGELEMENT |  | fixa_bench:Colour - (Light grey-S2000-N):888315 | Level 1 |  | Finishes | Furnishing | fixa_bench:Colour - (Light grey-S2000-N):888315 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 306.88 | 306.88 | 172.11 | 134.77 | 0.43916 | 56% | In Progress
3pFbansyD0KOHFtJHrTsKN | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888864 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888864 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 202.41 | 0.0083241 | 0.01 | -0.0016759 | -0.20133 | 56% | In Progress
3pFbansyD0KOHFtJHrTsKM | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:888865 | Level 1 |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:888865 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 273.6 | 273.6 | 159.41 | 114.19 | 0.41736 | 62% | In Progress
3pFbansyD0KOHFtJHrTsKL | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888866 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888866 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 154.74 | 0.0063637 | 0.01 | -0.0036363 | -0.57141 | 60% | In Progress
3pFbansyD0KOHFtJHrTsKK | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888867 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888867 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 203.88 | 0.0083846 | 0.01 | -0.0016154 | -0.19266 | 64% | In Progress
3pFbansyD0KOHFtJHrTsVP | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:889582 | Level 1 |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:889582 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 270.6 | 270.6 | 147.5 | 123.1 | 0.45492 | 58% | In Progress
3pFbansyD0KOHFtJHrTsVO | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:889583 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:889583 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 196.97 | 0.0081004 | 0.01 | -0.0018996 | -0.23451 | 63% | In Progress
3pFbansyD0KOHFtJHrTsV7 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:889584 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:889584 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 153.45 | 0.0063106 | 0.01 | -0.0036894 | -0.58462 | 55% | In Progress
3pFbansyD0KOHFtJHrTsV6 | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:889585 | Level 1 |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:889585 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 320.25 | 320.25 | 175.87 | 144.38 | 0.45084 | 57% | In Progress
3pFbansyD0KOHFtJHrTsKe | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888863 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888863 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 159.29 | 0.0065508 | 0.01 | -0.0034492 | -0.52653 | 60% | In Progress
3pFbansyD0KOHFtJHrTsV5 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:889586 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:889586 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 179.25 | 0.0073717 | 0.01 | -0.0026283 | -0.35654 | 59% | In Progress
3pFbansyD0KOHFtJHrTsPJ | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:889700 | Level 1 |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:889700 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 271.79 | 271.79 | 156.73 | 115.06 | 0.42334 | 56% | In Progress
3pFbansyD0KOHFtJHrTsPI | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:889701 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:889701 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 155.91 | 0.0064118 | 0.01 | -0.0035882 | -0.55962 | 60% | In Progress
3pFbansyD0KOHFtJHrTsPH | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:889702 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:889702 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 159.68 | 0.0065669 | 0.01 | -0.0034331 | -0.5228 | 63% | In Progress
3pFbansyD0KOHFtJHrTsPG | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:889703 | Level 1 |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:889703 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 254.98 | 254.98 | 159.89 | 95.09 | 0.37293 | 64% | In Progress
3pFbansyD0KOHFtJHrTsPV | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:889704 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:889704 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 188.48 | 0.0077513 | 0.01 | -0.0022487 | -0.29011 | 56% | In Progress
3pFbansyD0KOHFtJHrTsPU | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:889705 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:889705 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 204.56 | 0.0084126 | 0.01 | -0.0015874 | -0.1887 | 55% | In Progress
3pFbansyD0KOHFtJHrTsPT | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:889706 | Level 1 |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:889706 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 263.5 | 263.5 | 162.3 | 101.2 | 0.38406 | 62% | In Progress
3pFbansyD0KOHFtJHrTsPS | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:889707 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:889707 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 189.5 | 0.0077932 | 0.01 | -0.0022068 | -0.28317 | 60% | In Progress
3pFbansyD0KOHFtJHrTsV4 | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:889587 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:889587 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 160.54 | 0.0066022 | 0.01 | -0.0033978 | -0.51464 | 60% | In Progress
3pFbansyD0KOHFtJHrTsKf | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:888862 | Level 1 |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:888862 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 318.81 | 318.81 | 199.59 | 119.22 | 0.37395 | 63% | In Progress
3pFbansyD0KOHFtJHrTtfJ | IFCDOOR |  | M_Single-Flush:Generic Door:888676 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:888676 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 397.83 | 1268.9102 | 831.02 | 437.8902 | 0.34509 | 66% | In Progress
3pFbansyD0KOHFtJHrTtfb | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:888658 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:888658 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.68 | 101.21 | 1991.8128 | 1733.02 | 258.7928 | 0.12993 | 92% | In Progress
3pFbansyD0KOHFtJHrTtiK | IFCFURNISHINGELEMENT |  | fixa_bench:Colour - (Light grey-S2000-N):888355 | Level 1 |  | Finishes | Furnishing | fixa_bench:Colour - (Light grey-S2000-N):888355 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 292.71 | 292.71 | 161.3 | 131.41 | 0.44894 | 56% | In Progress
3pFbansyD0KOHFtJHrTtiJ | IFCFURNISHINGELEMENT |  | fixa_bench:Colour - (Light grey-S2000-N):888356 | Level 1 |  | Finishes | Furnishing | fixa_bench:Colour - (Light grey-S2000-N):888356 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 290.42 | 290.42 | 176.76 | 113.66 | 0.39136 | 63% | In Progress
3pFbansyD0KOHFtJHrTtjW | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:888407 | Level 1 |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:888407 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 283.33 | 283.33 | 174.2 | 109.13 | 0.38517 | 62% | In Progress
3pFbansyD0KOHFtJHrTtjl | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888408 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888408 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 162.41 | 0.0066791 | 0.01 | -0.0033209 | -0.4972 | 63% | In Progress
3pFbansyD0KOHFtJHrTtjk | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888409 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888409 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 191.43 | 0.0078726 | 0.01 | -0.0021274 | -0.27023 | 64% | In Progress
3pFbansyD0KOHFtJHrTtjj | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:888410 | Level 1 |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:888410 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 290.06 | 290.06 | 148.45 | 141.61 | 0.48821 | 55% | In Progress
3pFbansyD0KOHFtJHrTtji | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888411 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888411 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 192.69 | 0.0079244 | 0.01 | -0.0020756 | -0.26193 | 58% | In Progress
3pFbansyD0KOHFtJHrTtjh | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888412 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888412 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 186.68 | 0.0076772 | 0.01 | -0.0023228 | -0.30255 | 61% | In Progress
3pFbansyD0KOHFtJHrTtlJ | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:888548 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:888548 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.63 | 94.91 | 1863.0833 | 1766 | 97.0833 | 0.052109 | 92% | In Progress
3pFbansyD0KOHFtJHrTtez | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:888586 | Level 1 |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:888586 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 289.25 | 289.25 | 168.68 | 120.57 | 0.41684 | 60% | In Progress
3pFbansyD0KOHFtJHrTtey | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888587 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888587 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 153.28 | 0.0063037 | 0.01 | -0.0036963 | -0.58638 | 65% | In Progress
3pFbansyD0KOHFtJHrTtex | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888588 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888588 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 189.58 | 0.0077965 | 0.01 | -0.0022035 | -0.28263 | 63% | In Progress
3pFbansyD0KOHFtJHrTtew | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:888589 | Level 1 |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:888589 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 258.05 | 258.05 | 136.57 | 121.48 | 0.47076 | 57% | In Progress
3pFbansyD0KOHFtJHrTtev | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888590 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888590 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 174.32 | 0.0071689 | 0.01 | -0.0028311 | -0.39491 | 57% | In Progress
3pFbansyD0KOHFtJHrTteu | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888591 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888591 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 170 | 0.0069913 | 0.01 | -0.0030087 | -0.43036 | 57% | In Progress
3pFbansyD0KOHFtJHrTted | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:888592 | Level 1 |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:888592 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 297.9 | 297.9 | 159.9 | 138 | 0.46324 | 58% | In Progress
3pFbansyD0KOHFtJHrTtec | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888593 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888593 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 196.31 | 0.0080733 | 0.01 | -0.0019267 | -0.23866 | 60% | In Progress
3pFbansyD0KOHFtJHrTteb | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888594 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:888594 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 185.57 | 0.0076316 | 0.01 | -0.0023684 | -0.31034 | 64% | In Progress
3pFbansyD0KOHFtJHrTteh | IFCDOOR |  | M_Single-Flush:Generic Door:888604 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:888604 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 350.09 | 1116.6397 | 688.45 | 428.1897 | 0.38346 | 67% | In Progress
3pFbansyD0KOHFtJHrTtZD | IFCFURNISHINGELEMENT |  | fixa_bench:Colour - (Light grey-S2000-N):888314 | Level 1 |  | Finishes | Furnishing | fixa_bench:Colour - (Light grey-S2000-N):888314 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 275.81 | 275.81 | 151.56 | 124.25 | 0.45049 | 59% | In Progress
3pFbansyD0KOHFtJHrTuXa | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:884051 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:884051 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.78 | 98.67 | 1655.6826 | 1496.55 | 159.1326 | 0.096113 | 92% | In Progress
3pFbansyD0KOHFtJHrTukr | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:884354 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:884354 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 10.07 | 93.57 | 942.2499 | 845.84 | 96.4099 | 0.10232 | 95% | In Progress
3pFbansyD0KOHFtJHrTucY | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:883861 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:883861 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 12.79 | 95.15 | 1216.9685 | 1181.93 | 35.0385 | 0.028792 | 100% | Completed
2BLn4xX2vF_gM9G5wfbPRX | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:838093 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:838093 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.65 | 92.71 | 1358.2015 | 1163.85 | 194.3515 | 0.14309 | 93% | In Progress
2BLn4xX2vF_gM9G5wfbPR8 | IFCDOOR |  | M_Single-Flush:Generic Door:838116 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:838116 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 420.93 | 1342.5895 | 875.44 | 467.1495 | 0.34795 | 68% | In Progress
2BLn4xX2vF_gM9G5wfbPLu | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:838228 | Level 1 |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:838228 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 515.68 | 3894.463 | 2824.34 | 1070.123 | 0.27478 | 73% | In Progress
2BLn4xX2vF_gM9G5wfbPMI | IFCBUILDINGELEMENTPROXY |  | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:838334 | Level 1 |  | Not Assigned | Not Assigned | K\X2\00F6\X0\k - Kyl frys-en d\X2\00F6\X0\rr:Frys:838334 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.75803 | m³ |  |  | 165.35 | 125.3401 | 75.64 | 49.7001 | 0.39652 | 62% | In Progress
2BLn4xX2vF_gM9G5wfbPMJ | IFCBUILDINGELEMENTPROXY |  | Handtag kylfrys:Handtag kyl/frys:838335 | Level 1 |  | Not Assigned | Not Assigned | Handtag kylfrys:Handtag kyl/frys:838335 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 2.5901e-05 | m³ |  |  | 201.02 | 0.0052067 | 0.01 | -0.0047933 | -0.92061 | 63% | In Progress
2BLn4xX2vF_gM9G5wfbPNi | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:838336 | Level 1 |  | Finishes | Furnishing | K\X2\00F6\X0\k - Undersk\X2\00E5\X0\p parluckor:800 mm:838336 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 306.68 | 306.68 | 193.27 | 113.41 | 0.3698 | 63% | In Progress
2BLn4xX2vF_gM9G5wfbPNj | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:838337 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:838337 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 160.24 | 0.0065899 | 0.01 | -0.0034101 | -0.51748 | 54% | In Progress
2BLn4xX2vF_gM9G5wfbPNk | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:838338 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:838338 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 202.3 | 0.0083196 | 0.01 | -0.0016804 | -0.20198 | 64% | In Progress
2BLn4xX2vF_gM9G5wfbPQf | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:838021 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:838021 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 10.5 | 95.42 | 1001.91 | 958.42 | 43.49 | 0.043407 | 93% | In Progress
2BLn4xX2vF_gM9G5wfbPNy | IFCFURNISHINGELEMENT |  | K\X2\00F6\X0\k - Diskb\X2\00E4\X0\nk med sk\X2\00E5\X0\p:H14H:838352 | Level 1 |  | Finishes | Furnishing | K\X2\00F6\X0\k - Diskb\X2\00E4\X0\nk med sk\X2\00E5\X0\p:H14H:838352 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 299.32 | 299.32 | 184.77 | 114.55 | 0.3827 | 61% | In Progress
2BLn4xX2vF_gM9G5wfbPN_ | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:838354 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:838354 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 162.36 | 0.0066771 | 0.01 | -0.0033229 | -0.49766 | 62% | In Progress
2BLn4xX2vF_gM9G5wfbPG9 | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:838437 | Level 1 |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:838437 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 306.41 | 306.41 | 182.36 | 124.05 | 0.40485 | 60% | In Progress
2BLn4xX2vF_gM9G5wfbPGQ | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:838454 | Level 1 |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:838454 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 272.22 | 272.22 | 141.05 | 131.17 | 0.48185 | 55% | In Progress
2BLn4xX2vF_gM9G5wfbPHV | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:838515 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:838515 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.57 | 87.08 | 1617.0756 | 1592.76 | 24.3156 | 0.015037 | 100% | Completed
2BLn4xX2vF_gM9G5wfbPB_ | IFCDOOR |  | M_Single-Flush:Generic Door:839122 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:839122 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 369.56 | 1178.7408 | 782.79 | 395.9508 | 0.33591 | 70% | In Progress
2BLn4xX2vF_gM9G5wfbP4L | IFCWALL |  | Basic Wall:MockUp Interior:839225 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:839225 | Includes RC walls, block walls, brick walls | Dimensions | Area | 13.099 | m² |  |  | 87.42 | 1145.1132 | 1138.73 | 6.3832 | 0.0055743 | 100% | Completed
3pFbansyD0KOHFtJHrTuWx | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:883980 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:883980 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.28 | 97.52 | 1880.1856 | 1571.03 | 309.1556 | 0.16443 | 90% | In Progress
2BLn4xX2vF_gM9G5wfbP1t | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:839515 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:839515 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 13.24 | 93.39 | 1236.4836 | 1218.49 | 17.9936 | 0.014552 | 100% | Completed
2BLn4xX2vF_gM9G5wfbPNz | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:838353 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:838353 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 174.49 | 0.0071759 | 0.01 | -0.0028241 | -0.39355 | 63% | In Progress
2BLn4xX2vF_gM9G5wfbPVo | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:837854 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:837854 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 157.21 | 0.0064653 | 0.01 | -0.0035347 | -0.54672 | 66% | In Progress
2BLn4xX2vF_gM9G5wfbPVn | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:837853 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:837853 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 175.12 | 0.0072018 | 0.01 | -0.0027982 | -0.38854 | 58% | In Progress
2BLn4xX2vF_gM9G5wfbPVm | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:837852 | Level 1 |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:837852 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 255.21 | 255.21 | 157.34 | 97.87 | 0.38349 | 65% | In Progress
2BLn4xX2vF_gM9G5wfbPcl | IFCFURNISHINGELEMENT |  | Inredning - Skrivbord:1600x800:837251 | Level 1 |  | Finishes | Furnishing | Inredning - Skrivbord:1600x800:837251 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 308.13 | 308.13 | 182.58 | 125.55 | 0.40746 | 59% | In Progress
2BLn4xX2vF_gM9G5wfbPce | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:837252 | Level 1 |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:837252 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 293.87 | 293.87 | 166.68 | 127.19 | 0.43281 | 57% | In Progress
2BLn4xX2vF_gM9G5wfbPcx | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:837271 | Level 1 |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:837271 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 303.82 | 303.82 | 178.92 | 124.9 | 0.4111 | 61% | In Progress
2BLn4xX2vF_gM9G5wfbPcq | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:837272 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:837272 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 174.67 | 0.0071833 | 0.01 | -0.0028167 | -0.39211 | 64% | In Progress
2BLn4xX2vF_gM9G5wfbPcr | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:837273 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:837273 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 173.09 | 0.0071183 | 0.01 | -0.0028817 | -0.40482 | 62% | In Progress
2BLn4xX2vF_gM9G5wfbPcN | IFCFURNISHINGELEMENT |  | Furniture-Wieland_Healthcare-Rally-Compose-Sofa:64343HC:837307 | Level 1 |  | Finishes | Furnishing | Furniture-Wieland_Healthcare-Rally-Compose-Sofa:64343HC:837307 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 952.04 | 952.04 | 545.84 | 406.2 | 0.42666 | 61% | In Progress
2BLn4xX2vF_gM9G5wfbPdz | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:837329 | Level 1 |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:837329 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 275.97 | 275.97 | 147.86 | 128.11 | 0.46422 | 58% | In Progress
2BLn4xX2vF_gM9G5wfbPd3 | IFCDOOR |  | M_Single-Flush:Generic Door:837359 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:837359 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 415.61 | 1325.6209 | 900.6 | 425.0209 | 0.32062 | 66% | In Progress
2BLn4xX2vF_gM9G5wfbPWX | IFCWINDOW |  | BALANS Fixed Single Window:BALANS 15M PRIVATE:837389 | Level 1 |  | Finishes | Glazing / Aluminium | BALANS Fixed Single Window:BALANS 15M PRIVATE:837389 | Windows. Check OverallHeight × OverallWidth for area | Custom_Pset | NetArea | 7.5521 | m² |  |  | 540.94 | 4085.2289 | 2827.04 | 1258.1889 | 0.30798 | 72% | In Progress
2BLn4xX2vF_gM9G5wfbPXR | IFCFURNISHINGELEMENT |  | Inredning - Skrivbord:1600x800:837495 | Level 1 |  | Finishes | Furnishing | Inredning - Skrivbord:1600x800:837495 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 281.72 | 281.72 | 143.02 | 138.7 | 0.49233 | 54% | In Progress
2BLn4xX2vF_gM9G5wfbPXK | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:837496 | Level 1 |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:837496 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 309.37 | 309.37 | 180.65 | 128.72 | 0.41607 | 58% | In Progress
2BLn4xX2vF_gM9G5wfbPYe | IFCFURNISHINGELEMENT |  | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:837508 | Level 1 |  | Finishes | Furnishing | Inredning - sk\X2\00E5\X0\p - pard\X2\00F6\X0\rr:1200 mm:837508 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 299.12 | 299.12 | 175.63 | 123.49 | 0.41284 | 62% | In Progress
2BLn4xX2vF_gM9G5wfbPYf | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:837509 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:837509 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 185.4 | 0.0076246 | 0.01 | -0.0023754 | -0.31155 | 56% | In Progress
2BLn4xX2vF_gM9G5wfbPYg | IFCBUILDINGELEMENTPROXY |  | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:837510 | Level 1 |  | Not Assigned | Not Assigned | Handtag sk\X2\00E5\X0\p1:Handtag sk\X2\00E5\X0\p:837510 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 4.1125e-05 | m³ |  |  | 182.52 | 0.0075062 | 0.01 | -0.0024938 | -0.33224 | 57% | In Progress
2BLn4xX2vF_gM9G5wfbPTJ | IFCFURNISHINGELEMENT |  | Inredning - Skrivbord:1600x800:837759 | Level 1 |  | Finishes | Furnishing | Inredning - Skrivbord:1600x800:837759 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 301.93 | 301.93 | 174.44 | 127.49 | 0.42225 | 56% | In Progress
2BLn4xX2vF_gM9G5wfbPUi | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:837760 | Level 1 |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:837760 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 289.85 | 289.85 | 176.77 | 113.08 | 0.39013 | 64% | In Progress
2BLn4xX2vF_gM9G5wfbPUD | IFCFURNISHINGELEMENT |  | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:837793 | Level 1 |  | Finishes | Furnishing | Inredning - bokhylla h\X2\00F6\X0\g:Inredning - bokhylla h\X2\00F6\X0\g:837793 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 253.56 | 253.56 | 156.79 | 96.77 | 0.38165 | 65% | In Progress
2BLn4xX2vF_gM9G5wfbPVs | IFCFURNISHINGELEMENT |  | Inredning - Skrivbord:1600x800:837850 | Level 1 |  | Finishes | Furnishing | Inredning - Skrivbord:1600x800:837850 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 310.88 | 310.88 | 184.15 | 126.73 | 0.40765 | 60% | In Progress
2BLn4xX2vF_gM9G5wfbPVt | IFCFURNISHINGELEMENT |  | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:837851 | Level 1 |  | Finishes | Furnishing | Inredning - Kontorsstol:m Armst\X2\00F6\X0\d:837851 | Generic furnishing — furniture, fittings | Default (count unit) | 1 per element | 1 | ea |  |  | 299.41 | 299.41 | 187.38 | 112.03 | 0.37417 | 64% | In Progress
2BLn4xX2vF_gM9G5wfbP3_ | IFCDOOR |  | M_Single-Flush:Generic Door:839634 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:839634 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 425.04 | 1355.6987 | 1009.76 | 345.9387 | 0.25517 | 74% | In Progress
2BLn4xX2vF_gM9G5wfbP36 | IFCDOOR |  | M_Single-Flush:Generic Door:839658 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:839658 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 358.7 | 1144.102 | 715.75 | 428.352 | 0.3744 | 68% | In Progress
2BLn4xX2vF_gM9G5wfbP7V | IFCDOOR |  | M_Single-Flush:Generic Door:839411 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:839411 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 348.73 | 1112.3019 | 767.36 | 344.9419 | 0.31012 | 70% | In Progress
2BLn4xX2vF_gM9G5wfbOe6 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:841002 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:841002 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.88 | 92.05 | 1737.904 | 1470.31 | 267.594 | 0.15398 | 90% | In Progress
1k8pVOGqX51f_yJjFvAcjy | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:313594 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:313594 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.79 | 97 | 1822.63 | 1791.47 | 31.16 | 0.017096 | 100% | Completed
2BLn4xX2vF_gM9G5wfbOzp | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior:839775 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:839775 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 13.13 | 92.88 | 1219.5144 | 1224.07 | -4.5556 | -0.0037356 | 100% | Completed
1k8pVOGqX51f_yJjFvAci9 | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:313487 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:313487 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.44 | 97.3 | 1794.212 | 1663.45 | 130.762 | 0.07288 | 90% | In Progress
1k8pVOGqX51f_yJjFvAclL | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:313427 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:313427 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 22.34 | 100.37 | 2242.2658 | 2216.43 | 25.8358 | 0.011522 | 100% | Completed
1k8pVOGqX51f_yJjFvAckQ | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:313372 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:313372 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 24.07 | 94.76 | 2280.8732 | 1946.78 | 334.0932 | 0.14648 | 91% | In Progress
1k8pVOGqX51f_yJjFvAcGC | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:313226 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:313226 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 25.71 | 94.61 | 2432.4231 | 2159.41 | 273.0131 | 0.11224 | 89% | In Progress
1k8pVOGqX51f_yJjFvAcLC | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:313034 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:313034 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 25.56 | 100.58 | 2570.8248 | 2383.62 | 187.2048 | 0.072819 | 91% | In Progress
1k8pVOGqX51f_yJjFvAcNa | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:312930 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:312930 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.15 | 85.78 | 1642.687 | 1461.67 | 181.017 | 0.1102 | 90% | In Progress
1k8pVOGqX51f_yJjFvAcgM | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:313616 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:313616 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.7 | 88.86 | 1483.962 | 1307.45 | 176.512 | 0.11895 | 91% | In Progress
1k8pVOGqX51f_yJjFvAcPr | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:312819 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:312819 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.55 | 89.08 | 1296.114 | 1107.48 | 188.634 | 0.14554 | 89% | In Progress
1k8pVOGqX51f_yJjFvAcOc | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:312736 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:312736 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 15.82 | 100.06 | 1582.9492 | 1568.77 | 14.1792 | 0.0089575 | 100% | Completed
1k8pVOGqX51f_yJjFvAcO4 | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:312706 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:312706 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 21.2 | 99.24 | 2103.888 | 1878.32 | 225.568 | 0.10721 | 92% | In Progress
1k8pVOGqX51f_yJjFvAcRl | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:312681 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:312681 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 22.42 | 101.64 | 2278.7688 | 2248.51 | 30.2588 | 0.013279 | 100% | Completed
1k8pVOGqX51f_yJjFvAcRD | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:312651 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:312651 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.88 | 94.27 | 2251.1676 | 2332.54 | -81.3724 | -0.036147 | 100% | Completed
1k8pVOGqX51f_yJjFvAcTR | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:312541 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:312541 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.48 | 90.68 | 1766.4464 | 1836.22 | -69.7736 | -0.039499 | 100% | Completed
3pFbansyD0KOHFtJHrTuw8 | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:883647 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:883647 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 12.28 | 91.47 | 1123.2516 | 1041.12 | 82.1316 | 0.07312 | 94% | In Progress
3pFbansyD0KOHFtJHrTuxk | IFCDOOR |  | M_Single-Flush:Generic Door:883673 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:883673 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 388.5 | 1239.1514 | 913.79 | 325.3614 | 0.26257 | 74% | In Progress
3pFbansyD0KOHFtJHrTubo | IFCWALLSTANDARDCASE |  | Basic Wall:MockUp Interior between App:883781 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior between App:883781 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.49 | 86.46 | 1685.1054 | 1465.37 | 219.7354 | 0.1304 | 92% | In Progress
1k8pVOGqX51f_yJjFvAcPJ | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:312789 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:312789 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 24.42 | 95.3 | 2327.226 | 2275.72 | 51.506 | 0.022132 | 100% | Completed
1k8pVOGqX51f_yJjFvAch0 | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:313670 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:313670 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.03 | 99.82 | 1400.4746 | 1285.22 | 115.2546 | 0.082297 | 95% | In Progress
1k8pVOGqX51f_yJjFvAcjU | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:313560 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:313560 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 22.87 | 92.07 | 2105.6409 | 1751.47 | 354.1709 | 0.1682 | 90% | In Progress
1k8pVOGqX51f_yJjFvAce7 | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:313729 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:313729 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.29 | 98.69 | 1706.3501 | 1422.86 | 283.4901 | 0.16614 | 90% | In Progress
2BLn4xX2vF_gM9G5wfbOeO | IFCDOOR |  | M_Single-Flush:Generic Door:841012 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:841012 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 387.13 | 1234.7817 | 798.51 | 436.2717 | 0.35332 | 69% | In Progress
2BLn4xX2vF_gM9G5wfbObm | IFCWALL |  | Basic Wall:MockUp Interior:841308 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:MockUp Interior:841308 | Includes RC walls, block walls, brick walls | Dimensions | Area | 11.3676 | m² |  |  | 96.27 | 1094.3624 | 970.1 | 124.2624 | 0.11355 | 95% | In Progress
34Ni6yH0HDjQqrjEsXbUMJ | IFCDOOR |  | M_Single-Flush:Generic Door:841486 | Level 1 |  | Finishes | Joinery / Metal | M_Single-Flush:Generic Door:841486 | Doors. Check PredefinedType: DOOR/GATE/TRAPDOOR | Custom_Pset | NetArea | 3.1896 | m² |  |  | 409.87 | 1307.3127 | 879.28 | 428.0327 | 0.32741 | 67% | In Progress
1k8pVOGqX51f_yJjFvAcxH | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:314711 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:314711 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.15 | 93.06 | 1502.919 | 1528.19 | -25.271 | -0.016815 | 100% | Completed
1k8pVOGqX51f_yJjFvAcwv | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:314687 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:314687 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.16 | 86.48 | 1570.4768 | 1398.02 | 172.4568 | 0.10981 | 93% | In Progress
1k8pVOGqX51f_yJjFvAchc | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:313696 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:313696 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 14.77 | 95.62 | 1412.3074 | 1409.39 | 2.9174 | 0.0020657 | 100% | Completed
1k8pVOGqX51f_yJjFvAcyV | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:314521 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:314521 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 22.56 | 97.49 | 2199.3744 | 2122.89 | 76.4844 | 0.034776 | 94% | In Progress
1k8pVOGqX51f_yJjFvAc$r | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:314483 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:314483 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 20.22 | 91.3 | 1846.086 | 1893.71 | -47.624 | -0.025797 | 100% | Completed
1k8pVOGqX51f_yJjFvAc_Q | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:314396 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:314396 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 16.64 | 89.77 | 1493.7728 | 1365.63 | 128.1428 | 0.085785 | 94% | In Progress
1k8pVOGqX51f_yJjFvAczG | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:314582 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:314582 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 25.33 | 88.88 | 2251.3304 | 2278.48 | -27.1496 | -0.012059 | 100% | Completed
1k8pVOGqX51f_yJjFvAcX0 | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:314310 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:314310 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.43 | 98.04 | 1708.8372 | 1557.38 | 151.4572 | 0.088632 | 89% | In Progress
1k8pVOGqX51f_yJjFvAcev | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:313791 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:313791 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.31 | 98.5 | 2296.035 | 2370.49 | -74.455 | -0.032428 | 100% | Completed
1k8pVOGqX51f_yJjFvAcXu | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:314366 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:314366 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 24.59 | 85.82 | 2110.3138 | 1905.36 | 204.9538 | 0.09712 | 90% | In Progress
1k8pVOGqX51f_yJjFvAcc0 | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:313862 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:313862 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 17.87 | 93.77 | 1675.6699 | 1636.38 | 39.2899 | 0.023447 | 100% | Completed
1k8pVOGqX51f_yJjFvAcdu | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:313982 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:313982 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.96 | 90.63 | 1808.9748 | 1675.37 | 133.6048 | 0.073857 | 91% | In Progress
1k8pVOGqX51f_yJjFvAcff | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:313839 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:313839 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 22.85 | 101.38 | 2316.533 | 2364.47 | -47.937 | -0.020693 | 100% | Completed
1k8pVOGqX51f_yJjFvAcbd | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:314081 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:314081 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 19.93 | 98.33 | 1959.7169 | 2044.75 | -85.0331 | -0.043391 | 100% | Completed
1k8pVOGqX51f_yJjFvAcZJ | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:314197 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:314197 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 22.68 | 86.65 | 1965.222 | 1993.77 | -28.548 | -0.014527 | 100% | Completed
1k8pVOGqX51f_yJjFvAcZg | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:314220 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:314220 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 23.1 | 95.92 | 2215.752 | 2133.88 | 81.872 | 0.03695 | 94% | In Progress
1k8pVOGqX51f_yJjFvAcab | IFCWALLSTANDARDCASE |  | Basic Wall:Generic - 200mm:314019 | Level 1 |  | Structure | Concrete / Masonry | Basic Wall:Generic - 200mm:314019 | Standard wall – most common in Revit/ArchiCAD | Not Found | Not Found |  | m² |  | 18.45 | 97.39 | 1796.8455 | 1554.91 | 241.9355 | 0.13464 | 88% | In Progress
2fypDDb212M80XzLYYLlSG | IFCRAILING | NOTDEFINED | Railing:Glass Panel - Bottom Fill:965153 | Level 1 |  | Finishes | Metal / Timber | Railing:Glass Panel - Bottom Fill:965153 | Balustrades, handrails, guard rails | Custom_Pset | Length | 30847.9728 | m |  |  | 226.96 | 7001255.8993 | 5411393.11 | 1589862.7893 | 0.22708 | 78% | In Progress
0qKJYWbnv5I8o6vyLfHje6 | IFCBUILDINGELEMENTPROXY |  | Display-LCD-Panasonic-Standard:47, 1080p Full HD LCD w/ built-in speaker:899857 | Level 2 |  | Not Assigned | Not Assigned | Display-LCD-Panasonic-Standard:47, 1080p Full HD LCD w/ built-in speaker:899857 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.065323 | m³ |  |  | 196.41 | 12.8301 | 5.47 | 7.3601 | 0.57366 | 43% | In Progress
2v8sGyGFXDsRc80mj95l5L | IFCBUILDINGELEMENTPROXY |  | Display-LCD-Panasonic-Standard:47, 1080p Full HD LCD w/ built-in speaker:725313 | Level 2 |  | Not Assigned | Not Assigned | Display-LCD-Panasonic-Standard:47, 1080p Full HD LCD w/ built-in speaker:725313 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.065323 | m³ |  |  | 202.31 | 13.2155 | 4.62 | 8.5955 | 0.65041 | 37% | In Progress
2m6FhmO0r2OgRBRP7hD4Bx | IFCBUILDINGELEMENTPROXY |  | Display-LCD-Panasonic-Standard:47, 1080p Full HD LCD w/ built-in speaker:711446 | Level 2 |  | Not Assigned | Not Assigned | Display-LCD-Panasonic-Standard:47, 1080p Full HD LCD w/ built-in speaker:711446 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.065323 | m³ |  |  | 163.96 | 10.7103 | 4.48 | 6.2303 | 0.58171 | 43% | In Progress
3GzoWuxxn4WO8bCtw8H3Gz | IFCBUILDINGELEMENTPROXY |  | Display-LCD-Panasonic-Standard:47, 1080p Full HD LCD w/ built-in speaker:697592 | Level 2 |  | Not Assigned | Not Assigned | Display-LCD-Panasonic-Standard:47, 1080p Full HD LCD w/ built-in speaker:697592 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.065323 | m³ |  |  | 173.78 | 11.3518 | 4.52 | 6.8318 | 0.60183 | 39% | In Progress
11MreptMzBDAizZWBG8_Z3 | IFCBUILDINGELEMENTPROXY |  | Display-LCD-Panasonic-Standard:47, 1080p Full HD LCD w/ built-in speaker:687696 | Level 2 |  | Not Assigned | Not Assigned | Display-LCD-Panasonic-Standard:47, 1080p Full HD LCD w/ built-in speaker:687696 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.065323 | m³ |  |  | 167.01 | 10.9096 | 4.2 | 6.7096 | 0.61502 | 38% | In Progress
0X2$ayW0v5dBNxK3e4nxzo | IFCBUILDINGELEMENTPROXY |  | Display-LCD-Panasonic-Standard:47, 1080p Full HD LCD w/ built-in speaker:686531 | Level 2 |  | Not Assigned | Not Assigned | Display-LCD-Panasonic-Standard:47, 1080p Full HD LCD w/ built-in speaker:686531 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.065323 | m³ |  |  | 199.54 | 13.0345 | 3.92 | 9.1145 | 0.69926 | 32% | In Progress
1KGNuJkf5FjQZDFQ6WeE55 | IFCBUILDINGELEMENTPROXY |  | Display-LCD-Panasonic-Standard:47, 1080p Full HD LCD w/ built-in speaker:675104 | Level 2 |  | Not Assigned | Not Assigned | Display-LCD-Panasonic-Standard:47, 1080p Full HD LCD w/ built-in speaker:675104 | Catch-all. Check Name/Description/ObjectType for actual element type | Dimensions | Volume | 0.065323 | m³ |  |  | 170.54 | 11.1402 | 4.53 | 6.6102 | 0.59336 | 40% | In Progress

## Summary
Total Budget (€) | Total Actual (€) | Variance (€) | Weighted % Completion | Done | In Progress | Not Started
45545145.4716 | 25910759.54 | 19634385.9316 | 58.33% | 193 | 1494 | 29
Cost Breakdown by Status
Status | items No. | Cost Budgeted | Cost Actual | Variance | % Var Avg | % Complete Avg
Completed | 193 | 763269.5537 | 750374.37 | 12895.1837 | -0.3891% | 99.39%
In Progress | 1494 | 44753256.0994 | 25138553.26 | 19614702.8394 | 28.59% | 63.83%
Not Started | 29 | 28619.8185 | 21831.91 | 6787.9085 | 22.77% | 8.207%
Grand Total | 1716 | 45545145.4716 | 25910759.54 | 19634385.9316 | 25.27% | 0.6689

## Breakdown_By_Discipline
Cost Breakdown by Discipline
Discipline | items No. | Cost Budgeted | Cost Actual | Variance | % Var Avg | % Complete Avg
(Info Only) | 26 | 0 | 0 | 0 |  | 0
Finishes | 756 | 42396310.7051 | 23228748.59 | 19167562.1151 | 43.82% | 0.57443
MEP | 49 | 44302.1 | 30557.15 | 13744.95 | 30.98% | 0.70041
Not Assigned | 358 | 33723.2914 | 16361.54 | 17361.7514 | 8.984% | 0.54858
Structure | 527 | 3070809.3751 | 2635092.26 | 435717.1151 | 9.18% | 0.91622
Grand Total | 1716 | 45545145.4716 | 25910759.54 | 19634385.9316 | 25.27% | 0.6689

## Breakdown_By_Storey
Cost Breakdown by Building Storey
Storey | items No. | Cost Budgeted | Cost Actual | Variance | % Var Avg | % Complete Avg
1 - First Floor | 734 | 604839.8001 | 442068.84 | 162770.9601 | 25.47% | 0.61989
-1 - Garage | 165 | 282827.1688 | 276009.02 | 6818.1488 | 9.453% | 0.90564
2 - Second Floor | 39 | 235221.4706 | 148048.44 | 87173.0306 | 43.55% | 0.58179
3 - Third Floor | 39 | 234251.9072 | 126418.22 | 107833.6872 | 50.46% | 0.50795
4 - Fourth Floor | 39 | 234523.2807 | 110787.62 | 123735.6607 | 57.47% | 0.43564
5 - Fifth Floor | 39 | 228076.848 | 98744.94 | 129331.908 | 63.32% | 0.37154
6 - Sixth Floor | 53 | 12023564.2761 | 3630128.02 | 8393436.2561 | 74.75% | 0.22358
Level 1 | 486 | 8393587.9993 | 6667268.13 | 1726319.8693 | 16.37% | 0.75319
Level 2 | 7 | 83.192 | 31.74 | 51.452 | 61.65% | 0.38857
(blank) | 115 | 23308169.5289 | 14411254.57 | 8896914.9589 | 22.89% | 0.77217
Grand Total | 1716 | 45545145.4716 | 25910759.54 | 19634385.9316 | 25.27% | 0.6689

## Breakdown_By_Entity
Cost Breakdown by Entity
Entity | Unit | items No. | Cost Budgeted | Cost Actual | Variance | % Var Avg | % Complete Avg
IFCBUILDINGELEMENTPROXY | m³ | 358 | 33723.2914 | 16361.54 | 17361.7514 | 8.984% | 0.54858
IFCDOOR | m² | 126 | 174005.2604 | 119456.18 | 54549.0804 | 30.2% | 0.71246
IFCFLOWTERMINAL | ea | 49 | 44302.1 | 30557.15 | 13744.95 | 30.98% | 0.70041
IFCFURNISHINGELEMENT | ea | 407 | 119415.75 | 64955.37 | 54460.38 | 45.29% | 0.55936
IFCMEMBER | m³ | 83 | 906044.8434 | 722108.83 | 183936.0134 | 19.59% | 0.81771
IFCRAILING | m | 19 | 41237294.1922 | 22608983.5 | 18628310.6922 | 39.49% | 0.61842
IFCRAMPFLIGHT | m² | 2 | 48415.9806 | 36829.4 | 11586.5806 | 23.93% | 0.795
IFCSITE | m² | 18 | 0 | 0 | 0 |  | 0
IFCSLAB | m² | 43 | 1404957.8889 | 1215009.92 | 189947.9689 | 11.11% | 0.90023
IFCSPACE | m² | 8 | 0 | 0 | 0 |  | 0
IFCSTAIRFLIGHT | m³ | 9 | 31676.7428 | 24294.4 | 7382.3428 | 22.95% | 0.79111
IFCWALL | m² | 9 | 9317.2859 | 8749.52 | 567.7659 | 3.393% | 0.97778
IFCWALLSTANDARDCASE | m² | 381 | 670396.6335 | 628100.19 | 42296.4435 | 6.429% | 0.94163
IFCWINDOW | m² | 204 | 865595.5025 | 435353.54 | 430241.9625 | 49.71% | 0.51515
Grand Total |  | 1716 | 45545145.4716 | 25910759.54 | 19634385.9316 | 25.27% | 0.6689

## Budgeted Matrix
Budget Matrix — Storey × Cost Category
Budgeted | Category
Storey | Finishes | MEP | Not Assigned | Structure | Total
1 - First Floor | 312601.4992 | 36195.13 | 2035.7511 | 254007.4198 | 604839.8001
Completed |  |  |  | 9674.9448 | 9674.9448
In Progress | 312601.4992 | 36195.13 | 2035.7511 | 244332.475 | 595164.8553
-1 - Garage | 48078.9162 | 4376.57 | 4276.1205 | 226095.562 | 282827.1688
Completed |  |  |  | 226095.562 | 226095.562
In Progress | 48078.9162 | 4376.57 | 4276.1205 |  | 56731.6067
2 - Second Floor | 161510.7416 |  |  | 73710.7289 | 235221.4706
In Progress | 161510.7416 |  |  | 73710.7289 | 235221.4706
3 - Third Floor | 163611.7763 |  |  | 70640.1309 | 234251.9072
In Progress | 163611.7763 |  |  | 70640.1309 | 234251.9072
4 - Fourth Floor | 163244.4654 |  |  | 71278.8153 | 234523.2807
In Progress | 163244.4654 |  |  | 71278.8153 | 234523.2807
5 - Fifth Floor | 164838.9053 |  |  | 63237.9426 | 228076.848
In Progress | 164838.9053 |  |  | 63237.9426 | 228076.848
6 - Sixth Floor | 11987322.5072 |  | 10037.9463 | 26203.8226 | 12023564.2761
In Progress | 11987322.5072 |  | 10037.9463 | 26203.8226 | 12023564.2761
Level 1 | 7130566.4828 | 3730.4 | 17290.2815 | 1242000.835 | 8393587.9993
Completed |  |  |  | 426986.4034 | 426986.4034
In Progress | 7130566.4828 | 3730.4 | 17290.2815 | 815014.4316 | 7966601.5959
Level 2 |  |  | 83.192 |  | 83.192
In Progress |  |  | 83.192 |  | 83.192
(blank) | 22264535.411 |  |  | 1043634.1178 | 23308169.5289
Completed |  |  |  | 100512.6434 | 100512.6434
In Progress | 22264535.411 |  |  | 914501.6559 | 23179037.067
Not Started |  |  |  | 28619.8185 | 28619.8185
Total | 42396310.7051 | 44302.1 | 33723.2914 | 3070809.3751 | 45545145.4716

## Actual Cost Matrix
Actual Matrix — Storey × Cost Category
Actual | Category
Storey | Finishes | MEP | Not Assigned | Structure | Total
1 - First Floor | 192126.36 | 24265.68 | 1158.43 | 224518.37 | 442068.84
Completed |  |  |  | 9748.02 | 9748.02
In Progress | 192126.36 | 24265.68 | 1158.43 | 214770.35 | 432320.82
-1 - Garage | 38522.91 | 3597.46 | 3076.98 | 230811.67 | 276009.02
Completed |  |  |  | 230811.67 | 230811.67
In Progress | 38522.91 | 3597.46 | 3076.98 |  | 45197.35
2 - Second Floor | 89963.38 |  |  | 58085.06 | 148048.44
In Progress | 89963.38 |  |  | 58085.06 | 148048.44
3 - Third Floor | 80618.7 |  |  | 45799.52 | 126418.22
In Progress | 80618.7 |  |  | 45799.52 | 126418.22
4 - Fourth Floor | 68045.09 |  |  | 42742.53 | 110787.62
In Progress | 68045.09 |  |  | 42742.53 | 110787.62
5 - Fifth Floor | 59398.75 |  |  | 39346.19 | 98744.94
In Progress | 59398.75 |  |  | 39346.19 | 98744.94
6 - Sixth Floor | 3614633.76 |  | 1798.52 | 13695.74 | 3630128.02
In Progress | 3614633.76 |  | 1798.52 | 13695.74 | 3630128.02
Level 1 | 5497822.77 | 2694.01 | 10295.87 | 1156455.48 | 6667268.13
Completed |  |  |  | 429986.08 | 429986.08
In Progress | 5497822.77 | 2694.01 | 10295.87 | 726469.4 | 6237282.05
Level 2 |  |  | 31.74 |  | 31.74
In Progress |  |  | 31.74 |  | 31.74
(blank) | 13587616.87 |  |  | 823637.7 | 14411254.57
Completed |  |  |  | 79828.6 | 79828.6
In Progress | 13587616.87 |  |  | 721977.19 | 14309594.06
Not Started |  |  |  | 21831.91 | 21831.91
Total | 23228748.59 | 30557.15 | 16361.54 | 2635092.26 | 25910759.54